## 2023-24 closures
Activities due 2023/24 - closures booked
Rebaselined SP New Planned Finish | - all -
Resource (formula) | - all -
Yearly Pass 1-6 | - multiple -
Actual Start | Area 12 TM Reference | ScAR | Activity Name | TM Needed? | Qts Remaining
2023-12-08 | YNE17 Closure 1 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 49
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 2
| YNE20 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 85
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 4
| YNE41 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 11
| YNE41 Closure 1 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 22
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | (empty) | 5
2023-12-11 | YNE70 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 13981.75
| YNE71 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 14579.25
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | No | 1515
| YNE72 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | No | 10264.5
| YNE89 Closure 2 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 7665
| YNE89 Closure 2 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 7665
2023-12-12 | YNE89 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 7665
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | (empty) | 604
| WS Link Langham | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 17
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 1
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | (empty) | 1427
2023-12-13 | YNE15 Closure 2 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 14
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 3326.9091
| YNE15 Closure 2 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 15
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 3326.9091
| YNE89 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 7665
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | (empty) | 469
2023-12-14 | YNE72 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 10264.5
| YNE74 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 6773
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | Yes | 2240
| YNE88 Closure 1 NB NS | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | (empty) | 505
| YNE88 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 7659.5
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | (empty) | 621
2023-12-15 | YNE6 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 23
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 9
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 15689.5
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | (empty) | 6957
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | (empty) | 19249
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | Yes | 5296
|  |  | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | Yes | 2148
| YNE90 Closure 1 EB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 4097.5
| YNE90 Closure 1 WB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 4097.5
2023-12-18 | YNE69 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 6994
| YNE69 Closure 2 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | No | 6994
| YNE91 Closure 1 EB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 8878.25
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | No | 8556
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | No | 6809
| YNE91 Closure 2 EB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 8878.25
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | No | 3619
2024-01-08 | YNE82 Closure 1 NB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 90
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 7
| YNE82 Closure 1 SB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 1
2024-01-09 | YNE3 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 63
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 5
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 2766.75
| YNE5 Closure 1 WB NS | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 8
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | (empty) | 12
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 15819
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | Yes | 1179
| YNE54 Closure 2 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 43
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 3
2024-01-10 | YNE9 Closure 1 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 35
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 4
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 10946.25
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | (empty) | 1068
2024-01-12 | YNE3 Closure 1 EB OS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 8300.25
| YNE3 Closure 1 WB OS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 2766.75
| YNE5 Closure 1 EB OS | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | (empty) | 633
2024-01-15 | YNE54 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 58
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 3
| YNE6 Closure 1 EB OS | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | (empty) | 6957
2024-01-17 | YNE78 Closure 1 EB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 11
| YNE78 Closure 1 WB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 161
2024-01-19 | YNE106 Closure 2 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 6991
| YNE106 Closure 2 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 6991
2024-01-22 | YNE106 Closure 3 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 6991
| YNE106 Closure 3 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 6991
2024-01-24 | YNE108 Closure 1 NB NS | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | No | 544
| YNE108 Closure 1 SB NS | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | No | 547
2024-01-25 | YNE109 Closure 1 NB NS | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | No | 375
| YNE109 Closure 1 SB NS | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | No | 343
2024-01-26 | YNE83 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 15548
| YNE83 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 15548
| YNE84 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 6795.3636
| YNE84 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 6795.3636
2024-01-29 | YNE110 Closure 1 NB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 81
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 3
| YNE110 Closure 1 SB NS | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 |  | 108
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | (empty) | 4
| YNE84 Closure 2 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 3397.6818
| YNE84 Closure 2 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 3397.6818
2024-01-30 | YNE84 Closure 3 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 3397.6818
| YNE84 Closure 3 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 3397.6818
2024-01-31 | YNE85 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 13092.6136
| YNE85 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 13092.6136
2024-02-01 | YNE86 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 5863.4167
| YNE86 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 5863.4167
2024-02-02 | YNE86 Closure 2 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 5863.4167
| YNE86 Closure 2 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 5863.4167
2024-02-05 | YNE86 Closure 3 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 5863.4167
| YNE86 Closure 3 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 5863.4167
2024-02-06 | YNE87 Closure 1 NB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 13731.5
| YNE87 Closure 1 SB NS | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | (empty) | 13731.5
Total Result |  |  |  |  | 444752.5

## 2023-24 Due - no date
Actual Start | (empty)
Resource (formula) | - all -
Asset Type | - all -
Rebaselined SP New Planned Finish | Area 12 Maintenance Segments | ScAR | Activity Name | Qts Remaining
2023-12-31 | YNE15: M62 J37-38 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 6796.9
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 63
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 15
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 45
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 4
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 3
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 61
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 7
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 34438
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 6653.8182
| YNE16: A63 North Cave - South Cave | 4.3.1.1 | Gullies - Emptying / clear covers | 282
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 90
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 3
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 69
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 69
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 85845
| YNE17: A63 South Cave - Welton | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 0
| YNE18: A63 Welton - Melton | 4.2.1 | VRS - Check all Road Restraint System - ILM | 1990.63
|  | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2331.8
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 147
|  | 4.3.2.1 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 1088.7
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 169.97
|  | 4.3.3.3 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 11
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 105
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 2
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 36
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 5
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 75
|  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 91
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 98
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 47164
| YNE19: A63 Melton - WesternInt | 4.2.1 | VRS - Check all Road Restraint System - ILM | 3277.43
|  | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1616.99
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 110
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 8
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 48
|  | 4.5.1 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 16
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 16
|  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 54
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 57
| YNE20: A63 Western Int - Priory Way | 4.2.1 | VRS - Check all Road Restraint System - ILM | 1642.91
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 8
|  |  | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 24
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 126
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 1
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 44
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 2
| YNE3: M62 J24-25 | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1993.63
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 90
|  |  | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 4
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 72
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 9
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 3
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 72
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 2
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 5533.5
| YNE45: A64 Bilbrough - Askham | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE54: A64 Pickering Int - Brambling | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE56: A64 Rillington - Sherburn | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
| YNE57: A64 Sherburn - Staxton | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE67: M1 J35-35a | 4.3.1.1 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 70
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 3
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 5128.5
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 22529
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2550
| YNE68: M1 J35a-36 | 4.3.1.1 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 14
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
| YNE69: M1 J36-37 | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
| YNE71: M1 J38-39 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 3
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 11
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 2
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 2
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 2
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 3 - ILM | 1359
|  |  | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 1359
| YNE88: M18 J5-6 | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.8.2 | Woodland - Thin / coppice | 33686
| YNE89: M18 J6-7 | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 2
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 2
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 2
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1
|  | 4.8.2 | Woodland - Thin / coppice | 51269
| YNE90: M180 Ings - J1 | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
| YNE91: M180 J1-2 | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
2024-01-30 | YNE92: M180 J2-3 | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1
2024-01-31 | DBFO 27 - technology assets only | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 5
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 5
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 9
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 45
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 16
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 16
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 16
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 17
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 17
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 15
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 65
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 12
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 40
| YNE1: M62 J22-23 | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 4
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 34
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 5
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 5
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 5
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 8
|  | 4.6.6 | Meteorological sites - Clean fog sensors | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6
| YNE10: M62 J32-33 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 25
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 3
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 3
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 3
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 3
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 3
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 3
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 19
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 21
| YNE106: A1M J34-35 | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 300
|  | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 5934.17
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 17
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 6991
| YNE107: A1M J35-36 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 15
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 4221
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 6924.75
| YNE109: A1M J37-38 | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 11
| YNE11: M62 J33-34 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 3760.54
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 11
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 11
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 7
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 24830
| YNE110: A1 Redhouse - Barnsdale | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 23
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 5
| YNE114: A58 Chainbar | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3
| YNE12: M62 J34-35 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 7848.51
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 508
|  |  | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 3
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 233.42
|  | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 21377.62
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 53
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 2
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 93
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 8
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 3
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 16
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 2
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 2
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 2
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 19
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 13
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 54849
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 14604
| YNE13: M62 J35-36 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 8750.11
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 159
|  |  | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 136
|  | 4.3.2.1 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 846
|  | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 1374.66
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 282
|  | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 2376.71
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 57
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 8
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 46
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 21
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 9
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 4
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 50276
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 50176.5
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2431
| YNE14: M62 J36-37 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 9321.13
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 589
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 223
|  | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 1477.85
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 74
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 9
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 45
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 8
|  | 4.6.6 | Meteorological sites - Clean fog sensors | 1
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 36251
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 36408
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2124
| YNE15: M62 J37-38 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 4424
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 659
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 6236.73
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 127
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 80
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 8
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 83
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 16
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 19
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 2
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 1
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 47652
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 13307.6364
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2394
| YNE17: A63 South Cave - Welton | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
| YNE19: A63 Melton - WesternInt | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.3 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 3
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
| YNE2: M62 J23-24 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 10
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 20
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 1
|  |  | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 23
| YNE20: A63 Western Int - Priory Way | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1
| YNE25: A63 Garrison - Southcoates | 4.6.3 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 1
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1
| YNE26: A1033 Southcoates - Northern Gate | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2
| YNE27: A1033 Northern Gate - Marfleet | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2
| YNE28: A1033 Marfleet - Somerden | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3
| YNE29: A1033 Somerden - Salt End | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 3
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 3
| YNE3: M62 J24-25 | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 4
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 4
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 19
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 5
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 5
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 5
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 20
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 23
| YNE30: M606 J1-2 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 8
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 9
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 3
| YNE31: M606 J2-3 | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6
| YNE32: M621 Gildersome - J1 | 4.6.1.1 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 1
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 9
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 2
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 2
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 2
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 11
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6
| YNE4: M62 J25-26 | 4.6.11 | Ramp Metering Traffic Light Signals - Check alignment and condition of site | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 17
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 5
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 5
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 5
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 4
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 7
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 13
| YNE5: M62 J26-27 | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 17
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 4
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 4
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 4
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 5
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 5
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 5
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 11
| YNE54: A64 Pickering Int - Brambling | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE6: M62 J27-28 | 4.6.1.1 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 31
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 13
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 8
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 8
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 8
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 7
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 6
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 6
| YNE62: M1 J31-32 | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 5336
| YNE63: M1 J32-33 | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 13603
| YNE7: M62 J28-29 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 9884.49
|  | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 238.2
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 167
|  |  | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 141
|  | 4.3.2.1 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 1565
|  | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 5855.11
|  | 4.3.3.1 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 66
|  | 4.3.3.3 | G&CD - Clear Weed/vegetation growth and debris, clear, recut Counterfort drains | 18
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 106
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 17
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 35
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 81
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 40
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 14
|  | 4.5.8 | BC - Lamps (LED) for Illuminated Signs and Bollards | 1
|  | 4.6.1.1 | CCTV - Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using WashWipe | 11
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 26
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 6
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 6
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 6
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 7
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 7
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 7
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 11
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 3
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 16
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 23998.5
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 6533
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 35283
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 5916
| YNE8: M62 J29-31 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 9089.6
|  | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3540.59
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 441
|  | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 2310
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 203
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 77
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 8
|  | 4.4.1.3 | Traffic Signs - Clean all traffic sign faces and reference numbers of all Gantry Signs | 5
|  | 4.4.2 | Marker Posts - Clean all marker post faces and reference numbers | 104
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 3
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 83
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 25
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 6
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 6
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 6
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 15
|  | 4.8.17 | Wildlife structures and tunnels - Remove all material that could impair operation | 1
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 20550.5
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 2 - ILM | 2834
| YNE9: M62 J31-32 | 4.2.1 | VRS - Check all Road Restraint System - ILM | 4804.02
|  | 4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2522.15
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 43
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 16
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 5
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 5
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 5
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 8
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 11
| YNE91: M180 J1-2 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 4
|  | 4.8.17 | Wildlife structures and tunnels - Remove all material that could impair operation | 2
| YNE92: M180 J2-3 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 27
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 9924.1667
| YNE94: M180 J4-5 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 5
| YNE96: A180 Barnetby - Brocklesby | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 831.11
|  |  | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 831.11
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 19
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 17
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1
| YNE97: A180 Brocklesby - Stallingborough | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1204.27
|  |  | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 1204.27
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 6
|  | 4.8.17 | Wildlife structures and tunnels - Remove all material that could impair operation | 1
| YNE98: A180 Stallingborough - Great Coates | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 2
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 217
| YNE99: A180 Great Coates - Pyewipe | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 23
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
| YNE11: M62 J33-34 (actually J32a-33) | 4.3.1.1 | Gullies - Emptying / clear covers | 72
|  | 4.3.4 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 52
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 11286.25
2024-02-29 | YNE43: A64 A162 - Tadcaster | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 1615.21
| YNE44: A64 Tadcaster - Bilbrough | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 635.53
| YNE48: A64 Fulford - Grimston | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 5556.82
| YNE49: A64 Grimston - Hopgrove | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 3267.48
| YNE61: M1 J30-31 | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 10
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 8
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 8
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 8
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 8
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 8
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 8
| YNE62: M1 J31-32 | 4.3.1.1 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 24
|  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 3
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 3
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 9
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 9
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 9
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 8
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 8
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 8
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2660
| YNE63: M1 J32-33 | 4.3.1.1 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 53
|  | 4.5.7 | BC - Lamps (LED) for Road Lighting | 3
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 6
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 2
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 2
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 2
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 3
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 3
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 3
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 3
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 6795
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 18677
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9261
| YNE64: M1 J33-34 South | 4.3.1.1 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 4
|  | 4.5.7 | BC - Lamps (LED) for Road Lighting | 2
|  | 4.5.8 | BC - Lamps (LED) for Illuminated Signs and Bollards | 1
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 14
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 11
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 9
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 12
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 12
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 12
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 12
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 12
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 12
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7532
| YNE65: M1 Tinsley | 4.3.2.1 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 2 - ILM | 74
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 5
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2104
| YNE66: M1 J34 North - 35 | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 892.27
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 4
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 11
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 31
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 20
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 20
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 20
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 19
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 19
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 19
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 8
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8159
| YNE67: M1 J35-35a | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 1
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2546
| YNE68: M1 J35a-36 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 5
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N]
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1056
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 8315
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1944
| YNE69: M1 J36-37 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 3
|  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 2
| YNE70: M1 J37-38 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 5
| YNE71: M1 J38-39 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 3
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 1
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 4 - ILM | 1515
| YNE72: M1 J39-40 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 1
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system
|  | 4.6.9 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N]
| YNE73: M1 J40-41 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 9
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N]
|  | 4.6.11 | Ramp Metering Traffic Light Signals - Check alignment and condition of site
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2
|  | 4.9.2 | Sweeping - Paved non-running areas - Full Sweep 02 | 23145
|  | 4.9.3 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 11771
|  | 4.9.4 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 22002
|  | 4.9.5 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7413
| YNE77: A628 Crowden - Flouch | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE85: M18 J2-3 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 2495.94
| YNE86: M18 J3-4 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 11378.63
|  | 4.8.2 | Woodland - Thin / coppice | 161474
| YNE87: M18 J4-5 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 7422.6
|  | 4.8.2 | Woodland - Thin / coppice | 26629
| YNE88: M18 J5-6 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 4825.7
| YNE89: M18 J6-7 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 18866.84
2024-03-31 | YNE100: A160 Brocklesby - Habrough | 4.3.2.3 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 2 - ILM | 6113.31
| YNE101: A160 Habrough - Manby | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 3137.75
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 2
|  | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1
| YNE106: A1M J34-35 | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE107: A1M J35-36 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 4
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2
| YNE108: A1M J36-37 | 4.6.10.1 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2
|  | 4.6.10.2 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2
|  | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4
| YNE109: A1M J37-38 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 3
|  | 4.6.13.1 | CCTV PTZ Cameras - Clean camera lens | 1
|  | 4.6.13.2 | CCTV PTZ Cameras - Check camera functionality | 1
|  | 4.6.13.3 | CCTV PTZ Cameras - Check data and power supplies | 1
|  | 4.6.2.1 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2
|  | 4.6.2.2 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2
|  | 4.6.2.3 | CCTV Masts - Check mast breaking system | 2
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 4
| YNE113: A1 Darrington - A162 | 4.6.12.2 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1
|  | 4.6.4 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2
| YNE12: M62 J34-35 | 4.3.1.1 | Gullies - Emptying / clear covers | 22
| YNE15: M62 J37-38 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 4219.54
| YNE16: A63 North Cave - South Cave | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 995.92
| YNE24: A63 Mytongate - Garrison | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 223
| YNE25: A63 Garrison - Southcoates | 4.2.1 | VRS - Check all Road Restraint System - ILM | 4499.99
|  | 4.3.1.1 | Gullies - Emptying / clear covers | 1
|  | 4.3.2.1 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System | 4120
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 1816.02
|  | 4.3.3.1 | G&CD - Clear weed / vegetation growth and debris, clear, recut drainage Grip inlet and non-piped drainage Grip | 24
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 57
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 5
|  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 90
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 105
|  | 4.8.9 | Grassland (Open Grassland) - Maintain habitat integrity, including removal of scrub encroachment | 781
| YNE26: A1033 Southcoates - Northern Gate | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 1174.23
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 94
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 1
|  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 11
| YNE27: A1033 Northern Gate - Marfleet | 4.3.1.1 | Gullies - Emptying / clear covers | 3
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 636.41
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 60
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 3
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 17
|  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 2
| YNE28: A1033 Marfleet - Somerden | 4.3.1.1 | Gullies - Emptying / clear covers | 15
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 988.94
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 146
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 6
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 1
| YNE29: A1033 Somerden - Salt End | 4.3.1.1 | Gullies - Emptying / clear covers | 2
|  | 4.3.2.2 | LDS - Cleaning, rodding, jetting and proving Linear Drainage Channel (slot drains) | 640.22
|  | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 3038.48
|  | 4.4.1.1 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 80
|  | 4.4.1.2 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 1
| YNE84: M18 J1-2 | 4.8.2 | Woodland - Thin / coppice | 175011
| YNE85: M18 J2-3 | 4.8.2 | Woodland - Thin / coppice | 6873
| YNE87: M18 J4-5 | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE91: M180 J1-2 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 16569.86
| YNE92: M180 J2-3 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 9197.33
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE93: M180 J3-4 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 15252.95
|  | 4.4.3 | Bollards - Clean all illuminated and non-illuminated bollards | 15
| YNE94: M180 J4-5 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 7414.67
|  | 4.6.7 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 2
| YNE95: M181 | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 41.66
| YNE96: A180 Barnetby - Brocklesby | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 5055.49
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE97: A180 Brocklesby - Stallingborough | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 2960.83
| YNE98: A180 Stallingborough - GreatCoates | 4.6.12.1 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1
|  | 4.6.5 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 1
| YNE83: M18 Link-J1 | 4.8.2 | Woodland - Thin / coppice | 133349
| YNE45: A64 Bilbrough-Askham | 4.3.5 | Ditches - Clean ditches by removing all material that could impair operation | 448.63
Total Result |  |  |  | 1720243.7012

## DPCache_2023-24 Service Program (hidden)
Concatinate+A2:X2 (formula) | Unique ID | Activity Name | TM Cost Allocation (formula) | ScAR | A Number | Cost (formula) | Margin (formula) | Resource (formula) | Asset Type | Actual Start | Actual Start Month (formula) | Actual Finish | Planned Start | Planned Finish | Rebaselined SP New Planned Finish | Rebaselined SP Roadspace Comment | Original Duration | Direction | H.E. Asset Quantity | Asset Quantity Completed | Asset Quantity Remaining | Activity Progress | Night Report Information | Excluded Y/N | CPF Comment | Area 12 Chart Section | Area 12 Maintenance Segments | Area 12 TM Reference | Traffic Management Layout | Yearly Pass 1-6 | TM Needed? | Shift | Intervention Period | Taper MP (formula) | End MP (formula) | Confirm Job Number | Shift Start (formula) | Shift Finish (formula) | Shift (formula) | Road Space Status (formula) | Comments
YNE1 Closure 1 EB NS Bettamix 45048 VRS - Carry out bolt and weld check and clean cattlegrid to remove detritus. CEMAR GC332 - ILM | 1 | VRS - Carry out bolt and weld check and clean cattlegrid to remove detritus. CEMAR GC332 - ILM |  | TBC | 0 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 1 | 0 | 1 | 0 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | ILM Annually |  |  | 52033795
YNE1 Closure 1 WB NS Bettamix 45048 VRS - Carry out bolt and weld check and clean cattlegrid to remove detritus. CEMAR GC332 - ILM | 2 | VRS - Carry out bolt and weld check and clean cattlegrid to remove detritus. CEMAR GC332 - ILM |  | TBC | 0 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1 | 0 | 1 | 0 |  | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | ILM Annually |  |  | 52033796
YNE1 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 3 | VRS - Check all Road Restraint System - ILM | 2.3049 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 179.14 | 179.14 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 4 | VRS - Check all Road Restraint System - ILM | 2.935 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 228.11 | 228.11 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 3 | VRS - Check all Road Restraint System - ILM | 8.0244 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 623.67 | 623.67 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 4 | VRS - Check all Road Restraint System - ILM | 2.6739 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 207.82 | 207.82 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 3 | VRS - Check all Road Restraint System - ILM | 3.3525 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 260.56 | 260.56 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 4 | VRS - Check all Road Restraint System - ILM | 7.0651 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 549.11 | 549.11 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 3 | VRS - Check all Road Restraint System - ILM | 5.8491 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 454.6 | 454.6 | 0 | 1 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 4 | VRS - Check all Road Restraint System - ILM | 5.6485 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 439.01 | 439.01 | 0 | 1 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 3 | VRS - Check all Road Restraint System - ILM | 23.0121 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1788.54 | 1788.54 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 4 | VRS - Check all Road Restraint System - ILM | 17.2072 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1337.37 | 1337.37 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 3 | VRS - Check all Road Restraint System - ILM | 23.8539 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1853.97 | 1853.97 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 4 | VRS - Check all Road Restraint System - ILM | 21.0304 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1634.52 | 1634.52 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 5 | VRS - Check all Road Restraint System - ILM | 14.8781 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1156.35 | 1156.35 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 6 | VRS - Check all Road Restraint System - ILM | 5.4153 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 420.89 | 420.89 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 5 | VRS - Check all Road Restraint System - ILM | 3.2401 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 251.83 | 251.83 | 0 | 1 |  | N |  | 4700M62/308 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 5 | VRS - Check all Road Restraint System - ILM | 16.8137 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1306.79 | 1306.79 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 6 | VRS - Check all Road Restraint System - ILM | 0.56767 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 44.12 | 44.12 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 7 | VRS - Check all Road Restraint System - ILM | 14.0365 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1090.94 | 1090.94 | 0 | 1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 8 | VRS - Check all Road Restraint System - ILM | 1.2423 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 96.55 | 96.55 | 0 | 1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 7 | VRS - Check all Road Restraint System - ILM | 22.0798 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1716.08 | 1716.08 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 8 | VRS - Check all Road Restraint System - ILM | 3.4123 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 265.21 | 265.21 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 7 | VRS - Check all Road Restraint System - ILM | 10.4991 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 816.01 | 816.01 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 8 | VRS - Check all Road Restraint System - ILM | 5.1494 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 400.22 | 400.22 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 7 | VRS - Check all Road Restraint System - ILM | 0.21924 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17.04 | 17.04 | 0 | 1 |  | N |  | 4700M62/315 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 8 | VRS - Check all Road Restraint System - ILM | 3.453 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 268.37 | 268.37 | 0 | 1 |  | N |  | 4700M62/315 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 7 | VRS - Check all Road Restraint System - ILM | 3.9161 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 304.37 | 304.37 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 8 | VRS - Check all Road Restraint System - ILM | 1.4498 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 112.68 | 112.68 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 9 | VRS - Check all Road Restraint System - ILM | 5.2478 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 407.87 | 407.87 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 10 | VRS - Check all Road Restraint System - ILM | 10.3156 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 801.75 | 801.75 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 9 | VRS - Check all Road Restraint System - ILM | 8.7148 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 677.33 | 677.33 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 10 | VRS - Check all Road Restraint System - ILM | 4.8925 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 380.25 | 380.25 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 9 | VRS - Check all Road Restraint System - ILM | 26.586 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2066.31 | 2066.31 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 10 | VRS - Check all Road Restraint System - ILM | 26.1098 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2029.3 | 2029.3 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 9 | VRS - Check all Road Restraint System - ILM | 14.0841 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1094.64 | 1094.64 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 10 | VRS - Check all Road Restraint System - ILM | 13.1273 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1020.28 | 1020.28 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 11 | VRS - Check all Road Restraint System - ILM | 16.6854 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1296.82 | 1296.82 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 12 | VRS - Check all Road Restraint System - ILM | 17.3986 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1352.25 | 1352.25 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 11 | VRS - Check all Road Restraint System - ILM | 2.4999 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 194.3 | 194.3 | 0 | 1 |  | N |  | 4700M62/488 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 12 | VRS - Check all Road Restraint System - ILM | 3.2161 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 249.96 | 249.96 | 0 | 1 |  | N |  | 4700M62/488 | YNE1: M62 J22-23 | YNE1 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 11 | VRS - Check all Road Restraint System - ILM | 14.2348 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1106.35 | 1106.35 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 12 | VRS - Check all Road Restraint System - ILM | 14.3234 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1113.24 | 1113.24 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 13 | VRS - Check all Road Restraint System - ILM | 23.3958 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1818.36 | 1818.36 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 14 | VRS - Check all Road Restraint System - ILM | 23.2819 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1809.51 | 1809.51 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 13 | VRS - Check all Road Restraint System - ILM | 24.3061 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1889.11 | 1889.11 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 14 | VRS - Check all Road Restraint System - ILM | 23.9446 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1861.02 | 1861.02 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 13 | VRS - Check all Road Restraint System - ILM | 7.9325 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 616.53 | 616.53 | 0 | 1 |  | N |  | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 14 | VRS - Check all Road Restraint System - ILM | 7.8462 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 609.82 | 609.82 | 0 | 1 |  | N |  | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 13 | VRS - Check all Road Restraint System - ILM | 7.09 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 551.05 | 551.05 | 0 | 1 |  | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 14 | VRS - Check all Road Restraint System - ILM | 3.955 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 307.39 | 307.39 | 0 | 1 |  | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 13 | VRS - Check all Road Restraint System - ILM | 3.9379 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 306.06 | 306.06 | 0 | 1 |  | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 14 | VRS - Check all Road Restraint System - ILM | 7.8367 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 609.08 | 609.08 | 0 | 1 |  | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 13 | VRS - Check all Road Restraint System - ILM | 1.8926 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 147.1 | 147.1 | 0 | 1 |  | N |  | 4700M62/496 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 14 | VRS - Check all Road Restraint System - ILM | 2.3583 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 183.29 | 183.29 | 0 | 1 |  | N |  | 4700M62/496 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 15 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-18 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 5 | 5 | 0 | 1 | 16 more gullies than on plan | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45785223
YNE1 Closure 3 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 16 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE1 Closure 3 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 17 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE1 Closure 3 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 16 | Gullies - Emptying / clear covers | 293.3542 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 62 | 38 | 0 | 0.6129 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45785223
YNE1 Closure 3 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 17 | Gullies - Emptying / clear covers | 77.1985 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE1 Closure 3 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 17 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/315 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45785223
YNE1 Closure 3 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 16 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE1 Closure 3 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 17 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE1 Closure 3 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 18 | Gullies - Emptying / clear covers | 216.1557 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 115 | 28 | 0 | 0.24348 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45785223
YNE1 Closure 3 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 19 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE1 Closure 3 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 18 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE1 Closure 3 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 19 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE1 Closure 3 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 18 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE1 Closure 3 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 18 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE1 Closure 2 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 20 | Gullies - Emptying / clear covers | 231.5954 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 30 | 30 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE1 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 21 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 1 | 0 | 1 | 0 | 18/9: cancelled heavy rain | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | ] | 1 |  |  | Every 2 years |  |  | 45785223
YNE1 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 22 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 28.211 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1145 | 1145 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE1 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 23 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.4638 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 100 | 100 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE1 Closure 3 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 24 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.9132 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 240 | 240 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE1 Closure 3 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 25 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.3974 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 422 | 422 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE1 Closure 3 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 26 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.7247 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 70 | 70 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE1 Closure 3 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 26 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.496 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 426 | 426 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE1 Closure 3 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 27 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.774 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 72 | 72 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE1 Closure 3 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 26 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 14.1671 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 575 | 575 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE1 Closure 2 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 28 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.0203 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 82 | 82 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE1 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 29 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 71.9613 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 932.16 | 932.16 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 29 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 15.8813 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 205.72 | 205.72 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 30 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 69.4323 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 899.4 | 899.4 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 4 - 3 - 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 2 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 31 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 45.93 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 594.96 | 594.96 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB OS | Lane 2 & 3 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 3 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 32 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 76.621 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 992.52 | 992.52 | 0 | 1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 3 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 32 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1.378 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17.85 | 17.85 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 3 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 32 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1.9724 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 25.55 | 25.55 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 3 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 33 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 77.2996 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1001.31 | 1001.31 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 3 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 3 WB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 34 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 37.4189 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 484.71 | 484.71 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 2 WB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 35 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 24.4874 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 317.2 | 317.2 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 1 WB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 36 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 57.0528 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 739.04 | 739.04 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 37 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 49.2001 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 637.32 | 637.32 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE1 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 38 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 364.5483 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-18 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 17 | 17 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 39 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 0 | 1 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 38 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 38 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 38 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 40 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 557.5445 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-17 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 26 | 26 | 0 | 1 | 17/11 no catchpits but 34 hullies emptied | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure 2 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 40 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/308 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 40 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 41 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 30 | 3 | 0 | 0.1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure 3 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 43 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure 3 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 43 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/315 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 43 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure 3 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 44 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 300.2163 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 14 | 14 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 3 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 44 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 428.8804 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 71 | 20 | 0 | 0.28169 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure 3 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 45 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure 3 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 44 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 46 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 686.2086 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-17 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 32 | 32 | 0 | 1 | 17/11 no catchpits but 34 hullies emptied | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure 2 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 47 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure 2 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 46 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/488 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 2 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 46 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 48 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE1 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 49 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 0 | 1 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791066
YNE1 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 50 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 252.9254 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 5276 | 5276 | 0 | 1 |  | N |  |  | YNE1: M62 J22-23 | YNE1 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 51 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 52 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 | 18/9: cancelled heavy rain |  |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037063
YNE1 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 53 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 | 18/9: cancelled heavy rain |  |  |  | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037063
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 54 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 54 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 55 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 56 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 57 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 58 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 25 | 25 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 91.0838 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 38 | 38 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 93.4807 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 39 | 39 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 60 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 20 | 20 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 60 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/308 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 60 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 61 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 15 | 15 | 0 | 1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 61 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 91.0838 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 38 | 38 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 61 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 61 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/315 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 61 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 19 | 19 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 32 | 32 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 63 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 63 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/488 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 63 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 21 | 21 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 88.6869 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 37 | 37 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 151.0074 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 63 | 63 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 20 | 20 | 0 | 1 |  | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/496 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 65 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 95.8777 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 66 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 66 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 66 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 66 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 66 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 92.6889 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 21 | 21 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 66 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 67 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 52.9651 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 67 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/308 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 67 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 68 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 68 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 70.6201 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 68 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 68 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 69 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 69 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 70 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 71 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 72 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.60998 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 29.45 | 29.45 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 73 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.29163 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 14.08 | 14.08 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 74 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.0816 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 178 | 178 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 74 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.2717 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 605 | 605 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 74 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.1559 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 671 | 671 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 74 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.7048 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 410 | 410 | 0 | 1 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 74 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 45.8199 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1605 | 1605 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 74 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 47.7041 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1671 | 1671 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 75 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.6616 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1039 | 1039 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 75 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.4234 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 225 | 225 | 0 | 1 |  | N |  | 4700M62/308 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 75 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.6861 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1215 | 1215 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 76 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.4055 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 995 | 995 | 0 | 1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 76 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 43.2506 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1515 | 1515 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 76 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.2684 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 745 | 745 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 76 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.9087 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 242 | 242 | 0 | 1 |  | N |  | 4700M62/315 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 76 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.5555 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 685 | 685 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 77 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.4405 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 716 | 716 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 77 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.9829 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 735 | 735 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 77 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 52.1862 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1828 | 1828 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 3 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 77 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.434 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 996 | 996 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 78 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.7432 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1217 | 1217 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 78 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.3092 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 221 | 221 | 0 | 1 |  | N |  | 4700M62/488 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 78 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.4055 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 995 | 995 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 79 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 46.7049 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1636 | 1636 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 79 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 48.7033 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1706 | 1706 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 79 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.8443 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 555 | 555 | 0 | 1 |  | N |  | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 79 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.0139 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 631 | 631 | 0 | 1 |  | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 79 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5588 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 545 | 545 | 0 | 1 |  | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 79 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.5392 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 159 | 159 | 0 | 1 |  | N |  | 4700M62/496 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE1 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 80 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 58.3356 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 649 | 649 | 0 | 1 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 & 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 80 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 69.8625 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 777.24 | 777.24 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 2 & 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 81 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 232.6844 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2588.68 | 2588.68 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 81 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 322.7351 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3590.52 | 3590.52 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 82 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 140.4153 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1562.16 | 1562.16 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 83 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 212.3847 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2362.84 | 2362.84 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 83 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 652.1091 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7254.9 | 7254.9 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 83 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 202.7112 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2255.22 | 2255.22 | 0 | 1 |  | N |  | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 84 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 4.8329 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 70 | 70 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 84 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 194.2128 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2813 | 2813 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 85 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 152.0287 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2202 | 2202 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 3 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 85 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 7.2493 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 105 | 105 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 2 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 86 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 12.4274 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 180 | 180 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 87 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 35.7633 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 518 | 518 | 0 | 1 |  | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE1 Closure 1 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 88 | Sweeping - Paved non-running areas - Full Sweep 01 | 54.058 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7257.85 | 7257.85 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE1 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 89 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 329.268 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13737 | 13737 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE1 Closure 1 EB OS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 90 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 329.268 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13737 | 13737 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB OS | Lane 3 Closure | 1 |  |  | Annually
YNE1 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 91 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1032.6986 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 21542 | 21542 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE1 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 92 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.329 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 178 | 178 | 0 | 1 |  | N |  | 4700M62/301 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 93 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.9161 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 605 | 605 | 0 | 1 |  | N |  | 4700M62/302 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE1 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 92 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.7797 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 671 | 671 | 0 | 1 |  | N |  | 4700M62/303 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 92 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.8564 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1059 | 1059 | 0 | 1 |  | N |  | 4700M62/304 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 92 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 31.1803 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2383 | 2383 | 0 | 1 |  | N |  | 4700M62/305 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE1 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 92 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.8641 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1671 | 1671 | 0 | 1 |  | N |  | 4700M62/306 | YNE1: M62 J22-23 | YNE1 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 2 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 94 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.5948 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1039 | 1039 | 0 | 1 |  | N |  | 4700M62/307 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 2 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 94 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.944 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 225 | 225 | 0 | 1 |  | N |  | 4700M62/308 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE1 Closure 2 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 94 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.8976 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1215 | 1215 | 0 | 1 |  | N |  | 4700M62/309 | YNE1: M62 J22-23 | YNE1 Closure 2 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 3 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 95 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.019 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 995 | 995 | 0 | 1 |  | N |  | 4700M62/311 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 3 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 95 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 19.823 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1515 | 1515 | 0 | 1 |  | N |  | 4700M62/313 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE1 Closure 3 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 95 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.7479 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 745 | 745 | 0 | 1 |  | N |  | 4700M62/314 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 3 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 95 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.1664 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 242 | 242 | 0 | 1 |  | N |  | 4700M62/315 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 3 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 96 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.9629 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 685 | 685 | 0 | 1 |  | N |  | 4700M62/316 | YNE1: M62 J22-23 | YNE1 Closure 3 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE1 Closure 3 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 97 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 43.231 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3304 | 3304 | 0 | 1 |  | N |  | 4700M62/483 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 3 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 98 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 9.6171 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 735 | 735 | 0 | 1 |  | N |  | 4700M62/484 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE1 Closure 3 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 97 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 70.8916 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5418 | 5418 | 0 | 1 |  | N |  | 4700M62/485 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 3 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 97 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.0321 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 996 | 996 | 0 | 1 |  | N |  | 4700M62/486 | YNE1: M62 J22-23 | YNE1 Closure 3 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 2 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 99 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.9238 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1217 | 1217 | 0 | 1 |  | N |  | 4700M62/487 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 2 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 99 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.8917 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 221 | 221 | 0 | 1 |  | N |  | 4700M62/488 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE1 Closure 2 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 99 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 33.47 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2558 | 2558 | 0 | 1 |  | N |  | 4700M62/489 | YNE1: M62 J22-23 | YNE1 Closure 2 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE1 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 100 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 52.3247 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3999 | 3999 | 0 | 1 |  | N |  | 4700M62/490 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE1 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 100 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 117.2367 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8960 | 8960 | 0 | 1 |  | N |  | 4700M62/491 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE1 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 100 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 36.7804 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2811 | 2811 | 0 | 1 |  | N |  | 4700M62/493 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE1 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 101 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.2563 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 631 | 631 | 0 | 1 |  | N |  | 4700M62/494 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE1 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 100 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.131 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 545 | 545 | 0 | 1 |  | N |  | 4700M62/495 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE1 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 100 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.0804 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 159 | 159 | 0 | 1 |  | N |  | 4700M62/496 | YNE1: M62 J22-23 | YNE1 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE2 Closure 2 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 102 | VRS - Check all Road Restraint System - ILM | 13.2022 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1026.1 | 1026.1 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 2 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 103 | VRS - Check all Road Restraint System - ILM | 38.5992 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 195.62 | 3000 | -2804.38 | 15.3359 | 15/9: 3000 Meters of barrier Checked. Job closed and commercial informed | Y |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028542
YNE2 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 104 | VRS - Check all Road Restraint System - ILM | 2.0158 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 156.67 | 156.67 | 0 | 1 |  | N |  | 4700M62/318 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 104 | VRS - Check all Road Restraint System - ILM | 1.9529 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 151.78 | 151.78 | 0 | 1 |  | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 105 | VRS - Check all Road Restraint System - ILM | 0.80248 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 62.37 | 62.37 | 0 | 1 |  | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 104 | VRS - Check all Road Restraint System - ILM | 10.1283 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 787.19 | 787.19 | 0 | 1 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 105 | VRS - Check all Road Restraint System - ILM | 3.4172 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 265.59 | 265.59 | 0 | 1 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 104 | VRS - Check all Road Restraint System - ILM | 5.5212 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 429.12 | 429.12 | 0 | 1 |  | N |  | 4700M62/321 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 105 | VRS - Check all Road Restraint System - ILM | 8.7202 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 677.75 | 677.75 | 0 | 1 |  | N |  | 4700M62/321 | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 106 | VRS - Check all Road Restraint System - ILM | 2.8608 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 222.35 | 222.35 | 0 | 1 |  | N |  | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 107 | VRS - Check all Road Restraint System - ILM | 3.2737 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 254.44 | 254.44 | 0 | 1 |  | Y |  | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028542
YNE2 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 106 | VRS - Check all Road Restraint System - ILM | 4.8459 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 376.63 | 376.63 | 0 | 1 |  | N |  | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 107 | VRS - Check all Road Restraint System - ILM | 7.9706 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 619.49 | 619.49 | 0 | 1 |  | Y |  | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028542
YNE2 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 106 | VRS - Check all Road Restraint System - ILM | 12.0035 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 932.93 | 932.93 | 0 | 1 |  | N |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 107 | VRS - Check all Road Restraint System - ILM | 3.1048 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 241.31 | 241.31 | 0 | 1 |  | Y |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028542
YNE2 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 107 | VRS - Check all Road Restraint System - ILM | 1.8975 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 147.48 | 147.48 | 0 | 1 |  | Y |  | 4700M62/480 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028542
YNE2 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 106 | VRS - Check all Road Restraint System - ILM | 2.9531 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 229.52 | 229.52 | 0 | 1 |  | N |  | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 107 | VRS - Check all Road Restraint System - ILM | 2.9218 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 227.09 | 227.09 | 0 | 1 |  | Y |  | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028542
YNE2 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 106 | VRS - Check all Road Restraint System - ILM | 13.2689 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1031.28 | 1031.28 | 0 | 1 |  | N |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 107 | VRS - Check all Road Restraint System - ILM | 12.3413 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 959.19 | 959.19 | 0 | 1 |  | Y |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028542
YNE2 Closure 2 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 108 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 131.2374 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 | 15/9: 22 suspended west 4 completed 41 suspended East 3 completed 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | Y |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45783285
YNE2 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 109 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 277.9145 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-22 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 31 | 36 | -5 | 1.1613 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45783285
YNE2 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 110 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 6 | 0 | 6 | 0 | 20/11 no crews allocated | N |  | 4700M62/318 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45783285
YNE2 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 110 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 7 | 0 | 7 | 0 | 20/11 no crews allocated | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45783285
YNE2 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 111 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 28 | 0 | 28 | 0 | 20/11 no crews allocated | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 112 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP |  | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 46 | 3 | 43 | 0.065217 | 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 111 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 17 | 0 | 17 | 0 | 20/11 no crews allocated | N |  | 4700M62/321 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 112 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 | 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | N |  | 4700M62/321 | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 111 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 2 | 0 | 2 | 0 | 20/11 no crews allocated | N |  | 4700M62/322 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 112 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 | 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | N |  | 4700M62/322 | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 113 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 8 | 0 | 8 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 114 | Gullies - Emptying / clear covers | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 | 15/9: 22 suspended west 4 completed 41 suspended East 3 completed 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | Y |  | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 113 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 14 | 0 | 14 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 114 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 | 15/9: 22 suspended west 4 completed 41 suspended East 3 completed 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | Y |  | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 113 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 15 | 0 | 15 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 114 | Gullies - Emptying / clear covers | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 14 | 14 | 0 | 1 | 15/9: 22 suspended west 4 completed 41 suspended East 3 completed 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | Y |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 114 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 | 15/9: 22 suspended west 4 completed 41 suspended East 3 completed 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | Y |  | 4700M62/480 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 114 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 | 15/9: 22 suspended west 4 completed 41 suspended East 3 completed 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | Y |  | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 113 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 25 | 0 | 25 | 0 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 114 | Gullies - Emptying / clear covers | 162.1168 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 21 | 21 | 0 | 1 | 15/9: 22 suspended west 4 completed 41 suspended East 3 completed 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | Y |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783285
YNE2 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 115 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.4595 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 181 | 181 | 0 | 1 |  | N |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE2 Closure 2 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 116 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-22 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791223
YNE2 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 117 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 | 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791223
YNE2 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 118 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 857.7607 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 44 | 40 | 4 | 0.90909 | 20/11 no crews allocated | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791223
YNE2 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 117 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 | 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791223
YNE2 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 119 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 600.4325 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 41 | 28 | 13 | 0.68293 | 23/11 cancelled due to strong winds | Y | Unable to access due to scheme works until April 2024 | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791223
YNE2 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 120 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 |  | 5 | 1 | 15/9: Catch pits on near side 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | Y |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791223
YNE2 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 119 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE2 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 120 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 |  | 4 | 1 | 15/9: Catch pits on near side 13/9: assets not on tablets and Enviro wouldn't do as not on tablets | Y |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791223
YNE2 Closure Amey 45048 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 121 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE2 Closure Amey 45048 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 122 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE2 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 123 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 61.5535 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1284 | 1284 | 0 | 1 |  | N |  |  | YNE2: M62 J23-24 | YNE2 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 124 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 125 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 126 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 127 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 128 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 19 | 19 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 129 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/318 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 129 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 129 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 29 | 29 | 0 | 1 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 129 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/321 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 129 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/322 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 130 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 130 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 130 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 130 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 130 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 2 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 131 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 155.8012 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 26 | 26 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 132 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 133 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 133 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 70.6201 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 134 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.57249 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 27.64 | 27.64 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 135 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.45754 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 22.09 | 22.09 | 0 | 1 |  | N |  | 4700M62/322 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 136 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 15.6824 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 757.15 | 757.15 | 0 | 1 |  | N |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 136 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.57539 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 27.78 | 27.78 | 0 | 1 |  | N |  | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 136 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.2171 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 107.04 | 107.04 | 0 | 1 |  | N |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 137 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.9503 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 909 | 909 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 138 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.3679 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 153 | 153 | 0 | 1 |  | N |  | 4700M62/318 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 138 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.854 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 135 | 135 | 0 | 1 |  | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 138 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.0955 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 809 | 809 | 0 | 1 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 138 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.1575 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 601 | 601 | 0 | 1 |  | N |  | 4700M62/321 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 138 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.5946 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 231 | 231 | 0 | 1 |  | N |  | 4700M62/322 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 139 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.4234 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 225 | 225 | 0 | 1 |  | N |  | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 139 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9299 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 558 | 558 | 0 | 1 |  | N |  | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 139 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 26.2929 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 921 | 921 | 0 | 1 |  | N |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 139 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.854 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 135 | 135 | 0 | 1 |  | N |  | 4700M62/480 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 139 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.7953 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 203 | 203 | 0 | 1 |  | N |  | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 139 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.6649 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 899 | 899 | 0 | 1 |  | N |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE2 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 140 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 132.5962 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1475.17 | 1475.17 | 0 | 1 |  | Y |  | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 140 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 9.2159 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 102.53 | 102.53 | 0 | 1 |  | Y |  | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 140 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 28.4307 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 316.3 | 316.3 | 0 | 1 |  | Y |  | 4700M62/480 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 140 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 245.1982 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2727.9 | 2727.9 | 0 | 1 |  | Y |  | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 140 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 43.6483 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 485.6 | 485.6 | 0 | 1 |  | Y |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE2 Closure 2 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 141 | Sweeping - Paved non-running areas - Full Sweep 01 | 92.6707 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12442 | 12442 | 0 | 1 |  | Y |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE2 Closure 2 EB NS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 142 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 593.2432 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 24750 | 24750 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE2 Closure 2 EB OS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 143 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 593.2432 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 24750 | 24750 | 0 | 1 | 15/9: complete | Y |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB OS | Lane 3 Closure | 1 |  |  | Annually |  |  | 52033923
YNE2 Closure 2 EB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 144 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 672.6299 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 14031 | 14031 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE2 Closure 2 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 145 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.8938 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 909 | 909 | 0 | 1 |  | N |  | 4700M62/317 | YNE2: M62 J23-24 | YNE2 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE2 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 146 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.0019 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 153 | 153 | 0 | 1 |  | N |  | 4700M62/318 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE2 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 146 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1.7664 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 135 | 135 | 0 | 1 |  | N |  | 4700M62/319 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE2 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 147 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 10.5853 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 809 | 809 | 0 | 1 |  | N |  | 4700M62/320 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE2 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 146 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.8638 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 601 | 601 | 0 | 1 |  | N |  | 4700M62/321 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE2 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 146 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.0225 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 231 | 231 | 0 | 1 |  | N |  | 4700M62/322 | YNE2: M62 J23-24 | YNE2 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE2 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 148 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 22.2436 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1700 | 1700 | 0 | 1 |  | N |  | 4700M62/474 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE2 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 148 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.6488 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 661 | 661 | 0 | 1 |  | N |  | 4700M62/476 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE2 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 149 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 12.0508 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 921 | 921 | 0 | 1 |  | N |  | 4700M62/478 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE2 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 148 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.9011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 451 | 451 | 0 | 1 |  | N |  | 4700M62/480 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE2 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 148 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 38.3505 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2931 | 2931 | 0 | 1 |  | N |  | 4700M62/481 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE2 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 148 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.122 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1385 | 1385 | 0 | 1 |  | N |  | 4700M62/482 | YNE2: M62 J23-24 | YNE2 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE3 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 150 | VRS - Check all Road Restraint System - ILM | 2.3856 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 185.41 | 185.41 | 0 | 1 |  | N |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 151 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 485.44 | 0 | 485.44 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 | 52028575 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 150 | VRS - Check all Road Restraint System - ILM | 1.0038 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 78.02 | 78.02 | 0 | 1 |  | N |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 150 | VRS - Check all Road Restraint System - ILM | 8.8493 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 687.78 | 687.78 | 0 | 1 |  | N |  | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 150 | VRS - Check all Road Restraint System - ILM | 16.3268 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1268.95 | 1268.95 | 0 | 1 |  | N |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 150 | VRS - Check all Road Restraint System - ILM | 19.0312 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1479.14 | 1479.14 | 0 | 1 |  | N |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 152 | VRS - Check all Road Restraint System - ILM | 21.9016 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1702.23 | 1702.23 | 0 | 1 |  | N |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 151 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | EB | 152.05 | 0 | 152.05 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 150 | VRS - Check all Road Restraint System - ILM | 3.301 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 256.56 | 256.56 | 0 | 1 |  | N |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 151 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | EB | 93.01 | 0 | 93.01 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 | 52028575 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 152 | VRS - Check all Road Restraint System - ILM | 0.050308 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3.91 | 3.91 | 0 | 1 |  | N |  | 4700M62/335 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 151 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | EB | 235.09 | 0 | 235.09 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/335 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 152 | VRS - Check all Road Restraint System - ILM | 3.1098 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 241.7 | 241.7 | 0 | 1 |  | N |  | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 151 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | EB | 343.81 | 0 | 343.81 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 153 | VRS - Check all Road Restraint System - ILM | 2.4884 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 193.4 | 193.4 | 0 | 1 |  | N |  | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 154 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 338.3 | 0 | 338.3 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 100/4 | 95/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 154 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 329.78 | 0 | 329.78 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/460 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 100/4 | 95/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 155 | VRS - Check all Road Restraint System - ILM | 4.1771 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 324.65 | 324.65 | 0 | 1 |  | N |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 2 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 153 | VRS - Check all Road Restraint System - ILM | 20.138 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1565.16 | 1565.16 | 0 | 1 |  | N |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 154 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 63.86 | 0 | 63.86 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 100/4 | 95/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 153 | VRS - Check all Road Restraint System - ILM | 17.957 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1395.65 | 1395.65 | 0 | 1 |  | N |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 155 | VRS - Check all Road Restraint System - ILM | 4.0298 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 313.2 | 313.2 | 0 | 1 |  | N |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 155 | VRS - Check all Road Restraint System - ILM | 14.6713 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1140.28 | 1140.28 | 0 | 1 |  | N |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 154 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 200.03 | 0 | 200.03 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 100/4 | 95/9 | 45917733 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 155 | VRS - Check all Road Restraint System - ILM | 2.4483 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 190.29 | 190.29 | 0 | 1 |  | N |  | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 154 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 635.54 | 0 | 635.54 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 100/4 | 95/9 | 45917733 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 156 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | EB | 2 | 0 | 2 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 95/5 | 101/1 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 157 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 3 | 0 | 3 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 95/3 | 100/9 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 157 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 35 | 5 | 30 | 0.14286 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 95/3 | 100/9 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 158 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | EB | 7 | 0 | 7 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 95/5 | 101/1 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 157 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 31 | 0 | 31 | 0 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 95/3 | 100/9 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 158 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | EB | 42 | 0 | 42 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 95/5 | 101/1 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 157 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 42 | 1 | 41 | 0.02381 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 95/3 | 100/9 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 158 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | EB | 2 | 0 | 2 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 95/5 | 101/1 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 159 | Gullies - Emptying / clear covers | 370.5526 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 48 | 48 | 0 | 1 |  | N |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE3 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 157 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 20 | 3 | 17 | 0.15 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 95/3 | 100/9 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 159 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/335 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE3 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 159 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE3 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 158 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | EB | 18 | 0 | 18 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 95/5 | 101/1 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 160 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 29 | 5 | 24 | 0.17241 |  | N |  | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE3 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 161 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 7 | 0 | 7 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 100/4 | 95/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 161 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 9 | 0 | 9 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/460 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 100/4 | 95/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 160 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 26 | 0 | 26 | 0 |  | N |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE3 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 162 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 208.4359 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 31 | 27 | 4 | 0.87097 |  | N |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE3 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 163 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 42 | 0 | 42 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 100/4 | 95/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 160 | Gullies - Emptying / clear covers | 378.2725 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 59 | 49 | 10 | 0.83051 |  | N |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE3 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 160 | Gullies - Emptying / clear covers | 293.3542 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 40 | 38 | 2 | 0.95 |  | N |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE3 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 161 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 2 | 0 | 2 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 100/4 | 95/9 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 160 | Gullies - Emptying / clear covers | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 45 | 22 | 23 | 0.48889 |  | N |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE3 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 161 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 6 | 0 | 6 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 100/4 | 95/9 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 160 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 5 | 0 | 5 | 0 |  | N |  | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE3 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 161 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-12-31 |  | 21dys | WB | 42 | 0 | 42 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 100/4 | 95/9 | 45783380 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 164 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 25.279 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1026 | 1026 | 0 | 1 |  | N |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 165 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-13 | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 270 | 0 | 270 | 0 |  | Y |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) | 95/5 | 101/1 | 52028601 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 164 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 20.7209 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 841 | 841 | 0 | 1 |  | N |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 165 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-13 | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1345 | 0 | 1345 | 0 |  | Y |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) | 95/5 | 101/1 | 52028601 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 166 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.6802 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 677 | 677 | 0 | 1 |  | N |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE3 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 167 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP |  | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1758 | 0 | 1758 | 0 |  | Y |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE3 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 164 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.9711 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 80 | 80 | 0 | 1 |  | N |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 165 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-13 | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 137 | 0 | 137 | 0 |  | Y |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) | 95/5 | 101/1 | 52028601 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 168 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.7595 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 112 | 112 | 0 | 1 |  | N |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE3 Closure 2 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 169 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 69.5295 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2822 | 2822 | 0 | 1 |  | N |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE3 Closure 2 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 169 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 39.52 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1604 | 1604 | 0 | 1 |  | N |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE3 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 170 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP |  | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 86 | 0 | 86 | 0 |  | Y |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE3 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 168 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 15.7439 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 639 | 639 | 0 | 1 |  | N |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE3 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 171 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-13 | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 567 | 0 | 567 | 0 |  | Y |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) | 100/4 | 95/9 | 52028601 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 168 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 37.1054 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1506 | 1506 | 0 | 1 |  | N |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE3 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 171 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-13 | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 865 | 0 | 865 | 0 |  | Y |  | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) | 100/4 | 95/9 | 52028601 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 172 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 | 45791124 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 172 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 | 45791124 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 172 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/327 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 | 45791124 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 173 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1329.5291 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 67 | 62 | 5 | 0.92537 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds - re-booked January | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 95/3 | 100/9 | 45791124 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 172 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 | 45791124 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 173 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 172 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 | 45791124 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 174 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 385.9923 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 2 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 175 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 173 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 172 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 95/5 | 101/1 | 45791124 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 174 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 2 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 175 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 2 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 176 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 177 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 2 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 178 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 578.9885 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 27 | 27 | 0 | 1 |  | N |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 2 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 176 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 2 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 178 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 2 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 176 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 177 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 343.1043 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 179 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 100/4 | 95/9 | 45791124 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 177 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE3 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 179 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 100/4 | 95/9 | 45791124 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 179 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 100/4 | 95/9 | 45791124 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE4 Closure Amey 45048 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 180 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 15.9796 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE4: M62 J25-26 | YNE4 Closure | Lane 1 Closure | 1 | Yes | Nights | 2 times per year |  |  | On ServiceNow
YNE3 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 181 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 152.829 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 3188 | 3188 | 0 | 1 |  | N |  |  | YNE3: M62 J24-25 | YNE3 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 182 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 95/5 | 101/1 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 183 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 184 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 100/4 | 95/9 | 52037023 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 185 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 185 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 95.8777 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 185 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 186 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 119.8471 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 185 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 187 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 187 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 187 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 187 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 74.3052 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 31 | 31 | 0 | 1 |  | N |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 187 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 74.3052 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 31 | 31 | 0 | 1 |  | N |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 188 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 127.0379 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 53 | 53 | 0 | 1 |  | N |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 187 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 22 | 22 | 0 | 1 |  | N |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 188 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 189 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 189 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/460 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 14 | 14 | 0 | 1 |  | N |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 189 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 83.893 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 35 | 35 | 0 | 1 |  | N |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 189 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 32 | 32 | 0 | 1 |  | N |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 21 | 21 | 0 | 1 |  | N |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 98.2746 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 41 | 41 | 0 | 1 |  | N |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 190 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 191 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 473.3961 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 79 | 79 | 0 | 1 |  | N |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 191 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 192 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 193 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 193 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 193 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 193 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 79.4476 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 193 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 83.8614 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 19 | 19 | 0 | 1 |  | N |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 194 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 83.8614 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 19 | 19 | 0 | 1 |  | N |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 193 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  | N |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 194 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 195 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.29991 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 14.48 | 14.48 | 0 | 1 |  | N |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 195 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.38256 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18.47 | 18.47 | 0 | 1 |  | N |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 196 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.62468 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 30.16 | 30.16 | 0 | 1 |  | N |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 197 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.1379 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 54.94 | 54.94 | 0 | 1 |  | N |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 196 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.38442 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 18.56 | 18.56 | 0 | 1 |  | N |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 196 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.19987 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9.65 | 9.65 | 0 | 1 |  | N |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 198 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.217 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 498 | 498 | 0 | 1 |  | N |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 198 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.3393 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 152 | 152 | 0 | 1 |  | N |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 198 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.3427 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1238 | 1238 | 0 | 1 |  | N |  | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 198 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.8133 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 659 | 659 | 0 | 1 |  | N |  | 4700M62/326 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 198 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.279 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 290 | 290 | 0 | 1 |  | N |  | 4700M62/327 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 198 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.0009 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1191 | 1191 | 0 | 1 |  | N |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 198 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 40.7669 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1428 | 1428 | 0 | 1 |  | N |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 199 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 45.1347 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1581 | 1581 | 0 | 1 |  | N |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 198 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.7602 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 482 | 482 | 0 | 1 |  | N |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 199 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.4234 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 225 | 225 | 0 | 1 |  | N |  | 4700M62/335 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 199 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.7929 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 308 | 308 | 0 | 1 |  | N |  | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 200 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.8499 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 310 | 310 | 0 | 1 |  | N |  | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 200 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.2504 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 289 | 289 | 0 | 1 |  | N |  | 4700M62/460 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 201 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.3589 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 538 | 538 | 0 | 1 |  | N |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 200 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 44.0785 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1544 | 1544 | 0 | 1 |  | N |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 200 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 41.9373 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1469 | 1469 | 0 | 1 |  | N |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 201 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.1534 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 776 | 776 | 0 | 1 |  | N |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 201 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 65.7751 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2304 | 2304 | 0 | 1 |  | N |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 201 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.3158 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1167 | 1167 | 0 | 1 |  | N |  | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE3 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 202 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 323.8703 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3603.15 | 3603.15 | 0 | 1 |  | Y |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 & 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 95/5 | 101/1 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 203 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 277.9039 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3091.76 | 3091.76 | 0 | 1 |  | Y |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB OS | Lane 2 & 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 2 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 203 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 70.933 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 789.15 | 789.15 | 0 | 1 |  | Y |  | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB OS | Lane 2 & 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 204 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 56.9334 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 633.4 | 633.4 | 0 | 1 |  | Y |  | 4700M62/460 | YNE3: M62 J24-25 | YNE3 Closure 2 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 204 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 28.9215 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 321.76 | 321.76 | 0 | 1 |  | Y |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 2 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE3 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 205 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 46.9318 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 522.13 | 522.13 | 0 | 1 |  | Y |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 100/4 | 95/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 205 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 322.763 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3590.83 | 3590.83 | 0 | 1 |  | Y |  | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 100/4 | 95/9 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 206 | Sweeping - Paved non-running areas - Full Sweep 01 | 20.6073 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2766.75 | 2766.75 | 0 | 1 |  | Y |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 207 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 83.9169 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3501 | 3501 | 0 | 1 |  | N |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB OS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 208 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 83.9169 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3501 | 3501 | 0 | 1 |  | Y |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually | 95/5 | 101/1 | 52033925 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 209 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 869.6107 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18140 | 18140 | 0 | 1 |  | N |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 210 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.5161 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 498 | 498 | 0 | 1 |  | N |  | 4700M62/323 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 211 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1.9888 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 152 | 152 | 0 | 1 |  | N |  | 4700M62/324 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 211 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 16.1986 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1238 | 1238 | 0 | 1 |  | N |  | 4700M62/325 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 211 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.6227 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 659 | 659 | 0 | 1 |  | N |  | 4700M62/326 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 210 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.7945 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 290 | 290 | 0 | 1 |  | N |  | 4700M62/327 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 210 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.5836 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1191 | 1191 | 0 | 1 |  | N |  | 4700M62/328 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 210 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 65.8279 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5031 | 5031 | 0 | 1 |  | N |  | 4700M62/329 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 212 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 61.1437 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4673 | 4673 | 0 | 1 |  | N |  | 4700M62/331 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE3 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 211 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.3067 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 482 | 482 | 0 | 1 |  | N |  | 4700M62/333 | YNE3: M62 J24-25 | YNE3 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 95/3 | 100/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE3 Closure 2 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 212 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.944 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 225 | 225 | 0 | 1 |  | N |  | 4700M62/335 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE3 Closure 2 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 212 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.3537 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1097 | 1097 | 0 | 1 |  | N |  | 4700M62/337 | YNE3: M62 J24-25 | YNE3 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE3 Closure 2 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 213 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.0562 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 310 | 310 | 0 | 1 |  | N |  | 4700M62/458 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE3 Closure 2 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 213 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.0639 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 922 | 922 | 0 | 1 |  | N |  | 4700M62/460 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE3 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 214 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.0394 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 538 | 538 | 0 | 1 |  | N |  | 4700M62/462 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE3 Closure 2 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 213 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 24.4156 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1866 | 1866 | 0 | 1 |  | N |  | 4700M62/464 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE3 Closure 2 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 213 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 19.2211 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1469 | 1469 | 0 | 1 |  | N |  | 4700M62/466 | YNE3: M62 J24-25 | YNE3 Closure 2 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE3 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 215 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.9836 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1298 | 1298 | 0 | 1 |  | N |  | 4700M62/468 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE3 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 214 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 30.1466 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2304 | 2304 | 0 | 1 |  | N |  | 4700M62/470 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE3 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 215 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 62.2559 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4758 | 4758 | 0 | 1 |  | N |  | 4700M62/472 | YNE3: M62 J24-25 | YNE3 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 1.9825 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | NB | 154.08 | 154.08 | 0 | 1 |  | N |  | 4700M606/5 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 3.8151 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 296.52 | 296.52 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 5.5039 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 427.77 | 427.77 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 5.7513 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 447 | 447 | 0 | 1 |  | N |  | 4700M62/602 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 0.46859 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 36.42 | 36.42 | 0 | 1 |  | N |  | 4700M62/603 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 6.412 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 498.35 | 498.35 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 7.7848 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 605.05 | 605.05 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 5.5215 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 429.14 | 429.14 | 0 | 1 |  | N |  | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 1.0441 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 81.15 | 81.15 | 0 | 1 |  | N |  | 4700M62/611 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 3.2548 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 252.97 | 252.97 | 0 | 1 |  | N |  | 4700M62/612 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 7.3188 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 568.83 | 568.83 | 0 | 1 |  | N |  | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 10.2054 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 793.18 | 793.18 | 0 | 1 |  | N |  | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 4.4923 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 349.15 | 349.15 | 0 | 1 |  | N |  | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 3.2953 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 256.12 | 256.12 | 0 | 1 |  | N |  | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 9.1654 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 712.35 | 712.35 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 3.9145 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 304.24 | 304.24 | 0 | 1 |  | N |  | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 0.76555 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 59.5 | 59.5 | 0 | 1 |  | N |  | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 5.1625 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 401.24 | 401.24 | 0 | 1 |  | N |  | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 0.60022 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 46.65 | 46.65 | 0 | 1 |  | N |  | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 6.7028 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 520.95 | 520.95 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 9.393 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 730.04 | 730.04 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 1.0705 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 83.2 | 83.2 | 0 | 1 |  | N |  | 4700M62/658 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 0.8771 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 68.17 | 68.17 | 0 | 1 |  | N |  | 4700M62/659 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 0.54541 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 42.39 | 42.39 | 0 | 1 |  | N |  | 4700M62/659 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 217 | VRS - Check all Road Restraint System - ILM | 2.7493 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 213.68 | 213.68 | 0 | 1 |  | N |  | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 216 | VRS - Check all Road Restraint System - ILM | 0.84674 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 65.81 | 65.81 | 0 | 1 |  | N |  | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 6.6441 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 516.39 | 516.39 | 0 | 1 |  | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 219 | VRS - Check all Road Restraint System - ILM | 9.621 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 747.76 | 747.76 | 0 | 1 |  | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 219 | VRS - Check all Road Restraint System - ILM | 3.9594 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 307.73 | 307.73 | 0 | 1 |  | N |  | 4700M62/924 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 13.5317 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 1051.71 | 1051.71 | 0 | 1 |  | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 9.1943 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 714.6 | 714.6 | 0 | 1 |  | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 3.3602 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 261.16 | 261.16 | 0 | 1 |  | N |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 2.1488 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 167.01 | 167.01 | 0 | 1 |  | N |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 219 | VRS - Check all Road Restraint System - ILM | 4.3802 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 340.44 | 340.44 | 0 | 1 |  | N |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 5.9184 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 459.99 | 459.99 | 0 | 1 |  | N |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 219 | VRS - Check all Road Restraint System - ILM | 7.3425 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 570.67 | 570.67 | 0 | 1 |  | N |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 6.1698 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 479.53 | 479.53 | 0 | 1 |  | N |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 219 | VRS - Check all Road Restraint System - ILM | 3.2732 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 254.4 | 254.4 | 0 | 1 |  | N |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 7.4991 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 582.84 | 582.84 | 0 | 1 |  | N |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 4.6084 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 358.17 | 358.17 | 0 | 1 |  | N |  | 4700M62/959 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 219 | VRS - Check all Road Restraint System - ILM | 1.6491 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 128.17 | 128.17 | 0 | 1 |  | N |  | 4700M62/959 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 4.7516 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 369.3 | 369.3 | 0 | 1 |  | N |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 219 | VRS - Check all Road Restraint System - ILM | 0.72785 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 56.57 | 56.57 | 0 | 1 |  | N |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 218 | VRS - Check all Road Restraint System - ILM | 10.9978 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 854.77 | 854.77 | 0 | 1 |  | N |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45914308
YNE4 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 220 | Gullies - Emptying / clear covers | 578.9885 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 182 | 75 | 107 | 0.41209 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  | Nights | Every 2 years |  |  | 45783817
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 221 | Gullies - Emptying / clear covers | 92.6382 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45786922
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 222 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-10-31 |  | 21dys | EB | 74 | 0 | 74 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45783817
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 222 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE4 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 220 | Gullies - Emptying / clear covers | 123.5175 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 221 | Gullies - Emptying / clear covers | 216.1557 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 28 | 28 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45786922
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 221 | Gullies - Emptying / clear covers | 138.9572 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/608 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 221 | Gullies - Emptying / clear covers | 131.2374 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  | N |  | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE4 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 220 | Gullies - Emptying / clear covers | 123.5175 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/611 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 221 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/611 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45786922
YNE4 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 220 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 223 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45783817
YNE4 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 223 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 115.7977 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 15 | 15 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 222 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45786922
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 221 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/653 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45786922
YNE4 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 220 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 220 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 221 | Gullies - Emptying / clear covers | 208.4359 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 27 | 27 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 221 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/658 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45786922
YNE4 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 220 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/659 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 220 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 221 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45786922
YNE4 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 224 | Gullies - Emptying / clear covers | 285.6343 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 37 | 37 | 0 | 1 |  | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 225 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45788290 - only 1 job
YNE4 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 225 | Gullies - Emptying / clear covers | 115.7977 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  | N |  | 4700M62/924 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45788290
YNE4 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 226 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 77.1985 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/925 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45788290
YNE4 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 224 | Gullies - Emptying / clear covers | 316.5137 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 41 | 41 | 0 | 1 |  | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 225 | Gullies - Emptying / clear covers | 185.2763 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 24 | 24 | 0 | 1 |  | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE4 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 224 | Gullies - Emptying / clear covers | 270.1946 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 35 | 35 | 0 | 1 |  | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 224 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 225 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE4 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 225 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45788290
YNE4 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 224 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 13 | 13 | 0 | 1 |  | N |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 225 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45788290
YNE4 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 224 | Gullies - Emptying / clear covers | 154.3969 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 20 | 20 | 0 | 1 |  | N |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 225 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45788290
YNE4 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 224 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 225 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45788290
YNE4 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 224 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/959 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 224 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 13 | 13 | 0 | 1 |  | N |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 224 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783817
YNE4 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 225 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45788290
YNE4 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 227 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.9711 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 80 | 80 | 0 | 1 |  | N |  | 4700M62/602 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 227 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.1596 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 250 | 250 | 0 | 1 |  | N |  | 4700M62/603 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 228 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.361 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 177 | 177 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 227 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.5624 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 104 | 104 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 227 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 9.5597 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 388 | 388 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 227 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.5045 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 264 | 264 | 0 | 1 |  | N |  | 4700M62/608 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 228 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.2812 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 52 | 52 | 0 | 1 |  | N |  | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 228 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.5699 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 429 | 429 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 227 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.8104 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 317 | 317 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 228 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0.68987 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 28 | 28 | 0 | 1 |  | N |  | 4700M62/653 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 228 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.2132 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 171 | 171 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 229 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP |  | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 85 | 0 | 85 | 0 | 18/10 - cancelled storm Babet | Y |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) |  |  | 52028694
YNE4 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 229 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP |  | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 34 | 0 | 34 | 0 | 18/10 - cancelled storm Babet | Y |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) |  |  | 52028694
YNE4 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 230 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.1928 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 89 | 89 | 0 | 1 |  | N |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE4 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 229 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP |  | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 60 | 0 | 60 | 0 | 18/10 - cancelled storm Babet | Y |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) |  |  | 52028694
YNE4 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 229 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP |  | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 102 | 0 | 102 | 0 | 18/10 - cancelled storm Babet | Y |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) |  |  | 52028694
YNE4 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 231 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 34.2151 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 443.21 | 443.21 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE4 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 232 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 28.5634 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 370 | 370 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE4 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 232 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 24.7035 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 320 | 320 | 0 | 1 |  | N |  | 4700M62/608 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE4 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 232 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 31.2654 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 405 | 405 | 0 | 1 |  | N |  | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE4 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 232 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 14.6677 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 190 | 190 | 0 | 1 |  | N |  | 4700M62/611 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE4 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 233 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 3.8599 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 50 | 50 | 0 | 1 |  | N |  | 4700M62/924 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE4 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 233 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 18.6048 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 241 | 241 | 0 | 1 |  | N |  | 4700M62/925 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE4 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 233 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 29.7214 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 385 | 385 | 0 | 1 |  | N |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE4 Closure 1 WB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 234 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 198.27 | 0 | 198.27 | 0 |  | Y |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route) |  |  | 45877333
YNE4 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 233 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2.7019 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 35 | 35 | 0 | 1 |  | N |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE4 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 233 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 35.5113 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 460 | 460 | 0 | 1 |  | N |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE4 Closure 1 WB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 234 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 131.76 | 0 | 131.76 | 0 |  | Y |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route) |  |  | 45877333
YNE4 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 300.2163 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | NB | 67 | 14 | 53 | 0.20896 | 22/11 - cancelled strong winds | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M606/5 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  | Nights | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 236 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/603 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 236 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 236 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/606 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 236 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 236 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/608 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 236 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 236 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 236 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 236 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/658 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y | 17/10 denied access by scheme despite share agreed2/10 cancelled rain - scheme restricting access and share lost | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 237 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 857.7607 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-12-01 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 40 | 40 | 0 | 1 |  | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 237 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 18/10 - cancelled storm Babet | Y |  | 4700M62/924 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 237 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 18/10 - cancelled storm Babet | Y |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 238 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/927 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE4 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 237 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 18/10 - cancelled storm Babet | Y |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 238 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 | All catchpits raised on near side. No jobs for this closure | N |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | N/A
YNE4 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 237 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 18/10 - cancelled storm Babet | Y |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 238 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 | All catchpits raised on near side. No jobs for this closure | N |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | N/A
YNE4 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 238 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 | All catchpits raised on near side. No jobs for this closure | N |  | 4700M62/957 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | N/A
YNE4 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 237 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 18/10 - cancelled storm Babet | Y |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 237 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 18/10 - cancelled storm Babet | Y |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791022
YNE4 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 239 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 240 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 241 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 242 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 95.8777 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 242 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 95.8777 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 242 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 95.8777 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 242 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 95.8777 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 242 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 242 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 242 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 143.8165 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/602 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 20 | 20 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/608 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/611 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 20 | 20 | 0 | 1 |  | N |  | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 110.2593 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 46 | 46 | 0 | 1 |  | N |  | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 24 | 24 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 112.6563 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 47 | 47 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/658 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/659 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 243 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 110.2593 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 46 | 46 | 0 | 1 |  | N |  | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  | Y |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 30 | 30 | 0 | 1 |  | Y |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 19 | 19 | 0 | 1 |  | Y |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | Y |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | Y |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | Y |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 17 | 17 | 0 | 1 |  | Y |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  | Y |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | Y |  | 4700M62/959 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | Y |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 67.1144 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 28 | 28 | 0 | 1 |  | Y |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 245 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 383.5108 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 64 | 64 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 245 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 245 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 246 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45904528
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 246 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45904528
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 247 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 247 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 247 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 247 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 39.7238 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 247 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 247 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 247 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 247 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 39.7238 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 247 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 83.8614 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 19 | 19 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 247 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 248 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 0 | 3 | 0 |  | Y |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 249 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.41653 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 20.11 | 20.11 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 249 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.89954 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 43.43 | 43.43 | 0 | 1 |  | N |  | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 249 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.82994 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 40.07 | 40.07 | 0 | 1 |  | N |  | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 249 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.6456 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 224.29 | 224.29 | 0 | 1 |  | N |  | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 249 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.5078 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 265.92 | 265.92 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 249 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.44469 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 21.47 | 21.47 | 0 | 1 |  | N |  | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 250 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.044 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 484.93 | 484.93 | 0 | 1 |  | Y |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 250 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.4159 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 20.08 | 20.08 | 0 | 1 |  | Y |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 250 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.88235 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 42.6 | 42.6 | 0 | 1 |  | Y |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 250 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.78748 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 38.02 | 38.02 | 0 | 1 |  | Y |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 250 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.9304 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 189.76 | 189.76 | 0 | 1 |  | Y |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 250 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.13919 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6.72 | 6.72 | 0 | 1 |  | Y |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 250 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.95691 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 46.2 | 46.2 | 0 | 1 |  | Y |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.4527 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | NB | 191 | 191 | 0 | 1 |  | N |  | 4700M606/5 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.1909 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 392 | 392 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.6191 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 407 | 407 | 0 | 1 |  | N |  | 4700M62/602 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.0522 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 212 | 212 | 0 | 1 |  | N |  | 4700M62/603 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.1591 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 531 | 531 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.1664 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 216 | 216 | 0 | 1 |  | N |  | 4700M62/606 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.1868 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 567 | 567 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.1077 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 284 | 284 | 0 | 1 |  | N |  | 4700M62/608 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.5343 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 369 | 369 | 0 | 1 |  | N |  | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.0368 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 877 | 877 | 0 | 1 |  | N |  | 4700M62/611 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.3663 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 223 | 223 | 0 | 1 |  | N |  | 4700M62/612 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4413 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 681 | 681 | 0 | 1 |  | N |  | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.7929 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 308 | 308 | 0 | 1 |  | N |  | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.2571 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1235 | 1235 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.2383 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 814 | 814 | 0 | 1 |  | N |  | 4700M62/653 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.8435 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 590 | 590 | 0 | 1 |  | N |  | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.7546 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 727 | 727 | 0 | 1 |  | N |  | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 65.404 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2291 | 2291 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.2162 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 533 | 533 | 0 | 1 |  | N |  | 4700M62/658 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.6843 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 59 | 59 | 0 | 1 |  | N |  | 4700M62/659 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 251 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.9894 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 455 | 455 | 0 | 1 |  | N |  | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.0131 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 666 | 666 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.1648 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 286 | 286 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/924 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.195 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 217 | 217 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/925 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 26.036 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 912 | 912 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.8238 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 204 | 204 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/927 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.1273 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 670 | 670 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.2219 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 288 | 288 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/929 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.9943 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 245 | 245 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.0694 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 703 | 703 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.7023 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 515 | 515 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.8728 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 556 | 556 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.8989 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 662 | 662 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/957 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.2318 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1094 | 1094 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.213 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 673 | 673 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/959 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.9544 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 734 | 734 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 252 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 65.8893 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2308 | 2308 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028708
YNE4 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 253 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 38.2022 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 425.01 | 425.01 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 253 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 73.3303 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 815.82 | 815.82 | 0 | 1 |  | N |  | 4700M62/602 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 253 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 40.3181 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 448.55 | 448.55 | 0 | 1 |  | N |  | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 254 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 81.0496 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 901.7 | 901.7 | 0 | 1 |  | N |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 254 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 65.3493 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 727.03 | 727.03 | 0 | 1 |  | N |  | 4700M62/924 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 254 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 83.117 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 924.7 | 924.7 | 0 | 1 |  | N |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 255 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 22.7836 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 330 | 330 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 255 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 253.0552 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3665.28 | 3665.28 | 0 | 1 |  | N |  | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE4 Closure 1 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 256 | Sweeping - Paved non-running areas - Full Sweep 01 | 98.2326 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13188.75 | 13188.75 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 257 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 100.6836 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4200.5 | 4200.5 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB OS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 258 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 100.6836 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4200.5 | 4200.5 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 259 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1685.0025 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 35149 | 35149 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.4991 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | NB | 191 | 191 | 0 | 1 |  | N |  | 4700M606/5 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.69 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 817 | 817 | 0 | 1 |  | N |  | 4700M62/601 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.0023 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1223 | 1223 | 0 | 1 |  | N |  | 4700M62/602 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.7739 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 212 | 212 | 0 | 1 |  | N |  | 4700M62/603 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.9478 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 531 | 531 | 0 | 1 |  | N |  | 4700M62/604 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.8262 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 216 | 216 | 0 | 1 |  | N |  | 4700M62/606 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.4189 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 567 | 567 | 0 | 1 |  | N |  | 4700M62/607 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.716 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 284 | 284 | 0 | 1 |  | N |  | 4700M62/608 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.8282 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 369 | 369 | 0 | 1 |  | N |  | 4700M62/609 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.4751 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 877 | 877 | 0 | 1 |  | N |  | 4700M62/611 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.9178 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 223 | 223 | 0 | 1 |  | N |  | 4700M62/612 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 260 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.7854 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1130 | 1130 | 0 | 1 |  | N |  | 4700M62/613 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 4.03 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 308 | 308 | 0 | 1 |  | N |  | 4700M62/651 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 16.1593 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1235 | 1235 | 0 | 1 |  | N |  | 4700M62/652 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 10.6507 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 814 | 814 | 0 | 1 |  | N |  | 4700M62/653 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.7198 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 590 | 590 | 0 | 1 |  | N |  | 4700M62/654 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 9.5124 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 727 | 727 | 0 | 1 |  | N |  | 4700M62/656 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 29.9765 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2291 | 2291 | 0 | 1 |  | N |  | 4700M62/657 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.974 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 533 | 533 | 0 | 1 |  | N |  | 4700M62/658 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0.77198 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 59 | 59 | 0 | 1 |  | N |  | 4700M62/659 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE4 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.9534 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 455 | 455 | 0 | 1 |  | N |  | 4700M62/660 | YNE4: M62 J25-26 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 20.5164 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1568 | 1568 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/923 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.2546 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1013 | 1013 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/924 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.8393 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 217 | 217 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/925 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.933 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 912 | 912 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/926 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.6692 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 204 | 204 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/927 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.7666 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 670 | 670 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/928 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.7683 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 288 | 288 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/929 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.2057 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 245 | 245 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/930 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.1984 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 703 | 703 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/931 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.8416 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1440 | 1440 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/932 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 263 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.275 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 556 | 556 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/956 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 263 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.6619 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 662 | 662 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/957 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 263 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 14.3144 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1094 | 1094 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/958 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 263 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.8058 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 673 | 673 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/959 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 263 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 9.604 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 734 | 734 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/960 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034134
YNE4 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 263 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 30.1989 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2308 | 2308 | 0 | 1 | 18/10 - cancelled storm Babet | Y |  | 4700M62/961 | YNE4: M62 J25-26 | YNE4 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034134
YNE5 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 264 | VRS - Check all Road Restraint System - ILM | 5.4904 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 426.72 | 426.72 | 0 | 1 |  |  |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028745
YNE5 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 265 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 600.57 | 0 | 600.57 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | ILM Every 2 years | 104/3 | 108/6 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 265 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 307.98 | 0 | 307.98 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/616 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | ILM Every 2 years | 104/3 | 108/6 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 265 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 108.73 | 0 | 108.73 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | ILM Every 2 years | 104/3 | 108/6 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 264 | VRS - Check all Road Restraint System - ILM | 13.0208 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1012 | 1012 | 0 | 1 |  |  |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028745
YNE5 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 264 | VRS - Check all Road Restraint System - ILM | 21.4254 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1665.22 | 1665.22 | 0 | 1 |  |  |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028745
YNE5 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 265 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 658.69 | 0 | 658.69 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/621 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | ILM Every 2 years | 104/3 | 108/6 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 264 | VRS - Check all Road Restraint System - ILM | 0.22156 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17.22 | 17.22 | 0 | 1 |  |  |  | 4700M62/622 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028745
YNE5 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 265 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 378.88 | 0 | 378.88 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/622 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | ILM Every 2 years | 104/3 | 108/6 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 264 | VRS - Check all Road Restraint System - ILM | 2.9446 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 228.86 | 228.86 | 0 | 1 |  |  |  | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028745
YNE5 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 265 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 676.05 | 0 | 676.05 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | ILM Every 2 years | 104/3 | 108/6 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 264 | VRS - Check all Road Restraint System - ILM | 15.1613 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1178.36 | 1178.36 | 0 | 1 |  |  |  | 4700M62/660 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028745
YNE5 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 264 | VRS - Check all Road Restraint System - ILM | 0.049536 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3.85 | 3.85 | 0 | 1 |  |  |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028745
YNE5 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 265 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 154.75 | 0 | 154.75 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | ILM Every 2 years | 104/3 | 108/6 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 264 | VRS - Check all Road Restraint System - ILM | 3.5567 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 276.43 | 276.43 | 0 | 1 |  |  |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028745
YNE5 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 265 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 548.46 | 0 | 548.46 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | ILM Every 2 years | 104/3 | 108/6 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 264 | VRS - Check all Road Restraint System - ILM | 11.1836 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 869.21 | 869.21 | 0 | 1 |  |  |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 52028745
YNE5 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 265 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 23.15 | 0 | 23.15 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | ILM Every 2 years | 104/3 | 108/6 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 266 | VRS - Check all Road Restraint System - ILM | 1.9105 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 148.49 | 148.49 | 0 | 1 |  |  |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/9 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 267 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 640.53 | 0 | 640.53 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/6 | 45919071 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 267 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 337.7 | 0 | 337.7 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/916 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/6 | 45919071 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 267 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 403.88 | 0 | 403.88 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/917 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/6 | 45919071 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 266 | VRS - Check all Road Restraint System - ILM | 3.6718 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 285.38 | 285.38 | 0 | 1 |  |  |  | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/9 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 267 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 285.21 | 0 | 285.21 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/6 | 45919071 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 266 | VRS - Check all Road Restraint System - ILM | 24.5918 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1911.32 | 1911.32 | 0 | 1 |  |  |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/9 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 267 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 30.78 | 0 | 30.78 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/6 | 45919071 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 266 | VRS - Check all Road Restraint System - ILM | 17.7704 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1381.15 | 1381.15 | 0 | 1 |  |  |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/9 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 266 | VRS - Check all Road Restraint System - ILM | 5.1979 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 403.99 | 403.99 | 0 | 1 |  |  |  | 4700M62/921 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/9 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 267 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 461.84 | 0 | 461.84 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/921 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/6 | 45919071 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 266 | VRS - Check all Road Restraint System - ILM | 5.2225 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 405.9 | 405.9 | 0 | 1 |  |  |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/9 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 267 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 597.86 | 0 | 597.86 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/6 | 45919071 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 266 | VRS - Check all Road Restraint System - ILM | 11.5005 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 893.84 | 893.84 | 0 | 1 |  |  |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/9 | 52028745 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 267 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 92.3 | 0 | 92.3 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/6 | 45919071 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 268 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 119 | 11 | 108 | 0.092437 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  | Nights | Every 2 years |  |  | 45786893
YNE5 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 269 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 | Only 4 gully jobs for this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 269 | Gullies - Emptying / clear covers | 138.9572 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 | Only 4 gully jobs for this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/616 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 269 | Gullies - Emptying / clear covers | 401.432 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 52 | 52 | 0 | 1 | Only 4 gully jobs for this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 269 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 4 | 0 | 4 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 1 Closure | 1 |  | Nights | Every 2 years | 104/3 | 108/6 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 269 | Gullies - Emptying / clear covers | 200.716 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 26 | 26 | 0 | 1 | Only 4 gully jobs for this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 268 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45786893
YNE5 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 269 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 | Only 4 gully jobs for this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 268 | Gullies - Emptying / clear covers | 77.1985 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 | Gully cart full - 82 completed |  |  | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45786893
YNE5 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 269 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 4 | 0 | 4 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | Every 2 years | 104/3 | 108/6 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 268 | Gullies - Emptying / clear covers | 146.6771 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 19 | 19 | 0 | 1 | Gully cart full - 82 completed |  |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45786893
YNE5 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 269 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 | Only 4 gully jobs for this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 268 | Gullies - Emptying / clear covers | 154.3969 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 20 | 20 | 0 | 1 | Gully cart full - 82 completed |  |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45786893
YNE5 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 268 | Gullies - Emptying / clear covers | 223.8756 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 29 | 29 | 0 | 1 | Gully cart full - 82 completed |  |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45786893
YNE5 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 269 | Gullies - Emptying / clear covers | 223.8756 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 29 | 29 | 0 | 1 | Only 4 gully jobs for this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 268 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/667 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45786893
YNE5 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 270 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 | Gully cart full - 82 completed |  |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 109/0 | 104/9 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 270 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 253 | 11 | 242 | 0.043478 |  | Y | Unable to access due to schemes - booked for January | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  | Nights | Every 2 years | 109/0 | 104/9 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 270 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y | Scheme shares meant limitation on TM layout installed | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 109/0 | 104/9 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 271 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 38 | 0 | 38 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 109/0 | 104/6 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 270 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y | Scheme shares meant limitation on TM layout installed | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 109/0 | 104/9 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 271 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 28 | 0 | 28 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 109/0 | 104/6 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 270 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y | Scheme shares meant limitation on TM layout installed | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 109/0 | 104/9 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 271 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 1 | 0 | 1 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 109/0 | 104/6 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 270 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y | Scheme shares meant limitation on TM layout installed | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 109/0 | 104/9 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 271 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 1 | 0 | 1 | 0 | 31/10 - TM cancelled on the night due to severe weather | Y | Unable to access due to schemes - booked for January | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 109/0 | 104/6 | 45786893 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 272 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP |  | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 16 | 0 | 16 | 0 | No resource assigned by CGS |  |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) |  |  | 52028778
YNE5 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 272 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP |  | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 25 | 0 | 25 | 0 | No resource assigned by CGS |  |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) |  |  | 52028778
YNE5 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 273 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-10 | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 57 | 0 | 57 | 0 | No resource assigned by CGS |  |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 109/0 | 104/9 | 52028778 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 273 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-10 | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 49 | 0 | 49 | 0 | No resource assigned by CGS |  |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 109/0 | 104/9 | 52028778 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 273 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | 2024-01-10 | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 180 | 0 | 180 | 0 | No resource assigned by CGS |  |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 109/0 | 104/9 | 52028778 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 274 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 278.88 | 0 | 278.88 | 0 |  | Y | 3/10 - Declined due to DBFO scheme | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 104/3 | 108/6 | Can jobs be cancelled and re-raised by asset? | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 274 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 770 | 0 | 770 | 0 |  | Y | 3/10 - Declined due to DBFO scheme | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 104/3 | 108/6 | Can jobs be cancelled and re-raised by asset? | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 275 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 3.2887 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 42.6 | 42.6 | 0 | 1 | No v-channel on EB |  |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) |  |  | 52028783
YNE5 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 274 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 708.8 | 0 | 708.8 | 0 |  | Y | 3/10 - Declined due to DBFO scheme | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 104/3 | 108/6 | Can jobs be cancelled and re-raised by asset? | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 275 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2.9752 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 38.54 | 38.54 | 0 | 1 | No v-channel on EB |  |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) |  |  | 52028783
YNE5 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 276 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1270 | 0 | 1270 | 0 |  | Y |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 109/0 | 104/6 | Can jobs be cancelled and re-raised by asset? | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 276 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 36.16 | 0 | 36.16 | 0 |  | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 109/0 | 104/6 | Can jobs be cancelled and re-raised by asset? | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 277 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 | No catchpit jobs plotted to this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 277 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 | No catchpit jobs plotted to this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/616 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 277 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 | No catchpit jobs plotted to this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514.6564 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 24 | 24 | 0 | 1 |  | Y |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791569
YNE5 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 13 | 0 | 13 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  | Nights | ILM Every 2 years |  |  | 45791569
YNE5 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | Y |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791569
YNE5 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 277 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 | No catchpit jobs plotted to this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/663 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791569
YNE5 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 277 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 | No catchpit jobs plotted to this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/663 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 277 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 | No catchpit jobs plotted to this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 214.4402 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | Y |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791569
YNE5 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 277 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 | No catchpit jobs plotted to this TM layout | Y | 3/10 - Declined due to DBFO scheme | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791569
YNE5 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 279 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | WB | 56 | 0 | 56 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  | Nights | ILM Every 2 years | 109/0 | 104/9 | 45791569 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 279 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 3/10 scheme shortened closure so could not access | Y | Scheme shares meant limitation on TM layout installed | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/9 | 45791569 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 280 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 | None on OS | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 280 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 | None on OS | Y |  | 4700M62/921 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 279 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 3/10 scheme shortened closure so could not access | Y | Scheme shares meant limitation on TM layout installed | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 109/0 | 104/9 | 45791569 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE4 Closure 1 EB NS Amey 45048 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 281 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 15.9796 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys |  | 2 | 1 | 1 | 0.5 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY |  | YNE5: M62 J26-27 | YNE4 Closure 1 EB NS | Lane 1 Closure | 1 |  | Nights | 2 times per year |  |  | 45814593
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 282 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 3718 | 0 | 3718 | 0 | Missed due to schemes no access | Y |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52037026
YNE5 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 283 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 104/3 | 108/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 284 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 285 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 286 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45817476
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 286 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 95.8777 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | Y |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45817476
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 286 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1342.2877 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 56 | 56 | 0 | 1 |  | Y |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45817476
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 286 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45817476
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 286 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 335.5719 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  | Y |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45817476
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 286 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 239.6942 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | Y |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45817476
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 287 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45817476 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 287 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 143.8165 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | Y |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45817476 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 287 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1006.7158 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 42 | 42 | 0 | 1 |  | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45817476 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | Y |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 21 | 21 | 0 | 1 |  | Y |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 146.2135 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 61 | 61 | 0 | 1 |  | Y |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | Y |  | 4700M62/622 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | Y |  | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 5 | 0 | 5 | 0 | 3/10 slips not completed - scheme share | Y |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 4 | 0 | 4 | 0 | 3/10 slips not completed - scheme share | Y |  | 4700M62/663 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 40 | 0 | 40 | 0 | 3/10 slips not completed - scheme share | Y |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 28 | 0 | 28 | 0 | 3/10 slips not completed - scheme share | Y |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 23 | 0 | 23 | 0 | 3/10 slips not completed - scheme share | Y |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 288 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 | 3/10 slips not completed - scheme share | Y |  | 4700M62/667 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898826
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | Y |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45898826 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | Y |  | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45898826 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 86.2899 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 36 | 36 | 0 | 1 |  | Y |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45898826 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 117.4502 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 49 | 49 | 0 | 1 |  | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45898826 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/921 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45898826 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 107.8624 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 45 | 45 | 0 | 1 |  | Y |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45898826 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 24 | 0 | 24 | 0 | 3/10 slips not completed - scheme share | Y |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45898826 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 290 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 359.5413 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 60 | 60 | 0 | 1 |  | Y |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898994
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 290 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 8 | 0 | 8 | 0 |  | Y |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898994
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 291 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | Y |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 45898994 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 292 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 75.0338 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  | Y |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52039169
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 292 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52039169
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 292 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | Y |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52039169
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 292 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 331.0317 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 75 | 75 | 0 | 1 |  | Y |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52039169
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 292 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | Y |  | 4700M62/621 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52039169
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 292 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | Y |  | 4700M62/622 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52039169
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 292 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52039169
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 292 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 52.9651 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | Y |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52039169
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 292 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 97.1026 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 22 | 22 | 0 | 1 |  | Y |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52039169
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 292 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 70.6201 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | Y |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52039169
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 293 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | Y |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039169 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 293 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 11 | 11 | 0 | 1 |  | Y |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039169 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 293 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 216.274 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 49 | 49 | 0 | 1 |  | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039169 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 293 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | Y |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52039169 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 294 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.1765 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 56.8 | 56.8 | 0 | 1 |  | Y |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45845027
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 294 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 8.0873 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 390.46 | 390.46 | 0 | 1 |  | Y |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45845027
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 294 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.3459 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16.7 | 16.7 | 0 | 1 |  | Y |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45845027
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 294 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.8678 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 235.02 | 235.02 | 0 | 1 |  | Y |  | 4700M62/663 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45845027
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 294 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.2579 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 109.01 | 109.01 | 0 | 1 |  | Y |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45845027
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 294 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.4627 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 70.62 | 70.62 | 0 | 1 |  | Y |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45845027
YNE5 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 294 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.1238 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 295.66 | 295.66 | 0 | 1 |  | Y |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45845027
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 295 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.2351 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 59.63 | 59.63 | 0 | 1 |  | Y |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 45845027 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 295 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.89747 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 43.33 | 43.33 | 0 | 1 |  | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 45845027 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 295 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.71147 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 34.35 | 34.35 | 0 | 1 |  | Y |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 45845027 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9299 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 558 | 558 | 0 | 1 |  | Y |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.9935 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 280 | 280 | 0 | 1 |  | Y |  | 4700M62/616 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.381 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 819 | 819 | 0 | 1 |  | Y |  | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 26.7211 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 936 | 936 | 0 | 1 |  | Y |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 43.9357 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1539 | 1539 | 0 | 1 |  | Y |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.4389 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 786 | 786 | 0 | 1 |  | Y |  | 4700M62/621 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.4209 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 330 | 330 | 0 | 1 |  | Y |  | 4700M62/622 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.2423 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 639 | 639 | 0 | 1 |  | Y |  | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.8752 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 451 | 451 | 0 | 1 |  | Y |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 558 | 0 | 558 | 0 |  | Y |  | 4700M62/662 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 554 | 0 | 554 | 0 |  | Y |  | 4700M62/663 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1442 | 0 | 1442 | 0 |  | Y |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1638 | 0 | 1638 | 0 |  | Y |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2047 | 0 | 2047 | 0 |  | Y |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 296 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 479 | 0 | 479 | 0 |  | Y |  | 4700M62/667 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 52028790
YNE5 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.5009 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 578 | 578 | 0 | 1 | 108/0 - 106/5 completed / No TM From 106/5 - 105/0 made closure shorter due to TM layouts requires M62 Jct 27 wb Entry closing, Putting merge on with lane 2 on M621 we would have missed a lot of n/s and only got 400yrds at the end. Richard Cooper said no TM Booked for Slip Road only M621 | Y |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 52028790 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 315 | 0 | 315 | 0 | 108/0 - 106/5 completed / No TM From 106/5 - 105/0 made closure shorter due to TM layouts requires M62 Jct 27 wb Entry closing, Putting merge on with lane 2 on M621 we would have missed a lot of n/s and only got 400yrds at the end. Richard Cooper said no TM Booked for Slip Road only M621 | Y |  | 4700M62/916 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 52028790 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 360 | 0 | 360 | 0 | 108/0 - 106/5 completed / No TM From 106/5 - 105/0 made closure shorter due to TM layouts requires M62 Jct 27 wb Entry closing, Putting merge on with lane 2 on M621 we would have missed a lot of n/s and only got 400yrds at the end. Richard Cooper said no TM Booked for Slip Road only M621 | Y |  | 4700M62/917 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 52028790 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 257 | 0 | 257 | 0 | 108/0 - 106/5 completed / No TM From 106/5 - 105/0 made closure shorter due to TM layouts requires M62 Jct 27 wb Entry closing, Putting merge on with lane 2 on M621 we would have missed a lot of n/s and only got 400yrds at the end. Richard Cooper said no TM Booked for Slip Road only M621 | Y |  | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 52028790 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1748 | 0 | 1748 | 0 | 108/0 - 106/5 completed / No TM From 106/5 - 105/0 made closure shorter due to TM layouts requires M62 Jct 27 wb Entry closing, Putting merge on with lane 2 on M621 we would have missed a lot of n/s and only got 400yrds at the end. Richard Cooper said no TM Booked for Slip Road only M621 | Y |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 52028790 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1296 | 0 | 1296 | 0 | 108/0 - 106/5 completed / No TM From 106/5 - 105/0 made closure shorter due to TM layouts requires M62 Jct 27 wb Entry closing, Putting merge on with lane 2 on M621 we would have missed a lot of n/s and only got 400yrds at the end. Richard Cooper said no TM Booked for Slip Road only M621 | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 52028790 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 766 | 0 | 766 | 0 | 108/0 - 106/5 completed / No TM From 106/5 - 105/0 made closure shorter due to TM layouts requires M62 Jct 27 wb Entry closing, Putting merge on with lane 2 on M621 we would have missed a lot of n/s and only got 400yrds at the end. Richard Cooper said no TM Booked for Slip Road only M621 | Y |  | 4700M62/921 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 52028790 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 536 | 0 | 536 | 0 | 108/0 - 106/5 completed / No TM From 106/5 - 105/0 made closure shorter due to TM layouts requires M62 Jct 27 wb Entry closing, Putting merge on with lane 2 on M621 we would have missed a lot of n/s and only got 400yrds at the end. Richard Cooper said no TM Booked for Slip Road only M621 | Y |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 52028790 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1179 | 0 | 1179 | 0 |  | Y |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 109/0 | 104/9 | 52028790 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 298 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 322.42 | 0 | 322.42 | 0 |  | Y | 3/10 - Declined due to DBFO scheme | 4700M62/616 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 104/3 | 108/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 298 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 2107.36 | 0 | 2107.36 | 0 |  | Y | 3/10 - Declined due to DBFO scheme | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 104/3 | 108/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 298 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 111.28 | 0 | 111.28 | 0 |  | Y | 3/10 - Declined due to DBFO scheme | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 104/3 | 108/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 298 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1103.48 | 0 | 1103.48 | 0 |  | Y | 3/10 - Declined due to DBFO scheme | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 104/3 | 108/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 299 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 691.72 | 0 | 691.72 | 0 |  | Y |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 299 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1386.64 | 0 | 1386.64 | 0 |  | Y |  | 4700M62/916 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 299 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1593.12 | 0 | 1593.12 | 0 |  | Y |  | 4700M62/917 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 299 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1044.6 | 0 | 1044.6 | 0 |  | Y |  | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 299 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 2420.92 | 0 | 2420.92 | 0 |  | Y |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 299 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 5108.48 | 0 | 5108.48 | 0 |  | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 299 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1081.42 | 0 | 1081.42 | 0 |  | Y |  | 4700M62/921 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 299 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1192.4 | 0 | 1192.4 | 0 |  | Y |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/6 | No jobs raised | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 300 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 42.0979 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 609.75 | 609.75 | 0 | 1 |  | Y |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52038263
YNE5 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 301 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 77.188 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1118 | 1118 | 0 | 1 |  | Y |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52038263 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 301 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 10.8395 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 157 | 157 | 0 | 1 |  | Y |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 109/0 | 104/9 | 52038263 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 302 | Sweeping - Paved non-running areas - Full Sweep 01 | 117.8233 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 15819 | 15819 | 0 | 1 |  | Y |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year |  |  | 52033914
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 303 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 15.1726 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 633 | 633 | 0 | 1 |  | Y |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | 52033929
YNE5 Closure 1 EB OS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 304 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-12 | 2024-1 | 2024-01-13 | 2023-05-02 | 2023-05-31 | 2023-11-30 | Subject to access via scheme shares | 21dys | EB | 633 | 0 | 633 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB OS | Lane 2 Closure | 1 |  | Nights | Annually | 104/3 | 108/6 | 52033930 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 305 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1302.834 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 27177 | 27177 | 0 | 1 |  | Y |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | 52033942
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 306 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.3011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 558 | 558 | 0 | 1 |  | Y |  | 4700M62/614 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 306 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.8768 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 602 | 602 | 0 | 1 |  | Y |  | 4700M62/616 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 306 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 38.2851 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2926 | 2926 | 0 | 1 |  | Y |  | 4700M62/617 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 306 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.2471 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 936 | 936 | 0 | 1 |  | Y |  | 4700M62/618 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 306 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.5894 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1650 | 1650 | 0 | 1 |  | Y |  | 4700M62/619 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 306 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.2844 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 786 | 786 | 0 | 1 |  | Y |  | 4700M62/621 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 306 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.3179 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 330 | 330 | 0 | 1 |  | Y |  | 4700M62/622 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 306 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 22.7931 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1742 | 1742 | 0 | 1 |  | Y |  | 4700M62/623 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 307 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.9011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 451 | 451 | 0 | 1 |  | Y |  | 4700M62/661 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 307 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.3011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 558 | 558 | 0 | 1 |  | Y |  | 4700M62/662 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 307 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.2488 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 554 | 554 | 0 | 1 |  | Y |  | 4700M62/663 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 307 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 18.8678 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1442 | 1442 | 0 | 1 |  | Y |  | 4700M62/664 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 307 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 21.4323 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1638 | 1638 | 0 | 1 |  | Y |  | 4700M62/665 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 307 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 26.7839 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2047 | 2047 | 0 | 1 |  | Y |  | 4700M62/666 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034135
YNE5 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 307 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.2675 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 479 | 479 | 0 | 1 |  | Y |  | 4700M62/667 | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52034135
YNE5 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 308 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.6173 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1270 | 1270 | 0 | 1 |  | Y |  | 4700M62/915 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually | 109/0 | 104/9 | 52034135 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 308 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 22.2697 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1702 | 1702 | 0 | 1 |  | Y |  | 4700M62/916 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 109/0 | 104/9 | 52034135 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 308 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 25.5539 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1953 | 1953 | 0 | 1 |  | Y |  | 4700M62/917 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 109/0 | 104/9 | 52034135 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 308 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 17.036 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1302 | 1302 | 0 | 1 |  | Y |  | 4700M62/918 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 109/0 | 104/9 | 52034135 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 308 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 54.5491 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4169 | 4169 | 0 | 1 |  | Y |  | 4700M62/919 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 109/0 | 104/9 | 52034135 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 308 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 83.7929 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6404 | 6404 | 0 | 1 |  | Y |  | 4700M62/920 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 109/0 | 104/9 | 52034135 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 308 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 24.167 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1847 | 1847 | 0 | 1 |  | Y |  | 4700M62/921 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 109/0 | 104/9 | 52034135 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 308 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 22.6099 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1728 | 1728 | 0 | 1 |  | Y |  | 4700M62/922 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 109/0 | 104/9 | 52034135 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE5 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 309 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 15.4266 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1179 | 1179 | 0 | 1 |  | Y |  | 4700M62/955 | YNE5: M62 J26-27 | YNE5 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) | 109/0 | 104/9 | 52034135 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 310 | VRS - Check all Road Restraint System - ILM | 0.48416 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 37.63 | 37.63 | 0 | 1 |  | N |  | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 52028814 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 311 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 230.08 | 0 | 230.08 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 311 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 497.81 | 0 | 497.81 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/626 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 310 | VRS - Check all Road Restraint System - ILM | 18.9424 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1472.24 | 1472.24 | 0 | 1 |  | N |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 52028814 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 311 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 209.82 | 0 | 209.82 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 310 | VRS - Check all Road Restraint System - ILM | 22.0031 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1710.12 | 1710.12 | 0 | 1 |  | N |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 52028814 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 311 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 152.44 | 0 | 152.44 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/629 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 310 | VRS - Check all Road Restraint System - ILM | 1.8694 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 145.29 | 145.29 | 0 | 1 |  | N |  | 4700M62/631 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 52028814 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 311 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 376.1 | 0 | 376.1 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/631 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 310 | VRS - Check all Road Restraint System - ILM | 0.92458 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 71.86 | 71.86 | 0 | 1 |  | N |  | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 52028814 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 311 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 122.04 | 0 | 122.04 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 310 | VRS - Check all Road Restraint System - ILM | 8.0379 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 624.72 | 624.72 | 0 | 1 |  | N |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 52028814 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 311 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 82.4 | 0 | 82.4 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 310 | VRS - Check all Road Restraint System - ILM | 11.0619 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 859.75 | 859.75 | 0 | 1 |  | N |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 52028814 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 312 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 67.57 | 0 | 67.57 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/907 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45920694
YNE6 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 313 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | WB | 122.48 | 0 | 122.48 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/907 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 312 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 125.08 | 0 | 125.08 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45920694
YNE6 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 313 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | WB | 417.7 | 0 | 417.7 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 313 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | WB | 111.89 | 0 | 111.89 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/909 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 312 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1928.35 | 0 | 1928.35 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45920694
YNE6 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 312 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 920.47 | 0 | 920.47 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45920694
YNE6 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 313 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | WB | 858.93 | 0 | 858.93 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 312 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 169.22 | 0 | 169.22 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45920694
YNE6 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 313 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | WB | 704.1 | 0 | 704.1 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 313 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | WB | 200.75 | 0 | 200.75 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/913 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 312 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 156.17 | 0 | 156.17 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45920694
YNE6 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 313 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | WB | 276.25 | 0 | 276.25 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 312 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 835.14 | 0 | 835.14 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45920694
YNE6 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 313 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | WB | 130.23 | 0 | 130.23 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 312 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 51.95 | 0 | 51.95 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/953 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45920694
YNE6 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 312 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 727.26 | 0 | 727.26 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45920694
YNE6 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 313 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | WB | 200.04 | 0 | 200.04 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 314 | Gullies - Emptying / clear covers | 432.3114 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 95 | 56 | 39 | 0.58947 | 71 Gullies On Tablet 5 not on Tablet but Cleaned Out | Y | Unable to access due to schemes | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 315 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 | 71 Gullies On Tablet 5 not on Tablet but Cleaned Out |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 316 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 1 | 0 | 1 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/629 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 314 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 | 71 Gullies On Tablet 5 not on Tablet but Cleaned Out |  |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 314 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 | 71 Gullies On Tablet 5 not on Tablet but Cleaned Out |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 317 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE6 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 318 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 317 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE6 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 319 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 49 | 0 | 49 | 0 | No Filter Drain Completed No men assigned from CGS |  |  | 4700M62/626 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 108/1 | 112/5 | 52028846 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 319 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 573 | 0 | 573 | 0 | No Filter Drain Completed No men assigned from CGS |  |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 108/1 | 112/5 | 52028846 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 320 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 143 | 0 | 143 | 0 |  | Y |  | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 320 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 211 | 0 | 211 | 0 |  | Y |  | 4700M62/913 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 321 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 178 | 0 | 178 | 0 |  | Y |  | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE6 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 320 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 193 | 0 | 193 | 0 |  | Y |  | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 321 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 486 | 0 | 486 | 0 |  | Y |  | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE6 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 320 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 170 | 0 | 170 | 0 |  | Y |  | 4700M62/953 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 321 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 126 | 0 | 126 | 0 |  | Y |  | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE6 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 320 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 126 | 0 | 126 | 0 |  | Y |  | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 322 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 160.15 | 0 | 160.15 | 0 |  | Y |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 322 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 315 | 0 | 315 | 0 |  | Y |  | 4700M62/629 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 323 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1737.17 | 0 | 1737.17 | 0 |  | Y |  | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 323 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 978.82 | 0 | 978.82 | 0 |  | Y |  | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 324 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/626 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 325 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 | only 4 catchpit in closure |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 45792609 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 325 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 | only 4 catchpit in closure |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 45792609 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 325 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 | only 4 catchpit in closure |  |  | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 45792609 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 325 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 | only 4 catchpit in closure |  |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/5 | 45792609 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 324 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 326 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 73 | 0 | 73 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/907 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45792916
YNE6 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 327 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/907 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 326 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE6 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 326 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE6 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 327 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 327 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/913 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 327 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 326 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE6 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 326 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE6 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 327 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/953 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 327 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure Amey 45048 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 328 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE6: M62 J27-28 | YNE6 Closure | Lane 1 Closure | 1 |  |  | 2 times per year |  |  | On ServiceNow
YNE6 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 329 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 2848 | 0 | 2848 | 0 |  | Y |  |  | YNE6: M62 J27-28 | YNE6 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE6 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 330 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 331 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE6 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 332 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 333 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 23.9694 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 | 3 complete more detail as to which 3 along with evidence needed |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45817477 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 333 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 32 | 0 | 32 | 0 | 3 complete more detail as to which 3 along with evidence needed |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45817477 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 333 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 | 3 complete more detail as to which 3 along with evidence needed |  |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45817477 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 333 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 12 | 0 | 12 | 0 | 3 complete more detail as to which 3 along with evidence needed |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45817477 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 334 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 40 | 0 | 40 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45817477
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 334 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 36 | 0 | 36 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45817477
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 334 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 19 | 0 | 19 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45817477
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 4 | 0 | 4 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 29 | 0 | 29 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 49 | 0 | 49 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/629 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 15 | 0 | 15 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/631 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 16 | 0 | 16 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 335 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 49 | 0 | 49 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45783591 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 10 | 0 | 10 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45899054
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 56 | 0 | 56 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45899054
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 27 | 0 | 27 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45899054
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 4 | 0 | 4 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45899054
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 4 | 0 | 4 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45899054
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 23 | 0 | 23 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45899054
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 2 | 0 | 2 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/953 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45899054
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 19 | 0 | 19 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45899054
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 336 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 23 | 0 | 23 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45899054
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 337 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 70 | 0 | 70 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 45899092 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 338 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 8 | 0 | 8 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898903
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 338 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 4 | 0 | 4 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898903
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 338 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 4 | 0 | 4 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45898903
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 339 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 21 | 0 | 21 | 0 | 10 Locations to Complete Majority with steps to strim for access to Feeder Pillar |  |  | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 45793092 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 339 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7 | 0 | 7 | 0 | 10 Locations to Complete Majority with steps to strim for access to Feeder Pillar |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 45793092 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 339 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 38 | 14 | 24 | 0.36842 | 10 Locations to Complete Majority with steps to strim for access to Feeder Pillar |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 45793092 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 339 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2 | 0 | 2 | 0 | 10 Locations to Complete Majority with steps to strim for access to Feeder Pillar |  |  | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 45793092 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 339 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3 | 0 | 3 | 0 | 10 Locations to Complete Majority with steps to strim for access to Feeder Pillar |  |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 45793092 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 339 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 22 | 0 | 22 | 0 | 10 Locations to Complete Majority with steps to strim for access to Feeder Pillar |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 45793092 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 3 | 0 | 3 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1 | 0 | 1 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/909 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 48 | 0 | 48 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 51 | 0 | 51 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 25 | 0 | 25 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 340 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1 | 0 | 1 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 341 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 255.9 | 0 | 255.9 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 45813682 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 341 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 292.77 | 0 | 292.77 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 45813682 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 341 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 65.17 | 0 | 65.17 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 45813682 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 341 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 66.27 | 0 | 66.27 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 45813682 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 342 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 185.55 | 0 | 185.55 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 342 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 98.25 | 0 | 98.25 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 342 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 44.48 | 0 | 44.48 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | Raised by route to be re-raise
YNE6 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.2521 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 219 | 219 | 0 | 1 |  |  |  | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 52028860 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.8752 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 451 | 451 | 0 | 1 |  |  |  | 4700M62/626 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 52028860 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 38.0833 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1334 | 1334 | 0 | 1 |  |  |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 52028860 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 43.9928 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1541 | 1541 | 0 | 1 |  |  |  | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 52028860 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.6436 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 583 | 583 | 0 | 1 |  |  |  | 4700M62/629 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 52028860 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.9062 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 347 | 347 | 0 | 1 |  |  |  | 4700M62/631 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 52028860 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.1403 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 110 | 110 | 0 | 1 |  |  |  | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 52028860 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.7416 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1287 | 1287 | 0 | 1 |  |  |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 52028860 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 343 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.58 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 861 | 861 | 0 | 1 |  |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 108/1 | 112/5 | 52028860 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 110 | 0 | 110 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/907 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 347 | 0 | 347 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 405 | 0 | 405 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/909 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1718 | 0 | 1718 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 819 | 0 | 819 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 720 | 0 | 720 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 207 | 0 | 207 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/913 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 246 | 0 | 246 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 2012 | 0 | 2012 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 572 | 0 | 572 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/953 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 189 | 0 | 189 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 344 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1348 | 0 | 1348 | 0 | 1/11 - works cancelled 10:10am due to bad weather forecast | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | Raised by route to be re-raise
YNE6 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 345 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 711.16 | 0 | 711.16 | 0 |  | Y |  | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 346 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 378.28 | 0 | 378.28 | 0 |  | Y |  | 4700M62/907 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 346 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1115.66 | 0 | 1115.66 | 0 |  | Y |  | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 346 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 448.84 | 0 | 448.84 | 0 |  | Y |  | 4700M62/909 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 346 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 830.08 | 0 | 830.08 | 0 |  | Y |  | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 346 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 979.16 | 0 | 979.16 | 0 |  | Y |  | 4700M62/913 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 346 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 908.16 | 0 | 908.16 | 0 |  | Y |  | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 346 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 76.84 | 0 | 76.84 | 0 |  | Y |  | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 113/3 | 108/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 347 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 297.78 | 0 | 297.78 | 0 | None complete - lack of CGS resource/understanding scope of work |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 108/1 | 112/5 | 52038560 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 348 | Sweeping - Paved non-running areas - Full Sweep 01 | 116.8587 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 15689.5 | 15689.5 | 0 | 1 |  |  |  | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year | 108/1 | 112/5 | 52033915 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 349 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 6957 |  | 6957 | 0 |  | Y | Unable to access due to schemes | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually | 108/1 | 112/5 | 52033931 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB OS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 350 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 6957 | 0 | 6957 | 0 |  | Y | Unable to access due to schemes - booked for January | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually | 108/1 | 112/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 351 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 0 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 19249 |  | 19249 | 0 |  | Y | Unable to access due to schemes | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually | 108/1 | 112/5 | 52033943 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 219 |  | 219 | 0 |  | Y | Unable to access due to schemes | 4700M62/624 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 108/1 | 112/5 | 52034159 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 451 |  | 451 | 0 |  | Y | Unable to access due to schemes | 4700M62/626 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually | 108/1 | 112/5 | 52034159 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 2045 |  | 2045 | 0 |  | Y | Unable to access due to schemes | 4700M62/627 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually | 108/1 | 112/5 | 52034159 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 1541 |  | 1541 | 0 |  | Y | Unable to access due to schemes | 4700M62/628 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually | 108/1 | 112/5 | 52034159 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 583 |  | 583 | 0 |  | Y | Unable to access due to schemes | 4700M62/629 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually | 108/1 | 112/5 | 52034159 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 347 |  | 347 | 0 |  | Y | Unable to access due to schemes | 4700M62/631 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually | 108/1 | 112/5 | 52034159 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 352 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-15 | 2023-12 | 2023-12-16 | 2023-05-02 | 2023-05-31 | 2023-12-31 | Subject to roadspace currently clashing with schemes | 21dys | EB | 110 |  | 110 | 0 |  | Y | Unable to access due to schemes | 4700M62/632 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually | 108/1 | 112/5 | 52034159 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 353 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 16.8397 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1287 | 1287 | 0 | 1 | 108/4 - 109/5 Completed on Doforms (Birdwell IRT) Had call out first thing got to closure 22:12hrs 10Bags collected and 1 pick-Up of large debris ( 1 Man ) |  |  | 4700M62/669 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) | 108/1 | 112/5 | 52034159 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 353 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 11.2657 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 861 | 861 | 0 | 1 | 108/4 - 109/5 Completed on Doforms (Birdwell IRT) Had call out first thing got to closure 22:12hrs 10Bags collected and 1 pick-Up of large debris ( 1 Man ) |  |  | 4700M62/670 | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) | 108/1 | 112/5 | 52034159 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 354 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 488 | 0 | 488 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/907 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 354 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1462 | 0 | 1462 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/908 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 354 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 854 | 0 | 854 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/909 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 354 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1718 | 0 | 1718 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/910 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 354 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 819 | 0 | 819 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/911 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 354 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1550 | 0 | 1550 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/912 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 354 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1186 | 0 | 1186 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/913 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 354 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1154 | 0 | 1154 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/914 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | Annually |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 355 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 2089 | 0 | 2089 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/952 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 355 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 572 | 0 | 572 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/953 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 355 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 189 | 0 | 189 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/954 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820525
YNE6 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 355 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 1348 | 0 | 1348 | 0 |  | Y | Unable to access due to schemes - liaising with Roadspace for suitable date before end of FY | 4700M62/962 | YNE6: M62 J27-28 | YNE6 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820525
YNE7 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 335.68 | 0 | 335.68 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 5.27 | 0 | 5.27 | 0 |  | Y |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 357 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 141.63 | 0 | 141.63 | 0 |  | Y |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 347.18 | 0 | 347.18 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 357 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 119.08 | 0 | 119.08 | 0 |  | Y |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | CW | 56.82 | 0 | 56.82 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 357 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | CW | 356.53 | 0 | 356.53 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 358 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 49.24 | 0 | 49.24 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 359 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 32.86 | 0 | 32.86 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 358 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 367.84 | 0 | 367.84 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 359 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 34.53 | 0 | 34.53 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 358 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 163.09 | 0 | 163.09 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 359 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 202.68 | 0 | 202.68 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 358 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 764.63 | 0 | 764.63 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 358 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 486.84 | 0 | 486.84 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 358 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 119.02 | 0 | 119.02 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 359 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 16.74 | 0 | 16.74 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 358 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 108.83 | 0 | 108.83 | 0 |  | Y |  | 4700M62/675 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 359 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 8.26 | 0 | 8.26 | 0 |  | Y |  | 4700M62/675 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 359 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 87.66 | 0 | 87.66 | 0 |  | Y |  | 4700M62/676 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 359 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 80.93 | 0 | 80.93 | 0 |  | Y |  | 4700M62/677 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 358 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 227.14 | 0 | 227.14 | 0 |  | Y |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 359 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 226.52 | 0 | 226.52 | 0 |  | Y |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 358 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 148.4 | 0 | 148.4 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 359 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 372.69 | 0 | 372.69 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 358 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 368.08 | 0 | 368.08 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 359 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 685.84 | 0 | 685.84 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 870.48 | 0 | 870.48 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 745.69 | 0 | 745.69 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 308.07 | 0 | 308.07 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 357 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 32.63 | 0 | 32.63 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 58.58 | 0 | 58.58 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 357 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 33.41 | 0 | 33.41 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 567.31 | 0 | 567.31 | 0 |  | Y |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 357 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 234.51 | 0 | 234.51 | 0 |  | Y |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 356 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 1063.23 | 0 | 1063.23 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 357 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 56.57 | 0 | 56.57 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 360 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 361 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 361 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 362 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 361 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 362 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 361 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 362 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 105 | 0 | 105 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 364 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | EB | 58 | 0 | 58 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 364 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/673 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/675 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/676 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 364 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/676 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 363 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 364 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 360 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 141 | 0 | 141 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE7 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 365 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 361 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 361 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 362 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 361 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 361 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 362 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 361 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 361 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 362 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 375 | 0 | 375 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 367 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 306 | 0 | 306 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 709 | 0 | 709 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 292 | 0 | 292 | 0 |  | Y |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 367 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1352 | 0 | 1352 | 0 |  | Y |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | CW | 204 | 0 | 204 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 367 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | CW | 102 | 0 | 102 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 368 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 111 | 0 | 111 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 369 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 31 | 0 | 31 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 368 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 398 | 0 | 398 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 368 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 830 | 0 | 830 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 368 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 697 | 0 | 697 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 369 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 94 | 0 | 94 | 0 |  | Y |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 368 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 31 | 0 | 31 | 0 |  | Y |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 369 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 94 | 0 | 94 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 368 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 359 | 0 | 359 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 369 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 93 | 0 | 93 | 0 |  | Y |  | 4700M62/673 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 368 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 76 | 0 | 76 | 0 |  | Y |  | 4700M62/676 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 368 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 532 | 0 | 532 | 0 |  | Y |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 368 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 796 | 0 | 796 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 369 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 186 | 0 | 186 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 368 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 2230 | 0 | 2230 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 369 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 78 | 0 | 78 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 24 | 0 | 24 | 0 |  | Y |  | 4700M62/901 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 367 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 285 | 0 | 285 | 0 |  | Y |  | 4700M62/901 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1333 | 0 | 1333 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 367 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 802 | 0 | 802 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 877 | 0 | 877 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 367 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 707 | 0 | 707 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 367 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 869 | 0 | 869 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 377 | 0 | 377 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 367 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 307 | 0 | 307 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 94 | 0 | 94 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 367 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 76 | 0 | 76 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 2672 | 0 | 2672 | 0 |  | Y |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 366 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 2073 | 0 | 2073 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE7 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 370 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 90.01 | 0 | 90.01 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 371 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 407.71 | 0 | 407.71 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 371 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1146.05 | 0 | 1146.05 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 371 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 559.79 | 0 | 559.79 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 372 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 178.42 | 0 | 178.42 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 371 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 319.57 | 0 | 319.57 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 372 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1018.04 | 0 | 1018.04 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 WB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 373 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1465.34 | 0 | 1465.34 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 WB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 373 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 544.36 | 0 | 544.36 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 370 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 125.82 | 0 | 125.82 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 375 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 375 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 375 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 377 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 377 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 377 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 377 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 377 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 377 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/676 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 377 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 376 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 377 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/901 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 375 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 375 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 375 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 375 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 374 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE7 Closure Amey 45048 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 378 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 0 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys |  | 6 | 0 | 6 | 0 |  | Y |  |  | YNE7: M62 J28-29 | YNE7 Closure | Lane 1 Closure | 1 |  |  | 2 times per year |  |  | On ServiceNow
YNE7 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 379 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys |  | 2621 | 0 | 2621 | 0 |  | Y |  |  | YNE7: M62 J28-29 | YNE7 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 380 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 381 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 382 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 383 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 2 | 0 | 2 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 384 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 384 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 16 | 0 | 16 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 384 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 10 | 0 | 10 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 384 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 383 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 383 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 2 | 0 | 2 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 17 | 0 | 17 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 9 | 0 | 9 | 0 |  | Y |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 19 | 0 | 19 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 9 | 0 | 9 | 0 |  | Y |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 13 | 0 | 13 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 29 | 0 | 29 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 29 | 0 | 29 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 21 | 0 | 21 | 0 |  | Y |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/673 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/675 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 2 | 0 | 2 | 0 |  | Y |  | 4700M62/677 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 3 | 0 | 3 | 0 |  | Y |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 12 | 0 | 12 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 386 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 24 | 0 | 24 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/901 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 27 | 0 | 27 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 25 | 0 | 25 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 7 | 0 | 7 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 12 | 0 | 12 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 2 | 0 | 2 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 24 | 0 | 24 | 0 |  | Y |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 26 | 0 | 26 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 385 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | CW | 25 | 0 | 25 | 0 |  | Y |  | 4700M62/952 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 387 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 20 | 0 | 20 | 0 |  | Y |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 387 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 9 | 0 | 9 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 387 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | CW | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 388 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 29 | 0 | 29 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 388 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 8 | 0 | 8 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 23 | 0 | 23 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 16 | 0 | 16 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/673 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 8 | 0 | 8 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 390 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 2 | 0 | 2 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 389 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 391 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 27.09 | 0 | 27.09 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 391 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 84.24 | 0 | 84.24 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 391 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 51.58 | 0 | 51.58 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 392 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 131.28 | 0 | 131.28 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 392 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 295.44 | 0 | 295.44 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 392 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 56.86 | 0 | 56.86 | 0 |  | Y |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 327 | 0 | 327 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 148 | 0 | 148 | 0 |  | Y |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 352 | 0 | 352 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 161 | 0 | 161 | 0 |  | Y |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | CW | 761 | 0 | 761 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 123 | 0 | 123 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 444 | 0 | 444 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 715 | 0 | 715 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 677 | 0 | 677 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 460 | 0 | 460 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 671 | 0 | 671 | 0 |  | Y |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 261 | 0 | 261 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 15 | 0 | 15 | 0 |  | Y |  | 4700M62/673 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 252 | 0 | 252 | 0 |  | Y |  | 4700M62/675 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 157 | 0 | 157 | 0 |  | Y |  | 4700M62/676 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 99 | 0 | 99 | 0 |  | Y |  | 4700M62/677 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 202 | 0 | 202 | 0 |  | Y |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 785 | 0 | 785 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 394 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1782 | 0 | 1782 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 256 | 0 | 256 | 0 |  | Y |  | 4700M62/901 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 801 | 0 | 801 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 689 | 0 | 689 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 758 | 0 | 758 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 419 | 0 | 419 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 125 | 0 | 125 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1021 | 0 | 1021 | 0 |  | Y |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 393 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 941 | 0 | 941 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE7 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 395 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 69.26 | 0 | 69.26 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 395 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 0 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 64.92 | 0 | 64.92 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 396 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 5286 | 0 | 5286 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 397 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 46 | 0 | 46 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE7 Closure 1 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 398 | Sweeping - Paved non-running areas - Full Sweep 01 | 89.373 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 11999.25 | 11999.25 | 0 | 1 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 399 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 3266.5 | 0 | 3266.5 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 WB OS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 400 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 3266.5 | 0 | 3266.5 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 401 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 0 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace - full closures | 21dys | WB | 35283 | 0 | 35283 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 327 | 0 | 327 | 0 |  | Y |  | 4700M62/273 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 403 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 148 | 0 | 148 | 0 |  | Y |  | 4700M62/289 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 403 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 352 | 0 | 352 | 0 |  | Y |  | 4700M62/405 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 403 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 161 | 0 | 161 | 0 |  | Y |  | 4700M62/406 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 761 | 0 | 761 | 0 |  | Y |  | 4700M62/598 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 404 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 123 | 0 | 123 | 0 |  | Y |  | 4700M62/641 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 404 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 444 | 0 | 444 | 0 |  | Y |  | 4700M62/642 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 404 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 715 | 0 | 715 | 0 |  | Y |  | 4700M62/643 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 404 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 677 | 0 | 677 | 0 |  | Y |  | 4700M62/646 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 404 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 460 | 0 | 460 | 0 |  | Y |  | 4700M62/647 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 404 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 671 | 0 | 671 | 0 |  | Y |  | 4700M62/648 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 404 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 261 | 0 | 261 | 0 |  | Y |  | 4700M62/649 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 405 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 15 | 0 | 15 | 0 |  | Y |  | 4700M62/673 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 405 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 252 | 0 | 252 | 0 |  | Y |  | 4700M62/675 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 405 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 157 | 0 | 157 | 0 |  | Y |  | 4700M62/676 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 405 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 99 | 0 | 99 | 0 |  | Y |  | 4700M62/677 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 405 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 203 | 0 | 203 | 0 |  | Y |  | 4700M62/678 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 405 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 785 | 0 | 785 | 0 |  | Y |  | 4700M62/679 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 405 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1782 | 0 | 1782 | 0 |  | Y |  | 4700M62/680 | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 256 | 0 | 256 | 0 |  | Y |  | 4700M62/901 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 801 | 0 | 801 | 0 |  | Y |  | 4700M62/902 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 689 | 0 | 689 | 0 |  | Y |  | 4700M62/903 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 758 | 0 | 758 | 0 |  | Y |  | 4700M62/904 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 488 | 0 | 488 | 0 |  | Y |  | 4700M62/905 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 402 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 190 | 0 | 190 | 0 |  | Y |  | 4700M62/906 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 403 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1021 | 0 | 1021 | 0 |  | Y |  | 4700M62/950 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE7 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 403 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 941 | 0 | 941 | 0 |  | Y |  | 4700M62/951 | YNE7: M62 J28-29 | YNE7 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE8 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 406 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 240.05 | 0 | 240.05 | 0 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 406 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 728.2 | 0 | 728.2 | 0 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 406 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 1204.35 | 0 | 1204.35 | 0 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 406 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 155.38 | 0 | 155.38 | 0 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 407 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 124 | 0 | 124 | 0 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 406 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 1373.11 | 0 | 1373.11 | 0 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 407 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 128 | 0 | 128 | 0 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 406 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 285.42 | 0 | 285.42 | 0 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 407 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 260.36 | 0 | 260.36 | 0 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 406 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 313.62 | 0 | 313.62 | 0 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 408 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 71.57 | 0 | 71.57 | 0 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 408 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 119.75 | 0 | 119.75 | 0 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 409 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 184.13 | 0 | 184.13 | 0 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 408 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 1028.93 | 0 | 1028.93 | 0 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 409 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 126 | 0 | 126 | 0 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 408 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 153.48 | 0 | 153.48 | 0 |  | Y |  | 4700M62/530 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 409 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 128 | 0 | 128 | 0 |  | Y |  | 4700M62/530 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 408 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 1559.93 | 0 | 1559.93 | 0 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 408 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 738.65 | 0 | 738.65 | 0 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 409 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 79.15 | 0 | 79.15 | 0 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 408 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 87.52 | 0 | 87.52 | 0 |  | Y |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 410 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 236 | 0 | 236 | 0 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 411 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 410 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 411 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 412 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE8 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 413 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 & 3 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE8 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 410 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 410 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 410 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 411 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 410 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 411 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 414 | Gullies - Emptying / clear covers | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 221 | 22 | 199 | 0.099548 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 415 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 414 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 415 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 414 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 415 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 414 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/530 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 414 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 415 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 414 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 415 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 414 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 415 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE8 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 416 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 163 | 0 | 163 | 0 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 416 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 687 | 0 | 687 | 0 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 417 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 338 | 0 | 338 | 0 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 416 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1295 | 0 | 1295 | 0 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 417 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 60 | 0 | 60 | 0 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 416 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 181 | 0 | 181 | 0 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 417 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 149 | 0 | 149 | 0 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 416 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 2004 | 0 | 2004 | 0 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 417 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 896 | 0 | 896 | 0 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 416 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 1720 | 0 | 1720 | 0 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 417 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 69 | 0 | 69 | 0 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 416 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 343 | 0 | 343 | 0 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 417 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 586 | 0 | 586 | 0 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 418 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 365 | 0 | 365 | 0 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 418 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 2092 | 0 | 2092 | 0 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 418 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1061 | 0 | 1061 | 0 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 418 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 151 | 0 | 151 | 0 |  | Y |  | 4700M62/530 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 418 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 1197 | 0 | 1197 | 0 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 418 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 858 | 0 | 858 | 0 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 419 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 212 | 0 | 212 | 0 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 418 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 117 | 0 | 117 | 0 |  | Y |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 419 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 74 | 0 | 74 | 0 |  | Y |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE8 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 420 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 440 | 0 | 440 | 0 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 & 3 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE8 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 420 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 460 | 0 | 460 | 0 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 & 3 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE8 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 421 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1410 | 0 | 1410 | 0 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 & 3 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE8 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 422 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 423 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 12 | 0 | 12 | 0 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 422 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 25 | 0 | 25 | 0 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 423 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 5 | 0 | 5 | 0 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 422 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 29 | 0 | 29 | 0 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 423 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 15 | 0 | 15 | 0 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 422 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 423 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 2 | 0 | 2 | 0 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 422 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 30 | 0 | 30 | 0 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 423 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 422 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 25 | 0 | 25 | 0 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 423 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 3 | 0 | 3 | 0 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 422 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 423 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 8 | 0 | 8 | 0 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 424 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 425 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 2 | 0 | 2 | 0 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 424 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 424 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 425 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 11 | 0 | 11 | 0 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 424 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/530 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 425 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/530 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 424 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 425 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 424 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 425 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 9 | 0 | 9 | 0 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 424 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 425 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 3 | 0 | 3 | 0 |  | Y |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE8 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 426 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 126.7982 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2645 | 2645 | 0 | 1 |  | Y |  |  | YNE8: M62 J29-31 | YNE8 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 427 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB |  | 0 | 0 | 0 |  | Y |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 428 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB |  | 0 | 0 | 0 |  | Y |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 429 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB |  | 0 | 0 | 0 |  | Y |  |  | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 430 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 430 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 430 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 430 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 431 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 431 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 432 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 432 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 20 | 20 | 0 | 1 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 432 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 20 | 20 | 0 | 1 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 432 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 432 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 81.496 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 34 | 34 | 0 | 1 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 432 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 432 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 433 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 433 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 433 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 29 | 29 | 0 | 1 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 433 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/530 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 433 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 30 | 30 | 0 | 1 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 433 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 22 | 22 | 0 | 1 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 433 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 434 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 434 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 435 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 551.2967 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 92 | 92 | 0 | 1 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 435 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 436 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 436 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 436 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 57.3788 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 13 | 13 | 0 | 1 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 436 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 436 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 437 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 88.2751 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 20 | 20 | 0 | 1 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 437 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 437 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 437 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 437 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 438 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.41756 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 20.16 | 20.16 | 0 | 1 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 438 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.47991 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 23.17 | 23.17 | 0 | 1 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 439 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.21852 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10.55 | 10.55 | 0 | 1 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 439 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.2925 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 62.4 | 62.4 | 0 | 1 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 439 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.2094 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10.11 | 10.11 | 0 | 1 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 439 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.3954 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 19.09 | 19.09 | 0 | 1 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 440 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.5743 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1106 | 1106 | 0 | 1 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 440 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.8631 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 976 | 976 | 0 | 1 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 440 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.9161 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1153 | 1153 | 0 | 1 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 440 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.8516 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 240 | 240 | 0 | 1 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 440 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 42.0801 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1474 | 1474 | 0 | 1 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 440 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.3589 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 538 | 538 | 0 | 1 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 440 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.0727 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 563 | 563 | 0 | 1 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 441 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.2701 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 675 | 675 | 0 | 1 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 441 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.8426 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 625 | 625 | 0 | 1 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 441 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.8533 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1396 | 1396 | 0 | 1 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 441 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.7945 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 238 | 238 | 0 | 1 |  | Y |  | 4700M62/530 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 441 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 44.0214 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1542 | 1542 | 0 | 1 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 441 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.8125 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 694 | 694 | 0 | 1 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 441 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4413 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 681 | 681 | 0 | 1 |  | Y |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE8 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 442 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4.0035 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 44.54 | 44.54 | 0 | 1 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 442 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 91.7657 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1020.92 | 1020.92 | 0 | 1 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 442 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 14.8562 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 165.28 | 165.28 | 0 | 1 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 442 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 117.5377 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1307.64 | 1307.64 | 0 | 1 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 442 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 47.7723 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 531.48 | 531.48 | 0 | 1 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 443 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 5.7841 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 64.35 | 64.35 | 0 | 1 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 443 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 4.2893 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 47.72 | 47.72 | 0 | 1 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 444 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 21.4718 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 311 | 311 | 0 | 1 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 445 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 5.8685 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 85 | 85 | 0 | 1 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE8 Closure 1 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 446 | Sweeping - Paved non-running areas - Full Sweep 01 | 76.5322 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10275.25 | 10275.25 | 0 | 1 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE8 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 447 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1101.6347 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 22980 | 22980 | 0 | 1 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE8 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 448 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.0602 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1151 | 1151 | 0 | 1 |  | Y |  | 4700M62/253 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE8 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 449 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 12.7704 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 976 | 976 | 0 | 1 |  | Y |  | 4700M62/256 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE8 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 448 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 28.4456 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2174 | 2174 | 0 | 1 |  | Y |  | 4700M62/259 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE8 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 448 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.3123 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 406 | 406 | 0 | 1 |  | Y |  | 4700M62/262 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE8 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 448 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 36.401 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2782 | 2782 | 0 | 1 |  | Y |  | 4700M62/265 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE8 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 449 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.0394 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 538 | 538 | 0 | 1 |  | Y |  | 4700M62/267 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE8 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 448 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.3144 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1094 | 1094 | 0 | 1 |  | Y |  | 4700M62/270 | YNE8: M62 J29-31 | YNE8 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE8 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 450 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.6694 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 739 | 739 | 0 | 1 |  | Y |  | 4700M62/521 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE8 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 451 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.1909 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 626 | 626 | 0 | 1 |  | Y |  | 4700M62/524 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE8 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 450 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.894 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1444 | 1444 | 0 | 1 |  | Y |  | 4700M62/527 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE8 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 450 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.1141 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 238 | 238 | 0 | 1 |  | Y |  | 4700M62/530 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE8 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 450 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 20.1762 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1542 | 1542 | 0 | 1 |  | Y |  | 4700M62/532 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE8 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 451 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 9.0806 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 694 | 694 | 0 | 1 |  | Y |  | 4700M62/534 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE8 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 450 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.9105 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 681 | 681 | 0 | 1 |  | Y |  | 4700M62/538 | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE9 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 452 | VRS - Check all Road Restraint System - ILM | 2.8817 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 223.97 | 223.97 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 453 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 708.95 |  | 708.95 | 0 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029051
YNE9 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 452 | VRS - Check all Road Restraint System - ILM | 6.7496 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 524.59 | 524.59 | 0 | 1 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 453 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 125.2 |  | 125.2 | 0 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029051
YNE9 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 452 | VRS - Check all Road Restraint System - ILM | 10.1995 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 792.72 | 792.72 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 453 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 1866.8 |  | 1866.8 | 0 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029051
YNE9 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 452 | VRS - Check all Road Restraint System - ILM | 10.3608 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 805.26 | 805.26 | 0 | 1 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 453 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 1397.41 |  | 1397.41 | 0 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029051
YNE9 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 452 | VRS - Check all Road Restraint System - ILM | 6.0958 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 473.78 | 473.78 | 0 | 1 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 453 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 210.05 |  | 210.05 | 0 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029051
YNE9 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 452 | VRS - Check all Road Restraint System - ILM | 2.3206 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 180.36 | 180.36 | 0 | 1 |  | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 453 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 206.06 |  | 206.06 | 0 |  | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029051
YNE9 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 454 | VRS - Check all Road Restraint System - ILM | 3.9079 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 303.73 | 303.73 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 454 | VRS - Check all Road Restraint System - ILM | 7.5158 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 584.14 | 584.14 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 454 | VRS - Check all Road Restraint System - ILM | 10.5098 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 816.84 | 816.84 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 455 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 115.92 |  | 115.92 | 0 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029051
YNE9 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 454 | VRS - Check all Road Restraint System - ILM | 12.7796 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 993.25 | 993.25 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 455 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 93.17 |  | 93.17 | 0 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029051
YNE9 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 454 | VRS - Check all Road Restraint System - ILM | 6.562 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 510.01 | 510.01 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 455 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 80.46 |  | 80.46 | 0 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029051
YNE9 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 454 | VRS - Check all Road Restraint System - ILM | 3.3764 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 262.42 | 262.42 | 0 | 1 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 456 | Gullies - Emptying / clear covers | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-10 | 2024-1 | 2024-01-11 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 195 | 22 | 173 | 0.11282 | 22/11 - cancelled strong winds | N | 22/11 - cancelled strong winds | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 129/5 | 124/5 | 45782450 | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 457 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE9 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 458 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 459 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE9 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 458 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 459 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1551.6892 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 201 | 201 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE9 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 456 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 456 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 457 | Gullies - Emptying / clear covers | 841.4633 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | WB | 112 | 109 | 3 | 0.97321 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782450
YNE9 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 456 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 460 | Gullies - Emptying / clear covers | 1605.7281 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-24 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 158 | 208 | -50 | 1.3165 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782450
YNE9 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 461 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE9 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 462 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE9 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 463 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE9 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 460 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE9 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 461 | Gullies - Emptying / clear covers | 972.7007 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 126 | 126 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE9 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 460 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE9 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 461 | Gullies - Emptying / clear covers | 1065.3388 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2024-01-31 | Subject to roadspace approval | 21dys | EB | 178 | 138 | 40 | 0.77528 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782450
YNE9 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 460 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE9 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 461 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782450
YNE9 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 460 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE9 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 461 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782450
YNE9 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 464 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.4713 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 425 | 425 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 465 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.6974 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 353 | 353 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 464 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 48.0695 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1951 | 1951 | 0 | 1 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 465 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.2453 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 497 | 497 | 0 | 1 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 464 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 260.4771 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10572 | 10572 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 465 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 103.6291 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4206 | 4206 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 464 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 168.8469 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6853 | 6853 | 0 | 1 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 465 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 66.2526 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2689 | 2689 | 0 | 1 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 464 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 35.8242 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1454 | 1454 | 0 | 1 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 465 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 22.6427 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 919 | 919 | 0 | 1 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 464 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0.68987 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 28 | 28 | 0 | 1 |  | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 465 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 26.3384 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1069 | 1069 | 0 | 1 |  | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 466 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.8495 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 278 | 278 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 467 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 11.3829 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 462 | 462 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 466 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 57.2596 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2324 | 2324 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 467 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 15.5715 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 632 | 632 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 466 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 90.7186 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3682 | 3682 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 467 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 29.5661 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1200 | 1200 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 466 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 128.5631 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5218 | 5218 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 467 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 29.3197 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1190 | 1190 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 466 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 43.4375 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1763 | 1763 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 467 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.0091 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 528 | 528 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 467 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 49.1782 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1996 | 1996 | 0 | 1 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE9 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 468 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 469 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 468 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 469 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9 | 0 | 9 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45808774
YNE9 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 468 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 469 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 450.3244 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 21 | 21 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 468 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 469 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 214.4402 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 468 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 469 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 19 | 0 | 19 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45808774
YNE9 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 468 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 469 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 14 | 0 | 14 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45808774
YNE9 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 470 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 471 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 171.5521 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 8 | 2 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45808774
YNE9 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 470 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 471 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 0 | 12 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45808774
YNE9 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 470 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 471 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 33 | 0 | 33 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45808774
YNE9 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 470 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 471 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1029.3129 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 48 | 48 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 470 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE9 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 471 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 0 | 8 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45808774
YNE9 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 471 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 26 | 7 | 19 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45808774
YNE9 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 472 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 108.7253 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 2268 | 2268 | 0 | 1 |  | N |  |  | YNE9: M62 J31-32 | YNE9 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 473 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 474 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 475 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 476 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 477 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 477 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 143.8165 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 477 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 478 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 478 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 478 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 32 | 32 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 478 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 25 | 25 | 0 | 1 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 478 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 478 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 479 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 479 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 479 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 479 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 86.2899 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 36 | 36 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 479 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 21 | 21 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 479 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 480 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 480 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 481 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 83.893 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 482 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 482 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 483 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 483 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 483 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 483 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 483 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 484 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.26781 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 12.93 | 12.93 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 484 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.7299 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 83.52 | 83.52 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 484 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.19987 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9.65 | 9.65 | 0 | 1 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 484 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.7452 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 132.54 | 132.54 | 0 | 1 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 485 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.8747 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 90.51 | 90.51 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 485 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.2108 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 58.46 | 58.46 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 486 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.2994 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 641 | 641 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 486 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.9862 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 595 | 595 | 0 | 1 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 486 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 48.3321 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1693 | 1693 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 486 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.7424 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1252 | 1252 | 0 | 1 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 486 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.5033 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 473 | 473 | 0 | 1 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 486 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.7619 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 412 | 412 | 0 | 1 |  | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 487 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.6697 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 689 | 689 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 487 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.0433 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 597 | 597 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 487 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.7489 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 972 | 972 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 487 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 48.7033 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1706 | 1706 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 487 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9299 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 558 | 558 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 487 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.6143 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 617 | 617 | 0 | 1 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE9 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 488 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 179.7042 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1999.26 | 1999.26 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 488 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 389.4866 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4333.15 | 4333.15 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 488 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 47.6284 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 529.88 | 529.88 | 0 | 1 |  | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 489 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 9.5171 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 105.88 | 105.88 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 490 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1.0356 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 491 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 49.0192 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 710 | 710 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE9 Closure 1 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 492 | Sweeping - Paved non-running areas - Full Sweep 01 | 81.53 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10946.25 | 10946.25 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 493 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 864.3853 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 18031 | 18031 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 494 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 34.543 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2640 | 2640 | 0 | 1 |  | N |  | 4700M62/234 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 495 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.7853 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 595 | 595 | 0 | 1 |  | N |  | 4700M62/237 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 494 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 78.8469 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6026 | 6026 | 0 | 1 |  | N |  | 4700M62/240 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 494 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.3817 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1252 | 1252 | 0 | 1 |  | N |  | 4700M62/243 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 495 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.1889 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 473 | 473 | 0 | 1 |  | N |  | 4700M62/247 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 494 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.3256 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 942 | 942 | 0 | 1 |  | N |  | 4700M62/250 | YNE9: M62 J31-32 | YNE9 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually | 129/5 | 124/5 |  | 22:30 | 6:00 |  | Approved | 0
YNE9 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 496 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.0152 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 689 | 689 | 0 | 1 |  | N |  | 4700M62/542 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE9 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 497 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.8114 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 597 | 597 | 0 | 1 |  | N |  | 4700M62/545 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE9 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 496 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.7181 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 972 | 972 | 0 | 1 |  | N |  | 4700M62/548 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE9 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 496 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.696 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1811 | 1811 | 0 | 1 |  | N |  | 4700M62/550 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE9 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 497 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.3011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 558 | 558 | 0 | 1 |  | N |  | 4700M62/552 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE9 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 496 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.0731 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 617 | 617 | 0 | 1 |  | N |  | 4700M62/554 | YNE9: M62 J31-32 | YNE9 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 498 | VRS - Check all Road Restraint System - ILM | 3.4388 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 267.27 | 267.27 | 0 | 1 |  | N |  | 4700A1M/460 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 499 | VRS - Check all Road Restraint System - ILM | 2.8365 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 220.46 | 220.46 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 498 | VRS - Check all Road Restraint System - ILM | 4.947 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 384.49 | 384.49 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 499 | VRS - Check all Road Restraint System - ILM | 6.4269 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 499.51 | 499.51 | 0 | 1 |  | N |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 499 | VRS - Check all Road Restraint System - ILM | 6.9112 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 537.15 | 537.15 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 500 | VRS - Check all Road Restraint System - ILM | 1.6373 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 127.25 | 127.25 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 498 | VRS - Check all Road Restraint System - ILM | 1.7264 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 134.18 | 134.18 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 501 | VRS - Check all Road Restraint System - ILM | 1.5679 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 121.86 | 121.86 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 499 | VRS - Check all Road Restraint System - ILM | 1.3057 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 101.48 | 101.48 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 500 | VRS - Check all Road Restraint System - ILM | 0.83696 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 65.05 | 65.05 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 498 | VRS - Check all Road Restraint System - ILM | 3.4244 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 266.15 | 266.15 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 501 | VRS - Check all Road Restraint System - ILM | 1.4192 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 110.3 | 110.3 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 499 | VRS - Check all Road Restraint System - ILM | 3.5156 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 273.24 | 273.24 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 500 | VRS - Check all Road Restraint System - ILM | 4.8984 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 380.71 | 380.71 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 498 | VRS - Check all Road Restraint System - ILM | 17.1233 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1330.85 | 1330.85 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 501 | VRS - Check all Road Restraint System - ILM | 7.876 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 612.14 | 612.14 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 499 | VRS - Check all Road Restraint System - ILM | 14.3844 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1117.98 | 1117.98 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 500 | VRS - Check all Road Restraint System - ILM | 14.5297 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1129.27 | 1129.27 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 501 | VRS - Check all Road Restraint System - ILM | 2.3298 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 181.08 | 181.08 | 0 | 1 |  | N |  | 4700M62/802 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 500 | VRS - Check all Road Restraint System - ILM | 6.3837 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 496.15 | 496.15 | 0 | 1 |  | N |  | 4700M62/803 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 498 | VRS - Check all Road Restraint System - ILM | 10.9193 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 848.67 | 848.67 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 501 | VRS - Check all Road Restraint System - ILM | 4.211 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 327.29 | 327.29 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 499 | VRS - Check all Road Restraint System - ILM | 9.2018 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 715.18 | 715.18 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 500 | VRS - Check all Road Restraint System - ILM | 14.5904 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1133.99 | 1133.99 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 498 | VRS - Check all Road Restraint System - ILM | 11.4678 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 891.3 | 891.3 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 501 | VRS - Check all Road Restraint System - ILM | 5.4907 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 426.75 | 426.75 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 499 | VRS - Check all Road Restraint System - ILM | 11.2752 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 876.33 | 876.33 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 500 | VRS - Check all Road Restraint System - ILM | 13.6293 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1059.29 | 1059.29 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 498 | VRS - Check all Road Restraint System - ILM | 3.5269 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 274.12 | 274.12 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 499 | VRS - Check all Road Restraint System - ILM | 4.7158 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 366.52 | 366.52 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 500 | VRS - Check all Road Restraint System - ILM | 10.6857 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 830.51 | 830.51 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 498 | VRS - Check all Road Restraint System - ILM | 3.0915 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 240.28 | 240.28 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 499 | VRS - Check all Road Restraint System - ILM | 3.4608 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 268.98 | 268.98 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 502 | Gullies - Emptying / clear covers | 1358.693 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-22 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 176 | 176 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 503 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 9 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 504 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 505 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | Y |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 502 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 0 | 0 | 0 | 1 |  | Y |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 505 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | Y |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 503 | Gullies - Emptying / clear covers | 447.7511 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-25 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 58 | 58 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 504 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 502 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 0 | 0 | 0 | 1 |  | Y |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 505 | Gullies - Emptying / clear covers | 254.7549 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 33 | 33 | 0 | 1 |  | Y |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 504 | Gullies - Emptying / clear covers | 293.3542 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 38 | 38 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 502 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 0 | 0 | 0 | 1 |  | Y |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 505 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | Y |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 503 | Gullies - Emptying / clear covers | 200.716 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 32 | 26 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 504 | Gullies - Emptying / clear covers | 385.9923 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 50 | 50 | 0 | 1 |  | Y |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 506 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 0 | 0 | 0 | 1 |  | Y |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE10 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 507 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | Y |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 & 3 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45783659
YNE10 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 503 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 0 | 0 | 1 |  | Y |  | 4700M62/802 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 504 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | Y |  | 4700M62/802 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 503 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 506 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 0 | 0 | 0 | 1 |  | Y |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE10 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 507 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | Y |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 & 3 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45783659
YNE10 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 503 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 9 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 504 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 506 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 0 | 0 | 0 | 1 |  | Y |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE10 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 507 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 92.6382 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  | Y |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 & 3 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45783659
YNE10 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 503 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 0 | 0 | 1 |  | Y |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 504 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | Y |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 503 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 0 | 0 | 1 |  | Y |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 504 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | Y |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 502 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 0 | 0 | 0 | 1 |  | Y |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 505 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | Y |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45783659
YNE10 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 508 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 20.4991 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 832 | 832 | 0 | 1 |  | N |  | 4700A1M/460 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 509 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.361 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 177 | 177 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 510 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.6261 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 66 | 66 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 508 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.4901 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 304 | 304 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 511 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.3015 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 134 | 134 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 509 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.0075 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 325 | 325 | 0 | 1 |  | N |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 509 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 50.6565 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2056 | 2056 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 510 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.3771 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 340 | 340 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 508 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 25.1065 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1019 | 1019 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 511 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.1596 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 250 | 250 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 509 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.4772 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 547 | 547 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 510 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 26.437 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 1073 | 1073 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 511 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 15.8918 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 645 | 645 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 509 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 14.4135 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 585 | 585 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 510 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.6989 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 556 | 556 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 508 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 48.6608 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1975 | 1975 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 511 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 22.2977 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 905 | 905 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 509 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 35.6271 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1446 | 1446 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 510 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 25.4515 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1033 | 1033 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 510 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.1569 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 534 | 534 | 0 | 1 |  | N |  | 4700M62/803 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 508 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 20.376 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 827 | 827 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 511 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 15.2512 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 619 | 619 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 509 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 60.438 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2453 | 2453 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 510 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.2206 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 496 | 496 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 508 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 25.0326 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1016 | 1016 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 511 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.8773 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 685 | 685 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 509 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 19.3165 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 784 | 784 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 510 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.8682 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 157 | 157 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 508 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.2319 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 50 | 50 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 511 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 11.7279 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 476 | 476 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 510 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.7016 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 272 | 272 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 508 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 28.2849 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1148 | 1148 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 511 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 14.2164 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 577 | 577 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 509 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.3294 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 541 | 541 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 510 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.0337 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 529 | 529 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE10 Closure 1 WB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 512 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2.7876 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 36.11 | 36.11 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE10 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 513 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 2337.398 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-25 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 109 | 109 | 0 | 1 |  | N |  | 4700A1M/460 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 4760.5721 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-22 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 222 | 222 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 515 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 0 | 1 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 513 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 515 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 0 | 7 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 513 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 516 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 0 | 5 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 515 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 15 | 0 | 15 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 513 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 516 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13 | 7 | 6 | 1 | 15/9: No jobs - catchpits on NS? | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 515 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 0 | 6 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 513 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 516 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 0 | 16 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 515 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 0 | 6 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 516 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 0 | 1 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/802 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 515 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 0 | 3 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/803 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 513 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 516 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13 | 0 | 13 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 515 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 0 | 1 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 513 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 516 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13 | 0 | 13 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 515 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 0 | 5 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 513 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 516 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 0 | 2 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 515 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 0 | 7 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 EB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 513 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 EB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 516 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 0 | 10 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure 1 WB NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 514 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE10 Closure 1 WB OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 515 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 0 | 10 | 1 | 15/9: No jobs - catchpits on NS? | Y |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45791012
YNE10 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 517 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 139.8376 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2917 | 2917 | 0 | 1 |  | N |  |  | YNE10: M62 J32-33 | YNE10 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 518 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 519 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 520 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB |  |  | 0 | 0 |  |  |  |  | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 521 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 143.8165 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 522 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 239.6942 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 100 | 100 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 98.2746 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 41 | 41 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 27 | 27 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/802 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 19 | 19 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 19 | 19 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 26 | 26 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 55.1297 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 23 | 23 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 524 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 523 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 525 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 526 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 239.6942 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 40 | 40 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 525 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1090.6087 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 182 | 182 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 525 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 526 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 528 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 5 | 5 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 528 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 101.5164 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 23 | 23 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 528 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 75.0338 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 528 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 528 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 528 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 527 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 528 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 529 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.86785 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 41.9 | 41.9 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 529 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.71603 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 34.57 | 34.57 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 530 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 178.8155 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | SB | 4316.64 | 4316.64 | 0 | 1 |  | N |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.558 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 580 | 580 | 0 | 1 |  | N |  | 4700A1M/460 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.4478 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 401 | 401 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.8777 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 346 | 346 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.2464 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 464 | 464 | 0 | 1 |  | N |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.054 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1368 | 1368 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.7766 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1008 | 1008 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.7807 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 833 | 833 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.4788 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 297 | 297 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.8777 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 346 | 346 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.9137 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1258 | 1258 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.9471 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1049 | 1049 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.8777 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 346 | 346 | 0 | 1 |  | N |  | 4700M62/802 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.0465 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 457 | 457 | 0 | 1 |  | N |  | 4700M62/803 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.2905 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1026 | 1026 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.9756 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1050 | 1050 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.2032 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1093 | 1093 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.3207 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 957 | 957 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.7284 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 621 | 621 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.0678 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 773 | 773 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 531 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.9886 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 490 | 490 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 532 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.2439 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 569 | 569 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE10 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 65.3394 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 726.92 | 726.92 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 244.6265 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2721.54 | 2721.54 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 185.4595 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2063.29 | 2063.29 | 0 | 1 |  | N |  | 4700M62/803 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 534 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 82.2649 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 915.22 | 915.22 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 219.9818 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2447.36 | 2447.36 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 534 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 76.0457 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 846.03 | 846.03 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 110.6372 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1230.87 | 1230.87 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 534 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 47.0145 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 523.05 | 523.05 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 533 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 19.9231 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 221.65 | 221.65 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 535 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 8.2159 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 119 | 119 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 535 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 4.6948 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 68 | 68 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 535 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 18.7102 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 271 | 271 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 535 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 22.5765 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 327 | 327 | 0 | 1 |  | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE10 Closure 1 WB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 536 | Sweeping - Paved non-running areas - Full Sweep 01 | 70.3968 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9451.5 | 9451.5 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 537 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 64.8852 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2707 | 2707 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 WB OS Amey 45048 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 538 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 64.8852 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2707 | 2707 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 539 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1105.1822 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 23054 | 23054 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 540 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 9.7872 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 748 | 748 | 0 | 1 |  | N |  | 4700A1M/460 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 541 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.2469 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 401 | 401 | 0 | 1 |  | N |  | 4700A1M/461 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE10 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 540 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 4.5272 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 346 | 346 | 0 | 1 |  | N |  | 4700A1M/464 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 541 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 62.5568 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4781 | 4781 | 0 | 1 |  | N |  | 4700A1M/465 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 541 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 17.8995 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1368 | 1368 | 0 | 1 |  | N |  | 4700M62/221 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE10 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 540 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 13.1891 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1008 | 1008 | 0 | 1 |  | N |  | 4700M62/574 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 542 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.8994 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 833 | 833 | 0 | 1 |  | N |  | 4700M62/599 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 543 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.8861 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 297 | 297 | 0 | 1 |  | N |  | 4700M62/798 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 542 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.0396 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1073 | 1073 | 0 | 1 |  | N |  | 4700M62/799 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 543 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.4602 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1258 | 1258 | 0 | 1 |  | N |  | 4700M62/800 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 542 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 49.3415 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3771 | 3771 | 0 | 1 |  | N |  | 4700M62/801 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 543 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.5272 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 346 | 346 | 0 | 1 |  | N |  | 4700M62/802 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 542 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 32.9728 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2520 | 2520 | 0 | 1 |  | N |  | 4700M62/803 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 543 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 25.3969 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1941 | 1941 | 0 | 1 |  | N |  | 4700M62/804 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 542 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 45.7694 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3498 | 3498 | 0 | 1 |  | N |  | 4700M62/805 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 543 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 25.3838 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1940 | 1940 | 0 | 1 |  | N |  | 4700M62/806 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 542 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 28.6288 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2188 | 2188 | 0 | 1 |  | N |  | 4700M62/807 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 543 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.9686 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1144 | 1144 | 0 | 1 |  | N |  | 4700M62/808 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 542 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.019 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 995 | 995 | 0 | 1 |  | N |  | 4700M62/809 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE10 Closure 1 EB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 540 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.4114 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 490 | 490 | 0 | 1 | 0 | N |  | 4700M62/820 | YNE10: M62 J32-33 | YNE10 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE10 Closure 1 WB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 541 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.4451 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 569 | 569 | 0 | 1 |  | N |  | 4700M62/821 | YNE10: M62 J32-33 | YNE10 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE11 Closure 2 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 544 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 857.14 |  | 857.14 | 0 |  | Y |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 & 3 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE11 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 545 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 61.07 | 0 | 61.07 | 0 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 & 3 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE11 Closure 2 WB NS Bettamix 45048 VRS - Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334 - ILM | 546 | VRS - Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334 - ILM |  | TBC | 0 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 2 WB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 547 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 5.3344 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | 2023-11-30 |  | 43dys | WB | 69.1 | 69.1 | 0 | 1 |  | N |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE13 Closure 1 WB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 548 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 16.6772 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 216.03 | 216.03 | 0 | 1 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE13 Closure 1 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 549 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 89.4445 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 1158.63 | 1158.63 | 0 | 1 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE15 Closure 2 WB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 550 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 3.0756 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 39.84 | 39.84 | 0 | 1 |  |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE16 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 551 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 1372.3753 | 0 | 1372.3753 | 0 |  | N |  | 2000A63/408 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 552 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 232.6122 | 0 | 232.6122 | 0 |  | N |  | 2000A63/409 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 552 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 1514.9453 | 0 | 1514.9453 | 0 |  | N |  | 2000A63/411 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 551 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 876.8711 | 0 | 876.8711 | 0 |  | N |  | 2000A63/901 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE16 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 551 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 1068.0506 | 0 | 1068.0506 | 0 |  | N |  | 2000A63/902 | YNE16: A63 North Cave - South Cave | YNE16 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE16 Closure 2 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 552 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 634.13 | 0 | 634.13 | 0 |  | N |  | 2000A63/906 | YNE16: A63 North Cave - South Cave | YNE16 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE17 Closure 2 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 553 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 1438.4044 | 0 | 1438.4044 | 0 |  | N |  | 2000A63/416 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE17 Closure 2 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 554 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 2955.5305 | 0 | 2955.5305 | 0 |  | N |  | 2000A63/422 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE17 Closure 2 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 554 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 515.1221 | 0 | 515.1221 | 0 |  | N |  | 2000A63/424 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE17 Closure 2 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 554 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 731.0331 | 0 | 731.0331 | 0 |  | N |  | 2000A63/904 | YNE17: A63 South Cave - Welton | YNE17 Closure 2 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE17 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 555 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 782.7788 | 0 | 782.7788 | 0 |  | N |  | 2000A63/905 | YNE17: A63 South Cave - Welton | YNE17 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 189/5 | 184/5 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 GW requested Consent from Alan Hosty for his Jct 37 to western works LA consents for diversion
YNE18 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 556 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 613.3748 | 0 | 613.3748 | 0 |  | N |  | 2000A63/425 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 557 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 1858.5221 | 0 | 1858.5221 | 0 |  | N |  | 2000A63/429 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE17 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 558 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 7375.3702 | 0 | 7375.3702 | 0 |  | N |  | 2000A63/601 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 557 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 10480.3804 | 0 | 10480.3804 | 0 |  | N |  | 2000A63/624 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE18 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 557 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 229.7705 | 0 | 229.7705 | 0 |  | N |  | 2000A63/630 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE18 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 556 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 303.9865 | 0 | 303.9865 | 0 |  | Y |  | 2000A63/440 | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE20 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 559 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 960.6729 | 0 | 960.6729 | 0 |  | Y |  | 2000A63/452 | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 560 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3211.097 | 0 | 3211.097 | 0 |  | Y |  | 2000A63/305 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 561 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1579.7247 | 0 | 1579.7247 | 0 |  | Y |  | 2000A63/306 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE23 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 560 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2029.9158 | 0 | 2029.9158 | 0 |  | Y |  | 2000A63/310 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 561 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1091.461 | 0 | 1091.461 | 0 |  | Y |  | 2000A63/312 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE23 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 561 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 566.0252 | 0 | 566.0252 | 0 |  | Y |  | 2000A63/314 | YNE23: A63 Daltry St - Mytongate | YNE23 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE24 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 562 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 866.3851 | 0 | 866.3851 | 0 |  | Y |  | 2000A63/350 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 563 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 517.0486 | 0 | 517.0486 | 0 |  | Y |  | 2000A63/353 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE24 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 564 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 198.765 | 0 | 198.765 | 0 |  | Y |  | 2000A63/356 | YNE24: A63 Mytongate - Garrison | YNE24 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 563 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 977.4687 | 0 | 977.4687 | 0 |  | Y |  | 2000A63/357 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 563 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 838.1969 | 0 | 838.1969 | 0 |  | Y |  | 2000A63/517 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE24 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 563 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 671.5316 | 0 | 671.5316 | 0 |  | Y |  | 2000A63/519 | YNE24: A63 Mytongate - Garrison | YNE24 Closure | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 565 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 7638.3874 | 0 | 7638.3874 | 0 |  | Y |  | 2000A63/344 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 565 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3142.0736 | 0 | 3142.0736 | 0 |  | Y |  | 2000A63/346 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE25 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 565 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1337.7921 | 0 | 1337.7921 | 0 |  | Y |  | 2000A63/348 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE25 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 566 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 11495.9468 | 0 | 11495.9468 | 0 |  | Y |  | 2000A63/359 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 567 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 1800.0377 | 0 | 1800.0377 | 0 |  | Y |  | 2000A63/501 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 567 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 4509.209 | 0 | 4509.209 | 0 |  | Y |  | 2000A63/503 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 567 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 3244.3866 | 0 | 3244.3866 | 0 |  | Y |  | 2000A63/505 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE25 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 567 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 602.1929 | 0 | 602.1929 | 0 |  | Y |  | 2000A63/511 | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE25 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 566 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | WB | 153.337 | 0 | 153.337 | 0 |  | Y |  | 2000A63/515 | YNE25: A63 Garrison - Southcoates | YNE25 Closure | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE26 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 568 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 56.2133 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 1357 | 1357 | 0 | 1 |  | N |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 568 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 143.6609 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3468 | 3468 | 0 | 1 |  | N |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 568 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 106.6686 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 2575 | 2575 | 0 | 1 |  | N |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 569 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 19.1382 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 462 | 462 | 0 | 1 |  | N |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 570 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 13.6287 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 329 | 329 | 0 | 1 |  | N |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 570 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 55.7577 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 1346 | 1346 | 0 | 1 |  | N |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 571 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 8.2435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 199 | 199 | 0 | 1 |  | N |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 572 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 320.0887 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7727 | 7727 | 0 | 1 |  | N |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 572 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 107.0829 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 2585 | 2585 | 0 | 1 |  | N |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 573 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 344.9435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8327 | 8327 | 0 | 1 |  | N |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 574 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 18.144 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 438 | 438 | 0 | 1 |  | N |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 574 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 159.5265 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3851 | 3851 | 0 | 1 |  | N |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 574 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 247.3469 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5971 | 5971 | 0 | 1 |  | N |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 575 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 277.3384 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6695 | 6695 | 0 | 1 |  | N |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 575 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 16.6113 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 401 | 401 | 0 | 1 |  | N |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 575 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 45.7743 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1105 | 1105 | 0 | 1 |  | N |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE30 Closure 1 NB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 576 | VRS - Check all Road Restraint System - ILM | 1.062 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 82.54 | 82.54 | 0 | 1 |  |  |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 NB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 577 | VRS - Check all Road Restraint System - ILM | 6.8595 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 533.13 | 533.13 | 0 | 1 |  |  |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 NB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 577 | VRS - Check all Road Restraint System - ILM | 3.5985 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 279.68 | 279.68 | 0 | 1 |  |  |  | 4700M606/14 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 578 | VRS - Check all Road Restraint System - ILM | 6.7836 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 527.23 | 527.23 | 0 | 1 |  |  |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 579 | VRS - Check all Road Restraint System - ILM | 8.138 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 632.5 | 632.5 | 0 | 1 |  |  |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 578 | VRS - Check all Road Restraint System - ILM | 2.4426 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 189.84 | 189.84 | 0 | 1 |  |  |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 579 | VRS - Check all Road Restraint System - ILM | 3.4008 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 264.32 | 264.32 | 0 | 1 |  |  |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 578 | VRS - Check all Road Restraint System - ILM | 5.3046 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 412.28 | 412.28 | 0 | 1 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 579 | VRS - Check all Road Restraint System - ILM | 4.9395 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 383.91 | 383.91 | 0 | 1 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 579 | VRS - Check all Road Restraint System - ILM | 4.5142 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 350.85 | 350.85 | 0 | 1 |  |  |  | 4700M606/148 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 579 | VRS - Check all Road Restraint System - ILM | 0.82615 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 64.21 | 64.21 | 0 | 1 |  |  |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 578 | VRS - Check all Road Restraint System - ILM | 4.8847 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 379.65 | 379.65 | 0 | 1 |  |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 579 | VRS - Check all Road Restraint System - ILM | 8.4474 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 656.55 | 656.55 | 0 | 1 |  |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 NB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 577 | VRS - Check all Road Restraint System - ILM | 2.7234 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 211.67 | 211.67 | 0 | 1 |  |  |  | 4700M606/16 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 578 | VRS - Check all Road Restraint System - ILM | 3.4625 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 269.11 | 269.11 | 0 | 1 |  |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 579 | VRS - Check all Road Restraint System - ILM | 3.0361 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 235.97 | 235.97 | 0 | 1 |  |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 579 | VRS - Check all Road Restraint System - ILM | 2.4863 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 193.24 | 193.24 | 0 | 1 |  |  |  | 4700M606/171 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 NB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 576 | VRS - Check all Road Restraint System - ILM | 1.6186 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 125.8 | 125.8 | 0 | 1 |  |  |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 NB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 576 | VRS - Check all Road Restraint System - ILM | 2.8561 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 221.98 | 221.98 | 0 | 1 |  |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 NB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 577 | VRS - Check all Road Restraint System - ILM | 4.1362 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 321.47 | 321.47 | 0 | 1 |  |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 NB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 576 | VRS - Check all Road Restraint System - ILM | 8.7476 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 679.88 | 679.88 | 0 | 1 |  |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 NB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 577 | VRS - Check all Road Restraint System - ILM | 9.3397 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 725.9 | 725.9 | 0 | 1 |  |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 NB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 576 | VRS - Check all Road Restraint System - ILM | 0.83979 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 65.27 | 65.27 | 0 | 1 |  |  |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 NB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 576 | VRS - Check all Road Restraint System - ILM | 3.8204 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 296.93 | 296.93 | 0 | 1 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE30 Closure 1 NB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 577 | VRS - Check all Road Restraint System - ILM | 1.5127 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 117.57 | 117.57 | 0 | 1 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 52029205
YNE30 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 580 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 293.3542 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-29 | 2023-05-02 | 2023-06-30 | 2023-11-30 |  | 43dys | NB | 38 | 38 | 0 | 1 |  | N |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45801790
YNE30 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 581 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 13 | 13 | 0 | 1 |  |  |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE30 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 581 | Gullies - Emptying / clear covers | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 22 | 22 | 0 | 1 |  |  |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE30 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 581 | Gullies - Emptying / clear covers | 563.5488 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-29 | 2023-05-02 | 2023-06-30 | 2023-11-30 |  | 43dys | SB | 73 | 73 | 0 | 1 |  | N |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45801790
YNE30 Closure 1 SB OS Enviroflow 45048 Gullies - Emptying / clear covers | 582 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | SB | 0 | 0 | 0 | 0 | 22/9: Check and close jobs |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45801790
YNE30 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 581 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE30 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 581 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | SB | 0 | 0 | 0 | 0 |  |  |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE30 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 581 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | SB | 0 | 0 | 0 | 0 |  |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE30 Closure 1 SB OS Enviroflow 45048 Gullies - Emptying / clear covers | 582 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 5 | 5 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45801790
YNE30 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers | 583 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | NB | 0 | 0 | 0 | 0 |  |  |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE30 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 581 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE30 Closure 1 SB OS Enviroflow 45048 Gullies - Emptying / clear covers | 582 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45801790
YNE30 Closure 1 NB OS Enviroflow 45048 Gullies - Emptying / clear covers | 584 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45801790
YNE30 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers | 583 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | NB | 0 | 0 | 0 | 0 |  |  |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE30 Closure 1 NB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 585 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 1 | 1 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45801790
YNE30 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 580 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | NB | 0 | 0 | 0 | 0 |  |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE30 Closure 1 NB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 585 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 192.9962 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 25 | 25 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45801790
YNE30 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 580 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE30 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers | 583 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | NB | 0 | 0 | 0 | 0 |  |  |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE30 Closure 1 NB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 585 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 1 | 1 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45801790
YNE30 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 580 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | NB | 0 | 0 | 0 | 0 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE30 Closure 1 SB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 586 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.3551 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 55 | 55 | 0 | 1 |  |  |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE30 Closure 1 NB NS Enviroflow 45048 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 587 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 109.9306 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-29 | 2023-05-02 | 2023-06-30 | 2023-11-30 |  | 43dys | NB | 89 | 89 | 0 | 1 |  | N |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45902911
YNE30 Closure 1 SB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 588 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2.1168 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 27.42 | 27.42 | 0 | 1 |  |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE30 Closure Amey 45048 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 589 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 15.9796 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 1 |  |  | 2 times per year |  |  | On ServiceNow
YNE30 Closure Amey 45048 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 590 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE30 Closure Amey 45048 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 591 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE30 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 592 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 81.9754 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 1710 | 1710 | 0 | 1 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 593 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 | 22/9: Check and close jobs |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 594 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 595 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 | 22/9: Check and close jobs |  |  |  | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 596 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  |  |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 596 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 7 | 7 | 0 | 1 |  |  |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 5 | 5 | 0 | 1 |  |  |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 14 | 14 | 0 | 1 |  |  |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 9 | 9 | 0 | 1 |  |  |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 30 | 30 | 0 | 1 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4700M606/148 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 6 | 6 | 0 | 1 |  |  |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 16 | 16 | 0 | 1 |  |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 32 | 32 | 0 | 1 |  |  |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 598 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M606/171 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  |  |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 18 | 18 | 0 | 1 |  |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 12 | 12 | 0 | 1 |  |  |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 597 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 16 | 16 | 0 | 1 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 599 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 8 | 8 | 0 | 1 |  |  |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 600 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 8 | 8 | 0 | 1 |  |  |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 600 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 600 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 12 | 12 | 0 | 1 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 600 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4700M606/148 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 600 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 8 | 8 | 0 | 1 |  |  |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 599 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 8 | 8 | 0 | 1 |  |  |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 599 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 12 | 12 | 0 | 1 |  |  |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 599 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 95.8777 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 16 | 16 | 0 | 1 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 601 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 3 | 3 | 0 | 1 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 601 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 2 | 2 | 0 | 1 |  |  |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 602 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  |  |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 602 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  |  |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 602 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 602 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 602 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  |  |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 602 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 603 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.81151 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 39.18 | 39.18 | 0 | 1 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.6175 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 477 | 477 | 0 | 1 |  |  |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.792 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 343 | 343 | 0 | 1 |  |  |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.1942 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 252 | 252 | 0 | 1 |  |  |  | 4700M606/14 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.2439 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 569 | 569 | 0 | 1 |  |  |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.8801 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 241 | 241 | 0 | 1 |  |  |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 49.3313 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 1728 | 1728 | 0 | 1 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.0212 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 316 | 316 | 0 | 1 |  |  |  | 4700M606/148 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.9878 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 525 | 525 | 0 | 1 |  |  |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4128 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 680 | 680 | 0 | 1 |  |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.3671 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 188 | 188 | 0 | 1 |  |  |  | 4700M606/16 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.9935 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 280 | 280 | 0 | 1 |  |  |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.1632 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 356 | 356 | 0 | 1 |  |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.965 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 279 | 279 | 0 | 1 |  |  |  | 4700M606/171 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.4919 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 963 | 963 | 0 | 1 |  |  |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.7578 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 587 | 587 | 0 | 1 |  |  |  | 4700M606/21 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.4503 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 296 | 296 | 0 | 1 |  |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.7847 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 658 | 658 | 0 | 1 |  |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.7937 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 273 | 273 | 0 | 1 |  |  |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.2496 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 324 | 324 | 0 | 1 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE30 Closure 1 NB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 606 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 11.8037 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 131.32 | 131.32 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 606 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 51.2679 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 570.37 | 570.37 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/14 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 607 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 45.9251 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 510.93 | 510.93 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 606 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 79.5701 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 885.24 | 885.24 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/16 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 607 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 170.8855 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 1901.15 | 1901.15 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 607 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 80.3431 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 893.84 | 893.84 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/171 | YNE30: M606 J1-2 | YNE30 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 606 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 116.3116 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 1294 | 1294 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 606 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 244.7128 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 2722.5 | 2722.5 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 SB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 608 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 72.2861 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 1047 | 1047 | 0 | 1 |  |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE30 Closure 1 NB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 609 | Sweeping - Paved non-running areas - Full Sweep 01 | 52.6235 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 7065.25 | 7065.25 | 0 | 1 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 610 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1122.6319 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 23418 | 23418 | 0 | 1 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 611 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 34.4121 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 2630 | 2630 | 0 | 1 |  |  |  | 4700M606/12 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE30 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 612 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 4.5011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 344 | 344 | 0 | 1 |  |  |  | 4700M606/135 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | 4 times per year (ILM Certain Sections)
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 611 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.7554 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 822 | 822 | 0 | 1 |  |  |  | 4700M606/14 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE30 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 613 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.4451 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 569 | 569 | 0 | 1 |  |  |  | 4700M606/140 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually
YNE30 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 613 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.1534 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 241 | 241 | 0 | 1 |  |  |  | 4700M606/144 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually
YNE30 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 612 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 22.6099 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 1728 | 1728 | 0 | 1 |  |  |  | 4700M606/146 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE30 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 613 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.1347 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 316 | 316 | 0 | 1 |  |  |  | 4700M606/148 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually
YNE30 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 612 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.8693 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 525 | 525 | 0 | 1 |  |  |  | 4700M606/150 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE30 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 613 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.5836 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 1191 | 1191 | 0 | 1 |  |  |  | 4700M606/155 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 611 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.0396 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 1073 | 1073 | 0 | 1 |  |  |  | 4700M606/16 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 614 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3.6636 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 280 | 280 | 0 | 1 |  |  |  | 4700M606/17 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE30 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 612 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 29.5447 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 2258 | 2258 | 0 | 1 |  |  |  | 4700M606/170 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE30 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 612 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 15.3481 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 1173 | 1173 | 0 | 1 |  |  |  | 4700M606/171 | YNE30: M606 J1-2 | YNE30 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 614 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 12.6003 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 963 | 963 | 0 | 1 |  |  |  | 4700M606/19 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 614 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.6806 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 587 | 587 | 0 | 1 |  |  |  | 4700M606/21 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 611 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 20.8043 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 1590 | 1590 | 0 | 1 |  |  |  | 4700M606/23 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 611 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 44.2255 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 3380 | 3380 | 0 | 1 |  |  |  | 4700M606/30 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 614 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 3.5721 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 273 | 273 | 0 | 1 |  |  |  | 4700M606/35 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE30 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 611 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.2394 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 324 | 324 | 0 | 1 |  |  |  | 4700M606/8 | YNE30: M606 J1-2 | YNE30 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE31 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 615 | VRS - Check all Road Restraint System - ILM | 1.1863 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 92.2 | 92.2 | 0 | 1 |  |  |  | 4700M606/102 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 616 | VRS - Check all Road Restraint System - ILM | 1.8126 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 140.88 | 140.88 | 0 | 1 |  |  |  | 4700M606/102 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 615 | VRS - Check all Road Restraint System - ILM | 0.90785 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 70.56 | 70.56 | 0 | 1 |  |  |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 616 | VRS - Check all Road Restraint System - ILM | 8.0066 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 622.29 | 622.29 | 0 | 1 |  |  |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 615 | VRS - Check all Road Restraint System - ILM | 0.76324 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 59.32 | 59.32 | 0 | 1 |  |  |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 616 | VRS - Check all Road Restraint System - ILM | 1.2617 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 98.06 | 98.06 | 0 | 1 |  |  |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 615 | VRS - Check all Road Restraint System - ILM | 4.7598 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 369.94 | 369.94 | 0 | 1 |  |  |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 616 | VRS - Check all Road Restraint System - ILM | 4.9111 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 381.7 | 381.7 | 0 | 1 |  |  |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 615 | VRS - Check all Road Restraint System - ILM | 2.4499 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 190.41 | 190.41 | 0 | 1 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 615 | VRS - Check all Road Restraint System - ILM | 1.6371 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 127.24 | 127.24 | 0 | 1 |  |  |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 616 | VRS - Check all Road Restraint System - ILM | 11.4776 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 892.06 | 892.06 | 0 | 1 |  |  |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 NB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 617 | VRS - Check all Road Restraint System - ILM | 11.4725 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 891.66 | 891.66 | 0 | 1 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 NB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 618 | VRS - Check all Road Restraint System - ILM | 17.0785 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 1327.37 | 1327.37 | 0 | 1 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 NB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 617 | VRS - Check all Road Restraint System - ILM | 3.2048 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 249.08 | 249.08 | 0 | 1 |  |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 NB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 618 | VRS - Check all Road Restraint System - ILM | 1.6613 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 129.12 | 129.12 | 0 | 1 |  |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 NB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 617 | VRS - Check all Road Restraint System - ILM | 2.3338 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 181.39 | 181.39 | 0 | 1 |  |  |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 NB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 618 | VRS - Check all Road Restraint System - ILM | 6.3711 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 495.17 | 495.17 | 0 | 1 |  |  |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 NB NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 617 | VRS - Check all Road Restraint System - ILM | 1.9671 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 152.89 | 152.89 | 0 | 1 |  |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 NB OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 618 | VRS - Check all Road Restraint System - ILM | 2.0169 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 156.76 | 156.76 | 0 | 1 |  |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE31 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 619 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 2 | 2 | 0 | 1 |  |  |  | 4700M606/102 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE31 Closure 1 SB OS Enviroflow 45048 Gullies - Emptying / clear covers | 620 | Gullies - Emptying / clear covers | 146.6771 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 19 | 19 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE31 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 619 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE31 Closure 1 SB OS Enviroflow 45048 Gullies - Emptying / clear covers | 620 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 5 | 5 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE31 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 619 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 7 | 7 | 0 | 1 |  |  |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE31 Closure 1 SB OS Enviroflow 45048 Gullies - Emptying / clear covers | 620 | Gullies - Emptying / clear covers | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 6 | 6 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45801941
YNE31 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 619 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 11 | 11 | 0 | 1 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE31 Closure 1 SB NS Enviroflow 45048 Gullies - Emptying / clear covers | 619 | Gullies - Emptying / clear covers | 123.5175 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 16 | 16 | 0 | 1 |  |  |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE31 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 621 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 301.074 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 39 | 39 | 0 | 1 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE31 Closure 1 NB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 622 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 13 | 13 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE31 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers | 623 | Gullies - Emptying / clear covers | 146.6771 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-29 | 2023-05-02 | 2023-06-30 | 2023-11-30 |  | 43dys | NB | 19 | 19 | 0 | 1 |  | N |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45802112
YNE31 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers | 623 | Gullies - Emptying / clear covers | 146.6771 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 19 | 19 | 0 | 1 |  |  |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE31 Closure 1 NB OS Enviroflow 45048 Gullies - Emptying / clear covers | 624 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE31 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers | 623 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE31 Closure 1 SB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 625 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.3364 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 176 | 176 | 0 | 1 |  |  |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE31 Closure 1 SB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 625 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.6567 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 189 | 189 | 0 | 1 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE31 Closure 1 SB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 625 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.9379 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 241 | 241 | 0 | 1 |  |  |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE31 Closure Amey 45048 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 626 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE31 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 627 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 54.075 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 1128 | 1128 | 0 | 1 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 628 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 629 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 | 22/9: Check and close jobs |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 SB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 630 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 | 22/9: Check and close jobs |  |  |  | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 8 | 8 | 0 | 1 |  |  |  | 4700M606/102 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 3 | 3 | 0 | 1 |  |  |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 15 | 15 | 0 | 1 |  |  |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 12 | 12 | 0 | 1 |  |  |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 17 | 17 | 0 | 1 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 631 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 8 | 8 | 0 | 1 |  |  |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 632 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 32 | 32 | 0 | 1 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 632 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 17 | 17 | 0 | 1 |  |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 632 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 14 | 14 | 0 | 1 |  |  |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 632 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 14 | 14 | 0 | 1 |  |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 633 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 633 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 53.9312 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 9 | 9 | 0 | 1 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 633 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 634 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 89.8853 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 15 | 15 | 0 | 1 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 634 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 12 | 12 | 0 | 1 |  |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 634 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 8 | 8 | 0 | 1 |  |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 635 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 39.7238 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 9 | 9 | 0 | 1 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 635 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 635 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 636 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.52112 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 25.16 | 25.16 | 0 | 1 |  |  |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 636 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.4948 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 72.17 | 72.17 | 0 | 1 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 637 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.61329 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 29.61 | 29.61 | 0 | 1 |  |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 638 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.7105 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 165 | 165 | 0 | 1 |  |  |  | 4700M606/102 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 638 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.558 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 580 | 580 | 0 | 1 |  |  |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 638 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.3875 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 539 | 539 | 0 | 1 |  |  |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 638 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.6493 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 338 | 338 | 0 | 1 |  |  |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 638 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.5898 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 441 | 441 | 0 | 1 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 638 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.1241 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 810 | 810 | 0 | 1 |  |  |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 639 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.1722 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 1197 | 1197 | 0 | 1 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 639 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.7048 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 410 | 410 | 0 | 1 |  |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 639 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.9038 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 452 | 452 | 0 | 1 |  |  |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 639 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.1395 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 145 | 145 | 0 | 1 |  |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE31 Closure 1 SB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 640 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 181.7419 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 2021.93 | 2021.93 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/12 | YNE31: M606 J2-3 | YNE31 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 641 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 330.1021 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 3672.48 | 3672.48 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 641 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 85.8836 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 955.48 | 955.48 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 641 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 17.7775 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 197.78 | 197.78 | 0 | 1 | 22/9: Check and close jobs |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE31 Closure 1 NB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 642 | Sweeping - Paved non-running areas - Full Sweep 01 | 34.893 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 4684.75 | 4684.75 | 0 | 1 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE31 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 643 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 540.7022 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 11279 | 11279 | 0 | 1 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE31 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 644 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.1589 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 165 | 165 | 0 | 1 |  |  |  | 4700M606/102 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually
YNE31 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 644 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.589 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 580 | 580 | 0 | 1 |  |  |  | 4700M606/105 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually
YNE31 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 645 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.0525 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 539 | 539 | 0 | 1 |  |  |  | 4700M606/110 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE31 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 644 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.4225 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 338 | 338 | 0 | 1 |  |  |  | 4700M606/120 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually
YNE31 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 645 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.7702 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 441 | 441 | 0 | 1 |  |  |  | 4700M606/125 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | 4 times per year (ILM Certain Sections)
YNE31 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 644 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.5984 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 810 | 810 | 0 | 1 |  |  |  | 4700M606/130 | YNE31: M606 J2-3 | YNE31 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually
YNE31 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 646 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 63.7082 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 4869 | 4869 | 0 | 1 |  |  |  | 4700M606/40 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE31 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 647 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.3646 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 410 | 410 | 0 | 1 |  |  |  | 4700M606/45 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE31 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 646 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.4098 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 1407 | 1407 | 0 | 1 |  |  |  | 4700M606/51 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE31 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 646 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.488 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 343 | 343 | 0 | 1 |  |  |  | 4700M606/60 | YNE31: M606 J2-3 | YNE31 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE31 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 627 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 54.075 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 1128 | 1128 | 0 | 1 |  |  |  |  | YNE31: M606 J2-3 | YNE31 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 648 | VRS - Check all Road Restraint System - ILM | 5.162 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 401.2 | 401.2 | 0 | 1 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 649 | VRS - Check all Road Restraint System - ILM | 1.6666 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 129.53 | 129.53 | 0 | 1 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 650 | VRS - Check all Road Restraint System - ILM | 4.1008 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 318.72 | 318.72 | 0 | 1 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 651 | VRS - Check all Road Restraint System - ILM | 4.5056 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 350.18 | 350.18 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 650 | VRS - Check all Road Restraint System - ILM | 12.7509 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 991.02 | 991.02 | 0 | 1 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 ACW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 652 | VRS - Check all Road Restraint System - ILM | 9.4829 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 737.03 | 737.03 | 0 | 1 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 650 | VRS - Check all Road Restraint System - ILM | 4.0595 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 315.51 | 315.51 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 ACW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 652 | VRS - Check all Road Restraint System - ILM | 17.8996 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1391.19 | 1391.19 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 651 | VRS - Check all Road Restraint System - ILM | 2.3005 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 178.8 | 178.8 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 653 | VRS - Check all Road Restraint System - ILM | 7.5148 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 584.06 | 584.06 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 651 | VRS - Check all Road Restraint System - ILM | 12.6734 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 985 | 985 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 653 | VRS - Check all Road Restraint System - ILM | 4.7656 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 370.39 | 370.39 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 651 | VRS - Check all Road Restraint System - ILM | 6.8259 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 530.52 | 530.52 | 0 | 1 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 653 | VRS - Check all Road Restraint System - ILM | 1.7506 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 136.06 | 136.06 | 0 | 1 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 651 | VRS - Check all Road Restraint System - ILM | 1.7603 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 136.81 | 136.81 | 0 | 1 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 653 | VRS - Check all Road Restraint System - ILM | 6.2715 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 487.43 | 487.43 | 0 | 1 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 648 | VRS - Check all Road Restraint System - ILM | 3.1434 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 244.31 | 244.31 | 0 | 1 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 649 | VRS - Check all Road Restraint System - ILM | 6.0534 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 470.48 | 470.48 | 0 | 1 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 648 | VRS - Check all Road Restraint System - ILM | 1.9011 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 147.76 | 147.76 | 0 | 1 |  |  |  | 4700M621/16 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 649 | VRS - Check all Road Restraint System - ILM | 6.2132 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 482.9 | 482.9 | 0 | 1 |  |  |  | 4700M621/16 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 648 | VRS - Check all Road Restraint System - ILM | 5.7081 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 443.64 | 443.64 | 0 | 1 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 649 | VRS - Check all Road Restraint System - ILM | 1.6662 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 129.5 | 129.5 | 0 | 1 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 651 | VRS - Check all Road Restraint System - ILM | 0.4812 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 37.4 | 37.4 | 0 | 1 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 653 | VRS - Check all Road Restraint System - ILM | 6.4332 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 500 | 500 | 0 | 1 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 651 | VRS - Check all Road Restraint System - ILM | 3.9528 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 307.22 | 307.22 | 0 | 1 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 651 | VRS - Check all Road Restraint System - ILM | 9.8926 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 768.87 | 768.87 | 0 | 1 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 653 | VRS - Check all Road Restraint System - ILM | 1.0975 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 85.3 | 85.3 | 0 | 1 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 648 | VRS - Check all Road Restraint System - ILM | 4.1008 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 318.72 | 318.72 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 649 | VRS - Check all Road Restraint System - ILM | 10.1463 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 788.59 | 788.59 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 648 | VRS - Check all Road Restraint System - ILM | 0.59185 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 46 | 46 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 649 | VRS - Check all Road Restraint System - ILM | 7.8152 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 607.41 | 607.41 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 654 | VRS - Check all Road Restraint System - ILM | 2.6926 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 209.27 | 209.27 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 655 | VRS - Check all Road Restraint System - ILM | 17.8552 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1387.74 | 1387.74 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 654 | VRS - Check all Road Restraint System - ILM | 9.6876 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 752.94 | 752.94 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 655 | VRS - Check all Road Restraint System - ILM | 9.6882 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 752.98 | 752.98 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 648 | VRS - Check all Road Restraint System - ILM | 6.8119 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 529.43 | 529.43 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 649 | VRS - Check all Road Restraint System - ILM | 1.3623 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 105.88 | 105.88 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 654 | VRS - Check all Road Restraint System - ILM | 5.2095 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 404.89 | 404.89 | 0 | 1 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 648 | VRS - Check all Road Restraint System - ILM | 2.9063 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 225.88 | 225.88 | 0 | 1 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 649 | VRS - Check all Road Restraint System - ILM | 3.5951 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 279.42 | 279.42 | 0 | 1 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 656 | Gullies - Emptying / clear covers | 393.7122 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 168 | 51 | 117 | 0.30357 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 657 | Gullies - Emptying / clear covers | 192.9962 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | CW | 92 | 25 | 67 | 0.27174 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 2 ACW NS Enviroflow 45048 Gullies - Emptying / clear covers | 658 | Gullies - Emptying / clear covers | 270.1946 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 130 | 35 | 95 | 0.26923 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Gullies - Emptying / clear covers | 659 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 42 | 11 | 31 | 0.2619 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Gullies - Emptying / clear covers | 660 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 2 ACW NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 661 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | ACW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE32 Closure 1 ACW OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 662 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 31 | 0 | 31 | 0 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE32 Closure 2 ACW NS Enviroflow 45048 Gullies - Emptying / clear covers | 658 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | ACW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 2 ACW OS Enviroflow 45048 Gullies - Emptying / clear covers | 663 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 13 | 13 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Gullies - Emptying / clear covers | 659 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | ACW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Gullies - Emptying / clear covers | 660 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 5 | 5 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Gullies - Emptying / clear covers | 660 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | ACW | 85 | 1 | 84 | 0.011765 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Gullies - Emptying / clear covers | 659 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | ACW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Gullies - Emptying / clear covers | 660 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | ACW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Gullies - Emptying / clear covers | 659 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | ACW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Gullies - Emptying / clear covers | 660 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | ACW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 657 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 657 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/16 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 656 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 657 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Gullies - Emptying / clear covers | 659 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Gullies - Emptying / clear covers | 660 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Gullies - Emptying / clear covers | 659 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Gullies - Emptying / clear covers | 659 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Gullies - Emptying / clear covers | 660 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 656 | Gullies - Emptying / clear covers | 308.7939 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 40 | 40 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 657 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 656 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 657 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 2 | 2 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 2 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 664 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 2 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 665 | Gullies - Emptying / clear covers | 185.2763 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 24 | 24 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 2 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 664 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 2 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 665 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 2 | 2 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 656 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 657 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 2 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 664 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 2 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 665 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 656 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 657 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE32 Closure 2 ACW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 666 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.3915 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 300 | 300 | 0 | 1 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 ACW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 667 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.0798 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 125 | 125 | 0 | 1 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 668 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.3845 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 665 | 665 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 ACW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 669 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.9191 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 362 | 362 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 ACW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 666 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.7975 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 560 | 560 | 0 | 1 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 ACW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 667 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.6743 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 555 | 555 | 0 | 1 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 ACW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 666 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 69.5049 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 2821 | 2821 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 ACW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 667 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.158 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 47 | 47 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 668 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 15.7932 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 641 | 641 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 ACW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 669 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.9073 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 118 | 118 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 668 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 24.7369 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1004 | 1004 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 ACW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 669 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.015 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 650 | 650 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 668 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.3899 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 97 | 97 | 0 | 1 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 CW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 670 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 34.6169 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1405 | 1405 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 CW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 671 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 15.3251 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 622 | 622 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 CW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 670 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.5077 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 670 | 670 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 CW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 671 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 11.4569 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 465 | 465 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 CW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 672 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 52.874 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 2146 | 2146 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 CW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 673 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 33.5821 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1363 | 1363 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 CW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 672 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 26.3877 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1071 | 1071 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 CW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 673 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 15.8178 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 642 | 642 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 CW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 670 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 17.5672 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 713 | 713 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 1 CW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 671 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 9.0669 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 368 | 368 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 CW NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 672 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.1264 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 411 | 411 | 0 | 1 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 CW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 673 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.2566 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 51 | 51 | 0 | 1 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE32 Closure 2 CW OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 674 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 17.6074 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 228.08 | 228.08 | 0 | 1 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE32 Closure 2 ACW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 675 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278.7722 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 13 | 13 | 0 | 1 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 676 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 192.9962 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 9 | 9 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 677 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 343.1043 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 16 | 16 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 ACW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 675 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 471.7684 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 22 | 22 | 0 | 1 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 ACW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 678 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235.8842 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 11 | 11 | 0 | 1 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 ACW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 675 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1093.6449 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 51 | 51 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 ACW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 678 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 4 | 4 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 677 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 171.5521 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 8 | 8 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 676 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 3 | 3 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 677 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 278.7722 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 13 | 13 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 676 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 321.6603 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 15 | 15 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 676 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 6 | 6 | 0 | 1 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 679 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 677 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 676 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 ACW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 676 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 680 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 171.5521 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 8 | 8 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 679 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 493.2124 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 23 | 23 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 679 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 214.4402 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 10 | 10 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 680 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 4 | 4 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 681 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 836.3167 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 39 | 39 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 682 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 300.2163 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 14 | 14 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 681 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 879.2048 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 41 | 41 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 682 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 679 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 235.8842 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 11 | 11 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 680 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 7 | 7 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 681 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 214.4402 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 10 | 10 | 0 | 1 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 2 CW OS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 682 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 5 | 5 | 0 | 1 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure 1 CW NS Enviroflow 45048 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 679 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE32 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 683 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 106.2325 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 2216 | 2216 | 0 | 1 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 684 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 23.9694 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 685 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 23.9694 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 684 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 2 | 2 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 684 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 3 | 3 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 684 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 2 | 2 | 0 | 1 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 686 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 186.9615 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 78 | 78 | 0 | 1 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 687 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 8 | 8 | 0 | 1 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 14 | 14 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 687 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 18 | 18 | 0 | 1 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 687 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 55.1297 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 23 | 23 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 11 | 11 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 20 | 20 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 20 | 20 | 0 | 1 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 6 | 6 | 0 | 1 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 686 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 13 | 13 | 0 | 1 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 686 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 10 | 10 | 0 | 1 |  |  |  | 4700M621/16 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 686 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 9 | 9 | 0 | 1 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 20 | 20 | 0 | 1 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 18 | 18 | 0 | 1 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 686 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 14 | 14 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 686 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 9 | 9 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 689 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 19 | 19 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 689 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 25 | 25 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 686 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 19 | 19 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 689 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 8 | 8 | 0 | 1 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 686 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 26 | 26 | 0 | 1 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 690 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 4 | 4 | 0 | 1 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 691 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 2 | 2 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 691 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 4 | 4 | 0 | 1 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 691 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 4 | 4 | 0 | 1 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 690 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 2 | 2 | 0 | 1 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 690 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 179.7707 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 30 | 30 | 0 | 1 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 3 | 3 | 0 | 1 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 693 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 693 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 693 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 2 | 2 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 694 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 2 | 2 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 694 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 3 | 3 | 0 | 1 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 694 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 694 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 694 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 7 | 7 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 8 | 8 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 695 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 3 | 3 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 695 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 4 | 4 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 10 | 10 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 5 | 5 | 0 | 1 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 696 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.80281 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 38.76 | 38.76 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 697 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.18165 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 8.77 | 8.77 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 696 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.35501 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 17.14 | 17.14 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 696 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.49461 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 23.88 | 23.88 | 0 | 1 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 696 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.1421 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 151.7 | 151.7 | 0 | 1 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 696 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.9221 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 237.64 | 237.64 | 0 | 1 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 698 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.4565 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 118.6 | 118.6 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 698 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.6653 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 80.4 | 80.4 | 0 | 1 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 699 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.7195 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1006 | 1006 | 0 | 1 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 700 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.1297 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 565 | 565 | 0 | 1 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 701 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.474 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 507 | 507 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 700 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.2032 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1093 | 1093 | 0 | 1 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 700 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.8566 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1256 | 1256 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 701 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.7586 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 552 | 552 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 701 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.2081 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 883 | 883 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 701 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 26.0931 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 914 | 914 | 0 | 1 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 701 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.5033 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 473 | 473 | 0 | 1 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 699 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.2464 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 464 | 464 | 0 | 1 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 699 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.0465 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 457 | 457 | 0 | 1 |  |  |  | 4700M621/16 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 699 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.8761 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 416 | 416 | 0 | 1 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 701 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.2146 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 603 | 603 | 0 | 1 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 701 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.4993 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 648 | 648 | 0 | 1 |  |  |  | 4700M621/201 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 701 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.8157 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 554 | 554 | 0 | 1 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 701 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 46.3909 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1625 | 1625 | 0 | 1 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 ACW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 701 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.6175 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 477 | 477 | 0 | 1 |  |  |  | 4700M621/204 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 699 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.2407 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 709 | 709 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 699 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.416 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 540 | 540 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 702 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.7424 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1252 | 1252 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 702 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.0319 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1087 | 1087 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 699 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.9463 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1084 | 1084 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 702 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.2439 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 569 | 569 | 0 | 1 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 699 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.677 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 374 | 374 | 0 | 1 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE32 Closure 2 ACW OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 703 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 23.8214 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 265.02 | 265.02 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 704 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 327.4028 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 3642.45 | 3642.45 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 704 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 291.5062 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 3243.09 | 3243.09 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 705 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 12.6345 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 183 | 183 | 0 | 1 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 706 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 12.6345 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 183 | 183 | 0 | 1 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 705 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 29.9639 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 434 | 434 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 ACW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 706 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 29.9639 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 434 | 434 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 707 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1.7951 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 26 | 26 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 708 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 1.7951 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 26 | 26 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 707 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 25.5452 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 370 | 370 | 0 | 1 |  |  |  | 4700M621/201 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 708 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 25.5452 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 370 | 370 | 0 | 1 |  |  |  | 4700M621/201 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 707 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 16.6389 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 241 | 241 | 0 | 1 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 ACW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 708 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 16.6389 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 241 | 241 | 0 | 1 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 709 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 13.6011 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 197 | 197 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 CW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 710 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 13.6011 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 197 | 197 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 711 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 69.1793 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1002 | 1002 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 712 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 69.1793 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1002 | 1002 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 711 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 322.6985 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 4674 | 4674 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 2 CW NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 712 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 2 | 322.6985 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 4674 | 4674 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE32 Closure 1 AW NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 713 | Sweeping - Paved non-running areas - Full Sweep 01 | 51.6776 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 6938.25 | 6938.25 | 0 | 1 |  |  |  |  | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 AW NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE32 Closure 1 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 13.163 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1006 | 1006 | 0 | 1 |  |  |  | 4700M621/10 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | 6 times per year (ILM Certain Sections)
YNE32 Closure 2 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 715 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.3927 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 565 | 565 | 0 | 1 |  |  |  | 4700M621/108 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.6338 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 507 | 507 | 0 | 1 |  |  |  | 4700M621/110 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | 6 times per year (ILM Certain Sections)
YNE32 Closure 2 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 715 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 14.3013 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1093 | 1093 | 0 | 1 |  |  |  | 4700M621/115 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 2 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 715 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 19.9015 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 1521 | 1521 | 0 | 1 |  |  |  | 4700M621/120 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 ACW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.2226 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 552 | 552 | 0 | 1 |  |  |  | 4700M621/124 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 11.5536 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 883 | 883 | 0 | 1 |  |  |  | 4700M621/125 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 11.9592 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 914 | 914 | 0 | 1 |  |  |  | 4700M621/130 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.1889 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | ACW | 473 | 473 | 0 | 1 |  |  |  | 4700M621/135 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.0712 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 464 | 464 | 0 | 1 |  |  |  | 4700M621/15 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.9796 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 457 | 457 | 0 | 1 |  |  |  | 4700M621/16 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.4431 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 416 | 416 | 0 | 1 |  |  |  | 4700M621/20 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.8899 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 603 | 603 | 0 | 1 |  |  |  | 4700M621/200 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.4787 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 648 | 648 | 0 | 1 |  |  |  | 4700M621/201 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.2488 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 554 | 554 | 0 | 1 |  |  |  | 4700M621/202 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 21.2622 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1625 | 1625 | 0 | 1 |  |  |  | 4700M621/203 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | 6 times per year (ILM Certain Sections)
YNE32 Closure 1 ACW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 716 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.2413 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 477 | 477 | 0 | 1 |  |  |  | 4700M621/204 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 ACW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 9.2769 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 709 | 709 | 0 | 1 |  |  |  | 4700M621/25 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.0656 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 540 | 540 | 0 | 1 |  |  |  | 4700M621/26 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 2 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 717 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 64.0353 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 4894 | 4894 | 0 | 1 |  |  |  | 4700M621/30 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 2 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 717 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 56.6557 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 4330 | 4330 | 0 | 1 |  |  |  | 4700M621/35 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 14.1836 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1084 | 1084 | 0 | 1 |  |  |  | 4700M621/40 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | 6 times per year (ILM Certain Sections)
YNE32 Closure 2 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 717 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.4451 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 569 | 569 | 0 | 1 |  |  |  | 4700M621/45 | YNE32: M621 Gildersome - J1 | YNE32 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE32 Closure 1 CW NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 714 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 4.8936 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 374 | 374 | 0 | 1 |  |  |  | 4700M621/6 | YNE32: M621 Gildersome - J1 | YNE32 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | 6 times per year (ILM Certain Sections)
YNE41 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 718 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 18.7266 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 109.16 | 109.16 | 0 | 1 |  | N |  | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 719 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 29.4229 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 171.51 | 171.51 | 0 | 1 |  | N |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 720 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6.8466 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 39.91 | 39.91 | 0 | 1 |  | N |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE41 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 719 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 27.2511 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 158.85 | 158.85 | 0 | 1 |  | N |  | 2700A64/121 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 721 | Gullies - Emptying / clear covers | 331.9534 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 43 | 43 | 0 | 1 |  | N |  | 2700A64/114 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 722 | Gullies - Emptying / clear covers | 185.2763 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 26 | 24 | 2 | 0.92308 | 9/11 Enviro driver took ill no drainage completed within closure | N | Drainage driver took ill - rebooked for December | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 2/6 | 0/0 | 45782332 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 721 | Gullies - Emptying / clear covers | 138.9572 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 721 | Gullies - Emptying / clear covers | 185.2763 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 28 | 24 | 4 | 0.85714 | 9/11 Enviro driver took ill no drainage completed within closure | N | Drainage driver took ill - rebooked for December | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 | 45782332 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 723 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE41 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 722 | Gullies - Emptying / clear covers | 216.1557 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 38 | 28 | 10 | 0.73684 | 9/11 Enviro driver took ill no drainage completed within closure | N | Drainage driver took ill - rebooked for December | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 2/6 | 0/0 | 45782332 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 724 | Gullies - Emptying / clear covers | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE41 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 722 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/121 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 721 | Gullies - Emptying / clear covers | 123.5175 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 2700A64/122 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 722 | Gullies - Emptying / clear covers | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-08 | 2023-12 | 2023-12-09 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 9 | 6 | 3 | 0.66667 | 9/11 Enviro driver took ill no drainage completed within closure | N | Drainage driver took ill - rebooked for December | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 2/6 | 0/0 | 45782332 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 725 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 15.7193 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 638 | 638 | 0 | 1 |  | N |  | 2700A64/114 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 726 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 11.6786 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 474 | 474 | 0 | 1 |  | N |  | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 727 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 14.9309 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 606 | 606 | 0 | 1 |  | N |  | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE41 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 725 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.4638 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 100 | 100 | 0 | 1 |  | N |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 725 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.9207 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 565 | 565 | 0 | 1 |  | N |  | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 728 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.2871 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 174 | 174 | 0 | 1 |  | N |  | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE41 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 726 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 18.8976 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 767 | 767 | 0 | 1 |  | N |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 727 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.828 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 683 | 683 | 0 | 1 |  | N |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE41 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 728 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.3669 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 299 | 299 | 0 | 1 |  | N |  | 2700A64/120 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE41 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 726 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.1044 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 126 | 126 | 0 | 1 |  | N |  | 2700A64/121 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 725 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.7552 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 193 | 193 | 0 | 1 |  | N |  | 2700A64/122 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 727 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.3406 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 95 | 95 | 0 | 1 |  | N |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE41 Closure Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 729 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 126dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE41 Closure Amey 45048 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 730 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 118.6486 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 43dys |  | 3 | 3 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE41 Closure Amey 45048 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 731 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 105.4655 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 20dys |  | 4 | 4 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE41 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 732 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 74.449 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1553 | 1553 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 733 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 |  |  |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 734 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 |  |  |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 735 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 |  |  |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 736 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 79.0991 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 33 | 33 | 0 | 1 |  | N |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 736 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 27 | 27 | 0 | 1 |  | N |  | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 737 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/114 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 736 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 20 | 20 | 0 | 1 |  | N |  | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 737 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 737 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 736 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 737 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/120 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 736 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/121 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 737 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/122 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 736 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 738 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 641.1821 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 107 | 107 | 0 | 1 |  | N |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 738 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 738 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/121 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 739 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 3 | 3 | 0 | 1 |  | N |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 740 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 35.31 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 741 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 12.8785 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 621.78 | 621.78 | 0 | 1 |  | N |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 742 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 13.3845 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 646.21 | 646.21 | 0 | 1 |  | N |  | 2700A64/114 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 741 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.8987 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 91.67 | 91.67 | 0 | 1 |  | N |  | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 742 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 16.5703 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 800.02 | 800.02 | 0 | 1 |  | N |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 742 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.7748 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 327.09 | 327.09 | 0 | 1 |  | N |  | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 741 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 12.2758 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 592.68 | 592.68 | 0 | 1 |  | N |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 741 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.1073 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 53.46 | 53.46 | 0 | 1 |  | N |  | 2700A64/121 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 742 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 13.1907 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 636.85 | 636.85 | 0 | 1 |  | N |  | 2700A64/122 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 741 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.1607 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 56.04 | 56.04 | 0 | 1 |  | N |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 743 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.7317 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 481 | 481 | 0 | 1 |  | N |  | 2700A64/101 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 743 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.461 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1067 | 1067 | 0 | 1 |  | N |  | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 744 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.9862 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 595 | 595 | 0 | 1 |  | N |  | 2700A64/114 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 743 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.1314 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 495 | 495 | 0 | 1 |  | N |  | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 744 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.8892 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1082 | 1082 | 0 | 1 |  | N |  | 2700A64/116 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 744 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.058 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1193 | 1193 | 0 | 1 |  | N |  | 2700A64/118 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 743 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 56.4684 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1978 | 1978 | 0 | 1 |  | N |  | 2700A64/119 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 744 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5588 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 545 | 545 | 0 | 1 |  | N |  | 2700A64/120 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 743 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.1567 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 636 | 636 | 0 | 1 |  | N |  | 2700A64/121 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 744 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.7072 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 305 | 305 | 0 | 1 |  | N |  | 2700A64/122 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 & 0/0 R,Bout | 3/0 0/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 743 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.624 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 197 | 197 | 0 | 1 |  | N |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 2/6 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE41 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 745 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 33.3106 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 370.59 | 370.59 | 0 | 1 |  | N |  | 2700A64/103 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 745 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 49.0019 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 545.16 | 545.16 | 0 | 1 |  | N |  | 2700A64/115 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 746 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 66.4675 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 739.47 | 739.47 | 0 | 1 |  | N |  | 2700A64/120 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 745 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 18.4121 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 204.84 | 204.84 | 0 | 1 |  | N |  | 2700A64/123 | YNE41: A64 Bramham - Headley | YNE41 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE41 Closure Amey 45048 BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 747 | BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 0 | 4.5.2 | A40037 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 1 |  |  | Annually
YNE41 Closure Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 748 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 11 | 11 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 1 |  |  | Every 3 years
YNE41 Closure Amey 45048 Electrical Testing - Network cabling and electrical components | 749 | Electrical Testing - Network cabling and electrical components | 671.1438 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 35 | 35 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE41 Closure Amey 45048 CCTV PTZ Cameras - Clean camera lens | 750 | CCTV PTZ Cameras - Clean camera lens | 23.9694 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE41 Closure Amey 45048 CCTV PTZ Cameras - Check camera functionality | 751 | CCTV PTZ Cameras - Check camera functionality | 23.9694 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE41 Closure Amey 45048 CCTV PTZ Cameras - Check data and power supplies | 752 | CCTV PTZ Cameras - Check data and power supplies | 23.9694 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE41: A64 Bramham - Headley | YNE41 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE42 Closure 2 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 753 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 78.9792 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 460.38 | 460.38 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 754 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 11.7016 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 68.21 | 68.21 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 753 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 9.3753 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 54.65 | 54.65 | 0 | 1 |  | N |  | 2700A64/134 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 754 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 7.7027 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 44.9 | 44.9 | 0 | 1 |  | N |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 755 | Gullies - Emptying / clear covers | 223.8756 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-10 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 29 | 29 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 5/5 | 2/3 | 45782733 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 756 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 755 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 756 | Gullies - Emptying / clear covers | 123.5175 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-10 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 2700A64/134 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 1/7 | 5/7 | 45782733 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 757 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 53 | 0 | 53 | 0 | 4/9: not on programme | N |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782733
YNE42 Closure 2 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 758 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 32.2517 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1309 | 1309 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 759 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 29.64 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1203 | 1203 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE42 Closure 2 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 760 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 34.4691 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1399 | 1399 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 761 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.6888 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 515 | 515 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE42 Closure 2 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 758 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 29.0979 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1181 | 1181 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 759 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 22.963 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 932 | 932 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE42 Closure 2 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 760 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 20.1049 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 816 | 816 | 0 | 1 |  | N |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 761 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.6031 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 268 | 268 | 0 | 1 |  | N |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE42 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 761 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.1392 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 168 | 168 | 0 | 1 |  | N |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE42 Closure 2 EB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 762 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 763 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 11.1857 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 762 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.1908 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 763 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 762 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/134 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 763 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 764 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Amey 45048 Marker Posts - Clean all marker post faces and reference numbers | 765 | Marker Posts - Clean all marker post faces and reference numbers | 0.79898 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Amey 45048 Marker Posts - Clean all marker post faces and reference numbers | 766 | Marker Posts - Clean all marker post faces and reference numbers | 7.1908 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Amey 45048 Marker Posts - Clean all marker post faces and reference numbers | 766 | Marker Posts - Clean all marker post faces and reference numbers | 4.3944 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS Amey 45048 Marker Posts - Clean all marker post faces and reference numbers | 766 | Marker Posts - Clean all marker post faces and reference numbers | 2.3969 | 4.4.2 | A40034 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 767 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 126dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide | 1/7 | 5/7 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 768 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 70.3742 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1468 | 1468 | 0 | 1 |  | N |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 769 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 52036915
YNE42 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 770 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 771 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE42 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 772 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 773 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 32 | 32 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 772 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 773 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 21 | 21 | 0 | 1 |  | N |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 772 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/134 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 773 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 774 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 774 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 775 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.7808 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 327.38 | 327.38 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 775 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.9339 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 141.65 | 141.65 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 776 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 42.2799 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1481 | 1481 | 0 | 1 |  | N |  | 2700A64/124 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 777 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 49.5026 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1734 | 1734 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 776 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.7464 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1077 | 1077 | 0 | 1 |  | N |  | 2700A64/130 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 777 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.6608 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1074 | 1074 | 0 | 1 |  | N |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 776 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.3573 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 608 | 608 | 0 | 1 |  | N |  | 2700A64/134 | YNE42: A64 Headley - A162 | YNE42 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 1/7 | 5/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 777 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.0425 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 632 | 632 | 0 | 1 |  | N |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 5/5 | 2/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE42 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 778 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 186.6065 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2076.05 | 2076.05 | 0 | 1 |  | N |  | 2700A64/125 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE42 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 778 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 246.0971 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2737.9 | 2737.9 | 0 | 1 |  | N |  | 2700A64/131 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE42 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 778 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 99.2289 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1103.95 | 1103.95 | 0 | 1 |  | N |  | 2700A64/135 | YNE42: A64 Headley - A162 | YNE42 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 779 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0.96412 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5.62 | 5.62 | 0 | 1 |  | N |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE43 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 780 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE43 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 781 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE43 Closure 2 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 782 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/139 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE43 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 783 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE43 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 784 | Gullies - Emptying / clear covers | 301.074 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 39 | 39 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE43 Closure 2 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 782 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE43 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 785 | Gullies - Emptying / clear covers | 247.0351 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 32 | 32 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE43 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 780 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 1 | 0 | 1 | 0 | Not completed due to gritting | N | Not completed | 2700A64/152 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782733
YNE43 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 785 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE43 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 783 | Gullies - Emptying / clear covers | 741.1053 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 111 | 96 | 15 | 0.86486 | 5/9 not mentioned on night report | N |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782785
YNE43 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 786 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.7777 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 72.15 | 72.15 | 0 | 1 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE43 Closure 2 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 787 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.1741 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 210 | 210 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE43 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 788 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.8045 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 195 | 195 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE43 Closure 2 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 789 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.8163 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 439 | 439 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE43 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 790 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.4408 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 302 | 302 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE43 Closure 2 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 787 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.4279 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 545 | 545 | 0 | 1 |  | N |  | 2700A64/148 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE43 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 788 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 19.2179 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 780 | 780 | 0 | 1 |  | N |  | 2700A64/148 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE43 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 791 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.6004 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 552 | 552 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE43 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 786 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 14.8323 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 602 | 602 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE43 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 791 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.3058 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 53 | 53 | 0 | 1 |  | N |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE43 Closure Amey 45048 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 792 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 134.828 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 6 | 6 | 0 | 1 |  | N |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE43 Closure Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 793 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 5 | 5 | 0 | 1 |  | N |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure | Lane 1 Closure | 1 |  |  | Every 3 years
YNE43 Closure Amey 45048 BC - Lamps (LED) for Illuminated Signs and Bollards | 794 | BC - Lamps (LED) for Illuminated Signs and Bollards | 14.9809 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE43 Closure Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 795 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 126dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE43 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 796 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 84.66 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1766 | 1766 | 0 | 1 |  | N |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 797 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 798 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 799 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 | Missed intervention or complete? |  |  |  | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 800 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 32 | 32 | 0 | 1 |  | N |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 801 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/139 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 802 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 803 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 801 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 29 | 29 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 803 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/148 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 802 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 25 | 25 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 800 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  | N |  | 2700A64/152 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 802 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 802 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 802 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/156 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 802 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/157 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 802 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/174 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 804 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 804 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 53.9312 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 804 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 53.9312 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/156 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 804 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/157 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 804 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 29.9618 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/174 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 805 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 806 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 807 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.99419 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 48 | 48 | 0 | 1 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 808 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.3637 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 258.96 | 258.96 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 809 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 8.9608 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 432.63 | 432.63 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 810 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 7.5314 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 363.62 | 363.62 | 0 | 1 |  | N |  | 2700A64/152 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 807 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 15.9152 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 768.39 | 768.39 | 0 | 1 |  | N |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 807 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.6706 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 225.5 | 225.5 | 0 | 1 |  | N |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 807 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.082849 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/156 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 811 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 53.0407 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1280.4122 | 1280.4122 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE43 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 812 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 37.5124 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1314 | 1314 | 0 | 1 |  | N |  | 2700A64/136 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 813 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.6216 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 302 | 302 | 0 | 1 |  | N |  | 2700A64/138 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 814 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.3924 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 329 | 329 | 0 | 1 |  | N |  | 2700A64/139 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.9503 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 909 | 909 | 0 | 1 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 813 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.9185 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1048 | 1048 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 814 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.6616 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1039 | 1039 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 813 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.3998 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1240 | 1240 | 0 | 1 |  | N |  | 2700A64/148 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.3109 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1377 | 1377 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 812 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.5156 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1174 | 1174 | 0 | 1 |  | N |  | 2700A64/152 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.0303 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1157 | 1157 | 0 | 1 |  | N |  | 2700A64/154 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.6216 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 302 | 302 | 0 | 1 |  | N |  | 2700A64/155 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.0832 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 108 | 108 | 0 | 1 |  | N |  | 2700A64/156 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.2847 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 45 | 45 | 0 | 1 |  | N |  | 2700A64/157 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 815 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.1664 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 216 | 216 | 0 | 1 |  | N |  | 2700A64/174 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE43 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 816 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 75.252 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 837.2 | 837.2 | 0 | 1 |  | N |  | 2700A64/139 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 817 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 66.2482 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 737.03 | 737.03 | 0 | 1 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 818 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 5.7814 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 64.32 | 64.32 | 0 | 1 |  | N |  | 2700A64/142 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 816 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 128.9252 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1434.33 | 1434.33 | 0 | 1 |  | N |  | 2700A64/143 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 2 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 818 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 4.4206 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 49.18 | 49.18 | 0 | 1 |  | N |  | 2700A64/148 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 817 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 159.6723 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1776.4 | 1776.4 | 0 | 1 |  | N |  | 2700A64/149 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE43 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 819 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 118.1985 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1712 | 1712 | 0 | 1 |  | N |  | 2700A64/140 | YNE43: A64 A162 - Tadcaster | YNE43 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 820 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 9.4131 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 54.87 | 54.87 | 0 | 1 |  | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 821 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 10.5333 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 61.4 | 61.4 | 0 | 1 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE44 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 821 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 44.8866 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 261.65 | 261.65 | 0 | 1 |  | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE44 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 822 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 30.1434 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 175.71 | 175.71 | 0 | 1 |  | N |  | 2700A64/175 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE44 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 823 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete | 120 were actually completed | 21dys | EB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 9/1 | 15/6 | 45782352 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 824 | Gullies - Emptying / clear covers | 185.2763 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 24 | 24 | 0 | 1 | 6/9 - 38 done but jobs not colosed - asked for records | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 825 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 6 | 0 | 6 | 0 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 826 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 6/9 - gully cart full not complete | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 826 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 6/9 - gully cart full not complete | N |  | 2700A64/163 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 825 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 2 | 0 | 2 | 0 |  | N |  | 2700A64/165 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 826 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 6/9 - gully cart full not complete | N |  | 2700A64/165 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 823 | Gullies - Emptying / clear covers | 200.716 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 26 | 26 | 0 | 1 |  | N |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 9/1 | 15/6 | 45782352 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 824 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 | 6/9 - 38 done but jobs not colosed - asked for records | N |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 825 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 7 | 0 | 7 | 0 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 826 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 6/9 - gully cart full not complete | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 823 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/168 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 9/1 | 15/6 | 45782352 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 824 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 | 6/9 - 38 done but jobs not colosed - asked for records | N |  | 2700A64/168 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 823 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/169 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 9/1 | 15/6 | 45782352 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 825 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 5 | 0 | 5 | 0 |  | N |  | 2700A64/171 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 823 | Gullies - Emptying / clear covers | 247.0351 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 32 | 32 | 0 | 1 |  | N |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 9/1 | 15/6 | 45782352 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 824 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 | 6/9 - 38 done but jobs not colosed - asked for records | N |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 827 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 6/9 - gully cart full not complete | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45782352
YNE44 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 828 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE44 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 826 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 | 6/9 - gully cart full not complete | N |  | 2700A64/175 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782352
YNE44 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 829 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 79.8182 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1665 | 1665 | 0 | 1 |  | N |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 830 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 831 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 832 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 833 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 834 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 834 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/163 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 834 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 29 | 29 | 0 | 1 |  | N |  | 2700A64/165 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 833 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 21 | 21 | 0 | 1 |  | N |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 834 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 22 | 22 | 0 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 833 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/168 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 834 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/171 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 833 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 15 | 15 | 0 | 1 |  | N |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 834 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 88.6869 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 37 | 37 | 0 | 1 |  | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 834 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/175 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 835 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 836 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 52.3061 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2525.36 | 2525.36 | 0 | 1 |  | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 837 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 24.9832 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1206.2 | 1206.2 | 0 | 1 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 837 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 22.19 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1071.34 | 1071.34 | 0 | 1 |  | N |  | 2700A64/163 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 837 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 13.2658 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 640.48 | 640.48 | 0 | 1 |  | N |  | 2700A64/165 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 836 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 58.6421 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2831.26 | 2831.26 | 0 | 1 |  | N |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 837 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 33.1215 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1599.12 | 1599.12 | 0 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 836 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.2514 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 301.82 | 301.82 | 0 | 1 |  | N |  | 2700A64/168 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 837 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 7.2717 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 351.08 | 351.08 | 0 | 1 |  | N |  | 2700A64/171 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 836 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 29.2786 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1413.58 | 1413.58 | 0 | 1 |  | N |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 837 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 45.1716 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2180.9 | 2180.9 | 0 | 1 |  | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 838 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 26.3586 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 636.3024 | 636.3024 | 0 | 1 |  | N |  | 2700A64/165 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE44 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 838 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 112.0526 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2704.9673 | 2704.97 | -0.002688 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE44 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 839 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.1143 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1230 | 1230 | 0 | 1 |  | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 840 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.1273 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 670 | 670 | 0 | 1 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 840 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.2464 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 464 | 464 | 0 | 1 |  | N |  | 2700A64/163 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 840 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.1036 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 459 | 459 | 0 | 1 |  | N |  | 2700A64/165 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 839 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.5703 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1281 | 1281 | 0 | 1 |  | N |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 840 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.0906 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1019 | 1019 | 0 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 839 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.2219 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 288 | 288 | 0 | 1 |  | N |  | 2700A64/168 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 839 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.3638 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 328 | 328 | 0 | 1 |  | N |  | 2700A64/169 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 840 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.593 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 301 | 301 | 0 | 1 |  | N |  | 2700A64/171 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 839 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.527 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 684 | 684 | 0 | 1 |  | N |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 9/1 | 15/6 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE44 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 840 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.6339 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1003 | 1003 | 0 | 1 |  | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 840 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.3075 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 291 | 291 | 0 | 1 |  | N |  | 2700A64/175 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE44 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 841 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 121.0917 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1347.18 | 1347.18 | 0 | 1 |  | N |  | 2700A64/158 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 842 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 185.5269 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2064.04 | 2064.04 | 0 | 1 |  | N |  | 2700A64/159 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 841 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 140.347 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1561.4 | 1561.4 | 0 | 1 |  | N |  | 2700A64/166 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 842 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 85.2778 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 948.74 | 948.74 | 0 | 1 |  | N |  | 2700A64/167 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 841 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 68.1277 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 757.94 | 757.94 | 0 | 1 |  | N |  | 2700A64/169 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 841 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 49.8828 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 554.96 | 554.96 | 0 | 1 |  | N |  | 2700A64/172 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE44 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 842 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 93.7145 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1042.6 | 1042.6 | 0 | 1 |  | N |  | 2700A64/173 | YNE44: A64 Tadcaster - Bilbrough | YNE44 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 843 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6.1347 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 35.76 | 35.76 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 844 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/170 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 845 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/176 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 846 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 | 7/9: Attended no gulies in this portion of closure | N |  | 2700A64/176 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 847 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE45 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 848 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 146.6771 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 19 | 19 | 0 | 1 | 7/9: Attended no gulies in this portion of closure | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45782391
YNE45 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 844 | Gullies - Emptying / clear covers | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 22 | 22 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 849 | Gullies - Emptying / clear covers | 162.1168 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 21 | 21 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 845 | Gullies - Emptying / clear covers | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 846 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 | 7/9: Attended no gulies in this portion of closure | N |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 845 | Gullies - Emptying / clear covers | 131.2374 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 17 | 17 | 0 | 1 |  | N |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 846 | Gullies - Emptying / clear covers | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 22 | 22 | 0 | 1 | 7/9: Attended no gulies in this portion of closure | N |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 844 | Gullies - Emptying / clear covers | 262.4748 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 34 | 34 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 849 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 845 | Gullies - Emptying / clear covers | 115.7977 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 15 | 15 | 0 | 1 |  | N |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 846 | Gullies - Emptying / clear covers | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 14 | 14 | 0 | 1 | 7/9: Attended no gulies in this portion of closure | N |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 844 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 845 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 846 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 | 7/9: Attended no gulies in this portion of closure | N |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 844 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 845 | Gullies - Emptying / clear covers | 77.1985 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/187 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45782391
YNE45 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 845 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 850 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.5902 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 511 | 511 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE45 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 851 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.7161 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 232 | 232 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE45 Closure Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 852 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 20 | 20 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure | Lane 1 Closure | 1 |  |  | Every 3 years
YNE45 Closure Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 853 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 126dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE45 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 854 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 61.2179 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1277 | 1277 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 855 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 856 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 | complete or missed? |  |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 857 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 | complete or missed? |  |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 858 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/170 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 859 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/176 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 859 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 858 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 859 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 859 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 858 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 79.0991 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 33 | 33 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 859 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 858 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 859 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 858 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 859 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/187 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 859 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 860 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 860 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 861 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/187 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 861 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 862 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 862 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 862 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 863 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 9.693 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 467.98 | 467.98 | 0 | 1 |  | N |  | 2700A64/170 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 864 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.3094 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 256.34 | 256.34 | 0 | 1 |  | N |  | 2700A64/176 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 864 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 21.9224 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1058.42 | 1058.42 | 0 | 1 |  | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 863 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 35.3079 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1704.68 | 1704.68 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 864 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 21.1792 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1022.54 | 1022.54 | 0 | 1 |  | N |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 864 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 25.2919 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1221.1 | 1221.1 | 0 | 1 |  | N |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 863 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 53.5259 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2584.25 | 2584.25 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 864 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.51698 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 24.96 | 24.96 | 0 | 1 |  | N |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 863 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.8771 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 332.03 | 332.03 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 864 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 8.9208 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 430.7 | 430.7 | 0 | 1 |  | N |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 863 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 8.3719 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 404.2 | 404.2 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 863 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 31.1918 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 1505.95 | 1505.95 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 865 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.3916 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 364 | 364 | 0 | 1 |  | N |  | 2700A64/170 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 866 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.965 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 279 | 279 | 0 | 1 |  | N |  | 2700A64/176 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 866 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.3891 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 469 | 469 | 0 | 1 |  | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 865 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.9528 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 804 | 804 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 866 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.0465 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 457 | 457 | 0 | 1 |  | N |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 866 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.2994 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 641 | 641 | 0 | 1 |  | N |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 865 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.7717 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1218 | 1218 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 866 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.4478 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 401 | 401 | 0 | 1 |  | N |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 865 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.279 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 290 | 290 | 0 | 1 |  | N |  | 2700A64/184 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 866 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.8785 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 311 | 311 | 0 | 1 |  | N |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 865 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.6714 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 619 | 619 | 0 | 1 |  | N |  | 2700A64/186 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 866 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.9332 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 418 | 418 | 0 | 1 |  | N |  | 2700A64/187 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 865 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5588 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 545 | 545 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 866 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.3132 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 46 | 46 | 0 | 1 |  | N |  | 2700A64/193 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE45 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 867 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 60.0092 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 667.62 | 667.62 | 0 | 1 |  | N |  | 2700A64/177 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 868 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 32.6248 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 362.96 | 362.96 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 867 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 67.8365 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 754.7 | 754.7 | 0 | 1 |  | N |  | 2700A64/179 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 867 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 68.9789 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 767.41 | 767.41 | 0 | 1 |  | N |  | 2700A64/181 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 868 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 148.3836 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1650.81 | 1650.81 | 0 | 1 |  | N |  | 2700A64/182 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 867 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 32.5628 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 362.27 | 362.27 | 0 | 1 |  | N |  | 2700A64/183 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 867 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 88.6764 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 986.55 | 986.55 | 0 | 1 |  | N |  | 2700A64/185 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 868 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 9.1359 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 101.64 | 101.64 | 0 | 1 |  | N |  | 2700A64/191 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 867 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 8.2623 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 91.92 | 91.92 | 0 | 1 |  | N |  | 2700A64/193 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 869 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 8.7682 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 127 | 127 | 0 | 1 |  | N |  | 2700A64/178 | YNE45: A64 Bilbrough - Askham | YNE45 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE45 Closure Amey 45048 Electrical Testing - Network cabling and electrical components | 870 | Electrical Testing - Network cabling and electrical components | 38.3511 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE45 Closure Amey 45048 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 871 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE45: A64 Bilbrough - Askham | YNE45 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE46 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 872 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6.2891 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 36.66 | 36.66 | 0 | 1 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 873 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 14.46 | 0 | 14.46 | 0 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 874 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.1238 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12.38 | 12.38 | 0 | 1 |  | N |  | 2700A64/190 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 EB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 875 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 13.63 | 0 | 13.63 | 0 |  | N |  | 2700A64/190 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 872 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 44.1061 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 257.1 | 257.1 | 0 | 1 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 872 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 108.035 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 629.75 | 629.75 | 0 | 1 |  | N |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 873 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 192.84 | 0 | 192.84 | 0 |  | N |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 874 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 114.8593 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 669.53 | 669.53 | 0 | 1 |  | N |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 872 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.9009 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 16.91 | 16.91 | 0 | 1 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE45 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 873 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 613.42 | 0 | 613.42 | 0 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE45 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 872 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 24.9471 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 145.42 | 145.42 | 0 | 1 |  | N |  | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 872 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 112.1231 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 653.58 | 653.58 | 0 | 1 |  | N |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 876 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 877 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 878 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 876 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/190 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 876 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 879 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 877 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 878 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 877 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 878 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 876 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 877 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 876 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 8 | -3 | 1.6 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 879 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 877 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 878 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 877 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/216 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 878 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/216 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 877 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 878 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE46 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 880 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 162 | 0 | 162 | 0 |  | N |  | 2700A64/190 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE46 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 880 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 267 | 0 | 267 | 0 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE46 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 881 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 453 | 0 | 453 | 0 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE46 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 881 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 53 | 0 | 53 | 0 |  | N |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE46 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 880 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 842 | 0 | 842 | 0 |  | N |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE46 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 881 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 199 | 0 | 199 | 0 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE46 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 881 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 129 | 0 | 129 | 0 |  | N |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE46 Closure Amey 45048 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 882 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 44.9427 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE46 Closure Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 883 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure | Lane 1 Closure | 1 |  |  | Every 3 years
YNE46 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 884 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 77.4692 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1616 | 1616 | 0 | 1 |  | N |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 885 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 886 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 887 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  | N |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 888 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 889 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 888 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 889 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 29 | 29 | 0 | 1 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 889 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 888 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 889 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 888 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 67.1144 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 28 | 28 | 0 | 1 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 889 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 889 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/216 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 889 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 22 | 22 | 0 | 1 |  | N |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 890 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 891 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 892 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 892 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 893 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 15.654 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 755.78 | 755.78 | 0 | 1 |  | N |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 894 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.71913 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 34.72 | 34.72 | 0 | 1 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 893 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 7.0105 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 338.47 | 338.47 | 0 | 1 |  | N |  | 2700A64/190 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 893 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 28.1282 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1358.04 | 1358.04 | 0 | 1 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 894 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 14.4021 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 695.34 | 695.34 | 0 | 1 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 894 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.0253 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 49.5 | 49.5 | 0 | 1 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 893 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.93081 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 44.94 | 44.94 | 0 | 1 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 894 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.3686 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 259.2 | 259.2 | 0 | 1 |  | N |  | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 894 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.1089 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 150.1 | 150.1 | 0 | 1 |  | N |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 895 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.527 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 684 | 684 | 0 | 1 |  | N |  | 2700A64/188 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.9062 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 347 | 347 | 0 | 1 |  | N |  | 2700A64/189 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 895 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.4201 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 365 | 365 | 0 | 1 |  | N |  | 2700A64/190 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 895 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.0131 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 666 | 666 | 0 | 1 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.3231 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 852 | 852 | 0 | 1 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.3581 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 573 | 573 | 0 | 1 |  | N |  | 2700A64/195 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 895 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.2897 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1061 | 1061 | 0 | 1 |  | N |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.7562 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 657 | 657 | 0 | 1 |  | N |  | 2700A64/207 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 895 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.987 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 560 | 560 | 0 | 1 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.9552 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 699 | 699 | 0 | 1 |  | N |  | 2700A64/214 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.5955 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 196 | 196 | 0 | 1 |  | N |  | 2700A64/216 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 896 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.1168 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1125 | 1125 | 0 | 1 |  | N |  | 2700A64/223 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE46 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 897 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 124.4112 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1384.11 | 1384.11 | 0 | 1 |  | N |  | 2700A64/192 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 898 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 177.4795 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1974.51 | 1974.51 | 0 | 1 |  | N |  | 2700A64/194 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 897 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 272.7247 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3034.14 | 3034.14 | 0 | 1 |  | N |  | 2700A64/206 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure 1 EB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 899 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0.89754 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/212 | YNE46: A64 Askham - Bondhill | YNE46 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE46 Closure Amey 45048 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 900 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE46: A64 Askham - Bondhill | YNE46 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE47 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 901 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 10.113 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 58.95 | 58.95 | 0 | 1 |  | N |  | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 902 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 19.1967 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 111.9 | 111.9 | 0 | 1 |  | N |  | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 903 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 86.5721 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 504.64 | 504.64 | 0 | 1 |  | N |  | 2700A64/220 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 903 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 16.3472 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 95.29 | 95.29 | 0 | 1 |  | N |  | 2700A64/226 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 903 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 40.3113 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 234.98 | 234.98 | 0 | 1 |  | N |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 901 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 67.1215 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 391.26 | 391.26 | 0 | 1 |  | N |  | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 902 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 104.6228 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 609.86 | 609.86 | 0 | 1 |  | N |  | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 903 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5.819 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 33.92 | 33.92 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 901 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 29.6597 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 172.89 | 172.89 | 0 | 1 |  | N |  | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 902 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 105.345 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 614.07 | 614.07 | 0 | 1 |  | N |  | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 903 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5.3267 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 31.05 | 31.05 | 0 | 1 |  | N |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 901 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 58.6056 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 341.62 | 341.62 | 0 | 1 |  | N |  | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 902 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 38.5907 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 224.95 | 224.95 | 0 | 1 |  | N |  | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 901 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 10.7049 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 62.4 | 62.4 | 0 | 1 |  | N |  | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 902 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 74.584 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 434.76 | 434.76 | 0 | 1 |  | N |  | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 904 | Gullies - Emptying / clear covers | 115.7977 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 15 | 15 | 0 | 1 |  | N |  | 2700A64/220 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 905 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 | 13/9: no gullies in centre | N |  | 2700A64/220 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 904 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/226 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 904 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 906 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 4 | 0 | 4 | 0 | 13/11 cancelled due to bad weather | Y | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 904 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE47 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 906 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 19 | 0 | 19 | 0 | 13/11 cancelled due to bad weather | Y | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 904 | Gullies - Emptying / clear covers | 200.716 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | completed | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 32 | 26 | 0 | 0.8125 |  | N |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 906 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 41 | 0 | 41 | 0 | 13/11 cancelled due to bad weather | Y | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 904 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | completed | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 5 | 1 | 0 | 0.2 |  | N |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 905 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 | 13/9: no gullies in centre | N |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 906 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 16 | 0 | 16 | 0 | 13/11 cancelled due to bad weather | Y | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 907 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 905 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 | 13/9: no gullies in centre | N |  | 2700A64/252 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 906 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 5 | 0 | 5 | 0 | 13/11 cancelled due to bad weather | Y | Cancelled due to severe weather then unable to utilise contingency due to scheme clashes | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784095
YNE47 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 908 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.0482 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 489 | 489 | 0 | 1 |  | N |  | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE47 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 909 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 9.6582 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 392 | 392 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE47 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 908 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.2699 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 498 | 498 | 0 | 1 |  | N |  | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE47 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 909 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 17.0251 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 691 | 691 | 0 | 1 |  | N |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE47 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 910 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.79 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 235 | 235 | 0 | 1 |  | N |  | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE47 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 909 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.774 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 72 | 72 | 0 | 1 |  | N |  | 2700A64/252 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE47 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 908 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 9.4119 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 382 | 382 | 0 | 1 |  | N |  | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE47 Closure Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 911 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 3 | 3 | 0 | 1 |  | N |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure | Lane 1 Closure | 1 |  |  | Every 3 years
YNE47 Closure Amey 45048 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 912 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure | Lane 1 Closure | 1 |  |  | Every 3 years |  |  | On ServiceNow
YNE47 Closure Amey 45048 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 913 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure | Lane 1 Closure | 1 |  |  | Every 3 years |  |  | On ServiceNow
YNE47 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 914 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 85.7626 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1789 | 1789 | 0 | 1 |  | N |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 915 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 916 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 917 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 918 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 919 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/220 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 919 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/226 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 919 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 918 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 919 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 918 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 17 | 17 | 0 | 1 |  | N |  | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 919 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 20 | 20 | 0 | 1 |  | N |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 918 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 19 | 19 | 0 | 1 |  | N |  | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 919 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 67.1144 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 28 | 28 | 0 | 1 |  | N |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 918 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 19 | 19 | 0 | 1 |  | N |  | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 919 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/252 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 918 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 920 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 921 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 59.9236 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 922 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 923 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 924 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.7057 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 82.35 | 82.35 | 0 | 1 |  | N |  | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 925 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.82435 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 39.8 | 39.8 | 0 | 1 |  | N |  | 2700A64/226 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 925 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.5476 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 123 | 123 | 0 | 1 |  | N |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 924 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.020091 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 0.97 | 0.97 | 0 | 1 |  | N |  | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 925 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.4977 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 120.59 | 120.59 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 924 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.025 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 97.77 | 97.77 | 0 | 1 |  | N |  | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 924 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.8053 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 38.88 | 38.88 | 0 | 1 |  | N |  | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 925 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.2322 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 107.77 | 107.77 | 0 | 1 |  | N |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 924 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.7605 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 519.52 | 519.52 | 0 | 1 |  | N |  | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 924 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.68144 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 32.9 | 32.9 | 0 | 1 |  | N |  | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 926 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.5971 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 126 | 126 | 0 | 1 |  | N |  | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 927 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.6999 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 620 | 620 | 0 | 1 |  | N |  | 2700A64/220 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 927 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.9609 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 454 | 454 | 0 | 1 |  | N |  | 2700A64/226 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 927 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.6787 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 304 | 304 | 0 | 1 |  | N |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 926 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.642 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 653 | 653 | 0 | 1 |  | N |  | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 927 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.8394 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 765 | 765 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 926 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.3826 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 749 | 749 | 0 | 1 |  | N |  | 2700A64/237 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 927 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.0319 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1087 | 1087 | 0 | 1 |  | N |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 926 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.2065 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 953 | 953 | 0 | 1 |  | N |  | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 927 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.6183 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 442 | 442 | 0 | 1 |  | N |  | 2700A64/248 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 926 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.9267 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 698 | 698 | 0 | 1 |  | N |  | 2700A64/249 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 927 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.7309 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 516 | 516 | 0 | 1 |  | N |  | 2700A64/252 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 926 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.5555 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 685 | 685 | 0 | 1 |  | N |  | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE47 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 928 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 6.5526 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 72.9 | 72.9 | 0 | 1 |  | N |  | 2700A64/209 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 929 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 11.4109 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 126.95 | 126.95 | 0 | 1 |  | N |  | 2700A64/226 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 929 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 45.9269 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 510.95 | 510.95 | 0 | 1 |  | N |  | 2700A64/230 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 928 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 66.3713 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 738.4 | 738.4 | 0 | 1 |  | N |  | 2700A64/231 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 929 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 61.8986 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 688.64 | 688.64 | 0 | 1 |  | N |  | 2700A64/236 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 929 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 7.7427 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 86.14 | 86.14 | 0 | 1 |  | N |  | 2700A64/242 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 928 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 10.859 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 120.81 | 120.81 | 0 | 1 |  | N |  | 2700A64/244 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE47 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 928 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 21.6965 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 241.38 | 241.38 | 0 | 1 |  | N |  | 2700A64/253 | YNE47: A64 Bondhill - Fulford | YNE47 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 930 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5.6012 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 32.65 | 32.65 | 0 | 1 |  | N |  | 2700A64/256 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 931 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 19.9 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 116 | 116 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 932 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 72.2869 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 421.37 | 421.37 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 931 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 7.0937 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 41.35 | 41.35 | 0 | 1 |  | N |  | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 930 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 4.8858 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 28.48 | 28.48 | 0 | 1 |  | N |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 932 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 169.1813 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 986.18 | 986.18 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 930 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 9.7973 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 57.11 | 57.11 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 933 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 9.8317 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 57.31 | 57.31 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 934 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 251.7854 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1467.69 | 1467.69 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 935 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5.1534 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 30.04 | 30.04 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 EB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 936 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1.7069 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9.95 | 9.95 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 933 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 13.7516 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 80.16 | 80.16 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 934 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 188.3608 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1097.98 | 1097.98 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 935 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 8.4301 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 49.14 | 49.14 | 0 | 1 |  | N |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 933 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6.2788 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 36.6 | 36.6 | 0 | 1 |  | N |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 934 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 51.2701 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 298.86 | 298.86 | 0 | 1 |  | N |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 933 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 28.584 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 166.62 | 166.62 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 934 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 104.2831 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 607.88 | 607.88 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 930 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 20.835 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 121.45 | 121.45 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 EB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 937 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 7.3167 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 42.65 | 42.65 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 938 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/256 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 938 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 939 | Gullies - Emptying / clear covers | 123.5175 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 940 | Gullies - Emptying / clear covers | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 938 | Gullies - Emptying / clear covers | 138.9572 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 941 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 938 | Gullies - Emptying / clear covers | 223.8756 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 29 | 29 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 939 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 941 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 942 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 943 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 942 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 939 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 2 | 0 | 2 | 0 |  | N |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 938 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 939 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 941 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/317 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 940 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/317 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 938 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-16 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | CW | 9 | 9 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 939 | Gullies - Emptying / clear covers | 216.1557 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 28 | 28 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784419
YNE48 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 944 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.4033 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 544 | 544 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 944 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 18.7991 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 763 | 763 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 945 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.1103 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 248 | 248 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 946 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 33.1879 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1347 | 1347 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 947 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 17.2222 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 699 | 699 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 946 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.2206 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 496 | 496 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 947 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.8655 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 441 | 441 | 0 | 1 |  | N |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 946 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.6711 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 149 | 149 | 0 | 1 |  | N |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 2 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 948 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.8104 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 317 | 317 | 0 | 1 |  | N |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 947 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.4885 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 101 | 101 | 0 | 1 |  | N |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 946 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 9.88 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 401 | 401 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 949 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.587 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 105 | 105 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 949 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.2089 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 252 | 252 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 945 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.203 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 130 | 130 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE48 Closure Amey 45048 BC - Lamps (LED) for Illuminated Signs and Bollards | 950 | BC - Lamps (LED) for Illuminated Signs and Bollards | 14.9809 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE48 Closure Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 951 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 126dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE48 Closure Amey 45048 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 952 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 3 | 3 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE48 Closure Amey 45048 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 953 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 3 | 3 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE48 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 954 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 139.4541 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 2909 | 2909 | 0 | 1 |  | N |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 955 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 956 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 957 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/256 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 15 | 15 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 21 | 21 | 0 | 1 |  | N |  | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 19 | 19 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 960 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 20 | 20 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 961 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 960 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 961 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 960 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 961 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 960 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 32 | 32 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 959 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  | N |  | 2700A64/317 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 958 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 213.3279 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 89 | 89 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 962 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 963 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 964 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 962 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 125.8395 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 21 | 21 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 963 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 29.9618 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/317 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 962 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 167.786 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 28 | 28 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 965 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 965 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 966 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 965 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 3 | 3 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 967 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.69801 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 33.7 | 33.7 | 0 | 1 |  | N |  | 2700A64/256 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 968 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.26926 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 967 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 11.1263 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 537.18 | 537.18 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 968 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.944 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 190.42 | 190.42 | 0 | 1 |  | N |  | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 967 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.6466 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 224.34 | 224.34 | 0 | 1 |  | N |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 968 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.9768 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 143.72 | 143.72 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 967 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.0329 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 146.43 | 146.43 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 969 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.0665 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 148.05 | 148.05 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 970 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.4559 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 118.57 | 118.57 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 969 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.3743 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 66.35 | 66.35 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 967 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.62406 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 30.13 | 30.13 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 967 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 12.2416 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 591.03 | 591.03 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 971 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 22.3128 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 538.634 | 538.634 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 972 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 20.1197 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 485.6938 | 485.6938 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 973 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.6396 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 758 | 758 | 0 | 1 |  | N |  | 2700A64/256 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 974 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.4438 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 576 | 576 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 973 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 43.7359 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1532 | 1532 | 0 | 1 |  | N |  | 2700A64/262 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 974 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.2334 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1024 | 1024 | 0 | 1 |  | N |  | 2700A64/263 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 973 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.9838 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 700 | 700 | 0 | 1 |  | N |  | 2700A64/270 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 974 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.4365 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 891 | 891 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 973 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 40.7383 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1427 | 1427 | 0 | 1 |  | N |  | 2700A64/284 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 975 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 41.1094 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1440 | 1440 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 976 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.089 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1089 | 1089 | 0 | 1 |  | N |  | 2700A64/290 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 975 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.1176 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1090 | 1090 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 976 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.3606 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 468 | 468 | 0 | 1 |  | N |  | 2700A64/294 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 975 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.4495 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 331 | 331 | 0 | 1 |  | N |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 976 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.8157 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 554 | 554 | 0 | 1 |  | N |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 975 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.2121 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 708 | 708 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 973 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.0457 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 492 | 492 | 0 | 1 |  | N |  | 2700A64/316 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 974 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.3271 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 677 | 677 | 0 | 1 |  | N |  | 2700A64/317 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 973 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.4715 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 612 | 612 | 0 | 1 |  | N |  | 2700A64/322 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE48 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 977 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 220.6146 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2454.4 | 2454.4 | 0 | 1 |  | N |  | 2700A64/257 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 977 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 132.002 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1468.56 | 1468.56 | 0 | 1 |  | N |  | 2700A64/271 | YNE48: A64 Fulford - Grimston | YNE48 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 978 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 282.2435 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3140.04 | 3140.04 | 0 | 1 |  | N |  | 2700A64/285 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 978 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 215.3005 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2395.28 | 2395.28 | 0 | 1 |  | N |  | 2700A64/291 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 978 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 63.8689 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 710.56 | 710.56 | 0 | 1 |  | N |  | 2700A64/295 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 979 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 30.5008 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 339.33 | 339.33 | 0 | 1 |  | N |  | 2700A64/310 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 978 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 92.8947 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1033.48 | 1033.48 | 0 | 1 |  | N |  | 2700A64/311 | YNE48: A64 Fulford - Grimston | YNE48 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE48 Closure Amey 45048 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 980 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE48: A64 Fulford - Grimston | YNE48 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE49 Closure 2 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 981 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.0947 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 12.21 | 12.21 | 0 | 1 |  | N |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 982 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 98.0935 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 571.8 | 571.8 | 0 | 1 |  | N |  | 2700A64/313 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE49 Closure 2 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 981 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 9.4028 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 54.81 | 54.81 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 983 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 83.4412 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 486.39 | 486.39 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 984 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 228.7133 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1333.2 | 1333.2 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 985 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5.8328 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 34 | 34 | 0 | 1 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 984 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 143.1534 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 834.46 | 834.46 | 0 | 1 |  | N |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 983 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 41.5293 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 242.08 | 242.08 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 984 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 32.9706 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 192.19 | 192.19 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 985 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 30.2 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 176.04 | 176.04 | 0 | 1 |  | N |  | 2700A64/364 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 983 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 47.9608 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 279.57 | 279.57 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 984 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 32.1832 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 187.6 | 187.6 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE49 Closure 2 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 986 | Gullies - Emptying / clear covers | 123.5175 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  | N |  | 2700A64/313 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE49 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 987 | Gullies - Emptying / clear covers | 1381.8526 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-18 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | EB | 179 | 179 | 0 | 1 |  | N |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784589
YNE49 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 988 | Gullies - Emptying / clear covers | 4323.1141 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-18 | 2023-05-02 | 2023-05-31 | 2023-11-30 |  | 21dys | WB | 560 | 560 | 0 | 1 |  | N |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45784589
YNE49 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 989 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784589
YNE49 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 987 | Gullies - Emptying / clear covers | 77.1985 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 2 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 990 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45784589
YNE49 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 988 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 989 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 991 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 988 | Gullies - Emptying / clear covers | 115.7977 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  | N |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 988 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 991 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/364 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 2 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 990 | Gullies - Emptying / clear covers | 146.6771 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | EB | 25 | 19 | 6 | 0.76 |  | N |  | 2700A64/364 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 988 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE49 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 989 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE49 Closure 2 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 992 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.5538 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 266 | 266 | 0 | 1 |  | N |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE49 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 993 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.2206 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 496 | 496 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE49 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 994 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 27.9646 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1135 | 1135 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE49 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 995 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.8527 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 684 | 684 | 0 | 1 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE49 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 994 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.6379 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 310 | 310 | 0 | 1 |  | N |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE49 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 994 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.4146 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 98 | 98 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE49 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 995 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.4799 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 263 | 263 | 0 | 1 |  | N |  | 2700A64/355 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE49 Closure Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 996 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 6 | 6 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure | Lane 1 Closure | 1 |  |  | Every 3 years
YNE49 Closure Amey 45048 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 997 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE49 Closure Amey 45048 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 998 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE49 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 999 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 101.918 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 2126 | 2126 | 0 | 1 |  | N |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1000 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1001 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1002 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1003 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1004 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/313 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1005 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 9 | 9 | 0 | 1 |  | N |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1006 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 21 | 21 | 0 | 1 |  | N |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1003 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1006 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 20 | 20 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1005 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 19 | 19 | 0 | 1 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1006 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1006 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 14 | 14 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1005 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | N |  | 2700A64/354 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1005 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | N |  | 2700A64/355 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1005 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 13 | 13 | 0 | 1 |  | N |  | 2700A64/356 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1006 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 136.6257 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 57 | 57 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1005 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  | N |  | 2700A64/364 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1006 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 32 | 32 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1007 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1008 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 59.9236 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  | N |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1008 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1007 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 143.8165 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 24 | 24 | 0 | 1 |  | N |  | 2700A64/355 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1007 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | N |  | 2700A64/356 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1008 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 239.6942 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 40 | 40 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1007 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  | N |  | 2700A64/364 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1009 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1010 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1010 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 2 | 2 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1011 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.89125 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 43.03 | 43.03 | 0 | 1 |  | N |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1012 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.1884 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 491.9 | 491.9 | 0 | 1 |  | N |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1013 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.1093 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 150.12 | 150.12 | 0 | 1 |  | N |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1011 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 23.1707 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1118.69 | 1118.69 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1013 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.9212 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 285.88 | 285.88 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1012 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.0915 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 197.54 | 197.54 | 0 | 1 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1013 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 19.6318 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 947.83 | 947.83 | 0 | 1 |  | N |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1013 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 11.9852 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 578.65 | 578.65 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1013 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 7.735 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 373.45 | 373.45 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1013 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.8757 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 187.12 | 187.12 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1014 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.1559 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 671 | 671 | 0 | 1 |  | N |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1015 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.4454 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 506 | 506 | 0 | 1 |  | N |  | 2700A64/313 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1016 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.4569 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1242 | 1242 | 0 | 1 |  | N |  | 2700A64/328 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1017 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 26.6069 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 932 | 932 | 0 | 1 |  | N |  | 2700A64/329 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1014 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 42.594 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1492 | 1492 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1017 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 46.6763 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1635 | 1635 | 0 | 1 |  | N |  | 2700A64/335 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1016 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.1812 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 812 | 812 | 0 | 1 |  | N |  | 2700A64/346 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1017 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.5523 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 825 | 825 | 0 | 1 |  | N |  | 2700A64/347 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1017 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.1893 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 462 | 462 | 0 | 1 |  | N |  | 2700A64/353 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1016 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.6811 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 199 | 199 | 0 | 1 |  | N |  | 2700A64/354 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1016 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.9087 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 242 | 242 | 0 | 1 |  | N |  | 2700A64/355 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1016 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.5938 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 266 | 266 | 0 | 1 |  | N |  | 2700A64/356 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1017 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.412 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 715 | 715 | 0 | 1 |  | N |  | 2700A64/358 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1016 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.7309 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 516 | 516 | 0 | 1 |  | N |  | 2700A64/364 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1017 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.2456 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 499 | 499 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE49 Closure 2 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1018 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 26.144 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 290.86 | 290.86 | 0 | 1 |  | N |  | 2700A64/312 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1019 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 41.9045 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 466.2 | 466.2 | 0 | 1 |  | N |  | 2700A64/313 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 2 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1018 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 252.8537 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2813.07 | 2813.07 | 0 | 1 |  | N |  | 2700A64/334 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1020 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 98.7247 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1098.34 | 1098.34 | 0 | 1 |  | N |  | 2700A64/365 | YNE49: A64 Grimston - Hopgrove | YNE49 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE49 Closure Amey 45048 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 1021 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE49: A64 Grimston - Hopgrove | YNE49 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE50 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1022 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-05-31 | 2024-02-29 |  | 21dys | EB | 54 | 0 | 54 | 0 |  | N |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1023 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-05-31 | 2024-02-29 |  | 21dys | EB | 36 | 0 | 36 | 0 |  | N |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 WB NS | Lane 2 Closure | Days |  |  | Every 2 years
YNE50 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1022 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/422 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE50 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1024 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE50 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1022 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE50 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1024 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE50 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1022 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/442 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE50 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1022 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/446 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE50 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1024 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/446 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE50 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1022 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE50 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1024 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE50 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1022 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | N |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE50 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1025 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0.49277 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 20 | 20 | 0 | 1 |  | N |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE50 Closure Amey 45048 BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 1026 | BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 44.9427 | 4.5.2 | A40037 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure | Lane 1 Closure | 1 |  |  | Annually
YNE50 Closure Amey 45048 BC - Lamps (LED) for Illuminated Signs and Bollards | 1027 | BC - Lamps (LED) for Illuminated Signs and Bollards | 14.9809 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE50 Closure Amey 45048 Electrical Testing - Network cabling and electrical components | 1028 | Electrical Testing - Network cabling and electrical components | 19.1755 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE50 Closure Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 1029 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 126dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE50 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1030 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 91.2756 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys |  | 1904 | 1904 | 0 | 1 |  | N |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1031 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1032 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 146.2135 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 61 | 61 | 0 | 1 |  | N |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1032 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/420 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1032 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 21 | 21 | 0 | 1 |  | N |  | 2700A64/422 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1032 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 30 | 30 | 0 | 1 |  | N |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1032 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 167.786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 70 | 70 | 0 | 1 |  | N |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1032 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 79.0991 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 33 | 33 | 0 | 1 |  | N |  | 2700A64/442 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1032 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  | N |  | 2700A64/446 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1032 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 26 | 26 | 0 | 1 |  | N |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1032 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 88.6869 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 37 | 37 | 0 | 1 |  | N |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1032 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 26 | 26 | 0 | 1 |  | N |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1033 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 137.8242 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 23 | 23 | 0 | 1 |  | N |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1033 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 95.8777 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  | N |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1033 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 155.8012 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 26 | 26 | 0 | 1 |  | N |  | 2700A64/442 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1034 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1034 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  | N |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1034 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | N |  | 2700A64/442 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1034 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  | N |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1035 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.1559 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 200.65 | 200.65 | 0 | 1 |  | N |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1035 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.3695 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 210.96 | 210.96 | 0 | 1 |  | N |  | 2700A64/420 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1035 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.38214 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 18.45 | 18.45 | 0 | 1 |  | N |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1035 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 82.5099 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 3983.61 | 3983.61 | 0 | 1 |  | N |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1035 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 16.7099 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 806.76 | 806.76 | 0 | 1 |  | N |  | 2700A64/446 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1035 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.2013 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 58 | 58 | 0 | 1 |  | N |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1035 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.1219 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 488.69 | 488.69 | 0 | 1 |  | N |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1035 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.42191 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 20.37 | 20.37 | 0 | 1 |  | N |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1036 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 42.9228 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1036.1641 | 1036.1641 | 0 | 1 |  | N |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1036 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 33.8698 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 817.6232 | 817.6232 | 0 | 1 |  | N |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1037 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 66.5973 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2332.8 | 2332.8 | 0 | 1 |  | N |  | 2700A64/416 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1037 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.6371 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 372.6 | 372.6 | 0 | 1 |  | N |  | 2700A64/420 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1037 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.7416 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1287 | 1287 | 0 | 1 |  | N |  | 2700A64/422 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1037 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 43.576 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1526.4 | 1526.4 | 0 | 1 |  | N |  | 2700A64/428 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1037 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 77.7482 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2723.4 | 2723.4 | 0 | 1 |  | N |  | 2700A64/436 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1037 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 42.3427 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1483.2 | 1483.2 | 0 | 1 |  | N |  | 2700A64/442 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1037 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.9822 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1015.2 | 1015.2 | 0 | 1 |  | N |  | 2700A64/446 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1037 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 53.802 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1884.6 | 1884.6 | 0 | 1 |  | N |  | 2700A64/452 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1037 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 49.948 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 1749.6 | 1749.6 | 0 | 1 |  | N |  | 2700A64/458 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE50 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1037 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 78.8274 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2761.2 | 2761.2 | 0 | 1 |  | N |  | 2700A64/464 | YNE50: A64 North Hopgrove Single | YNE50 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1038 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 177.2957 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1033.48 | 1033.48 | 0 | 1 |  |  |  | 2700A64/523 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 52029548
YNE51 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1039 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 17.9701 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 104.75 | 104.75 | 0 | 1 |  |  |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE51 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1038 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 126.0239 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 734.61 | 734.61 | 0 | 1 |  |  |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 52029548
YNE51 Closure Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1040 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 15.136 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 88.23 | 88.23 | 0 | 1 |  |  |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 2 Closure | 1 |  |  | Every 2 years
YNE51 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1041 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 66.1625 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 385.67 | 385.67 | 0 | 1 |  |  |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE51 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1041 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 178.5206 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1040.62 | 1040.62 | 0 | 1 |  |  |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE51 Closure 2 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1042 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 14.1428 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 82.44 | 82.44 | 0 | 1 |  |  |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE51 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1041 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 120.2718 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 701.08 | 701.08 | 0 | 1 |  |  |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE51 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1043 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 123.1967 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 718.13 | 718.13 | 0 | 1 |  |  |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE51 Closure 2 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1044 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45796555
YNE51 Closure 2 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1045 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 11.654 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 473 | 473 | 0 | 1 |  |  |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE51 Closure Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 1046 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 19dys |  | 3 | 3 | 0 | 1 |  |  |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE51 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1047 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 104.9861 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 2190 | 2190 | 0 | 1 |  |  |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1048 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1049 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1050 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1051 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 55.1297 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 23 | 23 | 0 | 1 |  |  |  | 2700A64/522 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1052 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 22 | 22 | 0 | 1 |  |  |  | 2700A64/523 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1052 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  |  |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1053 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 81.496 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 34 | 34 | 0 | 1 |  |  |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1054 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 24 | 24 | 0 | 1 |  |  |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1053 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 79.0991 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 33 | 33 | 0 | 1 |  |  |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1054 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 30 | 30 | 0 | 1 |  |  |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1055 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 22 | 22 | 0 | 1 |  |  |  | 2700A64/546 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1055 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 93.4807 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 39 | 39 | 0 | 1 |  |  |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1054 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 26 | 26 | 0 | 1 |  |  |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1055 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 26 | 26 | 0 | 1 |  |  |  | 2700A64/558 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1054 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 74.3052 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 31 | 31 | 0 | 1 |  |  |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1056 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.6128 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 512.39 | 512.39 | 0 | 1 |  |  |  | 2700A64/522 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1057 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 41.7733 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 2016.83 | 2016.83 | 0 | 1 |  |  |  | 2700A64/523 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1057 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 28.0104 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1352.35 | 1352.35 | 0 | 1 |  |  |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1058 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 38.0925 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1839.12 | 1839.12 | 0 | 1 |  |  |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1059 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 28.7943 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1390.2 | 1390.2 | 0 | 1 |  |  |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1058 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 42.6571 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2059.5 | 2059.5 | 0 | 1 |  |  |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1059 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 45.9976 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 2220.78 | 2220.78 | 0 | 1 |  |  |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1060 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 12.8823 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 621.96 | 621.96 | 0 | 1 |  |  |  | 2700A64/546 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1060 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 38.478 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1857.73 | 1857.73 | 0 | 1 |  |  |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1059 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 28.6624 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1383.83 | 1383.83 | 0 | 1 |  |  |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1060 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 18.8893 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 911.98 | 911.98 | 0 | 1 |  |  |  | 2700A64/558 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1059 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 37.1072 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1791.55 | 1791.55 | 0 | 1 |  |  |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB OS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1061 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 27.2575 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 658 | 658 | 0 | 1 |  |  |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE51 Closure 2 EB OS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1062 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 51.5738 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1245 | 1245 | 0 | 1 |  |  |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE51 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1063 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.3476 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1028 | 1028 | 0 | 1 |  |  |  | 2700A64/522 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1064 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.8043 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1044 | 1044 | 0 | 1 |  |  |  | 2700A64/523 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1064 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.3834 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 714 | 714 | 0 | 1 |  |  |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1065 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.4087 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 855 | 855 | 0 | 1 |  |  |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1066 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4699 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 682 | 682 | 0 | 1 |  |  |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1065 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.6029 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1107 | 1107 | 0 | 1 |  |  |  | 2700A64/536 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1066 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.9194 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1013 | 1013 | 0 | 1 |  |  |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1067 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.6199 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 372 | 372 | 0 | 1 |  |  |  | 2700A64/546 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1067 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.6061 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 967 | 967 | 0 | 1 |  |  |  | 2700A64/552 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1066 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.9821 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 770 | 770 | 0 | 1 |  |  |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1067 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.5865 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 581 | 581 | 0 | 1 |  |  |  | 2700A64/558 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1066 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.6975 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 725 | 725 | 0 | 1 |  |  |  | 2700A64/559 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE51 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1068 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 326.1813 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3628.86 | 3628.86 | 0 | 1 |  |  |  | 2700A64/522 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1069 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 65.9039 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 733.2 | 733.2 | 0 | 1 |  |  |  | 2700A64/523 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1069 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 151.4622 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1685.06 | 1685.06 | 0 | 1 |  |  |  | 2700A64/529 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1070 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 57.7441 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 642.42 | 642.42 | 0 | 1 |  |  |  | 2700A64/530 | YNE51: A64 North Hopgrove Dual | YNE51 Closure | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1071 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 346.401 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 3853.81 | 3853.81 | 0 | 1 |  |  |  | 2700A64/535 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1071 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 382.676 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 4257.38 | 4257.38 | 0 | 1 |  |  |  | 2700A64/543 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1071 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 97.7314 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1087.29 | 1087.29 | 0 | 1 |  |  |  | 2700A64/553 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE51 Closure 2 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1072 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 145.9621 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1623.87 | 1623.87 | 0 | 1 |  |  |  | 2700A64/558 | YNE51: A64 North Hopgrove Dual | YNE51 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1073 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 132.5 | 0 | 132.5 | 0 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1074 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | WB | 193.13 | 0 | 193.13 | 0 |  |  |  | 2700A64/705 | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1075 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 8 | 0 | 8 | 0 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1076 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE52 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1075 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE52 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1076 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE52 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1075 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE52 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1076 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE52 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1077 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | WB | 10 | 0 | 10 | 0 |  |  |  | 2700A64/705 | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE52 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1078 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 127 | 0 | 127 | 0 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE52 Closure Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 1079 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 19dys |  | 3 | 3 | 0 | 1 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE52 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1080 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 59.3483 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 1238 | 1238 | 0 | 1 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1081 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1082 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1083 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE52: A64 South Musley Single | YNE52 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1084 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  |  |  | 2700A64/523 | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1085 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 81.496 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 34 | 34 | 0 | 1 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1085 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 74.3052 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 31 | 31 | 0 | 1 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1085 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 32 | 32 | 0 | 1 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1085 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 30 | 30 | 0 | 1 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1085 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 129.4349 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 54 | 54 | 0 | 1 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1085 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 18 | 18 | 0 | 1 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1086 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 41.7472 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2015.57 | 2015.57 | 0 | 1 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1086 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 37.9378 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1831.65 | 1831.65 | 0 | 1 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1086 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.413 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 68.22 | 68.22 | 0 | 1 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1086 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.2816 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 496.4 | 496.4 | 0 | 1 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1086 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 8.3885 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 405 | 405 | 0 | 1 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1086 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.6156 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 78 | 78 | 0 | 1 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1087 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.3562 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 500 | 500 | 0 | 1 |  |  |  | 2700A64/705 | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE52 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1088 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 16.5285 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 399 | 399 | 0 | 1 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1088 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 32.4355 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 783 | 783 | 0 | 1 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1088 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 9.8591 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 238 | 238 | 0 | 1 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1088 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 5.8823 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 142 | 142 | 0 | 1 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1089 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.974 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 874.8 | 874.8 | 0 | 1 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1089 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 53.4423 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1872 | 1872 | 0 | 1 |  |  |  | 2700A64/622 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1089 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 52.3632 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1834.2 | 1834.2 | 0 | 1 |  |  |  | 2700A64/628 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1089 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 47.2759 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1656 | 1656 | 0 | 1 |  |  |  | 2700A64/634 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1089 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 77.851 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2727 | 2727 | 0 | 1 |  |  |  | 2700A64/640 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1089 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.943 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1224 | 1224 | 0 | 1 |  |  |  | 2700A64/704 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1090 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.3492 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 958 | 958 | 0 | 1 |  |  |  | 2700A64/705 | YNE52: A64 South Musley Single | YNE52 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE52 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1091 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 6.0709 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 67.54 | 67.54 | 0 | 1 |  |  |  | 2700A64/616 | YNE52: A64 South Musley Single | YNE52 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1092 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 69.4769 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 404.99 | 404.99 | 0 | 1 |  |  |  | 2700A64/712 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1093 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 69.1184 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 402.9 | 402.9 | 0 | 1 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1094 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 182.607 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1064.44 | 1064.44 | 0 | 1 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1092 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 12.6846 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 73.94 | 73.94 | 0 | 1 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1093 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 22.3327 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 130.18 | 130.18 | 0 | 1 |  |  |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1094 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 198.0449 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1154.43 | 1154.43 | 0 | 1 |  |  |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1092 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1.9368 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 11.29 | 11.29 | 0 | 1 |  |  |  | 2700A64/734 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1093 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 14.7192 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 85.8 | 85.8 | 0 | 1 |  |  |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1094 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 17.0386 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 99.32 | 99.32 | 0 | 1 |  |  |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1094 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 155.3319 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 905.45 | 905.45 | 0 | 1 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1094 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 42.044 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 245.08 | 245.08 | 0 | 1 |  |  |  | 2700A64/749 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1092 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3.4602 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 20.17 | 20.17 | 0 | 1 |  |  |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1094 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 116.3793 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 678.39 | 678.39 | 0 | 1 |  |  |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1092 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 39.9717 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 233 | 233 | 0 | 1 |  |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1094 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 7.6118 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 44.37 | 44.37 | 0 | 1 |  |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1095 | Gullies - Emptying / clear covers | 648.4671 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-23 | 2023-05-02 | 2023-06-30 | 2023-11-30 |  | 21dys | EB | 84 | 84 | 0 | 1 |  | N |  | 2700A64/712 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 | 45795647 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1096 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2700A64/712 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1097 | Gullies - Emptying / clear covers | 779.7045 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-23 | 2023-05-02 | 2023-06-30 | 2023-11-30 |  | 21dys | WB | 101 | 101 | 0 | 1 |  | N |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45795647
YNE53 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1098 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45795647
YNE53 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1095 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1095 | Gullies - Emptying / clear covers | 385.9923 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 50 | 50 | 0 | 1 |  |  |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1099 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE53 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1095 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/748 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1097 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 11 | 11 | 0 | 1 |  |  |  | 2700A64/749 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1095 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1096 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 | works cancelled 19/09/2023 due to Adverse weather |  |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45795647
YNE53 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1097 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1095 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1096 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 | works cancelled 19/09/2023 due to Adverse weather |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45795647
YNE53 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1097 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE53 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1098 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 21dys | WB | 1 | 0 | 1 | 0 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45795647
YNE53 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1100 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 11.4076 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 463 | 463 | 0 | 1 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1101 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.6727 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 352 | 352 | 0 | 1 |  |  |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1100 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 14.9309 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 606 | 606 | 0 | 1 |  |  |  | 2700A64/734 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1102 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.1323 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 533 | 533 | 0 | 1 |  |  |  | 2700A64/734 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1101 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 15.8178 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 642 | 642 | 0 | 1 |  |  |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1103 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.9105 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 524 | 524 | 0 | 1 |  |  |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1100 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.7541 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 680 | 680 | 0 | 1 |  |  |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1102 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 14.6106 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 593 | 593 | 0 | 1 |  |  |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1101 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.6641 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 514 | 514 | 0 | 1 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1103 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0.36958 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 15 | 15 | 0 | 1 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1102 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 9.264 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 376 | 376 | 0 | 1 |  |  |  | 2700A64/748 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1103 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.79 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 235 | 235 | 0 | 1 |  |  |  | 2700A64/749 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1100 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.9625 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 242 | 242 | 0 | 1 |  |  |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1102 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.8409 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 440 | 440 | 0 | 1 |  |  |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1101 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.5742 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 348 | 348 | 0 | 1 |  |  |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE53 Closure Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 1104 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 126dys |  | 2 | 2 | 0 | 1 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE53 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1105 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 105.6093 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 2203 | 2203 | 0 | 1 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1106 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1107 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1108 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1109 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 11 | 11 | 0 | 1 |  |  |  | 2700A64/712 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1110 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 26 | 26 | 0 | 1 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1109 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1110 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 13 | 13 | 0 | 1 |  |  |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1109 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2700A64/734 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1110 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  |  |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1109 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1110 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 11 | 11 | 0 | 1 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1109 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 13 | 13 | 0 | 1 |  |  |  | 2700A64/748 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1109 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1110 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  |  |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1109 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 15 | 15 | 0 | 1 |  |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1110 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1111 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1112 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1113 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1113 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1113 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1114 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1115 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.7226 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 83.17 | 83.17 | 0 | 1 |  |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1116 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.8504 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 137.62 | 137.62 | 0 | 1 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1117 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 31.3999 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 758 | 758 | 0 | 1 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE53 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1117 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 61.9299 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1495 | 1495 | 0 | 1 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1118 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.6616 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1039 | 1039 | 0 | 1 |  |  |  | 2700A64/712 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1119 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.204 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1058 | 1058 | 0 | 1 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1118 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.4006 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1205 | 1205 | 0 | 1 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1119 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.8011 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1184 | 1184 | 0 | 1 |  |  |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1118 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.4438 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 576 | 576 | 0 | 1 |  |  |  | 2700A64/734 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1119 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.1583 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 566 | 566 | 0 | 1 |  |  |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1118 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.0099 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 806 | 806 | 0 | 1 |  |  |  | 2700A64/742 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1119 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.1812 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 812 | 812 | 0 | 1 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1118 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.2186 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 428 | 428 | 0 | 1 |  |  |  | 2700A64/748 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1119 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.2806 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 220 | 220 | 0 | 1 |  |  |  | 2700A64/749 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1118 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.8761 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 416 | 416 | 0 | 1 |  |  |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1119 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.5286 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 614 | 614 | 0 | 1 |  |  |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1118 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.5237 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 824 | 824 | 0 | 1 |  |  |  | 2700A64/762 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 50/5 | 50/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE53 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1119 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.5865 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 581 | 581 | 0 | 1 |  |  |  | 2700A64/763 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE53 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1120 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 155.7785 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1733.08 | 1733.08 | 0 | 1 |  |  |  | 2700A64/713 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1121 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 233.576 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2598.6 | 2598.6 | 0 | 1 |  |  |  | 2700A64/724 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1120 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 46.4348 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 516.6 | 516.6 | 0 | 1 |  |  |  | 2700A64/725 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1120 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 131.3288 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1461.07 | 1461.07 | 0 | 1 |  |  |  | 2700A64/735 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1120 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 186.4222 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 2074 | 2074 | 0 | 1 |  |  |  | 2700A64/743 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1121 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 102.7614 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1143.25 | 1143.25 | 0 | 1 |  |  |  | 2700A64/748 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1121 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 56.9253 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 633.31 | 633.31 | 0 | 1 |  |  |  | 2700A64/750 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1120 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 26.7337 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 297.42 | 297.42 | 0 | 1 |  |  |  | 2700A64/751 | YNE53: A64 Musley - Pickering Int | YNE53 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE53 Closure Amey 45048 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 1122 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE53: A64 Musley - Pickering Int | YNE53 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE54 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1123 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 89.6326 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 522.48 | 522.48 | 0 | 1 |  |  |  | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1124 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 8.3031 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 48.4 | 48.4 | 0 | 1 |  |  |  | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1123 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 36.3433 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 211.85 | 211.85 | 0 | 1 |  |  |  | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1124 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 74.512 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 434.34 | 434.34 | 0 | 1 |  |  |  | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1123 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 113.468 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 661.42 | 661.42 | 0 | 1 |  |  |  | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1124 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5.4125 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 31.55 | 31.55 | 0 | 1 |  |  |  | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1123 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 64.8604 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 378.08 | 378.08 | 0 | 1 |  |  |  | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1125 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 72.9543 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 425.26 | 425.26 | 0 | 1 |  |  |  | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1125 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 7.9823 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 46.53 | 46.53 | 0 | 1 |  |  |  | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 EB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1126 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5.9048 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 34.42 | 34.42 | 0 | 1 |  |  |  | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1125 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3.7433 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 21.82 | 21.82 | 0 | 1 |  |  |  | 2700A64/788 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 EB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1126 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.412 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 14.06 | 14.06 | 0 | 1 |  |  |  | 2700A64/788 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 WB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1124 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5.1483 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 30.01 | 30.01 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1123 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 38.5255 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 224.57 | 224.57 | 0 | 1 |  |  |  | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1127 | Gullies - Emptying / clear covers | 146.6771 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-09 | 2024-1 | 2024-01-10 | 2023-05-02 | 2023-06-30 | 2023-11-30 |  | 21dys | WB | 106 | 19 | 87 | 0.17925 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for January | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 | 55/0 | 45796200 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1128 | Gullies - Emptying / clear covers | 154.3969 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-01-15 | 2024-1 | 2024-01-16 | 2023-05-02 | 2023-06-30 | 2023-11-30 |  | 21dys | EB | 84 | 20 | 64 | 0.2381 | 23/11 Cancelled due to high winds | N | 23/11 cancelled due to high winds - rebooked for December | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 55/5 | 58/3 | 45796200 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1129 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 | no assets in this closure |  |  | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45796200
YNE54 Closure 2 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1127 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/771 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1127 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1130 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 |  |  |  | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1131 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1132 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE54 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1128 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1129 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  |  |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1131 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1132 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1133 | Gullies - Emptying / clear covers | 61.7588 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 5 | 8 | -3 | 1.6 | 8 gullies emptied 2 not present captured in confirm |  |  | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45796200
YNE54 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1134 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/798 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE54 Closure 2 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1135 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.7161 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 232 | 232 | 0 | 1 |  |  |  | 2700A64/756 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1136 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 17.3208 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 703 | 703 | 0 | 1 |  |  |  | 2700A64/756 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 2 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1137 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.8987 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 280 | 280 | 0 | 1 |  |  |  | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1138 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.2726 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 214 | 214 | 0 | 1 |  |  |  | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1139 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.2566 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 51 | 51 | 0 | 1 |  |  |  | 2700A64/771 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1136 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.0466 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 286 | 286 | 0 | 1 |  |  |  | 2700A64/774 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 2 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1137 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.2292 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 334 | 334 | 0 | 1 |  |  |  | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1140 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.4467 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 424 | 424 | 0 | 1 |  |  |  | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 2 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1137 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.774 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 72 | 72 | 0 | 1 |  |  |  | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1140 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 9.5597 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 388 | 388 | 0 | 1 |  |  |  | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 2 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1136 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.1784 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 129 | 129 | 0 | 1 |  |  |  | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1138 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.525 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 670.7 | 670.7 | 0 | 1 |  |  |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1141 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.3915 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 300 | 300 | 0 | 1 |  |  |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 2 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1135 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.6117 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 106 | 106 | 0 | 1 |  |  |  | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 2 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1135 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.3685 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 502 | 502 | 0 | 1 |  |  |  | 2700A64/788 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1140 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.5206 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 427 | 427 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1138 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.0971 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 288.05 | 288.05 | 0 | 1 |  |  |  | 2700A64/790 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1141 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.9563 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 79.4 | 79.4 | 0 | 1 |  |  |  | 2700A64/790 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 2 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1140 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.3364 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 176 | 176 | 0 | 1 |  |  |  | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1138 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 33.2039 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1347.65 | 1347.65 | 0 | 1 |  |  |  | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1141 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.8854 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 117.11 | 117.11 | 0 | 1 |  |  |  | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1139 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.7372 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 435.79 | 435.79 | 0 | 1 |  |  |  | 2700A64/798 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1138 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.8682 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 157 | 157 | 0 | 1 |  |  |  | 2700A64/799 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1141 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0.88698 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 36 | 36 | 0 | 1 |  |  |  | 2700A64/799 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE54 Closure Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 1142 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 25 | 25 | 0 | 1 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure | Lane 1 Closure | 1 |  |  | Every 3 years
YNE54 Closure Amey 45048 Electrical Testing - Network cabling and electrical components | 1143 | Electrical Testing - Network cabling and electrical components | 517.7395 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 27 | 27 | 0 | 1 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE54 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1144 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 74.0655 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 1545 | 1545 | 0 | 1 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1145 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1146 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1147 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1148 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 5 | 5 | 0 | 1 |  |  |  | 2700A64/756 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1150 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1151 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  |  |  | 2700A64/771 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1148 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2700A64/774 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 10 | 10 | 0 | 1 |  |  |  | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  |  |  | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 8 | 8 | 0 | 1 |  |  |  | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1148 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  |  |  | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1150 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  |  |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1148 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 2 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1148 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 13 | 13 | 0 | 1 |  |  |  | 2700A64/788 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 7 | 7 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1150 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 7 | 7 | 0 | 1 |  |  |  | 2700A64/790 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  |  |  | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1150 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 12 | 12 | 0 | 1 |  |  |  | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1151 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/798 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1150 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  |  |  | 2700A64/799 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1152 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1152 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1152 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 6 | 6 | 0 | 1 |  |  |  | 2700A64/790 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1152 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 4 | 4 | 0 | 1 |  |  |  | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1152 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 6 | 6 | 0 | 1 |  |  |  | 2700A64/799 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1153 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1154 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/771 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1155 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/788 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1156 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1153 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1157 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.92936 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 44.87 | 44.87 | 0 | 1 |  |  |  | 2700A64/774 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1157 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.1156 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 53.86 | 53.86 | 0 | 1 |  |  |  | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1158 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.01802 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 0.87 | 0.87 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1158 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.1184 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 247.12 | 247.12 | 0 | 1 |  |  |  | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1159 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.2146 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 603 | 603 | 0 | 1 |  |  |  | 2700A64/756 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1160 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.903 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 487 | 487 | 0 | 1 |  |  |  | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1161 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.4308 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1136 | 1136 | 0 | 1 |  |  |  | 2700A64/770 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1162 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 26.8353 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 940 | 940 | 0 | 1 |  |  |  | 2700A64/771 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1159 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.3663 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 223 | 223 | 0 | 1 |  |  |  | 2700A64/774 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1160 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.478 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 332 | 332 | 0 | 1 |  |  |  | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1160 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.1868 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 567 | 567 | 0 | 1 |  |  |  | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1160 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.4478 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 401 | 401 | 0 | 1 |  |  |  | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1159 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5873 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 546 | 546 | 0 | 1 |  |  |  | 2700A64/785 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1161 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 26.4071 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 925 | 925 | 0 | 1 |  |  |  | 2700A64/786 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1159 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.3899 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 434 | 434 | 0 | 1 |  |  |  | 2700A64/787 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 2 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1159 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.6738 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 514 | 514 | 0 | 1 |  |  |  | 2700A64/788 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1160 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.3336 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 397 | 397 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1161 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.4804 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 227 | 227 | 0 | 1 |  |  |  | 2700A64/790 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1160 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.6232 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 232 | 232 | 0 | 1 |  |  |  | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 58/3 | 55/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1161 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.7953 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 203 | 203 | 0 | 1 |  |  |  | 2700A64/797 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1162 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.6975 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 725 | 725 | 0 | 1 |  |  |  | 2700A64/798 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE54 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1161 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.8222 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 274 | 274 | 0 | 1 |  |  |  | 2700A64/799 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 55/5 | 58/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE54 Closure 2 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1163 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 107.022 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1190.65 | 1190.65 | 0 | 1 |  |  |  | 2700A64/756 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1164 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 28.3723 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 315.65 | 315.65 | 0 | 1 |  |  |  | 2700A64/757 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1163 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 12.2693 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 136.5 | 136.5 | 0 | 1 |  |  |  | 2700A64/774 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1164 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 18.2917 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 203.5 | 203.5 | 0 | 1 |  |  |  | 2700A64/775 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1164 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 38.9653 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 433.5 | 433.5 | 0 | 1 |  |  |  | 2700A64/777 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1164 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 70.8926 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 788.7 | 788.7 | 0 | 1 |  |  |  | 2700A64/779 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1164 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 78.0636 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 868.48 | 868.48 | 0 | 1 |  |  |  | 2700A64/789 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE54 Closure 2 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1164 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 21.0386 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 234.06 | 234.06 | 0 | 1 |  |  |  | 2700A64/795 | YNE54: A64 Pickering Int - Brambling | YNE54 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1165 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 2 | 0 | 2 | 0 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1166 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE55 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1167 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | WB | 7 | 0 | 7 | 0 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE55 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1168 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE55 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1169 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE55 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1170 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE55 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1169 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE55 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1171 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 503.8 | 0 | 503.8 | 0 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE55 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1172 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 293 | 0 | 293 | 0 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE55 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1173 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 985.65 | 0 | 985.65 | 0 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE55 Closure 1 WB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1174 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 323.01 | 0 | 323.01 | 0 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE55 Closure Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 1175 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 4 | 4 | 0 | 1 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure | Lane 1 Closure | 1 |  |  | Every 3 years
YNE55 Closure Amey 45048 Electrical Testing - Network cabling and electrical components | 1176 | Electrical Testing - Network cabling and electrical components | 76.7022 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 4 | 4 | 0 | 1 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE55 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1177 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 43.9599 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 917 | 917 | 0 | 1 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1178 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1179 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1180 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1181 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1181 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/794 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1182 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1181 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 19 | 19 | 0 | 1 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1181 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 25 | 25 | 0 | 1 |  |  |  | 2700A64/806 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1181 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 153.4043 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 64 | 64 | 0 | 1 |  |  |  | 2700A64/810 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1181 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 20 | 20 | 0 | 1 |  |  |  | 2700A64/813 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1181 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 112.6563 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 47 | 47 | 0 | 1 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1183 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1184 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1185 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1185 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1185 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1186 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.478 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 167.92 | 167.92 | 0 | 1 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1187 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 14.3046 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 690.63 | 690.63 | 0 | 1 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1187 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 20.5222 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 990.82 | 990.82 | 0 | 1 |  |  |  | 2700A64/806 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1187 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 42.7878 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2065.81 | 2065.81 | 0 | 1 |  |  |  | 2700A64/810 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1187 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 24.9984 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1206.93 | 1206.93 | 0 | 1 |  |  |  | 2700A64/813 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1187 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 48.1394 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2324.19 | 2324.19 | 0 | 1 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE55 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1188 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 63.7526 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1539 | 1539 | 0 | 1 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1188 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 86.1634 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2080 | 2080 | 0 | 1 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1189 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.4365 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 891 | 891 | 0 | 1 |  |  |  | 2700A64/791 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1189 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.5979 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 91 | 91 | 0 | 1 |  |  |  | 2700A64/794 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1190 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.2937 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 886 | 886 | 0 | 1 |  |  |  | 2700A64/796 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1189 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 49.5312 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1735 | 1735 | 0 | 1 |  |  |  | 2700A64/804 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1189 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.4887 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1103 | 1103 | 0 | 1 |  |  |  | 2700A64/806 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1189 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.8558 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1291 | 1291 | 0 | 1 |  |  |  | 2700A64/810 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1189 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.4087 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 855 | 855 | 0 | 1 |  |  |  | 2700A64/813 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE55 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1189 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 37.4553 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1312 | 1312 | 0 | 1 |  |  |  | 2700A64/815 | YNE55: A64 Brambling - Rillington | YNE55 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1191 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 16.02 | 0 | 16.02 | 0 |  | Y |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1192 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 380 | 0 | 380 | 0 |  | Y |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1193 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1192 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/822 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1193 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/822 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1192 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1193 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1192 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1193 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1194 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1195 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1194 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1195 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1192 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1193 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1192 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1193 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1192 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1193 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1192 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1193 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1192 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1193 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1194 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1195 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1195 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/864 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1194 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/864 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE56 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1195 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE56 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1194 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE56 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1196 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 373 | 0 | 373 | 0 |  | Y |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE56 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1197 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 193 | 0 | 193 | 0 |  | Y |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE56 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1196 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 60 | 0 | 60 | 0 |  | Y |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE56 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1196 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 65 | 0 | 65 | 0 |  | Y |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE56 Closure 1 EB NS Enviroflow 45048 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 1198 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 93 | 0 | 93 | 0 |  | Y |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45931265
YNE56 Closure 1 EB OS Enviroflow 45048 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 1199 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 82 | 0 | 82 | 0 |  | Y |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45931265
YNE56 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1200 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 186.46 | 0 | 186.46 | 0 |  | Y |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1200 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1531.22 | 0 | 1531.22 | 0 |  | Y |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1201 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 778.4 | 0 | 778.4 | 0 |  | Y |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1200 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 3058.2 | 0 | 3058.2 | 0 |  | Y |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1201 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2962.98 | 0 | 2962.98 | 0 |  | Y |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1200 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1898.82 | 0 | 1898.82 | 0 |  | Y |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1201 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1843.26 | 0 | 1843.26 | 0 |  | Y |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1201 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 538.1 | 0 | 538.1 | 0 |  | Y |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1200 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1799.4 | 0 | 1799.4 | 0 |  | Y |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1201 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2093.24 | 0 | 2093.24 | 0 |  | Y |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1200 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 954.48 | 0 | 954.48 | 0 |  | Y |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1201 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 253.02 | 0 | 253.02 | 0 |  | Y |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1200 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 5064.4 | 0 | 5064.4 | 0 |  | Y |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1201 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 5423.6 | 0 | 5423.6 | 0 |  | Y |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE56 Closure Amey 45048 BC - Lamps (LED) for Illuminated Signs and Bollards | 1202 | BC - Lamps (LED) for Illuminated Signs and Bollards | 14.9809 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE56 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1203 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 111.2661 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2321 | 2321 | 0 | 1 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1204 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1205 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1204 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 112.6563 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 47 | 47 | 0 | 1 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 93.4807 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 39 | 39 | 0 | 1 |  |  |  | 2700A64/822 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 91.0838 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 38 | 38 | 0 | 1 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 88.6869 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 37 | 37 | 0 | 1 |  |  |  | 2700A64/826 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  |  |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 25 | 25 | 0 | 1 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 95.8777 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 40 | 40 | 0 | 1 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 30 | 30 | 0 | 1 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 22 | 22 | 0 | 1 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 81.496 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 34 | 34 | 0 | 1 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 26 | 26 | 0 | 1 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 15 | 15 | 0 | 1 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  |  |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  |  |  | 2700A64/864 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1206 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 119.8471 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 50 | 50 | 0 | 1 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1207 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 119.8471 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 20 | 20 | 0 | 1 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1207 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 12 | 12 | 0 | 1 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1207 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 83.893 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 41.3402 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1995.92 | 1995.92 | 0 | 1 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 18.2436 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 880.81 | 880.81 | 0 | 1 |  |  |  | 2700A64/822 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 23.3668 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1128.16 | 1128.16 | 0 | 1 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.1938 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 154.2 | 154.2 | 0 | 1 |  |  |  | 2700A64/826 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 24.0823 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1162.7 | 1162.7 | 0 | 1 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 45.2894 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2186.59 | 2186.59 | 0 | 1 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 27.0754 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1307.21 | 1307.21 | 0 | 1 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 11.1702 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 539.3 | 539.3 | 0 | 1 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 11.7217 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 565.93 | 565.93 | 0 | 1 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 12.0446 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 581.52 | 581.52 | 0 | 1 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 18.0162 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 869.83 | 869.83 | 0 | 1 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 29.7313 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1435.44 | 1435.44 | 0 | 1 |  |  |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 20.2896 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 979.59 | 979.59 | 0 | 1 |  |  |  | 2700A64/864 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 44.7946 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2162.7 | 2162.7 | 0 | 1 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 49.9582 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1206 | 1206 | 0 | 1 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 16.5699 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 400 | 400 | 0 | 1 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 41.3419 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 998 | 998 | 0 | 1 |  |  |  | 2700A64/826 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 302.4832 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 7302 | 7302 | 0 | 1 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 55.6748 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1344 | 1344 | 0 | 1 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 15.5757 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 376 | 376 | 0 | 1 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 18.2269 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 440 | 440 | 0 | 1 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 346.9319 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 8375 | 8375 | 0 | 1 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 138.9385 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3354 | 3354 | 0 | 1 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 57.4146 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1386 | 1386 | 0 | 1 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 31.9799 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 772 | 772 | 0 | 1 |  |  |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1210 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 98.9636 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2389 | 2389 | 0 | 1 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 29.4903 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1033 | 1033 | 0 | 1 |  |  |  | 2700A64/818 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.7432 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1217 | 1217 | 0 | 1 |  |  |  | 2700A64/822 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 61.1503 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2142 | 2142 | 0 | 1 |  |  |  | 2700A64/824 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.1664 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 216 | 216 | 0 | 1 |  |  |  | 2700A64/826 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4128 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 680 | 680 | 0 | 1 |  |  |  | 2700A64/830 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 40.5385 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1420 | 1420 | 0 | 1 |  |  |  | 2700A64/832 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 79.7637 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2794 | 2794 | 0 | 1 |  |  |  | 2700A64/838 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 48.4463 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1697 | 1697 | 0 | 1 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.2407 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 709 | 709 | 0 | 1 |  |  |  | 2700A64/846 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 61.0361 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2138 | 2138 | 0 | 1 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.5507 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 895 | 895 | 0 | 1 |  |  |  | 2700A64/852 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.1208 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 950 | 950 | 0 | 1 |  |  |  | 2700A64/856 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 64.6332 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2264 | 2264 | 0 | 1 |  |  |  | 2700A64/860 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 41.9944 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1471 | 1471 | 0 | 1 |  |  |  | 2700A64/864 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.9708 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1260 | 1260 | 0 | 1 |  |  |  | 2700A64/868 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE56 Closure 1 EB NS CGS 45048 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 1212 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 50.0731 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 906.58 | 906.58 | 0 | 1 |  |  |  | 2700A64/844 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS CGS 45048 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 1212 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 666.3827 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 12064.95 | 12064.95 | 0 | 1 |  |  |  | 2700A64/850 | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE56 Closure 1 EB NS Amey 45048 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 1213 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 6 years
YNE56 Closure 1 EB NS Amey 45048 BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 1214 | BCC - UNSWITCHED Lamps (PL-L, PL-S, SOX) | 0 | 4.5.2 | A40037 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB |  |  | 0 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE56 Closure 1 EB NS Amey 45048 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 1215 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE56: A64 Rillington - Sherburn | YNE56 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 6 years
YNE57 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1216 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 46.3191 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 6 | 6 | 0 | 1 |  | Y | Only 6 gullies in this closure | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE57 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1218 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1219 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE57 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1218 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1219 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE57 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1216 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE57 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1218 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1219 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE57 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1216 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/889 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/889 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE57 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1216 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE57 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1218 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1219 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE57 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1216 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE57 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1216 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE57 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1220 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 936.31 | 0 | 936.31 | 0 |  | Y |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE58 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1221 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 2723.2 | 0 | 2723.2 | 0 |  | Y |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1220 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 714.4 | 0 | 714.4 | 0 |  | Y |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1220 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 1065.6 | 0 | 1065.6 | 0 |  | Y |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1220 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 309.96 | 0 | 309.96 | 0 |  | Y |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1220 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 367.84 | 0 | 367.84 | 0 |  | Y |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE58 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1221 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 863.36 | 0 | 863.36 | 0 |  | Y |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure 1 EB NS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1220 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 279.94 | 0 | 279.94 | 0 |  | Y |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE58 Closure 1 EB OS Amey 45048 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1221 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | EB | 91.57 | 0 | 91.57 | 0 |  | Y |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE57 Closure Amey 45048 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1222 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE57 Closure Amey 45048 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1223 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE57 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1224 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 72.3877 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 1510 | 1510 | 0 | 1 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1225 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1226 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1227 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 117.4502 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 49 | 49 | 0 | 1 |  |  |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1229 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 12 | 12 | 0 | 1 |  |  |  | 2700A64/878 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 24 | 24 | 0 | 1 |  |  |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 17 | 17 | 0 | 1 |  |  |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 30 | 30 | 0 | 1 |  |  |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  |  |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 21 | 21 | 0 | 1 |  |  |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 13 | 13 | 0 | 1 |  |  |  | 2700A64/889 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 110.2593 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 46 | 46 | 0 | 1 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 151.0074 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 63 | 63 | 0 | 1 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 14 | 14 | 0 | 1 |  |  |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 74.3052 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 31 | 31 | 0 | 1 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1228 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 14 | 14 | 0 | 1 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1230 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 77.9006 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 13 | 13 | 0 | 1 |  |  |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1230 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 8 | 8 | 0 | 1 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1230 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 95.8777 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 16 | 16 | 0 | 1 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1230 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1231 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 6 | 6 | 0 | 1 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1232 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1232 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1232 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1232 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 51.9228 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2506.85 | 2506.85 | 0 | 1 |  |  |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1234 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.99544 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 48.06 | 48.06 | 0 | 1 |  |  |  | 2700A64/878 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.7504 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 132.79 | 132.79 | 0 | 1 |  |  |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 13.3294 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 643.55 | 643.55 | 0 | 1 |  |  |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 15.6523 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 755.7 | 755.7 | 0 | 1 |  |  |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 14.9713 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 722.82 | 722.82 | 0 | 1 |  |  |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 33.8697 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1635.24 | 1635.24 | 0 | 1 |  |  |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.8481 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 523.75 | 523.75 | 0 | 1 |  |  |  | 2700A64/889 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 7.8688 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 379.91 | 379.91 | 0 | 1 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.7775 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 134.1 | 134.1 | 0 | 1 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.8434 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 89 | 89 | 0 | 1 |  |  |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 19.5632 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 944.52 | 944.52 | 0 | 1 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1233 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.6628 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 32 | 32 | 0 | 1 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1235 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 91.8386 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 2217 | 2217 | 0 | 1 |  |  |  | 2700A64/878 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1236 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 48.674 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 1175 | 1175 | 0 | 1 |  |  |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1236 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 33.6783 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 813 | 813 | 0 | 1 |  |  |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1236 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 110.4383 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2666 | 2666 | 0 | 1 |  |  |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1236 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 62.6342 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1512 | 1512 | 0 | 1 |  |  |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1236 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 15.2443 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 368 | 368 | 0 | 1 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1236 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 21.0438 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 508 | 508 | 0 | 1 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1236 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 30.1572 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 728 | 728 | 0 | 1 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 93.7295 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3283.2 | 3283.2 | 0 | 1 |  |  |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1238 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.2496 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 324 | 324 | 0 | 1 |  |  |  | 2700A64/878 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.08 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | NB | 248 | 248 | 0 | 1 |  |  |  | 2700A64/879 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 53.1853 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1863 | 1863 | 0 | 1 |  |  |  | 2700A64/880 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.4846 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1278 | 1278 | 0 | 1 |  |  |  | 2700A64/884 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.3223 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1132.2 | 1132.2 | 0 | 1 |  |  |  | 2700A64/886 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 63.9766 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2241 | 2241 | 0 | 1 |  |  |  | 2700A64/888 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.0563 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 527.4 | 527.4 | 0 | 1 |  |  |  | 2700A64/889 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.7717 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 482.4 | 482.4 | 0 | 1 |  |  |  | 2700A64/890 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.9258 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 487.8 | 487.8 | 0 | 1 |  |  |  | 2700A64/891 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.0963 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 774 | 774 | 0 | 1 |  |  |  | 2700A64/893 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.0882 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 633.6 | 633.6 | 0 | 1 |  |  |  | 2700A64/894 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1237 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.8785 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 311 | 311 | 0 | 1 |  |  |  | 2700A64/896 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE57 Closure 1 EB NS CGS 45048 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 1239 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 43.9102 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 795 | 795 | 0 | 1 |  |  |  | 2700A64/874 | YNE57: A64 Sherburn - Staxton | YNE57 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE57 Closure Amey 45048 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 1240 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE57: A64 Sherburn - Staxton | YNE57 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE58 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1241 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 13 | 0 | 13 | 0 |  | Y |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1241 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1241 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1242 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | WB | 248 | 0 | 248 | 0 |  | Y |  | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE58 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1241 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/934 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1217 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/934 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE58 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1243 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 82 | 0 | 82 | 0 |  | Y |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE58 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1243 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 86 | 0 | 86 | 0 |  | Y |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE58 Closure 1 WB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1244 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | WB | 81 | 0 | 81 | 0 |  | Y |  | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE58 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1243 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | CW | 85 | 0 | 85 | 0 |  | Y |  | 2700A64/934 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE58 Closure 1 EB NS Amey 45048 BC - Lamps (LED) for Illuminated Signs and Bollards | 1245 | BC - Lamps (LED) for Illuminated Signs and Bollards | 119.8471 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 8 | 8 | 0 | 1 |  | Y |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE58 Closure Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 1246 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 19dys |  | 1 | 1 | 0 | 1 |  | Y |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE58 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1247 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 26.6061 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 555 | 555 | 0 | 1 |  | Y |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1248 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1249 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1250 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 14 | 14 | 0 | 1 |  | Y |  | 2700A64/874 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 88.6869 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 37 | 37 | 0 | 1 |  | Y |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 127.0379 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 53 | 53 | 0 | 1 |  | Y |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1252 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | SB | 20 | 20 | 0 | 1 |  | Y |  | 2700A64/920 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 15 | 15 | 0 | 1 |  | Y |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1251 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 13 | 13 | 0 | 1 |  | Y |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1252 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 9 | 9 | 0 | 1 |  | Y |  | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1253 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | Y |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1253 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 4 | 4 | 0 | 1 |  | Y |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1253 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 101.87 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 17 | 17 | 0 | 1 |  | Y |  | 2700A64/934 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1254 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 26.1266 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1261.4 | 1261.4 | 0 | 1 |  | Y |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1254 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 47.6094 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2298.6 | 2298.6 | 0 | 1 |  | Y |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1254 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 7.5186 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 363 | 363 | 0 | 1 |  | Y |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1254 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 9.4339 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 455.47 | 455.47 | 0 | 1 |  | Y |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1255 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 9.6814 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 467.42 | 467.42 | 0 | 1 |  | Y |  | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1254 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.193 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 57.6 | 57.6 | 0 | 1 |  | Y |  | 2700A64/934 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1256 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 125.7654 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3036 | 3036 | 0 | 1 |  | Y |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1257 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.7766 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1008 | 1008 | 0 | 1 |  | Y |  | 2700A64/910 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1257 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 60.4937 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2119 | 2119 | 0 | 1 |  | Y |  | 2700A64/916 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1258 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.5653 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | SB | 265 | 265 | 0 | 1 |  | Y |  | 2700A64/920 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1257 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.0718 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 598 | 598 | 0 | 1 |  | Y |  | 2700A64/924 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1257 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.053 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 177 | 177 | 0 | 1 |  | Y |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1258 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.3671 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 188 | 188 | 0 | 1 |  | Y |  | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1257 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.8222 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 274 | 274 | 0 | 1 |  | Y |  | 2700A64/934 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE58 Closure 1 EB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1259 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 64.5071 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 717.66 | 717.66 | 0 | 1 |  | Y |  | 2700A64/930 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1260 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 58.7149 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 653.22 | 653.22 | 0 | 1 |  | Y |  | 2700A64/931 | YNE58: A64 Staxton - Seamer | YNE58 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE58 Closure Amey 45048 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 1261 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE58: A64 Staxton - Seamer | YNE58 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE59 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1262 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 768.15 | 0 | 768.15 | 0 |  | Y |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1262 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 777.27 | 0 | 777.27 | 0 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1263 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Single carriageway no offside assets | 21dys | EB | 81.54 | 0 | 81.54 | 0 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE59 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1264 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 90 | 0 | 90 | 0 |  | Y |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE59 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1265 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE59 Closure 1 WB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1266 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE59 Closure 1 WB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1267 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | WB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE59 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1264 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE59 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1265 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE59 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1264 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE59 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1265 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE59 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1264 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE59 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1268 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 364 | 0 | 364 | 0 |  | Y |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE59 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1269 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 301 | 0 | 301 | 0 |  | Y |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE59 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1269 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 734 | 0 | 734 | 0 |  | Y |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE59 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1268 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 404 | 0 | 404 | 0 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE59 Closure 1 EB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1269 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | EB | 640 | 0 | 640 | 0 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE59 Closure 1 EB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1268 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to complete within ADAMr timescales due to access | 21dys | CW | 69 | 0 | 69 | 0 |  | Y |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE59 Closure 1 EB NS Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 1270 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  | 0 |  | 0 | 0 |  | Y |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 3 years
YNE59 Closure 1 EB NS Amey 45048 BC - Lamps (LED) for Illuminated Signs and Bollards | 1271 | BC - Lamps (LED) for Illuminated Signs and Bollards | 89.8853 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 6 | 6 | 0 | 1 |  | Y |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE59 Closure 1 EB NS Amey 45048 Electrical Testing - Network cabling and electrical components | 1272 | Electrical Testing - Network cabling and electrical components | 19.1755 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | Y |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 6 years
YNE59 Closure Amey 45048 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 1273 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 19dys |  | 2 | 2 | 0 | 1 |  | Y |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE59 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1274 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 25.839 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 539 | 539 | 0 | 1 |  | Y |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1275 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1276 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1277 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1278 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 26 | 26 | 0 | 1 |  | Y |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1279 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 16 | 16 | 0 | 1 |  | Y |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1278 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 20 | 20 | 0 | 1 |  | Y |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1278 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 32 | 32 | 0 | 1 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1278 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 25 | 25 | 0 | 1 |  | Y |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1280 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 41.9465 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 7 | 7 | 0 | 1 |  | Y |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1280 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1280 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 12 | 12 | 0 | 1 |  | Y |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1281 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 2 | 2 | 0 | 1 |  | Y |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1282 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 1 | 1 | 0 | 1 |  | Y |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1283 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.72493 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 35 | 35 | 0 | 1 |  | Y |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1284 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 19.2702 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 930.37 | 930.37 | 0 | 1 |  | Y |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1283 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 41.3522 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1996.5 | 1996.5 | 0 | 1 |  | Y |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1283 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 54.5804 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2635.16 | 2635.16 | 0 | 1 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1283 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.91134 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 44 | 44 | 0 | 1 |  | Y |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE59 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1285 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 19.5939 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 473 | 473 | 0 | 1 |  | Y |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1285 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 27.5474 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 665 | 665 | 0 | 1 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1285 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 83.098 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 2006 | 2006 | 0 | 1 |  | Y |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1286 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.6216 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 302 | 302 | 0 | 1 |  | Y |  | 2700A64/936 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1287 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.6216 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 302 | 302 | 0 | 1 |  | Y |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1286 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 41.9944 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1471 | 1471 | 0 | 1 |  | Y |  | 2700A64/938 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1286 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 53.6992 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1881 | 1881 | 0 | 1 |  | Y |  | 2700A64/946 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1286 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 8.2219 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 288 | 288 | 0 | 1 |  | Y |  | 2700A64/954 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE59 Closure 1 WB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1288 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 197.0646 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 2192.4 | 2192.4 | 0 | 1 |  | Y |  | 2700A64/937 | YNE59: A64 Seamer - Dunslow | YNE59 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB NS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1289 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 293.8 | 0 | 293.8 | 0 |  | Y |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE60 Closure 1 EB OS Bettamix 45048 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1290 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Single carriageway no offside assets | 21dys | EB | 251.47 | 0 | 251.47 | 0 |  | Y |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE60 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1291 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2024-02-01 | 2024-2 | 2024-02-29 | 2023-05-02 | 2023-06-30 | 2024-02-29 |  | 21dys | EB | 61 | 0 | 61 | 0 |  | Y |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | Days |  |  | Every 2 years
YNE60 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1292 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | EB | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE60 Closure 1 EB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1291 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE60 Closure 1 EB OS Enviroflow 45048 Gullies - Emptying / clear covers | 1292 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys | CW | 0 | 0 | 0 | 0 |  | Y |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE60 Closure Amey 45048 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 1293 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 22.4713 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE60 Closure Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 1294 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 40 | 40 | 0 | 1 |  | N |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure | Lane 1 Closure | 1 |  |  | Every 3 years
YNE60 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1295 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 14.4296 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys |  | 301 | 301 | 0 | 1 |  | Y |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1296 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1297 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1298 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1299 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | Y |  | 2700A64/956 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1300 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 1 | 1 | 0 | 1 |  | Y |  | 2700A64/957 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1299 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 55.1297 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 23 | 23 | 0 | 1 |  | Y |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1299 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 83.893 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 35 | 35 | 0 | 1 |  | Y |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure 1 WB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1301 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 3 | 3 | 0 | 1 |  | Y |  | 2700A64/957 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1302 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 17.9771 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 3 | 3 | 0 | 1 |  | Y |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1302 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 89.8853 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 15 | 15 | 0 | 1 |  | Y |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1303 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 1 | 1 | 0 | 1 |  | Y |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1303 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 3 | 3 | 0 | 1 |  | Y |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1304 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.67605 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 32.64 | 32.64 | 0 | 1 |  | Y |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1304 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.6052 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 318.9 | 318.9 | 0 | 1 |  | Y |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE60 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1305 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 5.0538 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 122 | 122 | 0 | 1 |  | Y |  | 2700A64/957 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1306 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 202.6497 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 4892 | 4892 | 0 | 1 |  | Y |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1306 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 14.6643 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 354 | 354 | 0 | 1 |  | Y |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1307 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.0848 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 38 | 38 | 0 | 1 |  | Y |  | 2700A64/956 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure 1 WB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1308 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1.0277 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | WB | 36 | 36 | 0 | 1 |  | Y |  | 2700A64/957 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1307 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 58.5239 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | EB | 2050 | 2050 | 0 | 1 |  | Y |  | 2700A64/964 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure 1 EB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1307 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.5881 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 21dys | CW | 511 | 511 | 0 | 1 |  | Y |  | 2700A64/974 | YNE60: A64 Dunslow - Musham | YNE60 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE60 Closure Amey 45048 Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 1309 | Structural Testing - Lighting columns (<20m in height) Structural testing from 15 years old | 0 | 4.5.10 | A40045 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 21dys |  |  |  | 0 | 0 |  |  |  |  | YNE60: A64 Dunslow - Musham | YNE60 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE76 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1310 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 404.7546 | 0 | 404.7546 | 0 |  | N |  | 1000A628/105 | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE78 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1311 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 112.896 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | EB | 2355 | 2355 | 0 | 1 |  | Y |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1312 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1313 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | EB |  |  | 0 | 0 | There are no assets on the OS on this route, it is single carriageway route. |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB OS | Lane 2 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1314 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | WB |  |  | 0 | 0 | There are no assets on the OS on this route, it is single carriageway route. |  |  |  | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB OS | Lane 2 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1315 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  | Y |  | 4405A616/66 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1315 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  | Y |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1315 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  | Y |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1315 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  | Y |  | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.873 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 90.43 | 90.43 | 0 | 1 |  | Y |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.45588 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 22.01 | 22.01 | 0 | 1 |  | Y |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1317 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.6267 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | EB | 223.38 | 223.38 | 0 | 1 |  | Y |  | 4405A616/60 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.46499 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 22.45 | 22.45 | 0 | 1 |  | Y |  | 4405A616/62 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1317 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 4.9045 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | EB | 236.79 | 236.79 | 0 | 1 |  | Y |  | 4405A616/64 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 9.8556 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 475.83 | 475.83 | 0 | 1 |  | Y |  | 4405A616/68 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 7.1072 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 343.14 | 343.14 | 0 | 1 |  | Y |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 58.0646 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 2803.38 | 2803.38 | 0 | 1 |  | Y |  | 4405A616/75 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 27.7258 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 1338.61 | 1338.61 | 0 | 1 |  | Y |  | 4405A616/77 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.414 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 116.55 | 116.55 | 0 | 1 |  | Y |  | 4405A616/79 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.1667 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 249.45 | 249.45 | 0 | 1 |  | Y |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.39561 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 19.1 | 19.1 | 0 | 1 |  | Y |  | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 12.451 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 601.14 | 601.14 | 0 | 1 |  | Y |  | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1316 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.4678 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 312.27 | 312.27 | 0 | 1 |  | Y |  | 4405A616/89 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1317 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.1174 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 150.51 | 150.51 | 0 | 1 |  | Y |  | 4405A616/90 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1317 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.4163 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | EB | 164.94 | 164.94 | 0 | 1 |  | Y |  | 4405A616/92 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1318 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 22.3329 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | EB | 539.12 | 539.12 | 0 | 1 |  | Y |  | 4405A616/42 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 28.0077 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 676.11 | 676.11 | 0 | 1 |  | Y |  | 4405A616/46 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 10.3164 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 249.04 | 249.04 | 0 | 1 |  | Y |  | 4405A616/50 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 55.348 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 1336.11 | 1336.11 | 0 | 1 |  | Y |  | 4405A616/51 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1318 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 2.0348 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 49.12 | 49.12 | 0 | 1 |  | Y |  | 4405A616/53 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 63.024 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 1521.41 | 1521.41 | 0 | 1 |  | Y |  | 4405A616/55 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 12.4606 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 300.8 | 300.8 | 0 | 1 |  | Y |  | 4405A616/73 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 10.6507 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 257.11 | 257.11 | 0 | 1 |  | Y |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 27.5984 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 666.23 | 666.23 | 0 | 1 |  | Y |  | 4405A616/83 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1319 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 3.3629 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 81.18 | 81.18 | 0 | 1 |  | Y |  | 4405A616/85 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE78 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1320 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1.7951 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 26 | 26 | 0 | 1 |  | Y |  | 4405A616/81 | YNE78: A616 Flouch - Deepcar | YNE78 Closure 1 WB NS | Lane 1 Closure | 1 | Yes |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE79 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1321 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 582 | 0 | 582 | 0 |  | Y |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1322 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1323 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1324 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1325 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete | Unable to access due to schemes - intervention missed | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1326 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete | Unable to access due to schemes - intervention missed | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4405A616/36 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1327 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.46002 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 22.21 | 22.21 | 0 | 1 |  |  |  | 4405A616/30 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1327 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.5399 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | WB | 170.91 | 170.91 | 0 | 1 |  |  |  | 4405A616/32 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1328 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.5789 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | EB | 124.51 | 124.51 | 0 | 1 |  |  |  | 4405A616/34 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1329 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | EB | 943.13 | 0 | 943.13 | 0 |  | Y |  | 4405A616/38 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE79 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1330 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 663.33 | 0 | 663.33 | 0 |  | Y |  | 4405A616/44 | YNE79: A616 Deepcar - Wortley | YNE79 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1331 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 753 | 0 | 753 | 0 |  | Y |  |  | YNE80: A616 Wortley - Westwood | YNE80 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1332 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1333 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1334 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1335 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4405A616/111 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1336 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 9 | 0 | 9 | 0 |  | Y |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1336 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1336 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 2 | 0 | 2 | 0 |  | Y |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1336 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1336 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 2 | 0 | 2 | 0 |  | Y |  | 4405A616/29 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1337 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | CW | 99.23 | 0 | 99.23 | 0 |  | Y |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1338 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 46.12 | 0 | 46.12 | 0 |  | Y |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1338 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 219.2 | 0 | 219.2 | 0 |  | Y |  | 4405A616/18 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1337 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | EB | 157.31 | 0 | 157.31 | 0 |  | Y |  | 4405A616/20 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1338 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 36.12 | 0 | 36.12 | 0 |  | Y |  | 4405A616/24 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1339 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | CW | 303.37 | 0 | 303.37 | 0 |  | Y |  | 4405A616/14 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1340 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 233 | 0 | 233 | 0 |  | Y |  | 4405A616/16 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE80 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1340 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 33 | 0 | 33 | 0 |  | Y |  | 4405A616/22 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 20:00 | 6:00 | Night Shift | Approved | 25.5.23 GW e-mailed Andy Reddy about the works. Also upload local authority consent for diversions
YNE81 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1341 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 523 | 0 | 523 | 0 |  | Y |  |  | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 EB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1342 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 WB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1343 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 WB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1344 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1345 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1346 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1346 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | CW | 2 | 0 | 2 | 0 |  | Y |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1345 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1347 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 244.32 | 0 | 244.32 | 0 |  | Y |  | 4405A616/10 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1348 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | EB | 223.35 | 0 | 223.35 | 0 |  | Y |  | 4405A616/12 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 EB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1348 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | CW | 30.62 | 0 | 30.62 | 0 |  | Y |  | 4405A616/6 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 WB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1347 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 193.59 | 0 | 193.59 | 0 |  | Y |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE81 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1349 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 2192.08 | 0 | 2192.08 | 0 |  | Y |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE81 Closure 1 WB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1350 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | WB | 938 | 0 | 938 | 0 |  | Y |  | 4405A616/8 | YNE81: A616 Westwood - Newton Chambers | YNE81 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE82 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1351 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 576 | 0 | 576 | 0 |  | Y |  |  | YNE82: A61 | YNE82 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE82 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1352 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1353 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE82: A61 | YNE82 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | [5 empty] | Day Shift
YNE82 Closure 1 SB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1354 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE82: A61 | YNE82 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | [5 empty] | Day Shift
YNE82 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1355 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 10 | 0 | 10 | 0 |  | Y |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1356 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4 | 0 | 4 | 0 |  | Y |  | 4405A61/47 | YNE82: A61 | YNE82 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1355 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | CW | 4 | 0 | 4 | 0 |  | Y |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1357 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 2127.54 | 0 | 2127.54 | 0 |  | Y |  | 4405A61/30 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1357 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1160.02 | 0 | 1160.02 | 0 |  | Y |  | 4405A61/44 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1357 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | CW | 427.38 | 0 | 427.38 | 0 |  | Y |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE82 Closure 1 NB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1358 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | CW | 701 | 0 | 701 | 0 |  | Y |  | 4405A61/50 | YNE82: A61 | YNE82 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 0 | 0 |  | 0:00 | 0:00 |  | 0 | 0
YNE86 Closure 3 NB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1359 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | NB | 508.2991 | 0 | 508.2991 | 0 |  | N |  | 4400M18/251 | YNE86: M18 J3-4 | YNE86 Closure 3 NB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep) | 276/4 | 280/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE87 Closure 1 SB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1360 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | SB | 726.4171 | 0 | 726.4171 | 0 |  | N |  | 4400M18/144 | YNE87: M18 J4-5 | YNE87 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | 3 time per year (Apr - Sep) | 283/1 | 281/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1361 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 1069.3754 | 0 | 1069.3754 | 0 |  | N |  | 2000A180/107 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1361 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 489.8743 | 0 | 489.8743 | 0 |  | N |  | 2000A180/120 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 2 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1362 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 753.8297 | 0 | 753.8297 | 0 |  | N |  | 2000A180/126 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1363 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 571.4629 | 0 | 571.4629 | 0 |  | N |  | 2000A180/901 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 1 EB OS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1364 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 11.6386 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | 2023-10-31 | 2023-05-02 | 2023-05-31 | 2023-10-31 |  | 21dys | EB | 280.9579 | 280.9579 | 0 | 1 |  | N |  | 2000A180/903 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | 3 time per year (Apr - Sep) | 40/7 | 45/4 | 45854598 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE96 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1363 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 388.861 | 0 | 388.861 | 0 |  | N |  | 2000A180/905 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE96 Closure 2 EB OS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1365 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | Missed intervention |  |  |  | 2023-05-02 | 2023-05-31 | 2023-10-31 |  | 21dys | EB | 227.9313 | 0 | 227.9313 | 0 |  | N |  | 2000A180/907 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | 3 time per year (Apr - Sep) |  |  | 45854598
YNE97 Closure 2 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1366 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 247.3801 | 0 | 247.3801 | 0 |  | N |  | 2000A180/150 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1367 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 203.5426 | 0 | 203.5426 | 0 |  | N |  | 2000A180/152 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1367 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 457.4139 | 0 | 457.4139 | 0 |  | N |  | 2000A180/157 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE97 Closure 2 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1367 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 1119.1714 | 0 | 1119.1714 | 0 |  | N |  | 2000A180/162 | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE98 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1368 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | EB | 1168.5096 | 0 | 1168.5096 | 0 |  | N |  | 2000A180/169 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE98 Closure 1 WB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1369 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | WB | 442.3139 | 0 | 442.3139 | 0 |  | N |  | 2000A180/170 | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE99 Closure 1 EB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1370 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to locate asset due to no job numbers. Intervention missed. | 21dys | CW | 2458.1919 | 0 | 2458.1919 | 0 |  | N |  | 2000A180/197 | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep)
YNE100 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1371 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 2.1127 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 51 | 51 | 0 | 1 |  | N |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure 1 CW OS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1372 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 44.9458 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 1085 | 1085 | 0 | 1 |  | N |  | 2000A160/215 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1371 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 27.0918 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 654 | 654 | 0 | 1 |  | N |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1373 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 275.6197 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 6653.51 | 6653.51 | 0 | 1 |  | N |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1373 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 14.567 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 351.65 | 351.65 | 0 | 1 |  | N |  | 2000A160/223 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1373 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 9.6578 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 233.14 | 233.14 | 0 | 1 |  | N |  | 2000A160/227 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1373 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 16.1407 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 389.64 | 389.64 | 0 | 1 |  | N |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1373 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 95.3949 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | EB | 2302.85 | 2302.85 | 0 | 1 |  | N |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure 1 CW NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1374 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 75.3515 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | CW | 1819 | 1819 | 0 | 1 |  | N |  | 2000A160/240 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1373 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 380.413 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 9183.24 | 9183.24 | 0 | 1 |  | N |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1373 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 139.1514 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 3359.14 | 3359.14 | 0 | 1 |  | N |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1373 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 36.0109 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 869.31 | 869.31 | 0 | 1 |  | N |  | 2000A160/313 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1373 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 4.9573 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 119.67 | 119.67 | 0 | 1 |  | N |  | 2000A160/315 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1373 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 74.1792 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-05-31 | Complete |  | 21dys | WB | 1790.7 | 1790.7 | 0 | 1 |  | N |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 1 |  |  | 6 times per year (Mar - Oct)
YNE103 Closure 1 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 1375 | VRS - Check all Road Restraint System - ILM | 2.246 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 174.56 | 174.56 | 0 | 1 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE103 Closure 1 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 1376 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | CW | 13 | 0 | 13 | 0 |  |  |  | 4720A62/110 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1377 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 43dys | NB | 6 | 5 | 1 | 0.83333 |  |  |  | 4720A62/160 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 NB NS Enviroflow 45048 Gullies - Emptying / clear covers | 1377 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | NB | 0 | 0 | 0 | 0 |  |  |  | 4720A62/170 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 1378 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 7 | 7 | 0 | 1 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 1376 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | CW | 0 | 0 | 0 | 0 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 SB NS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1379 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0.27102 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 11 | 11 | 0 | 1 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE103 Closure 1 SB OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1380 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.7 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 69 | 69 | 0 | 1 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE103 Closure 1 CW OS CGS 45048 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1381 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.5276 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 62 | 62 | 0 | 1 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE103 Closure 1 CW NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1382 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 15.9796 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 20 | 20 | 0 | 1 |  |  |  | 4720A62/110 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 SB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1383 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 6.3918 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 8 | 8 | 0 | 1 |  |  |  | 4720A62/120 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 SB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1383 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 2.3969 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 3 | 3 | 0 | 1 |  |  |  | 4720A62/130 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 SB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1383 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 18.3766 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 23 | 23 | 0 | 1 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 NB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1384 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 8.7888 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 11 | 11 | 0 | 1 |  |  |  | 4720A62/160 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 NB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1384 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.9949 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  |  |  | 4720A62/170 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 CW NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 1382 | Traffic Signs - Clean all traffic sign faces and reference numbers areas less than 5m2 | 7.9898 | 4.4.1.1 | A40031 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 10 | 10 | 0 | 1 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 CW NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 1385 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 35.9541 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 3 | 3 | 0 | 1 |  |  |  | 4720A62/110 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 SB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 1386 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  |  |  | 4720A62/120 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 SB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 1386 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 23.9694 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 2 | 2 | 0 | 1 |  |  |  | 4720A62/130 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 SB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 1386 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 11.9847 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 NB NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 1387 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 35.9541 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  |  |  | 4720A62/160 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 CW NS Amey 45048 Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 1385 | Traffic Signs - Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 35.9541 | 4.4.1.2 | A40032 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 3 | 3 | 0 | 1 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE103 Closure 1 CW NS Amey 45048 Bollards - Clean all illuminated and non-illuminated bollards | 1388 | Bollards - Clean all illuminated and non-illuminated bollards | 13.1634 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 4 | 4 | 0 | 1 |  |  |  | 4720A62/110 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually
YNE103 Closure 1 SB NS Amey 45048 Bollards - Clean all illuminated and non-illuminated bollards | 1389 | Bollards - Clean all illuminated and non-illuminated bollards | 9.8725 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 3 | 3 | 0 | 1 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually
YNE103 Closure 1 NB NS Amey 45048 Bollards - Clean all illuminated and non-illuminated bollards | 1390 | Bollards - Clean all illuminated and non-illuminated bollards | 9.8725 | 4.4.3 | A40035 |  | 0 | Amey | 1200 - Traffic Signs & Road Markngs | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  |  |  | 4720A62/160 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually
YNE103 Closure Amey 45048 BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 1391 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 0 | 4.5.4 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 58 | 58 | 0 | 1 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure | Lane 1 Closure | 1 |  |  | Every 3 years
YNE103 Closure Amey 45048 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1392 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE103 Closure Amey 45048 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1393 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE103 Closure 1 CW NS CGS 45048 Wildlife structures and tunnels - Remove all material that could impair operation | 1394 | Wildlife structures and tunnels - Remove all material that could impair operation | 6.9041 | 4.8.17 | A40093 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 1 | 1 | 0 | 1 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually
YNE103 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1395 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 25.072 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 523 | 523 | 0 | 1 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 NB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1396 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | NB |  |  | 0 | 0 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1397 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | SB |  |  | 0 | 0 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1398 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys | SB |  |  | 0 | 0 |  |  |  |  | YNE103: A62 Gildersome | YNE103 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1399 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 131.8318 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 55 | 55 | 0 | 1 |  |  |  | 4720A62/110 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1400 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 10 | 10 | 0 | 1 |  |  |  | 4720A62/120 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1400 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 5 | 5 | 0 | 1 |  |  |  | 4720A62/130 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1400 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 27 | 27 | 0 | 1 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1401 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 17 | 17 | 0 | 1 |  |  |  | 4720A62/160 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 NB NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1401 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  |  |  | 4720A62/170 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1399 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 29 | 29 | 0 | 1 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 SB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1402 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 479.3885 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 80 | 80 | 0 | 1 |  |  |  | 4720A62/130 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 NB NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1403 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  |  |  | 4720A62/160 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1404 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 3 | 3 | 0 | 1 |  |  |  | 4720A62/130 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1405 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 12.3957 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 598.47 | 598.47 | 0 | 1 |  |  |  | 4720A62/110 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1406 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 8.7742 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 423.62 | 423.62 | 0 | 1 |  |  |  | 4720A62/120 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1406 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.32 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 256.85 | 256.85 | 0 | 1 |  |  |  | 4720A62/130 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1406 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 16.7186 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 807.18 | 807.18 | 0 | 1 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1405 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 7.6424 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 368.98 | 368.98 | 0 | 1 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1407 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.0204 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 351 | 351 | 0 | 1 |  |  |  | 4720A62/110 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1408 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.3981 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 84 | 84 | 0 | 1 |  |  |  | 4720A62/120 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1408 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.5082 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 263 | 263 | 0 | 1 |  |  |  | 4720A62/130 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 SB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1408 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.1053 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 389 | 389 | 0 | 1 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1409 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.9919 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 350 | 350 | 0 | 1 |  |  |  | 4720A62/160 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 NB NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1409 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2.3981 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 84 | 84 | 0 | 1 |  |  |  | 4720A62/170 | YNE103: A62 Gildersome | YNE103 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1407 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.5351 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 334 | 334 | 0 | 1 |  |  |  | 4720A62/190 | YNE103: A62 Gildersome | YNE103 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE103 Closure 1 SB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1410 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 16.5677 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | SB | 184.32 | 184.32 | 0 | 1 |  |  |  | 4720A62/140 | YNE103: A62 Gildersome | YNE103 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE103 Closure 1 NB OS CGS 45048 Grass & Vegetation - Grass cut the central reserve 1 - ILM | 1411 | Grass & Vegetation - Grass cut the central reserve 1 - ILM | 10.7961 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 120.11 | 120.11 | 0 | 1 |  |  |  | 4720A62/160 | YNE103: A62 Gildersome | YNE103 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1412 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys |  | 5079 | 0 | 5079 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  |  | YNE106: A1M J34-35 | YNE106 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1413 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 NB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1414 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 SB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1415 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  |  | YNE106: A1M J34-35 | YNE106 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1416 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 1 | 0 | 1 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/100 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 2 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1417 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 4 | 0 | 4 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/3 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 2 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1417 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 2 | 0 | 2 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/5 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 4/2 | 8/7 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1416 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 5 | 0 | 5 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/52 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 3 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1418 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 2 | 0 | 2 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/6 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 3 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1418 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 6 | 0 | 6 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/7 | YNE106: A1M J34-35 | YNE106 Closure 3 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 8/3 | 12/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE106 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1419 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 49.23 | 0 | 49.23 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/102 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1420 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 34.23 | 0 | 34.23 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/103 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1420 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 11.82 | 0 | 11.82 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/55 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE106 Closure 1 NB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 1421 | Sweeping - Paved non-running areas - Full Sweep 01 | 52.0705 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | NB | 6991 | 6991 | 0 | 1 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/1 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year
YNE106 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1422 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 1240 | 0 | 1240 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/102 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections)
YNE106 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1423 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 582 | 0 | 582 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/103 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections)
YNE106 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1422 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 465 | 0 | 465 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/52 | YNE106: A1M J34-35 | YNE106 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections)
YNE106 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1423 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 617 | 0 | 617 | 0 | Access became available to YNE8 which was unable to complete in May. A1M Works moved to W/C 17th July | Y |  | 4400A1M/55 | YNE106: A1M J34-35 | YNE106 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections)
YNE107 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1424 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys |  | 1669 | 0 | 1669 | 0 |  | Y |  |  | YNE107: A1M J35-36 | YNE107 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1425 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1426 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 SB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1427 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE107: A1M J35-36 | YNE107 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1428 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 4400A1M/10 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1428 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1428 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400A1M/71 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1428 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1429 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 15.59 | 0 | 15.59 | 0 |  | Y |  | 4400A1M/42 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1430 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 103.01 | 0 | 103.01 | 0 |  | Y |  | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1429 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 26.04 | 0 | 26.04 | 0 |  | Y |  | 4400A1M/59 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1430 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 30.47 | 0 | 30.47 | 0 |  | Y |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE107 Closure 1 NB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 1431 | Sweeping - Paved non-running areas - Full Sweep 01 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 6924.75 |  | 6924.75 | 0 |  | Y |  | 4400A1M/9 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year |  |  | 52033905
YNE107 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1432 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 516 | 0 | 516 | 0 |  | Y |  | 4400A1M/54 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections)
YNE107 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1433 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 494 | 0 | 494 | 0 |  | Y |  | 4400A1M/56 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections)
YNE107 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1432 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 492 | 0 | 492 | 0 |  | Y |  | 4400A1M/59 | YNE107: A1M J35-36 | YNE107 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections)
YNE107 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1433 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 468 | 0 | 468 | 0 |  | Y |  | 4400A1M/70 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections)
YNE107 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1433 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 389 | 0 | 389 | 0 |  | Y |  | 4400A1M/71 | YNE107: A1M J35-36 | YNE107 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections)
YNE108 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1434 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys |  | 2825 | 0 | 2825 | 0 |  | Y |  |  | YNE108: A1M J36-37 | YNE108 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1435 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1436 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 SB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1437 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE108: A1M J36-37 | YNE108 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE108 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1438 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1438 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400A1M/13 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1438 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 7 | 0 | 7 | 0 |  | Y |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1438 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400A1M/60 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1438 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1439 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 23.76 | 0 | 23.76 | 0 |  | Y |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1440 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 98.07 | 0 | 98.07 | 0 |  | Y |  | 4400A1M/58 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1439 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 39.96 | 0 | 39.96 | 0 |  | Y |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 1441 | Sweeping - Paved non-running areas - Full Sweep 01 | 33.032 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 11670.75 | 4434.885 | 7235.865 | 0.38 | 7/8: Centres completed so 50% of 18 sections - 24 sections in total - 38% conplete roughly | Y |  | 4400A1M/12 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year | 14/7 | 20/4 | 52037659 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1442 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 309 | 0 | 309 | 0 |  | Y |  | 4400A1M/57 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1443 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 315 | 0 | 315 | 0 |  | Y |  | 4400A1M/58 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1442 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 630 | 0 | 630 | 0 |  | Y |  | 4400A1M/60 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1443 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 631 | 0 | 631 | 0 |  | Y |  | 4400A1M/61 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1442 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 544 | 0 | 544 | 0 |  | Y |  | 4400A1M/62 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 3 times per year (ILM Certain Sections) | 14/7 | 20/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE108 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1443 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 547 | 0 | 547 | 0 |  | Y |  | 4400A1M/65 | YNE108: A1M J36-37 | YNE108 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 3 times per year (ILM Certain Sections) | 20/3 | 15/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1444 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys |  | 2113 | 0 | 2113 | 0 |  | Y |  |  | YNE109: A1M J37-38 | YNE109 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE109 Closure 1 SB NS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1445 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1446 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 20/1 | 23/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB OS CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1447 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE109: A1M J37-38 | YNE109 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 23/8 | 20/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1448 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400A1M/22 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1448 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400A1M/24 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1448 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 6 | 0 | 6 | 0 |  | Y |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1448 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400A1M/66 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1449 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4400A1M/67 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1450 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 40.09 | 0 | 40.09 | 0 |  | Y |  | 4400A1M/25 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS CGS 45048 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1451 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 42 | 0 | 42 | 0 |  | Y |  | 4400A1M/23 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45048 Sweeping - Paved non-running areas - Full Sweep 01 | 1452 | Sweeping - Paved non-running areas - Full Sweep 01 | 52.0004 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 8727 | 6981.6 | 1745.4 | 0.8 | 8/8 centres completed. 31/7: NS completed from 20/5--24/4, 1 load. 3 slips left | Y |  | 4400A1M/21 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1453 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 375 | 0 | 375 | 0 |  | Y |  | 4400A1M/63 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 3 times per year (ILM Certain Sections) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1454 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 343 | 0 | 343 | 0 |  | Y |  | 4400A1M/64 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 3 times per year (ILM Certain Sections) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 NB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1453 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | NB | 761 | 0 | 761 | 0 |  | Y |  | 4400A1M/66 | YNE109: A1M J37-38 | YNE109 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 20/1 | 24/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE109 Closure 1 SB NS Amey 45048 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1454 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-06-30 | N/A | First intervention missed due to access | 43dys | SB | 1262 | 0 | 1262 | 0 |  | Y |  | 4400A1M/67 | YNE109: A1M J37-38 | YNE109 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) | 285/8 | 19/9 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1455 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 364.4572 | 0 | 364.4572 | 0 |  | Y |  | 4700A1/323 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 NB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1455 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | NB | 426.4114 | 0 | 426.4114 | 0 |  | Y |  | 4700A1/357 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 285/8 | 289/4 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1456 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 244.605 | 0 | 244.605 | 0 |  | Y |  | 4700A1/665 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE110 Closure 1 SB NS CGS 45048 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 1456 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 1 | 0 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-05-02 | 2023-05-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 21dys | SB | 68.3478 | 0 | 68.3478 | 0 |  | Y |  | 4700A1/668 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | 3 time per year (Apr - Sep) | 290/2 | 285/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE114 Closure 1 CW NS Bettamix 45048 VRS - Check all Road Restraint System - ILM | 1457 | VRS - Check all Road Restraint System - ILM | 3.828 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 297.52 | 297.52 | 0 | 1 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE114 Closure 1 CW NS Enviroflow 45048 Gullies - Emptying / clear covers | 1458 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 13 | 13 | 0 | 1 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE114 Closure 1 CW OS Enviroflow 45048 Gullies - Emptying / clear covers | 1459 | Gullies - Emptying / clear covers | 277.9145 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 36 | 36 | 0 | 1 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45803571
YNE114 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1460 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 2 | 2 | 0 | 1 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE114 Closure 1 CW NS CGS 45048 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1461 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 239.6942 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 100 | 100 | 0 | 1 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE114 Closure 1 CW NS CGS 45048 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1462 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 419.4649 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 70 | 70 | 0 | 1 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE114 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1463 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 11 | 11 | 0 | 1 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE114 Closure 1 CW NS CGS 45048 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1464 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 25.0673 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 1210.26 | 1210.26 | 0 | 1 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE114 Closure 1 CW NS CGS 45048 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1465 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.6086 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys | CW | 862 | 862 | 0 | 1 |  |  |  | 4710A58/89 | YNE114: A58 Chainbar | YNE114 Closure 1 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE114 Closure CGS 45048 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1466 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 49.9043 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 1041 | 1041 | 0 | 1 |  |  |  |  | YNE114: A58 Chainbar | YNE114 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE114 Closure Amey 45048 BC - Lamps (LED) for Road Lighting | 1467 | BC - Lamps (LED) for Road Lighting | 134.828 | 4.5.7 | A40042 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 6 | 6 | 0 | 1 |  |  |  |  | YNE114: A58 Chainbar | YNE114 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE114 Closure Amey 45048 Electrical Testing - Network cabling and electrical components | 1468 | Electrical Testing - Network cabling and electrical components | 95.8777 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-05-02 | 2023-06-30 | Complete |  | 43dys |  | 5 | 5 | 0 | 1 |  |  |  |  | YNE114: A58 Chainbar | YNE114 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE11 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1469 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 5.711 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 33.29 | 33.29 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1470 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 36.4943 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 212.73 | 212.73 | 0 | 1 |  |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1471 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 12.4838 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 72.77 | 72.77 | 0 | 1 |  |  |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1471 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 132.0231 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 769.58 | 769.58 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1471 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 66.7475 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 389.08 | 389.08 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1470 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 37.5305 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 218.77 | 218.77 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1469 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 35.0327 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 204.21 | 204.21 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1469 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1.4136 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 8.24 | 8.24 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1469 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 13.424 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 78.25 | 78.25 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1472 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 | 0 |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1473 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1473 | Gullies - Emptying / clear covers | 185.2763 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 24 | 24 | 0 | 1 |  |  |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1474 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824962
YNE11 Closure 2 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1475 | Gullies - Emptying / clear covers | 941.8213 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 122 | 122 | 0 | 1 |  |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 2 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1475 | Gullies - Emptying / clear covers | 609.8679 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 79 | 79 | 0 | 1 |  |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 2 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1476 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 | 15/9: 18 completed no more gullies within this closure |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824962
YNE11 Closure 2 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1475 | Gullies - Emptying / clear covers | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 14 | 14 | 0 | 1 | 0 |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 2 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1476 | Gullies - Emptying / clear covers | 316.5137 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 41 | 41 | 0 | 1 | 15/9: 18 completed no more gullies within this closure |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824962
YNE11 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1473 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1474 | Gullies - Emptying / clear covers | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824962
YNE11 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1474 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 9 | 9 | 0 | 1 | 0 |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824962
YNE11 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1472 | Gullies - Emptying / clear covers | 247.0351 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 104 | 32 | 72 | 0.30769 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45824962
YNE11 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1472 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1477 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824962
YNE11 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1472 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1472 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 2 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1478 | Gullies - Emptying / clear covers | 578.9885 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 75 | 75 | 0 | 1 | 0 |  |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 2 EB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1479 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 594.4282 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-25 | 2023-06-01 | 2023-07-31 | 2023-11-30 |  | 43dys | EB | 77 | 77 | 0 | 1 |  | N |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45824962
YNE11 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1472 | Gullies - Emptying / clear covers | 131.2374 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 17 | 17 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1477 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1472 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/596 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE11 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1480 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.8843 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 320 | 320 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1481 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.0755 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 206 | 206 | 0 | 1 |  |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1482 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.4697 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 222 | 222 | 0 | 1 |  |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1482 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 11.1612 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 453 | 453 | 0 | 1 |  |  |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 2 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1483 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 31.5618 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1281 | 1281 | 0 | 1 |  |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 2 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1484 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 49.2768 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2000 | 2000 | 0 | 1 |  |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) |  |  | 45827837
YNE11 Closure 2 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1483 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.3262 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 135 | 135 | 0 | 1 |  |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 2 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1484 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 41.9592 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1703 | 1703 | 0 | 1 |  |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) |  |  | 45827837
YNE11 Closure 2 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1483 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 28.9255 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1174 | 1174 | 0 | 1 |  |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 2 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1484 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 26.5109 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1076 | 1076 | 0 | 1 |  |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept) |  |  | 45827837
YNE11 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1481 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 18.331 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 744 | 744 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1482 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 18.9716 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 770 | 770 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1481 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 19.0948 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 775 | 775 | 0 | 1 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1482 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.6004 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 552 | 552 | 0 | 1 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1481 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.7595 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 112 | 112 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1482 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.9019 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 686 | 686 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1480 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.1842 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 251 | 251 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1485 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.474 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 141 | 141 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1480 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 24.0224 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 975 | 975 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1485 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 9.5597 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 388 | 388 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1480 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.8366 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 521 | 521 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1480 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 32.0792 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1302 | 1302 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1485 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0.36958 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 15 | 15 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 2 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1486 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.3192 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 500 | 500 | 0 | 1 |  |  |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1480 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 3.0059 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 122 | 122 | 0 | 1 | 0 |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE11 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1487 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 707.6526 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 85 | 33 | 52 | 0.38824 | 0 |  |  | 2000M62/103 | YNE11: M62 J33-34 (actually J32a-33) | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1488 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 686.2086 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-21 | 2023-06-01 | 2023-07-31 | 2023-11-30 |  | 43dys | WB | 90 | 32 | 0 | 0.35556 |  | N |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1489 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2 | 0 | 2 | 1 | 15/9: No jobs - catchpits on NS? |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1489 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4 | 0 | 4 | 1 | 15/9: No jobs - catchpits on NS? |  |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1488 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 2 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1490 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 707.6526 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2023-11-30 |  | 43dys | WB | 57 | 33 | 24 | 0.57895 |  | N | 24/11 gully cart full following completion of EB | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 2 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1491 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 28 | 0 | 28 | 1 | 15/9: no catchpits in OS closure |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 2 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1490 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 2 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1491 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 14 | 0 | 14 | 1 | 15/9: no catchpits in OS closure |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 2 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1490 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 | 0 |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 2 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1491 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 257.3282 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 12 | 12 | 0 | 1 |  |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1488 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 192.9962 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 9 | 9 | 0 | 1 | 0 |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1489 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 192.9962 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 9 | 9 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1488 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 300.2163 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 14 | 14 | 0 | 1 | 0 |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1489 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 11 | 0 | 11 | 1 | 15/9: No jobs - catchpits on NS? |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1488 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1489 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 9 | 0 | 9 | 1 | 15/9: No jobs - catchpits on NS? |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1487 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1487 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1492 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 8 | 0 | 8 | 1 | 15/9: No jobs - catchpits on NS? |  |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1487 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 7 | 7 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1487 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1492 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 2 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1493 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 171.5521 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-25 | 2023-06-01 | 2023-07-31 | 2023-11-30 |  | 43dys | EB | 8 | 8 | 0 | 1 |  | N |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 2 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1493 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure 2 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1494 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829238
YNE11 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1487 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE11 Closure Amey 45078 BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 1495 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 44.9427 | 4.5.3 | A40038 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE11 Closure Amey 45078 Electrical Testing - Network cabling and electrical components | 1496 | Electrical Testing - Network cabling and electrical components | 95.8777 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 5 | 5 | 0 | 1 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE11 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1497 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 168.6489 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 3518 | 3518 | 0 | 1 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1498 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB |  | 0 | 0 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1499 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1500 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB |  | 0 | 0 | 0 |  |  |  |  | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1501 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1502 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1503 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1503 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1503 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 20 | 20 | 0 | 1 |  |  |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 2 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1504 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 74.3052 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 31 | 31 | 0 | 1 |  |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 2 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1504 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 25 | 25 | 0 | 1 |  |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 2 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1504 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 15 | 15 | 0 | 1 |  |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1503 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 22 | 22 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1503 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 13 | 13 | 0 | 1 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1503 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 9 | 9 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1502 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1502 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 13 | 13 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1502 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 19 | 19 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1502 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 14 | 14 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 2 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1505 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 27 | 27 | 0 | 1 |  |  |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 2 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1505 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 88.6869 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 37 | 37 | 0 | 1 |  |  |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1502 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 14 | 14 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1506 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1507 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 41.9465 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 7 | 7 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1508 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1509 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1509 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 2 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1510 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1509 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1509 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1509 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1508 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 6 | 6 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1508 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1508 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1508 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1511 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1511 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1508 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1508 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 4700M62/596 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 2 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1512 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.1035 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 246.4 | 246.4 | 0 | 1 |  |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 2 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1512 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.24192 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 11.68 | 11.68 | 0 | 1 |  |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.14478 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 6.99 | 6.99 | 0 | 1 |  |  |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1513 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.2945 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 110.78 | 110.78 | 0 | 1 |  |  |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1514 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.1085 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 249 | 249 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1515 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.7945 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 238 | 238 | 0 | 1 |  |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1515 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.2774 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 360 | 360 | 0 | 1 |  |  |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1515 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.5294 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 579 | 579 | 0 | 1 |  |  |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 2 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1516 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 56.1544 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1967 | 1967 | 0 | 1 |  |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 2 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1516 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 46.1054 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1615 | 1615 | 0 | 1 |  |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 2 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1516 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.2032 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1093 | 1093 | 0 | 1 |  |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1515 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.6404 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 723 | 723 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1515 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.5001 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 613 | 613 | 0 | 1 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1515 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.4691 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 717 | 717 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1514 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.7799 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 868 | 868 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1514 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.925 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 768 | 768 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1514 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.5865 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 581 | 581 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1514 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.9463 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1084 | 1084 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 2 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1517 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 46.3338 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1623 | 1623 | 0 | 1 |  |  |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 2 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1517 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 60.4651 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2118 | 2118 | 0 | 1 |  |  |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1514 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.2186 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 428 | 428 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1514 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.9666 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 209 | 209 | 0 | 1 |  |  |  | 4700M62/596 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE11 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1518 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 43.0191 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 478.6 | 478.6 | 0 | 1 |  |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1518 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 35.253 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 392.2 | 392.2 | 0 | 1 |  |  |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 2 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1519 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 603.9234 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 6718.82 | 6718.82 | 0 | 1 |  |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 2 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1519 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 445.4403 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4955.65 | 4955.65 | 0 | 1 |  |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 2 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1519 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 378.5791 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4211.8 | 4211.8 | 0 | 1 |  |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1518 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 193.3649 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2151.24 | 2151.24 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1518 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 212.6849 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2366.18 | 2366.18 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE11 Closure 1 EB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 1520 | Sweeping - Paved non-running areas - Full Sweep 01 | 84.0624 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 11286.25 | 11286.25 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE11 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1521 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 44.7869 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1868.5 | 1868.5 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 1 EB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1522 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 44.7869 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1868.5 | 1868.5 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually
YNE11 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1523 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 928.0961 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 19360 | 19360 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 | Yes |  | Annually
YNE11 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1524 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.258 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 249 | 249 | 0 | 1 |  |  |  | 2000M62/103 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1525 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.3816 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 717 | 717 | 0 | 1 |  |  |  | 2000M62/104 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1525 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.8395 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 752 | 752 | 0 | 1 |  |  |  | 4700M62/203 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1526 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.5759 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 579 | 579 | 0 | 1 |  |  |  | 4700M62/205 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE11 Closure 2 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1527 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 113.6385 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 8685 | 8685 | 0 | 1 |  |  |  | 4700M62/207 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 2 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1527 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 85.9649 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 6570 | 6570 | 0 | 1 |  |  |  | 4700M62/209 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 2 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1527 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 69.4 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 5304 | 5304 | 0 | 1 |  |  |  | 4700M62/211 | YNE11: M62 J33-34 | YNE11 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1525 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 37.6047 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2874 | 2874 | 0 | 1 |  |  |  | 4700M62/213 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1526 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.0208 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 613 | 613 | 0 | 1 |  |  |  | 4700M62/215 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE11 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1525 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 40.3394 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 3083 | 3083 | 0 | 1 |  |  |  | 4700M62/217 | YNE11: M62 J33-34 | YNE11 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1524 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.3573 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 868 | 868 | 0 | 1 |  |  |  | 4700M62/580 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1528 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 10.0489 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 768 | 768 | 0 | 1 |  |  |  | 4700M62/582 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 3 times per year (ILM Certain Sections)
YNE11 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1524 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.6021 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 581 | 581 | 0 | 1 |  |  |  | 4700M62/584 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1524 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.1836 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1084 | 1084 | 0 | 1 |  |  |  | 4700M62/588 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 2 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1529 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.2361 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1623 | 1623 | 0 | 1 |  |  |  | 4700M62/590 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 2 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1529 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 27.7129 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2118 | 2118 | 0 | 1 |  |  |  | 4700M62/592 | YNE11: M62 J33-34 | YNE11 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE11 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1528 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.6001 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 428 | 428 | 0 | 1 |  |  |  | 4700M62/594 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE11 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1524 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.7347 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 209 | 209 | 0 | 1 |  |  |  | 4700M62/596 | YNE11: M62 J33-34 | YNE11 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1530 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 11.4631 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 66.82 | 66.82 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1531 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 17.0832 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 99.58 | 99.58 | 0 | 1 |  |  |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1532 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 61.0949 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 356.13 | 356.13 | 0 | 1 |  |  |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1530 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 59.1975 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 345.07 | 345.07 | 0 | 1 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1531 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 222.462 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1296.76 | 1296.76 | 0 | 1 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1532 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 102.2845 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 596.23 | 596.23 | 0 | 1 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1530 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 93.4668 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 544.83 | 544.83 | 0 | 1 |  |  |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1531 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 52.4109 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 305.51 | 305.51 | 0 | 1 |  |  |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1530 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 37.6677 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 219.57 | 219.57 | 0 | 1 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1533 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 143.2581 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 835.07 | 835.07 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1534 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 173.8767 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1013.55 | 1013.55 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1533 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 137.2228 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 799.89 | 799.89 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1534 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 137.0564 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 798.92 | 798.92 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1535 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 110.5568 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 644.45 | 644.45 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1533 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 110.9136 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 646.53 | 646.53 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1534 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 186.7705 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1088.71 | 1088.71 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1535 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 82.6006 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 481.49 | 481.49 | 0 | 1 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1535 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 339.3696 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1978.23 | 1978.23 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 EB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1536 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 68.0427 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 396.63 | 396.63 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 3 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1537 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 336.8804 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1963.72 | 1963.72 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 3 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1538 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 306.6975 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1787.78 | 1787.78 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 3 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1539 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 244.551 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1425.52 | 1425.52 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 3 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1537 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 335.4754 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1955.53 | 1955.53 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 3 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1538 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 178.4571 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1040.25 | 1040.25 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 3 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1539 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 104.7171 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 610.41 | 610.41 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1531 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 239.3564 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1395.24 | 1395.24 | 0 | 1 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1540 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 10.4921 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 61.16 | 61.16 | 0 | 1 |  |  |  | 2000M62/125 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1530 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 58.3552 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 340.16 | 340.16 | 0 | 1 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1540 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 101.4405 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 591.31 | 591.31 | 0 | 1 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1531 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 51.2975 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 299.02 | 299.02 | 0 | 1 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1532 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 261.3202 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1523.27 | 1523.27 | 0 | 1 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1530 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 235.21 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1371.07 | 1371.07 | 0 | 1 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1540 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 46.2522 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 269.61 | 269.61 | 0 | 1 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1541 | Gullies - Emptying / clear covers | 440.0313 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2023-11-30 |  | 43dys | EB | 62 | 57 | 5 | 0.91935 |  | Y | Issues with jobs not being visible on tablets | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45824292
YNE12 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1542 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1543 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 14 | 14 | 0 | 1 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE12 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1544 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 3 | 0 | 3 | 0 |  | N | 2/10 cancelled rain | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45824292
YNE12 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1545 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 694.7862 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2023-11-30 |  | 43dys | WB | 97 | 90 | 7 | 0.92784 | 29/11 30 complete ni 2nd visit | N |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | Days |  |  | Annually for ILM Sections Within the Route |  |  | 45824292
YNE12 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1546 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 | no assets | N | 2/10 cancelled rain | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45824292
YNE12 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1543 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE12 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1544 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE12 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1542 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1547 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1541 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1548 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  | N | 2/10 cancelled rain | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824292
YNE12 Closure 2 WB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1549 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 517.2297 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-29 | 2023-06-01 | 2023-07-31 | 2023-11-30 |  | 43dys | WB | 67 | 67 | 0 | 1 |  | N |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45824292
YNE12 Closure 2 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1550 | Gullies - Emptying / clear covers | 262.4748 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 103 | 34 | 69 | 0.3301 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1551 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 9 | 9 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 WB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1549 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE12 Closure 2 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1551 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-03-31 |  | 43dys | EB | 22 | 0 | 22 | 0 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824292
YNE12 Closure 2 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1550 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 2 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1551 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824292
YNE12 Closure 3 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1552 | Gullies - Emptying / clear covers | 578.9885 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | WB | 276 | 75 | 201 | 0.27174 |  | N | 27/11 TM not established due to TM vehicle breakdown | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45830941
YNE12 Closure 3 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1553 | Gullies - Emptying / clear covers | 910.9419 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 118 | 118 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 3 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1554 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824292
YNE12 Closure 3 WB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1555 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE12 Closure 3 WB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1556 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE12 Closure 3 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1553 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 239 | 1 | 238 | 0.0041841 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1542 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1547 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1548 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  | N | 2/10 cancelled rain | 2000M62/125 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824292
YNE12 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1541 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1542 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1547 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1541 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE12 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1548 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  | N | 2/10 cancelled rain | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45824292
YNE12 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1557 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.1639 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 169 | 169 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1558 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.9453 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 566 | 566 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1559 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.0959 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 288 | 288 | 0 | 1 |  |  |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1560 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.4638 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 100 | 100 | 0 | 1 |  |  |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1557 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 28.4573 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1155 | 1155 | 0 | 1 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1558 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 27.9153 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1133 | 1133 | 0 | 1 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1559 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 14.1671 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 575 | 575 | 0 | 1 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1557 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.2582 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 254 | 254 | 0 | 1 |  |  |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1559 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.6567 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 189 | 189 | 0 | 1 |  |  |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1557 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 48.9811 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1988 | 1988 | 0 | 1 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1558 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 44.1766 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1793 | 1793 | 0 | 1 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1561 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 53.2436 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2161 | 2161 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1561 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 19.5629 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 794 | 794 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1562 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.1928 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 89 | 89 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1563 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 28.6052 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1161 | 1161 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1564 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 23.9978 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 974 | 974 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1561 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 29.2704 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1188 | 1188 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1562 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 4.5581 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 185 | 185 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1563 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 25.6978 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1043 | 1043 | 0 | 1 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1564 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 19.5382 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 793 | 793 | 0 | 1 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1563 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 23.4311 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 951 | 951 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 2 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1564 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 95.1535 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3862 | 3862 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 3 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1565 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 20.7702 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 843 | 843 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 3 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1566 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 30.4531 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1236 | 1236 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 3 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1567 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 132.1357 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 5363 | 5363 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 3 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1565 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 13.3294 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 541 | 541 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 3 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1566 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.7595 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 112 | 112 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 3 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1567 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 55.2886 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2244 | 2244 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1559 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 25.5747 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1038 | 1038 | 0 | 1 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1560 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 53.761 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2182 | 2182 | 0 | 1 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1557 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 10.496 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 426 | 426 | 0 | 1 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1558 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 43.3882 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1761 | 1761 | 0 | 1 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1559 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 19.2919 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 783 | 783 | 0 | 1 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1560 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 38.5591 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1565 | 1565 | 0 | 1 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1557 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 29.8864 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1213 | 1213 | 0 | 1 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1558 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 11.8264 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 480 | 480 | 0 | 1 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE12 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1568 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 536.1005 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2023-11-30 |  | 43dys | EB | 109 | 25 | 84 | 0.22936 |  | Y | Issues with jobs not being visible on tablets | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829226
YNE12 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1569 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  | N | 2/10 cancelled rain | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829227
YNE12 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1570 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 964.9808 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2023-11-30 |  | 43dys | WB | 70 | 45 | 25 | 0.64286 | 29/11 none completed | N |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | Days |  |  | ILM Every 2 years |  |  | 45829226
YNE12 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1571 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1568 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1569 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  | N | 2/10 cancelled rain | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829227
YNE12 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1570 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1568 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1570 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1568 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1569 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  | N | 2/10 cancelled rain | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829227
YNE12 Closure 2 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1572 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 664.7646 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | 2023-11-29 | 2023-06-01 | 2023-07-31 | 2023-11-30 |  | 43dys | WB | 31 | 31 | 0 | 1 |  | N |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829226
YNE12 Closure 2 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1573 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 2 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1572 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 2 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1573 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 2 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1574 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 2 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1575 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 2 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1572 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 2 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1573 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 2 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1574 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 2 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1574 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 2 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1575 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829227
YNE12 Closure 3 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1576 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 3 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1577 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 192.9962 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 9 | 9 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 3 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1578 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 321.6603 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 15 | 15 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 3 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1579 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829227
YNE12 Closure 3 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1576 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 3 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1577 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 3 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1578 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 3 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1579 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829227
YNE12 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1570 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1571 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  | N | 2/10 cancelled rain | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829227
YNE12 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1568 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1569 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  | N | 2/10 cancelled rain | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829227
YNE12 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1570 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1571 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  | N | 2/10 cancelled rain | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829227
YNE12 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1568 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE12 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1569 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  | N | 2/10 cancelled rain | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45829227
YNE12 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1580 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 291.3723 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 6078 | 6078 | 0 | 1 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1581 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1582 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1583 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 3 EB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1584 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1585 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 143.8165 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1586 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1587 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1586 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 20 | 20 | 0 | 1 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1587 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 19 | 19 | 0 | 1 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1586 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1587 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 12 | 12 | 0 | 1 |  |  |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1586 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 103.0685 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 43 | 43 | 0 | 1 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1588 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 88.6869 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 37 | 37 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1588 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 8 | 8 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1589 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 16 | 16 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1588 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 16 | 16 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1589 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1589 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 29 | 29 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 3 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1590 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 27 | 27 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 3 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1591 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 83.893 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 35 | 35 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 3 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1590 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 50.3358 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 21 | 21 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 3 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1591 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 24 | 24 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1587 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1586 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 93.4807 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 39 | 39 | 0 | 1 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1587 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 83.893 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 35 | 35 | 0 | 1 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1586 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 103.0685 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 43 | 43 | 0 | 1 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1592 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 5 | 5 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1592 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1593 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1592 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1594 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1595 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1596 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1596 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 7 | 7 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1592 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 11 | 11 | 0 | 1 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1593 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1592 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 92.6889 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 21 | 21 | 0 | 1 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1597 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.0205 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 49.27 | 49.27 | 0 | 1 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1598 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.48881 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 23.6 | 23.6 | 0 | 1 |  |  |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1597 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.41508 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 20.04 | 20.04 | 0 | 1 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1599 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.54246 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 26.19 | 26.19 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1600 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.0156 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 561 | 561 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1601 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.332 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 467 | 467 | 0 | 1 |  |  |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1600 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.43 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1171 | 1171 | 0 | 1 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1601 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.5425 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1245 | 1245 | 0 | 1 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1600 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.531 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 509 | 509 | 0 | 1 |  |  |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1601 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.9617 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 419 | 419 | 0 | 1 |  |  |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1600 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.7294 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1812 | 1812 | 0 | 1 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1602 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.4439 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1802 | 1802 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1602 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.6689 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 724 | 724 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1603 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.8321 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1080 | 1080 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1602 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.8892 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1082 | 1082 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1603 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.6404 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 723 | 723 | 0 | 1 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 2 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1603 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.6437 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1809 | 1809 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 3 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.7008 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1811 | 1811 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 3 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.7579 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1813 | 1813 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 3 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1604 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.3868 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1800 | 1800 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 3 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1605 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.2277 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1269 | 1269 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1601 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 43.1078 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1510 | 1510 | 0 | 1 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1600 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.7659 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 237 | 237 | 0 | 1 |  |  |  | 2000M62/125 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1600 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 50.5875 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1772 | 1772 | 0 | 1 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1601 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 50.3591 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1764 | 1764 | 0 | 1 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1600 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 55.926 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1959 | 1959 | 0 | 1 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE12 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1606 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 180.5293 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2008.44 | 2008.44 | 0 | 1 |  |  |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1606 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 309.1139 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 3438.98 | 3438.98 | 0 | 1 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1607 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 309.4204 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3442.39 | 3442.39 | 0 | 1 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1608 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 87.2274 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 970.43 | 970.43 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1608 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 161.1689 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1793.05 | 1793.05 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 EB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1609 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 183.7652 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2044.44 | 2044.44 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1608 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 203.9022 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2268.47 | 2268.47 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 EB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1609 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 78.1913 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 869.9 | 869.9 | 0 | 1 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 EB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1609 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 216.9419 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2413.54 | 2413.54 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 3 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1610 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 223.2797 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2484.05 | 2484.05 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 3 EB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1611 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 107.2017 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1192.65 | 1192.65 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 3 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1610 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 286.8646 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 3191.45 | 3191.45 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 3 EB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1611 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 114.9193 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1278.51 | 1278.51 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1606 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 21.2399 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 236.3 | 236.3 | 0 | 1 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1607 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 14.1695 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 157.64 | 157.64 | 0 | 1 |  |  |  | 2000M62/125 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1607 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 39.2502 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 436.67 | 436.67 | 0 | 1 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1606 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 197.7837 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2200.4 | 2200.4 | 0 | 1 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 2 EB NS CGS 45078 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 1612 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 306.6533 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 5552 | 5552 | 0 | 1 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE12 Closure 1 EB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 1613 | Sweeping - Paved non-running areas - Full Sweep 01 | 36.2579 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4868 | 4868 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE12 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1614 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 99.3413 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4144.5 | 4144.5 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 EB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1615 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 99.3413 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4144.5 | 4144.5 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually
YNE12 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1616 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1122.6319 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 23418 | 23418 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1617 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.3404 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 561 | 561 | 0 | 1 |  |  |  | 2000M62/101 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1618 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 32.384 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2475 | 2475 | 0 | 1 |  |  |  | 2000M62/102 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1617 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.3219 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1171 | 1171 | 0 | 1 |  |  |  | 2000M62/105 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1618 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 61.2876 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4684 | 4684 | 0 | 1 |  |  |  | 2000M62/106 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1619 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.66 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 509 | 509 | 0 | 1 |  |  |  | 2000M62/108 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE12 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1620 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.4824 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 419 | 419 | 0 | 1 |  |  |  | 2000M62/109 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE12 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1617 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 68.7457 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 5254 | 5254 | 0 | 1 |  |  |  | 2000M62/111 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 2 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1621 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 36.2701 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2772 | 2772 | 0 | 1 |  |  |  | 2000M62/112 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 2 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1621 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 32.9205 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2516 | 2516 | 0 | 1 |  |  |  | 2000M62/113 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 2 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1622 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 40.8758 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3124 | 3124 | 0 | 1 |  |  |  | 2000M62/114 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 2 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1621 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 43.8329 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 3350 | 3350 | 0 | 1 |  |  |  | 2000M62/115 | YNE12: M62 J34-35 | YNE12 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 2 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1622 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 20.8435 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1593 | 1593 | 0 | 1 |  |  |  | 2000M62/116 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 2 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1622 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 55.2557 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4223 | 4223 | 0 | 1 |  |  |  | 2000M62/117 | YNE12: M62 J34-35 | YNE12 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 3 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1623 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 56.1977 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4295 | 4295 | 0 | 1 |  |  |  | 2000M62/118 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 3 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1624 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 39.3188 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3005 | 3005 | 0 | 1 |  |  |  | 2000M62/120 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 3 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1623 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 65.3045 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4991 | 4991 | 0 | 1 |  |  |  | 2000M62/121 | YNE12: M62 J34-35 | YNE12 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 3 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1624 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 33.3392 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2548 | 2548 | 0 | 1 |  |  |  | 2000M62/123 | YNE12: M62 J34-35 | YNE12 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1618 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 22.8455 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1746 | 1746 | 0 | 1 |  |  |  | 2000M62/124 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1617 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.1553 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 394 | 394 | 0 | 1 |  |  |  | 2000M62/125 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1617 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 28.9036 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2209 | 2209 | 0 | 1 |  |  |  | 2000M62/126 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1618 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 51.8668 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 3964 | 3964 | 0 | 1 |  |  |  | 2000M62/128 | YNE12: M62 J34-35 | YNE12 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE12 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1619 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 25.6325 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1959 | 1959 | 0 | 1 |  |  |  | 2000M62/129 | YNE12: M62 J34-35 | YNE12 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE13 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1625 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 68.005 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 396.41 | 396.41 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1626 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.388 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 13.92 | 13.92 | 0 | 1 |  |  |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 EB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1627 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 9.2484 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 53.91 | 53.91 | 0 | 1 |  |  |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1626 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 76.7764 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 447.54 | 447.54 | 0 | 1 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1628 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 54.4335 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 317.3 | 317.3 | 0 | 1 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1628 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 86.3456 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 503.32 | 503.32 | 0 | 1 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1625 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 112.461 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 655.55 | 655.55 | 0 | 1 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1626 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 46.7737 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 272.65 | 272.65 | 0 | 1 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1626 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 18.2377 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 106.31 | 106.31 | 0 | 1 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Bettamix 45078 VRS - Re-tension Wire Rope safety barriers | 1629 | VRS - Re-tension Wire Rope safety barriers | 267.4532 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1559.02 | 1559.02 | 0 | 1 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Bettamix 45078 VRS - Re-tension Wire Rope safety barriers | 1629 | VRS - Re-tension Wire Rope safety barriers | 67.5281 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 393.63 | 393.63 | 0 | 1 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 EB NS Bettamix 45078 VRS - Re-tension Wire Rope safety barriers | 1630 | VRS - Re-tension Wire Rope safety barriers | 4.5839 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 26.72 | 26.72 | 0 | 1 |  |  |  | 2000M62/141 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Bettamix 45078 VRS - Re-tension Wire Rope safety barriers | 1629 | VRS - Re-tension Wire Rope safety barriers | 152.9336 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 891.47 | 891.47 | 0 | 1 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1631 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 486.3503 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | WB | 199 | 63 | 136 | 0.31658 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE13 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1632 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE13 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1633 | Gullies - Emptying / clear covers | 625.3076 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 240 | 81 | 159 | 0.3375 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1634 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1635 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1631 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE13 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1632 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE13 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1633 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1634 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1635 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1633 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1636 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1633 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/141 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1634 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1635 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  |  |  | 2000M62/303 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1634 | Gullies - Emptying / clear covers | 84.9183 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1635 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1634 | Gullies - Emptying / clear covers | 169.8366 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 22 | 22 | 0 | 1 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1635 | Gullies - Emptying / clear covers | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 13 | 13 | 0 | 1 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE13 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1637 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 18.1585 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 737 | 737 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE13 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1638 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.3899 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 97 | 97 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE13 Closure 1 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1639 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 17.6411 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 716 | 716 | 0 | 1 |  |  |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE13 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1640 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 31.3893 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1274 | 1274 | 0 | 1 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE13 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1637 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 51.7899 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2102 | 2102 | 0 | 1 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE13 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1638 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 31.5618 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1281 | 1281 | 0 | 1 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE13 Closure 1 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1637 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 14.0439 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 570 | 570 | 0 | 1 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE13 Closure 1 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1638 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 24.3674 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 989 | 989 | 0 | 1 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE13 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1641 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | WB | 186 | 5 | 181 | 0.026882 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1642 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1643 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1644 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 101 | 0 | 101 | 0 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1643 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1641 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1642 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1641 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1642 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1643 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1641 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1642 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1644 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1643 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1644 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/141 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1643 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/141 | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1641 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1642 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1641 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1642 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1641 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 428.8804 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 20 | 20 | 0 | 1 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1642 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE13 Closure Amey 45078 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 1645 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 31.9592 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure | Lane 1 Closure | 1 |  |  | 2 times per year |  |  | On ServiceNow
YNE13 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1646 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 105.4655 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2200 | 2200 | 0 | 1 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1647 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1648 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1649 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1650 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 119.8471 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 5 | 5 | 0 | 1 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1651 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1652 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 107.8624 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 45 | 45 | 0 | 1 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1651 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 22 | 22 | 0 | 1 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1651 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 27 | 27 | 0 | 1 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1652 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 12 | 12 | 0 | 1 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1651 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 6 | 6 | 0 | 1 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1652 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 18 | 18 | 0 | 1 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1652 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/141 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1651 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1651 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1651 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/303 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1651 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2.3969 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1651 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 9 | 9 | 0 | 1 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1653 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1653 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 83.893 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 14 | 14 | 0 | 1 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1654 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/303 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1655 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1655 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 75.0338 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 17 | 17 | 0 | 1 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1655 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1655 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 17.655 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1656 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1657 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.5306 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 73.9 | 73.9 | 0 | 1 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1658 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.57539 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 27.78 | 27.78 | 0 | 1 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.1917 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 357 | 357 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1660 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.8744 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 486 | 486 | 0 | 1 |  |  |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1660 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 47.9325 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1679 | 1679 | 0 | 1 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.1299 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1791 | 1791 | 0 | 1 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 40.7383 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1427 | 1427 | 0 | 1 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1660 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9014 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 557 | 557 | 0 | 1 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.6477 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 408 | 408 | 0 | 1 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1660 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.328 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 642 | 642 | 0 | 1 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1660 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.9267 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 698 | 698 | 0 | 1 |  |  |  | 2000M62/141 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.4373 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 856 | 856 | 0 | 1 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.7953 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 203 | 203 | 0 | 1 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.54 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 124 | 124 | 0 | 1 |  |  |  | 2000M62/303 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.0808 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 213 | 213 | 0 | 1 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1659 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.6567 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1249 | 1249 | 0 | 1 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE13 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1661 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 11.7354 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 130.56 | 130.56 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1661 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 386.0063 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4294.43 | 4294.43 | 0 | 1 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1661 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 117.153 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1303.36 | 1303.36 | 0 | 1 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1661 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 187.8478 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2089.86 | 2089.86 | 0 | 1 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE13 Closure 1 WB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 1662 | Sweeping - Paved non-running areas - Full Sweep 01 | 186.8626 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 25088.25 | 25088.25 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1663 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 41.8506 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1746 | 1746 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE13 Closure 1 WB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1664 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 41.8506 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1746 | 1746 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Annually
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1665 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1042.5261 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 21747 | 21747 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1666 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.3852 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 488 | 488 | 0 | 1 |  |  |  | 2000M62/119 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE13 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1667 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.359 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 486 | 486 | 0 | 1 |  |  |  | 2000M62/131 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE13 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1667 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.9688 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1679 | 1679 | 0 | 1 |  |  |  | 2000M62/132 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1666 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 79.6189 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 6085 | 6085 | 0 | 1 |  |  |  | 2000M62/133 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1668 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 18.6715 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1427 | 1427 | 0 | 1 |  |  |  | 2000M62/134 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE13 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1667 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.288 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 557 | 557 | 0 | 1 |  |  |  | 2000M62/135 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1666 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 22.3875 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1711 | 1711 | 0 | 1 |  |  |  | 2000M62/136 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE13 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1669 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.4002 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 642 | 642 | 0 | 1 |  |  |  | 2000M62/138 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE13 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1667 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 9.133 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 698 | 698 | 0 | 1 |  |  |  | 2000M62/141 | YNE13: M62 J35-36 | YNE13 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1666 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 38.5468 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2946 | 2946 | 0 | 1 |  |  |  | 2000M62/143 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1668 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2.6561 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 203 | 203 | 0 | 1 |  |  |  | 2000M62/301 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1668 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1.6225 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 124 | 124 | 0 | 1 |  |  |  | 2000M62/303 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1668 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2.787 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 213 | 213 | 0 | 1 |  |  |  | 2000M62/305 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE13 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1668 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 16.3425 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1249 | 1249 | 0 | 1 |  |  |  | 2000M62/307 | YNE13: M62 J35-36 | YNE13 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE14 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1670 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 136.5521 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 795.98 | 795.98 | 0 | 1 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1671 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 47.2386 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 275.36 | 275.36 | 0 | 1 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1670 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 26.172 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 152.56 | 152.56 | 0 | 1 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1670 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 0.22988 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1.34 | 1.34 | 0 | 1 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1670 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 40.4949 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 236.05 | 236.05 | 0 | 1 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1671 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 202.2085 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1178.7 | 1178.7 | 0 | 1 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1672 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 59.695 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 347.97 | 347.97 | 0 | 1 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1671 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3.2012 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 18.66 | 18.66 | 0 | 1 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1672 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.786 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 16.24 | 16.24 | 0 | 1 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1670 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 6.2582 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 36.48 | 36.48 | 0 | 1 |  |  |  | 2000M62/153 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1670 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 51.0625 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 297.65 | 297.65 | 0 | 1 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1671 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 3.5082 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 20.45 | 20.45 | 0 | 1 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1672 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 88.3734 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 515.14 | 515.14 | 0 | 1 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1671 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 47.3913 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 276.25 | 276.25 | 0 | 1 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Bettamix 45078 VRS - Re-tension Wire Rope safety barriers | 1673 | VRS - Re-tension Wire Rope safety barriers | 9.2329 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 53.82 | 53.82 | 0 | 1 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Bettamix 45078 VRS - Re-tension Wire Rope safety barriers | 1674 | VRS - Re-tension Wire Rope safety barriers | 91.8027 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 535.13 | 535.13 | 0 | 1 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Bettamix 45078 VRS - Re-tension Wire Rope safety barriers | 1674 | VRS - Re-tension Wire Rope safety barriers | 171.324 | 4.2.2.2 | A40003 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 998.67 | 998.67 | 0 | 1 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1675 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 422 | 0 | 422 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1676 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1677 | Gullies - Emptying / clear covers | 69.4786 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | WB | 176 | 9 | 167 | 0.051136 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1678 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1675 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1676 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1677 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1675 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1675 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1676 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1677 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1677 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1675 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/153 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1675 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1676 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1677 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1677 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1678 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1679 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 104 | 0 | 104 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1680 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1681 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 343.1043 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-01-31 | Subject to roadspace approval | 43dys | WB | 135 | 16 | 119 | 0.11852 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1679 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1680 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1681 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1682 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1679 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1680 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1679 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1680 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1681 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1682 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1681 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1680 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/153 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1679 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1680 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1681 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1681 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1682 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE14 Closure Amey 45078 BC - Lamps (LED) for Illuminated Signs and Bollards | 1683 | BC - Lamps (LED) for Illuminated Signs and Bollards | 29.9618 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE14 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1684 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 105.5134 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2201 | 2201 | 0 | 1 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1685 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1686 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1687 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 25 | 25 | 0 | 1 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1689 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 20 | 20 | 0 | 1 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 7 | 7 | 0 | 1 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1689 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 13 | 13 | 0 | 1 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1689 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 69.5113 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 29 | 29 | 0 | 1 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1689 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/153 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1688 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 15 | 15 | 0 | 1 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1689 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1689 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1690 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 12 | 12 | 0 | 1 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1691 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1691 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 47.9388 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 8 | 8 | 0 | 1 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1691 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1690 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11.9847 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1692 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 7 | 7 | 0 | 1 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1693 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.9532 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 94.3 | 94.3 | 0 | 1 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1694 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.7638 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 181.72 | 181.72 | 0 | 1 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1695 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 48.6462 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1704 | 1704 | 0 | 1 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1696 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.6452 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 513 | 513 | 0 | 1 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1695 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.1559 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 671 | 671 | 0 | 1 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1696 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.0449 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 527 | 527 | 0 | 1 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1695 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.6705 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 654 | 654 | 0 | 1 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1695 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.6021 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1142 | 1142 | 0 | 1 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1696 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 52.4145 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1836 | 1836 | 0 | 1 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1696 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.6918 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 970 | 970 | 0 | 1 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1695 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.0767 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 388 | 388 | 0 | 1 |  |  |  | 2000M62/153 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1695 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.1909 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 392 | 392 | 0 | 1 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1696 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9585 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 559 | 559 | 0 | 1 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1696 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.6444 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 548 | 548 | 0 | 1 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE14 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1697 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 143.4912 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1596.38 | 1596.38 | 0 | 1 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1697 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 150.1121 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1670.04 | 1670.04 | 0 | 1 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1697 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 21.6516 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 240.88 | 240.88 | 0 | 1 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1697 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 75.3823 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 838.65 | 838.65 | 0 | 1 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE14 Closure 1 EB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 1698 | Sweeping - Paved non-running areas - Full Sweep 01 | 67.7936 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 9102 | 9102 | 0 | 1 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE14 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1699 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 34.4441 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1437 | 1437 | 0 | 1 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE14 Closure 1 EB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1700 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 34.4441 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1437 | 1437 | 0 | 1 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually
YNE14 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1701 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 826.226 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 17235 | 17235 | 0 | 1 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE14 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1702 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 22.2959 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1704 | 1704 | 0 | 1 |  |  |  | 2000M62/137 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE14 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1703 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.7123 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 513 | 513 | 0 | 1 |  |  |  | 2000M62/142 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE14 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1704 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.7797 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 671 | 671 | 0 | 1 |  |  |  | 2000M62/144 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE14 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1705 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 27.7914 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 2124 | 2124 | 0 | 1 |  |  |  | 2000M62/145 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE14 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1702 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.5572 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 654 | 654 | 0 | 1 |  |  |  | 2000M62/147 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE14 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1702 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.9425 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 1142 | 1142 | 0 | 1 |  |  |  | 2000M62/150 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE14 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1705 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 45.8741 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 3506 | 3506 | 0 | 1 |  |  |  | 2000M62/151 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE14 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1705 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.8453 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1211 | 1211 | 0 | 1 |  |  |  | 2000M62/152 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE14 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1702 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.0768 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 388 | 388 | 0 | 1 |  |  |  | 2000M62/153 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE14 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1704 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.1291 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | EB | 392 | 392 | 0 | 1 |  |  |  | 2000M62/154 | YNE14: M62 J36-37 | YNE14 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE14 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1705 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.2921 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 1398 | 1398 | 0 | 1 |  |  |  | 2000M62/155 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE14 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1703 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.1703 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | WB | 548 | 548 | 0 | 1 |  |  |  | 2000M62/158 | YNE14: M62 J36-37 | YNE14 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE15 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1706 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.6728 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 15.58 | 15.58 | 0 | 1 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1707 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 130.6987 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 761.86 | 761.86 | 0 | 1 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1708 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 157.8108 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 919.9 | 919.9 | 0 | 1 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1706 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 2.9902 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 17.43 | 17.43 | 0 | 1 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 EB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1709 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 7.6632 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 44.67 | 44.67 | 0 | 1 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1706 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 30.0594 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 175.22 | 175.22 | 0 | 1 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1707 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 13.2335 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 77.14 | 77.14 | 0 | 1 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1708 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 63.2358 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 368.61 | 368.61 | 0 | 1 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1707 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 98.7763 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 575.78 | 575.78 | 0 | 1 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1708 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 134.2636 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 782.64 | 782.64 | 0 | 1 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1706 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 7.3733 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 42.98 | 42.98 | 0 | 1 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1710 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 147.8985 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 862.12 | 862.12 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1710 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 126.18 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 735.52 | 735.52 | 0 | 1 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 EB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1711 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 13.5561 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 79.02 | 79.02 | 0 | 1 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE15 Closure 2 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1712 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 135.1642 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 787.89 | 787.89 | 0 | 1 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1713 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 132.7625 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 773.89 | 773.89 | 0 | 1 |  |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1710 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 39.3661 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 229.47 | 229.47 | 0 | 1 |  |  |  | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 2 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1712 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 291.383 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1698.51 | 1698.51 | 0 | 1 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1714 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 262.0922 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1527.77 | 1527.77 | 0 | 1 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1714 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 132.5343 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 772.56 | 772.56 | 0 | 1 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1714 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 171.2176 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 998.05 | 998.05 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB OS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1715 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 87.7421 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 511.46 | 511.46 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1714 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 38.613 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 225.08 | 225.08 | 0 | 1 |  |  |  | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 EB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1710 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 32.3187 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 188.39 | 188.39 | 0 | 1 |  |  |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB NS Bettamix 45078 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1707 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers | 1.9214 | 4.2.2.1 | A40002 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 11.2 | 11.2 | 0 | 1 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1716 | Gullies - Emptying / clear covers | 108.0779 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-06-30 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 340 | 14 | 326 | 0.041176 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1717 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 | 1 gully in closure |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45815775
YNE15 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1718 | Gullies - Emptying / clear covers | 131.2374 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-06-30 | 2024-01-31 | Subject to roadspace approval | 43dys | WB | 350 | 17 | 333 | 0.048571 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1719 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 | 1 gully in closure |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45815775
YNE15 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1716 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1718 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1719 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 | 1 gully in closure |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45815775
YNE15 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1716 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1716 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1718 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1719 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 | 1 gully in closure |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45815775
YNE15 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1718 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1716 | Gullies - Emptying / clear covers | 679.3465 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB | 0 | 88 | -88 | 0 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1720 | Gullies - Emptying / clear covers | 486.3503 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 63 | 63 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 2 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1721 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-06-01 | 2023-06-30 | 2023-11-30 |  | 43dys | WB | 270 | 0 | 270 | 0 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 172/6 | 168/2 | 45816419 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1722 | Gullies - Emptying / clear covers | 679.3465 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 88 | 88 | 0 | 1 | All gullies on the near side |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45815775
YNE15 Closure 3 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1720 | Gullies - Emptying / clear covers | 1127.0976 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-06-30 | 2023-12-31 |  | 43dys | EB | 209 | 146 | 63 | 0.69856 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years |  |  | 45815775
YNE15 Closure 2 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1723 | Gullies - Emptying / clear covers | 841.4633 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-06-01 | 2023-06-30 | 2023-11-30 |  | 43dys | EB | 251 | 109 | 142 | 0.43426 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 168/2 | 172/8 | 45816419 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1724 | Gullies - Emptying / clear covers | 7.7198 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE15 Closure 2 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1721 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1722 | Gullies - Emptying / clear covers | 470.9106 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 61 | 61 | 0 | 1 | All gullies on the near side |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years |  |  | 45815775
YNE15 Closure 3 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1720 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 2 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1723 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1725 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1725 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1725 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1726 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1725 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1726 | Gullies - Emptying / clear covers | 15.4397 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/185 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1720 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 1 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1718 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1720 | Gullies - Emptying / clear covers | 30.8794 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 EB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1720 | Gullies - Emptying / clear covers | 38.5992 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 5 | 5 | 0 | 1 |  |  |  | 2000M62/194 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB NS Enviroflow 45078 Gullies - Emptying / clear covers | 1725 | Gullies - Emptying / clear covers | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB OS Enviroflow 45078 Gullies - Emptying / clear covers | 1726 | Gullies - Emptying / clear covers | 23.1595 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years
YNE15 Closure 3 WB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1727 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/196 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE15 Closure 1 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1728 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 9.8307 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 399 | 399 | 0 | 1 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 1 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1729 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 6.406 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 260 | 260 | 0 | 1 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1730 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 8.451 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 343 | 343 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1731 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.4392 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 99 | 99 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 2 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1732 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 11.3583 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 461 | 461 | 0 | 1 |  |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1733 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 58.7379 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 2384 | 2384 | 0 | 1 |  |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1730 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 16.9512 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 688 | 688 | 0 | 1 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1731 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.5409 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 509 | 509 | 0 | 1 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 2 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1734 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 30.2067 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1226 | 1226 | 0 | 1 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1735 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 12.4917 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 507 | 507 | 0 | 1 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 2 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1732 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 15.5715 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 632 | 632 | 0 | 1 |  |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1733 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 32.7937 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1331 | 1331 | 0 | 1 |  |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1730 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0.24638 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 |  |  |  | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1731 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.5393 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 306 | 306 | 0 | 1 |  |  |  | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 2 EB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1734 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 9.8307 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 399 | 399 | 0 | 1 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1735 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 7.7118 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 313 | 313 | 0 | 1 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1736 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.6176 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 228 | 228 | 0 | 1 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1737 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 47.6753 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1935 | 1935 | 0 | 1 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1737 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 20.647 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 838 | 838 | 0 | 1 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 WB NS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1736 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 21.189 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 860 | 860 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1737 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1.9464 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 79 | 79 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1737 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 5.1001 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 207 | 207 | 0 | 1 |  |  |  | 2000M62/185 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 3 WB OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 1737 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2.1435 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 87 | 87 | 0 | 1 |  |  |  | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE15 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1738 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-06-30 | 2024-01-31 | Subject to roadspace approval | 43dys | EB | 64 | 5 | 59 | 0.078125 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1739 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 | THERE WAS 22 CATCHPIT IN TOTAL IN THE W/B SIDE, ONLY 2 CATCHPITS WERE ON MAP FUNCTION WHICH GOT COMPLETED AND THE OTHER 22 GOT EMPTIED AND LOGGED ON PAPER (SEE IMAGES ON THE EMAIL) |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1740 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 | THERE WAS 22 CATCHPIT IN TOTAL IN THE W/B SIDE, ONLY 2 CATCHPITS WERE ON MAP FUNCTION WHICH GOT COMPLETED AND THE OTHER 22 GOT EMPTIED AND LOGGED ON PAPER (SEE IMAGES ON THE EMAIL) |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1739 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 214.4402 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 | THERE WAS 22 CATCHPIT IN TOTAL IN THE W/B SIDE, ONLY 2 CATCHPITS WERE ON MAP FUNCTION WHICH GOT COMPLETED AND THE OTHER 22 GOT EMPTIED AND LOGGED ON PAPER (SEE IMAGES ON THE EMAIL) |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1740 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 150.1081 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 7 | 7 | 0 | 1 | THERE WAS 22 CATCHPIT IN TOTAL IN THE W/B SIDE, ONLY 2 CATCHPITS WERE ON MAP FUNCTION WHICH GOT COMPLETED AND THE OTHER 22 GOT EMPTIED AND LOGGED ON PAPER (SEE IMAGES ON THE EMAIL) |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1738 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1739 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 5 | 5 | 0 | 1 | THERE WAS 22 CATCHPIT IN TOTAL IN THE W/B SIDE, ONLY 2 CATCHPITS WERE ON MAP FUNCTION WHICH GOT COMPLETED AND THE OTHER 22 GOT EMPTIED AND LOGGED ON PAPER (SEE IMAGES ON THE EMAIL) |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1739 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 | THERE WAS 22 CATCHPIT IN TOTAL IN THE W/B SIDE, ONLY 2 CATCHPITS WERE ON MAP FUNCTION WHICH GOT COMPLETED AND THE OTHER 22 GOT EMPTIED AND LOGGED ON PAPER (SEE IMAGES ON THE EMAIL) |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 1 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1741 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 493.2124 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-06-30 | 2024-01-31 | Subject to roadspace approval | 43dys | WB | 91 | 23 | 68 | 0.25275 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1740 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 2 | 2 | 0 | 1 | THERE WAS 22 CATCHPIT IN TOTAL IN THE W/B SIDE, ONLY 2 CATCHPITS WERE ON MAP FUNCTION WHICH GOT COMPLETED AND THE OTHER 22 GOT EMPTIED AND LOGGED ON PAPER (SEE IMAGES ON THE EMAIL) |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 1 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1740 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 343.1043 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 16 | 16 | 0 | 1 | THERE WAS 22 CATCHPIT IN TOTAL IN THE W/B SIDE, ONLY 2 CATCHPITS WERE ON MAP FUNCTION WHICH GOT COMPLETED AND THE OTHER 22 GOT EMPTIED AND LOGGED ON PAPER (SEE IMAGES ON THE EMAIL) |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 1 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1738 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 1 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1739 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1742 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1743 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 2 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1744 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 729.0966 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-06-01 | 2023-06-30 | 2023-11-30 |  | 43dys | WB | 62 | 34 | 28 | 0.54839 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 172/6 | 168/2 | 45815991 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1745 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 686.2086 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 32 | 32 | 0 | 1 | no catchpits2 in the e/b side of the closure. 6 x men x 3 gully carts. 28 catchpits in the w/b side of the closure. 6 x men x 3 gully carts |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 3 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1742 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-06-30 | 2023-12-31 |  | 43dys | EB | 19 | 4 | 15 | 0.21053 | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. |  | 1/12: Cancelled due to -6 degree forecasts. Yellow warning issues. | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 3 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1743 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 2 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1746 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 664.7646 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | 2023-12-13 | 2023-12 | 2023-12-14 | 2023-06-01 | 2023-06-30 | 2023-11-30 |  | 43dys | EB | 54 | 31 | 23 | 0.57407 |  | Y | Closure cancelled on safety grounds due to Severe Weather warning for snow and ice conditions - planned for December | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 168/2 | 172/8 | 45815991 | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1747 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 85.7761 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 2 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1744 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1745 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 471.7684 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 22 | 22 | 0 | 1 | no catchpits2 in the e/b side of the closure. 6 x men x 3 gully carts. 28 catchpits in the w/b side of the closure. 6 x men x 3 gully carts |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 2 EB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1746 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1747 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 42.888 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 | no catchpits2 in the e/b side of the closure. 6 x men x 3 gully carts. 28 catchpits in the w/b side of the closure. 6 x men x 3 gully carts |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45815956
YNE15 Closure 3 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1748 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1749 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 128.6641 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 6 | -6 | 0 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1748 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1749 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 107.2201 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 WB NS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1748 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1749 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 64.3321 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 3 | -3 | 0 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1749 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1749 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/185 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 EB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1743 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 21.444 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure 3 WB OS Enviroflow 45078 Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 1749 | Catch Pits - Clear vegetation around frames, Clean, empty catch pits - ILM | 0 | 4.3.4 | A40013 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB | 0 | 0 | 0 | 0 |  |  |  | 2000M62/196 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years
YNE15 Closure Amey 45078 Electrical Testing - Network cabling and electrical components | 1750 | Electrical Testing - Network cabling and electrical components | 460.2129 | 4.5.9 | A40044 |  | 0 | Amey | 1300 - Lighting | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys |  | 24 | 24 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure | Lane 1 Closure | 1 |  |  | Every 6 years
YNE15 Closure Amey 45078 Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 1751 | Fixed Text Message Signs - Check, clean and grease where required motor assemblies and rotate prisms | 15.9796 | 4.6.7 | ART012 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure | Lane 1 Closure | 1 |  |  | 2 times per year |  |  | On ServiceNow
YNE15 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1752 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 285.5717 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 5957 | 5957 | 0 | 1 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1753 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | EB |  |  | 0 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1754 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1755 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 43dys | WB |  |  | 0 | 0 |  |  |  |  | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1756 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 95.8777 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1757 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 11 | 11 | 0 | 1 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1758 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 14 | 14 | 0 | 1 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1757 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 22 | 22 | 0 | 1 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1758 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 67.1144 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 28 | 28 | 0 | 1 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1757 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1757 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 13 | 13 | 0 | 1 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1758 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1758 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 18 | 18 | 0 | 1 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1757 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 30 | 30 | 0 | 1 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 15 | 15 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 2 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1760 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 74.3052 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 31 | 31 | 0 | 1 |  |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 13 | 13 | 0 | 1 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 2 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1761 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 24 | 24 | 0 | 1 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1760 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 24 | 24 | 0 | 1 |  |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1761 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 32 | 32 | 0 | 1 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1762 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 83.893 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 35 | 35 | 0 | 1 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1762 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 12 | 12 | 0 | 1 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1762 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 11 | 11 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1762 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 6 | 6 | 0 | 1 |  |  |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1758 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 8 | 8 | 0 | 1 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1757 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 100.6716 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 42 | 42 | 0 | 1 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 EB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1759 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 10 | 10 | 0 | 1 |  |  |  | 2000M62/194 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1762 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 5 | 5 | 0 | 1 |  |  |  | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1762 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 8 | 8 | 0 | 1 |  |  |  | 2000M62/196 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1763 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 101.87 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 6 | 6 | 0 | 2.8333 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1764 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured |  | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 17 | 17 | 0 | 1 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1763 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 191.7554 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 32 | 32 | 0 | 1 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1763 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 179.7707 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 30 | 30 | 0 | 1 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1765 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 4 | 4 | 0 | 1 |  |  |  | 2000M62/196 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1766 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 57.3788 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 13 | 13 | 0 | 1 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1766 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1766 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1767 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1767 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1768 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1767 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1768 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2 | 2 | 0 | 1 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1767 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1767 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1 | 1 | 0 | 1 |  |  |  | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1769 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.11102 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 5.36 | 5.36 | 0 | 1 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1769 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.3865 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 115.22 | 115.22 | 0 | 1 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 2 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1770 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.8322 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 136.74 | 136.74 | 0 | 1 |  |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1771 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.1707 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 56.52 | 56.52 | 0 | 1 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1770 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.1794 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 56.94 | 56.94 | 0 | 1 |  |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1772 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5302 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 544 | 544 | 0 | 1 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1773 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.6379 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 828 | 828 | 0 | 1 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1772 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 44.5067 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1559 | 1559 | 0 | 1 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1773 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 47.3615 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1659 | 1659 | 0 | 1 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1772 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5302 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 544 | 544 | 0 | 1 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1772 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.8533 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1396 | 1396 | 0 | 1 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1773 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.2186 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 428 | 428 | 0 | 1 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1773 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.7106 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1391 | 1391 | 0 | 1 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1772 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 63.6054 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2228 | 2228 | 0 | 1 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1774 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.7734 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1148 | 1148 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 2 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1775 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 63.6911 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 2231 | 2231 | 0 | 1 |  |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1774 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.8704 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 661 | 661 | 0 | 1 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 2 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1776 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.5866 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1807 | 1807 | 0 | 1 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1775 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.6152 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1808 | 1808 | 0 | 1 |  |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1774 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.9666 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 209 | 209 | 0 | 1 |  |  |  | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 2 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1776 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.7579 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1813 | 1813 | 0 | 1 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1777 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.5581 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1806 | 1806 | 0 | 1 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1777 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.9503 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 909 | 909 | 0 | 1 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1777 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.8932 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 907 | 907 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1777 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.8238 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 204 | 204 | 0 | 1 |  |  |  | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1777 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 4.7105 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 165 | 165 | 0 | 1 |  |  |  | 2000M62/185 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1774 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.7627 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 377 | 377 | 0 | 1 |  |  |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1773 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.8435 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 590 | 590 | 0 | 1 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1772 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.3328 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 432 | 432 | 0 | 1 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1774 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.5066 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 333 | 333 | 0 | 1 |  |  |  | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 EB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1774 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 7.8793 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 276 | 276 | 0 | 1 |  |  |  | 2000M62/194 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1777 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.416 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 540 | 540 | 0 | 1 |  |  |  | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 3 WB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1777 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.1615 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 426 | 426 | 0 | 1 |  |  |  | 2000M62/196 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE15 Closure 1 EB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1778 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 479.247 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 5331.76 | 5331.76 | 0 | 1 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1779 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 29.8473 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 332.06 | 332.06 | 0 | 1 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1778 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 72.2247 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 803.52 | 803.52 | 0 | 1 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1779 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 76.2138 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 847.9 | 847.9 | 0 | 1 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1779 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 292.6118 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 3255.39 | 3255.39 | 0 | 1 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 3 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1780 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 423.7339 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 4714.16 | 4714.16 | 0 | 1 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 3 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1780 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 313.7412 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 3490.46 | 3490.46 | 0 | 1 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 3 WB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 1780 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 519.8222 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 5783.17 | 5783.17 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 1 EB NS CGS 45078 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 1781 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 44.6835 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 809 | 809 | 0 | 1 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE15 Closure 2 EB NS CGS 45078 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1782 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 11.0466 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 160 | 160 | 0 | 1 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 1 EB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 1783 | Sweeping - Paved non-running areas - Full Sweep 01 | 24.7795 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 3326.9091 | 3326.9091 | 0 | 1 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year
YNE15 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1784 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 367.3314 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 15325 | 15325 | 0 | 1 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 1 EB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1785 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 367.3314 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 15325 | 15325 | 0 | 1 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | Annually
YNE15 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1786 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 690.5111 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 14404 | 14404 | 0 | 1 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1787 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.1179 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 544 | 544 | 0 | 1 |  |  |  | 2000M62/156 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE15 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1788 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 10.8339 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 828 | 828 | 0 | 1 |  |  |  | 2000M62/160 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE15 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1789 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 90.165 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 6891 | 6891 | 0 | 1 |  |  |  | 2000M62/162 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1790 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 26.0512 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1991 | 1991 | 0 | 1 |  |  |  | 2000M62/164 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1789 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.1179 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 544 | 544 | 0 | 1 |  |  |  | 2000M62/165 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1789 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 28.7727 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2199 | 2199 | 0 | 1 |  |  |  | 2000M62/166 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1790 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.6958 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1276 | 1276 | 0 | 1 |  |  |  | 2000M62/167 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1790 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 60.7904 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 4646 | 4646 | 0 | 1 |  |  |  | 2000M62/169 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1789 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 29.1522 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 2228 | 2228 | 0 | 1 |  |  |  | 2000M62/170 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 3 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1791 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.021 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1148 | 1148 | 0 | 1 |  |  |  | 2000M62/171 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 2 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1792 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 29.1914 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 2231 | 2231 | 0 | 1 |  |  |  | 2000M62/172 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1791 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.6488 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 661 | 661 | 0 | 1 |  |  |  | 2000M62/173 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 2 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1793 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6436 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1807 | 1807 | 0 | 1 |  |  |  | 2000M62/174 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 2 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1792 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6567 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 1808 | 1808 | 0 | 1 |  |  |  | 2000M62/175 | YNE15: M62 J37-38 | YNE15 Closure 2 WB NS | Lane 1 Closure | 1 |  |  | Annually | 172/6 | 168/2 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1791 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.7347 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 209 | 209 | 0 | 1 |  |  |  | 2000M62/176 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 2 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1793 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.7352 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 1814 | 1814 | 0 | 1 |  |  |  | 2000M62/177 | YNE15: M62 J37-38 | YNE15 Closure 2 EB NS | Lane 1 Closure | 1 |  |  | Annually | 168/2 | 172/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE15 Closure 3 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1794 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 85.3107 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 6520 | 6520 | 0 | 1 |  |  |  | 2000M62/178 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 3 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1794 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 57.5585 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 4399 | 4399 | 0 | 1 |  |  |  | 2000M62/179 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 3 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1794 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 87.535 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 6690 | 6690 | 0 | 1 |  |  |  | 2000M62/181 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 3 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1794 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.6692 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 204 | 204 | 0 | 1 |  |  |  | 2000M62/183 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 3 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1794 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.1589 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 165 | 165 | 0 | 1 |  |  |  | 2000M62/185 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 3 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1791 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.9328 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 377 | 377 | 0 | 1 |  |  |  | 2000M62/187 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 1 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1788 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.7198 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 590 | 590 | 0 | 1 |  |  |  | 2000M62/188 | YNE15: M62 J37-38 | YNE15 Closure 1 WB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE15 Closure 1 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1787 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.6525 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 432 | 432 | 0 | 1 |  |  |  | 2000M62/190 | YNE15: M62 J37-38 | YNE15 Closure 1 EB NS | Lane 1 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE15 Closure 3 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1791 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.3571 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 333 | 333 | 0 | 1 |  |  |  | 2000M62/192 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 3 EB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1791 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 3.6113 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | EB | 276 | 276 | 0 | 1 |  |  |  | 2000M62/194 | YNE15: M62 J37-38 | YNE15 Closure 3 EB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 3 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1794 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.0656 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 540 | 540 | 0 | 1 |  |  |  | 2000M62/195 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE15 Closure 3 WB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1794 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.574 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 43dys | WB | 426 | 426 | 0 | 1 |  |  |  | 2000M62/196 | YNE15: M62 J37-38 | YNE15 Closure 3 WB NS | Lane 1 Closure | 1 |  |  | Annually
YNE26 Closure 1 EB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1795 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 56.2133 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | CW | 1357 | 1357 | 0 | 1 |  |  |  | 2000A1033/201 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1795 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 143.6609 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 3468 | 3468 | 0 | 1 |  |  |  | 2000A1033/203 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 EB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1795 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 106.6686 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | CW | 2575 | 2575 | 0 | 1 |  |  |  | 2000A1033/205 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE26 Closure 1 WB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1796 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 19.1382 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 462 | 462 | 0 | 1 |  |  |  | 2000A1033/313 | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 EB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1797 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 13.6287 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 329 | 329 | 0 | 1 |  |  |  | 2000A1033/207 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 EB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1797 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 55.7577 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | CW | 1346 | 1346 | 0 | 1 |  |  |  | 2000A1033/209 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 6 times per year (Mar - Oct)
YNE27 Closure 1 WB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1798 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 8.2435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 199 | 199 | 0 | 1 |  |  |  | 2000A1033/311 | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 EB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1799 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 320.0887 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 7727 | 7727 | 0 | 1 |  |  |  | 2000A1033/211 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 EB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1799 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 107.0829 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | CW | 2585 | 2585 | 0 | 1 |  |  |  | 2000A1033/213 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 EB NS | Lane 1 Closure | 2 | No |  | 6 times per year (Mar - Oct)
YNE28 Closure 1 WB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1800 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 344.9435 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 8327 | 8327 | 0 | 1 |  |  |  | 2000A1033/309 | YNE28: A1033 Marfleet - Somerden | YNE28 Closure 1 WB NS | Lane 1 Closure | 2 | No |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1801 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 18.144 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 438 | 438 | 0 | 1 |  |  |  | 2000A1033/215 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1801 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 159.5265 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 3851 | 3851 | 0 | 1 |  |  |  | 2000A1033/217 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 EB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1801 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 247.3469 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 5971 | 5971 | 0 | 1 |  |  |  | 2000A1033/219 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 EB NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1802 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 277.3384 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 6695 | 6695 | 0 | 1 |  |  |  | 2000A1033/302 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1802 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 16.6113 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 401 | 401 | 0 | 1 |  |  |  | 2000A1033/303 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE29 Closure 1 WB NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 1802 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 45.7743 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 1105 | 1105 | 0 | 1 |  |  |  | 2000A1033/305 | YNE29: A1033 Somerden - Salt End | YNE29 Closure 1 WB NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE61 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1803 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 77.1985 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1000 | 1000 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1803 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 7.7198 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 100 | 100 | 0 | 1 |  |  |  | 4400M1/420 | YNE61: M1 J30-31 | YNE61 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1803 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 54.0389 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 700 | 700 | 0 | 1 |  |  |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1804 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 56.3549 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 730 | 730 | 0 | 1 |  |  |  | 4400M1/926 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1804 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 50.951 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 660 | 660 | 0 | 1 |  |  |  | 4400M1/928 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1804 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 30.1074 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 390 | 390 | 0 | 1 |  |  |  | 4400M1/930 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1804 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 128.9214 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1670 | 1670 | 0 | 1 |  |  |  | 4400M1/932 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1804 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 14.6677 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 190 | 190 | 0 | 1 |  |  |  | 4400M1/934 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1804 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 16.9837 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 220 | 220 | 0 | 1 |  |  |  | 4400M1/940 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1804 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2.316 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 30 | 30 | 0 | 1 |  |  |  | 4400M1/942 | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE61 Closure Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1805 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1792.9128 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 68 | 68 | 0 | 1 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1806 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  | 0 | 0 | 0 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 6 years |  |  | On ServiceNow
YNE61 Closure 1 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1807 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 8 | 0 | 8 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure 1 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1808 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 8 | 0 | 8 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure 1 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 1809 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 8 | 0 | 8 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1810 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1305.1351 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 33 | 33 | 0 | 1 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 1811 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 10 | 10 | 0 | 1 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE61 Closure Vaisala 45078 Meteorological sites - Clean fog sensors | 1812 | Meteorological sites - Clean fog sensors | 0 | 4.6.6 | ART009 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 41dys |  | 1 | 1 | 0 | 1 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 1813 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 11 | 0 | 11 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE61 Closure Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 1814 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 11 | 0 | 11 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 1815 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 11 | 0 | 11 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Clean camera lens | 1816 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 41dys |  | 8 | 0 | 8 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check camera functionality | 1817 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 41dys |  | 8 | 0 | 8 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 1818 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 41dys |  | 8 | 0 | 8 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE61 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1819 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 189.694 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 3957 | 3957 | 0 | 1 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1820 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1821 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1822 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  |  |  |  | YNE61: M1 J30-31 | YNE61 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1823 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 575.2661 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 24 | 24 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1823 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  |  |  | 4400M1/412 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1823 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  |  |  | 4400M1/414 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1823 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 287.6331 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 12 | 12 | 0 | 1 |  |  |  | 4400M1/420 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1823 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 695.1133 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 29 | 29 | 0 | 1 |  |  |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1823 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 119.8471 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  |  |  | 4400M1/424 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1823 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 239.6942 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 10 | 10 | 0 | 1 |  |  |  | 4400M1/470 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1823 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 119.8471 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  |  |  | 4400M1/473 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1823 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 239.6942 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 10 | 10 | 0 | 1 |  |  |  | 4400M1/476 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1823 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 167.786 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 7 | 7 | 0 | 1 |  |  |  | 4400M1/479 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 103.0685 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 43 | 43 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 12 | 12 | 0 | 1 |  |  |  | 4400M1/412 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  |  |  | 4400M1/414 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  |  |  | 4400M1/416 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  |  |  | 4400M1/418 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 98.2746 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 41 | 41 | 0 | 1 |  |  |  | 4400M1/420 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 91.0838 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 38 | 38 | 0 | 1 |  |  |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 22 | 22 | 0 | 1 |  |  |  | 4400M1/424 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  |  |  | 4400M1/426 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 16 | 16 | 0 | 1 |  |  |  | 4400M1/470 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  |  |  | 4400M1/473 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  |  |  | 4400M1/476 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1824 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 8 | 8 | 0 | 1 |  |  |  | 4400M1/479 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 5 | 5 | 0 | 1 |  |  |  | 4400M1/926 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 13 | 13 | 0 | 1 |  |  |  | 4400M1/928 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 27 | 27 | 0 | 1 |  |  |  | 4400M1/930 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 79.0991 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 33 | 33 | 0 | 1 |  |  |  | 4400M1/932 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4400M1/934 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 3 | 3 | 0 | 1 |  |  |  | 4400M1/936 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 3 | 3 | 0 | 1 |  |  |  | 4400M1/938 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 9 | 9 | 0 | 1 |  |  |  | 4400M1/940 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 30 | 30 | 0 | 1 |  |  |  | 4400M1/942 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 11 | 11 | 0 | 1 |  |  |  | 4400M1/988 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 2 | 2 | 0 | 1 |  |  |  | 4400M1/991 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 2 | 2 | 0 | 1 |  |  |  | 4400M1/994 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1825 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4400M1/997 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1826 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 41.9465 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 7 | 7 | 0 | 1 |  |  |  | 4400M1/479 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1827 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4400M1/988 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1827 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  |  |  | 4400M1/997 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 180.964 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 41 | 41 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 14 | 14 | 0 | 1 |  |  |  | 4400M1/412 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  |  |  | 4400M1/414 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 163.309 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 37 | 37 | 0 | 1 |  |  |  | 4400M1/420 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 269.2391 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 61 | 61 | 0 | 1 |  |  |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 79.4476 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 18 | 18 | 0 | 1 |  |  |  | 4400M1/424 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 123.5852 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 28 | 28 | 0 | 1 |  |  |  | 4400M1/470 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 7 | 7 | 0 | 1 |  |  |  | 4400M1/473 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 83.8614 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 19 | 19 | 0 | 1 |  |  |  | 4400M1/476 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1828 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 83.8614 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 19 | 19 | 0 | 1 |  |  |  | 4400M1/479 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.9803 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 143.89 | 143.89 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.1634 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 56.17 | 56.17 | 0 | 1 |  |  |  | 4400M1/412 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.3074 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 63.12 | 63.12 | 0 | 1 |  |  |  | 4400M1/414 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 7.7881 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 376.01 | 376.01 | 0 | 1 |  |  |  | 4400M1/420 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 10.4867 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 506.3 | 506.3 | 0 | 1 |  |  |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.84817 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 40.95 | 40.95 | 0 | 1 |  |  |  | 4400M1/424 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.2129 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 155.12 | 155.12 | 0 | 1 |  |  |  | 4400M1/426 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.4378 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 117.7 | 117.7 | 0 | 1 |  |  |  | 4400M1/470 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.61226 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 29.56 | 29.56 | 0 | 1 |  |  |  | 4400M1/476 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1829 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.29142 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 14.07 | 14.07 | 0 | 1 |  |  |  | 4400M1/479 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.1651 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 56.25 | 56.25 | 0 | 1 |  |  |  | 4400M1/926 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.3239 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 112.2 | 112.2 | 0 | 1 |  |  |  | 4400M1/928 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.0553 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 244.07 | 244.07 | 0 | 1 |  |  |  | 4400M1/930 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 8.9407 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 431.66 | 431.66 | 0 | 1 |  |  |  | 4400M1/932 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.23301 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 11.25 | 11.25 | 0 | 1 |  |  |  | 4400M1/934 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.16984 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 8.2 | 8.2 | 0 | 1 |  |  |  | 4400M1/936 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.849 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 40.99 | 40.99 | 0 | 1 |  |  |  | 4400M1/938 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.9608 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 94.67 | 94.67 | 0 | 1 |  |  |  | 4400M1/940 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 5.2506 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 253.5 | 253.5 | 0 | 1 |  |  |  | 4400M1/942 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.0766 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 51.98 | 51.98 | 0 | 1 |  |  |  | 4400M1/988 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.3202 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 63.74 | 63.74 | 0 | 1 |  |  |  | 4400M1/991 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.0447 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 98.72 | 98.72 | 0 | 1 |  |  |  | 4400M1/994 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1830 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.2129 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 58.56 | 58.56 | 0 | 1 |  |  |  | 4400M1/997 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.3109 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1377 | 1377 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.2741 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 500 | 500 | 0 | 1 |  |  |  | 4400M1/412 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 5.9095 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 207 | 207 | 0 | 1 |  |  |  | 4400M1/414 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.7912 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 378 | 378 | 0 | 1 |  |  |  | 4400M1/416 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.6175 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 477 | 477 | 0 | 1 |  |  |  | 4400M1/418 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 49.0744 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1719 | 1719 | 0 | 1 |  |  |  | 4400M1/420 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.5678 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1386 | 1386 | 0 | 1 |  |  |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.2423 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 639 | 639 | 0 | 1 |  |  |  | 4400M1/424 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.4715 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 612 | 612 | 0 | 1 |  |  |  | 4400M1/426 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.1591 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 531 | 531 | 0 | 1 |  |  |  | 4400M1/470 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.1036 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 459 | 459 | 0 | 1 |  |  |  | 4400M1/473 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9299 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 558 | 558 | 0 | 1 |  |  |  | 4400M1/476 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1831 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.5302 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 544 | 544 | 0 | 1 |  |  |  | 4400M1/479 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.6134 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 652 | 652 | 0 | 1 |  |  |  | 4400M1/926 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.1004 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 599 | 599 | 0 | 1 |  |  |  | 4400M1/928 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 39.3109 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1377 | 1377 | 0 | 1 |  |  |  | 4400M1/930 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.5295 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1805 | 1805 | 0 | 1 |  |  |  | 4400M1/932 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.562 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 405 | 405 | 0 | 1 |  |  |  | 4400M1/934 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.9894 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 455 | 455 | 0 | 1 |  |  |  | 4400M1/936 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 3.9111 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 137 | 137 | 0 | 1 |  |  |  | 4400M1/938 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.2741 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 500 | 500 | 0 | 1 |  |  |  | 4400M1/940 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 41.1094 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1440 | 1440 | 0 | 1 |  |  |  | 4400M1/942 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.8435 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 590 | 590 | 0 | 1 |  |  |  | 4400M1/988 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.8467 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 450 | 450 | 0 | 1 |  |  |  | 4400M1/991 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.4438 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 576 | 576 | 0 | 1 |  |  |  | 4400M1/994 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1832 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.1036 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 459 | 459 | 0 | 1 |  |  |  | 4400M1/997 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 1833 | Sweeping - Paved non-running areas - Full Sweep 01 | 170.1097 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 22839 | 22839 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1834 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 320.6989 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 13379.5 | 13379.5 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1835 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 320.6989 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 13379.5 | 13379.5 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1836 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1037.4925 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 21642 | 21642 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1837 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.0173 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1377 | 1377 | 0 | 1 |  |  |  | 4400M1/410 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1837 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.5422 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 500 | 500 | 0 | 1 |  |  |  | 4400M1/412 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1837 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.7085 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 207 | 207 | 0 | 1 |  |  |  | 4400M1/414 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1837 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.9459 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 378 | 378 | 0 | 1 |  |  |  | 4400M1/416 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1837 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.2413 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 477 | 477 | 0 | 1 |  |  |  | 4400M1/418 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1837 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 22.4922 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1719 | 1719 | 0 | 1 |  |  |  | 4400M1/420 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1837 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.1351 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1386 | 1386 | 0 | 1 |  |  |  | 4400M1/422 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1837 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.361 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 639 | 639 | 0 | 1 |  |  |  | 4400M1/424 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1837 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.0077 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 612 | 612 | 0 | 1 |  |  |  | 4400M1/426 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1838 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.9478 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 531 | 531 | 0 | 1 |  |  |  | 4400M1/470 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1838 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.0058 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 459 | 459 | 0 | 1 |  |  |  | 4400M1/473 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1838 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.3011 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 558 | 558 | 0 | 1 |  |  |  | 4400M1/476 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE61 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1838 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.1179 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 544 | 544 | 0 | 1 |  |  |  | 4400M1/479 | YNE61: M1 J30-31 | YNE61 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1839 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.5311 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 652 | 652 | 0 | 1 |  |  |  | 4400M1/926 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1839 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.8376 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 599 | 599 | 0 | 1 |  |  |  | 4400M1/928 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1839 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.0173 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1377 | 1377 | 0 | 1 |  |  |  | 4400M1/930 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1839 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.6174 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1805 | 1805 | 0 | 1 |  |  |  | 4400M1/932 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1839 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.2992 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 405 | 405 | 0 | 1 |  |  |  | 4400M1/934 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1839 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.9534 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 455 | 455 | 0 | 1 |  |  |  | 4400M1/936 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1839 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1.7926 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 137 | 137 | 0 | 1 |  |  |  | 4400M1/938 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1839 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.5422 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 500 | 500 | 0 | 1 |  |  |  | 4400M1/940 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1839 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 18.8416 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1440 | 1440 | 0 | 1 |  |  |  | 4400M1/942 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1840 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.7198 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 590 | 590 | 0 | 1 |  |  |  | 4400M1/988 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1840 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.888 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 450 | 450 | 0 | 1 |  |  |  | 4400M1/991 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1840 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.5366 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 576 | 576 | 0 | 1 |  |  |  | 4400M1/994 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE61 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1840 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.0058 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 459 | 459 | 0 | 1 |  |  |  | 4400M1/997 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 244/8 | 238/8 |  | 20:00 | 6:00 | Night Shift | Approved | Please upload la consent for diversion
YNE62 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1841 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 24 | 0 | 24 | 0 |  | N |  | 4400M1/434 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE62 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1842 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 47.863 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 620 | 620 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE62 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1842 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 37.0553 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 480 | 480 | 0 | 1 |  | N |  | 4400M1/430 | YNE62: M1 J31-32 | YNE62 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE62 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1843 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 37.0553 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 480 | 480 | 0 | 1 |  | N |  | 4400M1/920 | YNE62: M1 J31-32 | YNE62 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE62 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1843 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 32.4234 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 420 | 420 | 0 | 1 |  | N |  | 4400M1/922 | YNE62: M1 J31-32 | YNE62 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE62 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1843 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 23.1595 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 300 | 300 | 0 | 1 |  | N |  | 4400M1/924 | YNE62: M1 J31-32 | YNE62 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE62 Closure Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1844 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 580.06 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 22 | 22 | 0 | 1 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure 1 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1845 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 4 | 0 | 4 | 0 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure 1 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1846 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 4 | 0 | 4 | 0 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure 1 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 1847 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 4 | 0 | 4 | 0 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1848 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 395.4955 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 10 | 10 | 0 | 1 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 1849 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 6 | 6 | 0 | 1 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE62 Closure Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 1850 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 6 | 0 | 6 | 0 |  | Y |  |  | YNE62: M1 J31-32 | YNE62 Closure | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE62 Closure Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 1851 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 6 | 0 | 6 | 0 |  | Y |  |  | YNE62: M1 J31-32 | YNE62 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 1852 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 6 | 0 | 6 | 0 |  | Y |  |  | YNE62: M1 J31-32 | YNE62 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure 1 NB NS Amey 45078 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1853 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure 1 NB NS Amey 45078 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1854 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 21dys |  | 0 | 0 | 0 | 0 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Clean camera lens | 1855 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 21dys |  | 5 | 0 | 5 | 0 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check camera functionality | 1856 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 21dys |  | 5 | 0 | 5 | 0 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 1857 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 21dys |  | 5 | 0 | 5 | 0 |  | N |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE62 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1858 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 1517 | 0 | 1517 | 0 |  | Y |  |  | YNE62: M1 J31-32 | YNE62 Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1859 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1860 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1861 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  |  |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1862 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/430 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1862 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 23 | 0 | 23 | 0 |  | Y |  | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1863 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1863 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 67.1144 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 28 | 28 | 0 | 1 |  | N |  | 4400M1/430 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1863 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400M1/432 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1863 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 12 | 12 | 0 | 1 |  | N |  | 4400M1/434 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1863 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 15 | 15 | 0 | 1 |  | N |  | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1864 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 9 | 0 | 9 | 0 |  | Y |  | 4400M1/918 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1864 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 13 | 0 | 13 | 0 |  | Y |  | 4400M1/922 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1864 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/924 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1864 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 6 | 0 | 6 | 0 |  | Y |  | 4400M1/985 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1865 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 95.8777 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 16 | 16 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1866 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 12 | 0 | 12 | 0 |  | Y |  | 4400M1/985 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1867 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 105.9301 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 24 | 24 | 0 | 1 |  | N |  | 4400M1/430 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1867 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/434 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1867 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 189.7915 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 43 | 43 | 0 | 1 |  | N |  | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1868 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/985 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1869 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.5267 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 73.71 | 73.71 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1869 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 3.5277 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 170.32 | 170.32 | 0 | 1 |  | N |  | 4400M1/430 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1869 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 6.7856 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 327.61 | 327.61 | 0 | 1 |  | N |  | 4400M1/432 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1869 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.8759 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 90.57 | 90.57 | 0 | 1 |  | N |  | 4400M1/434 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1869 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.3198 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 15.44 | 15.44 | 0 | 1 |  | N |  | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1870 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 26.85 | 0 | 26.85 | 0 |  | Y |  | 4400M1/920 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1870 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 324.82 | 0 | 324.82 | 0 |  | Y |  | 4400M1/922 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1870 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 61.74 | 0 | 61.74 | 0 |  | Y |  | 4400M1/924 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1870 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 144.37 | 0 | 144.37 | 0 |  | Y |  | 4400M1/985 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1871 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.1518 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 846 | 846 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1871 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.8394 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 765 | 765 | 0 | 1 |  | N |  | 4400M1/430 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1871 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.4478 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 401 | 401 | 0 | 1 |  | N |  | 4400M1/432 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1871 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.2423 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 639 | 639 | 0 | 1 |  | N |  | 4400M1/434 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1871 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.496 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 788 | 788 | 0 | 1 |  | N |  | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1872 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 513 | 0 | 513 | 0 |  | Y |  | 4400M1/918 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1872 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 509 | 0 | 509 | 0 |  | Y |  | 4400M1/920 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1872 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 846 | 0 | 846 | 0 |  | Y |  | 4400M1/922 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1872 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 792 | 0 | 792 | 0 |  | Y |  | 4400M1/924 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1872 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 729 | 0 | 729 | 0 |  | Y |  | 4400M1/985 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE62 Closure 1 SB NS CGS 45078 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1873 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4493 | 0 | 4493 | 0 |  | Y |  | 4400M1/922 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE62 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 1874 | Sweeping - Paved non-running areas - Full Sweep 01 | 48.9087 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6566.5 | 6566.5 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE62 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1875 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 54.5424 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2275.5 | 2275.5 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE62 Closure 1 NB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1876 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 54.5424 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2275.5 | 2275.5 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually
YNE62 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1877 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 589.6957 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 12301 | 12301 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE62 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1878 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.0695 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 846 | 846 | 0 | 1 |  | N |  | 4400M1/428 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE62 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1878 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.0096 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 765 | 765 | 0 | 1 |  | N |  | 4400M1/430 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE62 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1878 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.2469 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 401 | 401 | 0 | 1 |  | N |  | 4400M1/432 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE62 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1878 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.361 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 639 | 639 | 0 | 1 |  | N |  | 4400M1/434 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE62 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1879 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 10.3106 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 788 | 788 | 0 | 1 |  | N |  | 4400M1/482 | YNE62: M1 J31-32 | YNE62 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE62 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1880 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 513 | 0 | 513 | 0 |  | Y |  | 4400M1/918 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE62 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1880 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 509 | 0 | 509 | 0 |  | Y |  | 4400M1/920 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE62 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1880 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 846 | 0 | 846 | 0 |  | Y |  | 4400M1/922 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE62 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1880 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 792 | 0 | 792 | 0 |  | Y |  | 4400M1/924 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE62 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1881 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 729 | 0 | 729 | 0 |  | Y |  | 4400M1/985 | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE63 Closure 1 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1882 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3 | 0 | 3 | 0 |  | N |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE63 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1883 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 53 | 0 | 53 | 0 |  | Y |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE63 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1884 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 7.2265 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 93.61 | 93.61 | 0 | 1 |  | N |  | 4400M1/442 | YNE63: M1 J32-33 | YNE63 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE63 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1885 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 55.9589 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 724.87 | 724.87 | 0 | 1 |  | N |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE63 Closure 1 NB NS Amey 45078 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 1886 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 2 | 0 | 2 | 0 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 1887 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 2 | 0 | 2 | 0 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1888 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2357.6482 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 6 | 6 | 0 | 1 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 6 years |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1889 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 870.0901 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 37 | 33 | 4 | 0.89189 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1890 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 71.9083 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 7 | 6 | 1 | 0.85714 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1891 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 71.9083 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 7 | 6 | 1 | 0.85714 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 1892 | CCTV Masts - Check mast breaking system | 383.5108 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 7 | 6 | 1 | 0.85714 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1893 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 237.2973 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 7 | 6 | 1 | 0.85714 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 1894 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 5 | 5 | 0 | 1 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE63 Closure Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 1895 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 9 | 0 | 9 | 0 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE63 Closure Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 1896 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 9 | 0 | 9 | 0 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 1897 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 9 | 0 | 9 | 0 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Clean camera lens | 1898 | CCTV PTZ Cameras - Clean camera lens | 83.893 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 41dys |  | 7 | 7 | 0 | 1 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check camera functionality | 1899 | CCTV PTZ Cameras - Check camera functionality | 83.893 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 41dys |  | 7 | 7 | 0 | 1 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 1900 | CCTV PTZ Cameras - Check data and power supplies | 83.893 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 41dys |  | 7 | 7 | 0 | 1 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE63 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1901 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 2799 | 0 | 2799 | 0 |  | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1902 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1903 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1904 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE63: M1 J32-33 | YNE63 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1905 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1905 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/438 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1906 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/910 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1906 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 23 | 0 | 23 | 0 |  | Y |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1906 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/976 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1906 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/978 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1907 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 16 | 0 | 16 | 0 |  | Y |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1907 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400M1/438 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1907 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 29 | 0 | 29 | 0 |  | Y |  | 4400M1/440 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1907 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 18 | 0 | 18 | 0 |  | Y |  | 4400M1/442 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1907 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 28 | 0 | 28 | 0 |  | Y |  | 4400M1/490 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1908 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/910 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1908 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 42 | 0 | 42 | 0 |  | Y |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1908 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4 | 0 | 4 | 0 |  | Y |  | 4400M1/914 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1908 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 17 | 0 | 17 | 0 |  | Y |  | 4400M1/916 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1908 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 32 | 0 | 32 | 0 |  | Y |  | 4400M1/976 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1908 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 8 | 0 | 8 | 0 |  | Y |  | 4400M1/978 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1909 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 4400M1/490 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1910 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 26 | 0 | 26 | 0 |  | Y |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1910 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 17 | 0 | 17 | 0 |  | Y |  | 4400M1/438 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1910 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/440 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1910 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400M1/490 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1911 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 8 | 0 | 8 | 0 |  | Y |  | 4400M1/910 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1911 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 45 | 0 | 45 | 0 |  | Y |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1911 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4400M1/914 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1911 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4400M1/916 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1911 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 27 | 0 | 27 | 0 |  | Y |  | 4400M1/976 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1911 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 16 | 0 | 16 | 0 |  | Y |  | 4400M1/978 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1912 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 124.37 | 0 | 124.37 | 0 |  | Y |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1912 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 93.43 | 0 | 93.43 | 0 |  | Y |  | 4400M1/440 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1912 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 49.49 | 0 | 49.49 | 0 |  | Y |  | 4400M1/442 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1912 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 64.02 | 0 | 64.02 | 0 |  | Y |  | 4400M1/490 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1913 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 27.52 | 0 | 27.52 | 0 |  | Y |  | 4400M1/910 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1913 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 168.25 | 0 | 168.25 | 0 |  | Y |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1913 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 80.97 | 0 | 80.97 | 0 |  | Y |  | 4400M1/916 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1913 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 38.99 | 0 | 38.99 | 0 |  | Y |  | 4400M1/976 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1913 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 97.71 | 0 | 97.71 | 0 |  | Y |  | 4400M1/978 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE63 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1914 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1487 | 0 | 1487 | 0 |  | Y |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1914 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 972 | 0 | 972 | 0 |  | Y |  | 4400M1/438 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1914 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 864 | 0 | 864 | 0 |  | Y |  | 4400M1/440 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1914 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1292 | 0 | 1292 | 0 |  | Y |  | 4400M1/442 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1914 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1242 | 0 | 1242 | 0 |  | Y |  | 4400M1/490 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1915 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 801 | 0 | 801 | 0 |  | Y |  | 4400M1/910 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1915 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1501 | 0 | 1501 | 0 |  | Y |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1915 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1291 | 0 | 1291 | 0 |  | Y |  | 4400M1/914 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1915 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1053 | 0 | 1053 | 0 |  | Y |  | 4400M1/916 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1915 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1494 | 0 | 1494 | 0 |  | Y |  | 4400M1/976 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1915 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2691 | 0 | 2691 | 0 |  | Y |  | 4400M1/978 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE63 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 1916 | Sweeping - Paved non-running areas - Full Sweep 01 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 11731.25 | 0 | 11731.25 | 0 |  | Y |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE63 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1917 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 6795 | 0 | 6795 | 0 |  | Y |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE63 Closure 1 NB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 1918 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 162.8722 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6795 | 6795 | 0 | 1 |  | N |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually
YNE63 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1919 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 0 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 18677 | 0 | 18677 | 0 |  | Y |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE63 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1920 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 1487 | 0 | 1487 | 0 |  | Y |  | 4400M1/436 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE63 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1920 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 972 | 0 | 972 | 0 |  | Y |  | 4400M1/438 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE63 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1920 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 864 | 0 | 864 | 0 |  | Y |  | 4400M1/440 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE63 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1920 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 1292 | 0 | 1292 | 0 |  | Y |  | 4400M1/442 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE63 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1921 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1242 | 0 | 1242 | 0 |  | Y |  | 4400M1/490 | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE63 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1922 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 801 | 0 | 801 | 0 |  | Y |  | 4400M1/910 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE63 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1922 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1501 | 0 | 1501 | 0 |  | Y |  | 4400M1/912 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE63 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1922 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1291 | 0 | 1291 | 0 |  | Y |  | 4400M1/914 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE63 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1922 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1053 | 0 | 1053 | 0 |  | Y |  | 4400M1/916 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE63 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1923 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1494 | 0 | 1494 | 0 |  | Y |  | 4400M1/976 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE63 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1923 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2691 | 0 | 2691 | 0 |  | Y |  | 4400M1/978 | YNE63: M1 J32-33 | YNE63 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE64 Closure 1 SB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1924 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | SB | 0 | 0 | 0 | 0 |  | Y |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE64 Closure 1 SB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1925 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | SB | 0 | 0 | 0 | 0 |  | Y |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE64 Closure 1 SB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1924 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 285.6343 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 39 | 37 | 2 | 0.94872 |  | Y |  | 4400M1/970 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE64 Closure 1 SB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1925 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | SB | 0 | 0 | 0 | 0 |  | Y |  | 4400M1/970 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE64 Closure 1 SB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 1925 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | SB | 0 | 0 | 0 | 0 |  | Y |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE64 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1926 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 150 | 0 | 150 | 0 |  | Y |  | 4400M1/444 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE64 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1926 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1250 | 0 | 1250 | 0 |  | Y |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE64 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1926 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 80 | 0 | 80 | 0 |  | Y |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE64 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1926 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 500 | 0 | 500 | 0 |  | Y |  | 4400M1/450 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE64 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1927 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 95.53 | 0 | 95.53 | 0 |  | Y |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE64 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1928 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 6 | 0 | 6 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 6 years |  |  | On ServiceNow
YNE64 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1929 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 790.991 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 35 | 30 | 5 | 0.85714 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE64 Closure 1 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1930 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 8 | 0 | 8 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE64 Closure 1 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1931 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 8 | 0 | 8 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE64 Closure 1 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 1932 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 8 | 0 | 8 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE64 Closure 1 NB NS Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1933 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 316.3964 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 9 | 8 | 1 | 0.88889 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE64 Closure 1 NB NS Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 1934 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE64 Closure Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 1935 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 9 | 0 | 9 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE64 Closure Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 1936 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 9 | 0 | 9 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE64 Closure Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 1937 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 9 | 0 | 9 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE64 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Clean camera lens | 1938 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 8 | 0 | 8 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE64 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check camera functionality | 1939 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 8 | 0 | 8 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE64 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 1940 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 8 | 0 | 8 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE64Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1941 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 2463 | 0 | 2463 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1942 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1943 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1944 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1945 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 15 | 0 | 15 | 0 |  | Y |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1945 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1945 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 20 | 0 | 20 | 0 |  | Y |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1946 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1946 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 15 | 0 | 15 | 0 |  | Y |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1947 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 4400M1/444 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1947 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 34 | 0 | 34 | 0 |  | Y |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1947 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 15 | 0 | 15 | 0 |  | Y |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1947 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/450 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1947 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400M1/452 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1947 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 13 | 0 | 13 | 0 |  | Y |  | 4400M1/493 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1947 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 28 | 0 | 28 | 0 |  | Y |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1948 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 8 | 0 | 8 | 0 |  | Y |  | 4400M1/902 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1948 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 33 | 0 | 33 | 0 |  | Y |  | 4400M1/906 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1948 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 34 | 0 | 34 | 0 |  | Y |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1948 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 9 | 0 | 9 | 0 |  | Y |  | 4400M1/970 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1948 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 38 | 0 | 38 | 0 |  | Y |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1949 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 31 | 0 | 31 | 0 |  | Y |  | 4400M1/444 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1949 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 6 | 0 | 6 | 0 |  | Y |  | 4400M1/493 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1949 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 6 | 0 | 6 | 0 |  | Y |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1950 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2 | 0 | 2 | 0 |  | Y |  | 4400M1/970 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1951 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4400M1/444 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1951 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 33 | 0 | 33 | 0 |  | Y |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1951 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 18 | 0 | 18 | 0 |  | Y |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1951 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400M1/450 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1951 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/452 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1951 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400M1/493 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1951 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 47 | 0 | 47 | 0 |  | Y |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1952 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4400M1/906 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1952 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 14 | 0 | 14 | 0 |  | Y |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 1952 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 38 | 0 | 38 | 0 |  | Y |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1953 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 6.16 | 0 | 6.16 | 0 |  | Y |  | 4400M1/444 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1953 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 169.5 | 0 | 169.5 | 0 |  | Y |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1953 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 18.82 | 0 | 18.82 | 0 |  | Y |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1953 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 40.17 | 0 | 40.17 | 0 |  | Y |  | 4400M1/452 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1953 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 26.21 | 0 | 26.21 | 0 |  | Y |  | 4400M1/493 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1953 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 115.42 | 0 | 115.42 | 0 |  | Y |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1954 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 39.94 | 0 | 39.94 | 0 |  | Y |  | 4400M1/902 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1954 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 116.51 | 0 | 116.51 | 0 |  | Y |  | 4400M1/906 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1954 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 49.87 | 0 | 49.87 | 0 |  | Y |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1954 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 25.89 | 0 | 25.89 | 0 |  | Y |  | 4400M1/970 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1954 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 45.5 | 0 | 45.5 | 0 |  | Y |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1955 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 543 | 0 | 543 | 0 |  | Y |  | 4400M1/444 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1955 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1422 | 0 | 1422 | 0 |  | Y |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1955 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 671 | 0 | 671 | 0 |  | Y |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1955 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 774 | 0 | 774 | 0 |  | Y |  | 4400M1/450 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1955 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 371 | 0 | 371 | 0 |  | Y |  | 4400M1/452 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1955 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 482 | 0 | 482 | 0 |  | Y |  | 4400M1/493 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1955 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1067 | 0 | 1067 | 0 |  | Y |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1956 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 363 | 0 | 363 | 0 |  | Y |  | 4400M1/902 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1956 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 552 | 0 | 552 | 0 |  | Y |  | 4400M1/904 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1956 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1624 | 0 | 1624 | 0 |  | Y |  | 4400M1/906 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1956 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1213 | 0 | 1213 | 0 |  | Y |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1956 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1670 | 0 | 1670 | 0 |  | Y |  | 4400M1/970 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1956 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2335 | 0 | 2335 | 0 |  | Y |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE64 Closure 1 NB NS CGS 45078 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 1957 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 148 | 0 | 148 | 0 |  | Y |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE64 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 1958 | Sweeping - Paved non-running areas - Full Sweep 01 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 10321.75 | 0 | 10321.75 | 0 |  | Y |  |  | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE64 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1959 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 543 | 0 | 543 | 0 |  | Y |  | 4400M1/444 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE64 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1959 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 1422 | 0 | 1422 | 0 |  | Y |  | 4400M1/446 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE64 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1959 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 671 | 0 | 671 | 0 |  | Y |  | 4400M1/448 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE64 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1959 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 774 | 0 | 774 | 0 |  | Y |  | 4400M1/450 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE64 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1959 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 371 | 0 | 371 | 0 |  | Y |  | 4400M1/452 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE64 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1960 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 482 | 0 | 482 | 0 |  | Y |  | 4400M1/493 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE64 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1960 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1067 | 0 | 1067 | 0 |  | Y |  | 4400M1/496 | YNE64: M1 J33-34 South | YNE64 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE64 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1961 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 362 | 0 | 362 | 0 |  | Y |  | 4400M1/902 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE64 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1961 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 552 | 0 | 552 | 0 |  | Y |  | 4400M1/904 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE64 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1961 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1624 | 0 | 1624 | 0 |  | Y |  | 4400M1/906 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE64 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1961 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1213 | 0 | 1213 | 0 |  | Y |  | 4400M1/908 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE64 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1962 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1670 | 0 | 1670 | 0 |  | Y |  | 4400M1/970 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE64 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 1962 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2335 | 0 | 2335 | 0 |  | Y |  | 4400M1/973 | YNE64: M1 J33-34 South | YNE64 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE65 Closure 1 NB NS Enviroflow 45078 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 1963 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 20 | 0 | 20 | 0 |  | Y |  | 4400M1/454 | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45931410
YNE65 Closure 1 SB NS Enviroflow 45078 LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 1964 | LDS - Cleaning, rodding, low pressure / high volume jetting and proving Combined Kerb & Drainage System 1 - ILM | 0 | 4.3.2.1 | A40007 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 54 | 0 | 54 | 0 |  | Y |  | 4400M1/900 | YNE65: M1 Tinsley | YNE65 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) |  |  | 45931410
YNE65 Closure 1 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1965 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE65 Closure 1 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1966 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE65 Closure 1 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 1967 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE65 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Clean camera lens | 1968 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE65 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check camera functionality | 1969 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE65 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 1970 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE65 Closure 1 NB NS Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 1971 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 20dys |  | 4 | 0 | 4 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE65 Closure Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 1972 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE65 Closure Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 1973 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE65 Closure Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 1974 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE65 Closure 1 NB NS Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1975 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE65 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1976 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 20dys |  | 5 | 0 | 5 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE65 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1977 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 468 | 0 | 468 | 0 |  | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE65 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1978 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE65 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1979 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE65 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 1980 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE65: M1 Tinsley | YNE65 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE65 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1981 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 10 | 0 | 10 | 0 |  | Y |  | 4400M1/454 | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE65 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 1982 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 9 | 0 | 9 | 0 |  | Y |  | 4400M1/900 | YNE65: M1 Tinsley | YNE65 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE65 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1983 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 6 | 0 | 6 | 0 |  | Y |  | 4400M1/454 | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE65 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 1984 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4 | 0 | 4 | 0 |  | Y |  | 4400M1/900 | YNE65: M1 Tinsley | YNE65 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE65 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1985 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 55.73 | 0 | 55.73 | 0 |  | Y |  | 4400M1/900 | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE65 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1986 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1054 | 0 | 1054 | 0 |  | Y |  | 4400M1/454 | YNE65: M1 Tinsley | YNE65 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE65 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 1987 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1054 | 0 | 1054 | 0 |  | Y |  | 4400M1/900 | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE65 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1988 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 1052 | 0 | 1052 | 0 |  | Y |  | 4400M1/454 | YNE65: M1 Tinsley | YNE65 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE65 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 1989 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1052 | 0 | 1052 | 0 |  | Y |  | 4400M1/900 | YNE65: M1 Tinsley | YNE65 Closure 1 SB NS | Lane 1 Closure | 1 | Yes |  | Annually
YNE66 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1990 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 120 | 0 | 120 | 0 |  | Y |  | 4400M1/500 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1990 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 280 | 0 | 280 | 0 |  | Y |  | 4400M1/502 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 1 NB NS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1991 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 892.27 | 0 | 892.27 | 0 |  | Y |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1990 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 713.28 | 0 | 713.28 | 0 |  | Y |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 2 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1992 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3162.04 | 0 | 3162.04 | 0 |  | Y |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 2 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1992 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 804.67 | 0 | 804.67 | 0 |  | Y |  | 4400M1/508 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 2 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1993 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 604.79 | 0 | 604.79 | 0 |  | Y |  | 4400M1/838 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE66 Closure 1 SB NS Amey 45078 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 1994 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 3 | 0 | 3 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Every 6 years |  |  | On ServiceNow
YNE66 Closure 1 SB NS Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1995 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 131.8318 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 9 | 5 | 4 | 0.55556 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE66 Closure 1 SB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 1996 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 3 | 0 | 3 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE66 Closure 1 SB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 1997 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 3 | 0 | 3 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE66 Closure 1 SB NS Amey 45078 CCTV Masts - Check mast breaking system | 1998 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 3 | 0 | 3 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE66 Closure 1 SB NS Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 1999 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 158.1982 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 4 | 4 | 0 | 1 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE66 Closure 1 SB NS Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2000 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE66 Closure 1 SB NS Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 2001 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 10 | 0 | 10 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE66 Closure 1 SB NS Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 2002 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 10 | 0 | 10 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE66 Closure 1 SB NS Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 2003 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 10 | 0 | 10 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE66 Closure 1 SB NS Amey 45078 CCTV PTZ Cameras - Clean camera lens | 2004 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 41dys |  | 4 | 0 | 4 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE66 Closure 1 SB NS Amey 45078 CCTV PTZ Cameras - Check camera functionality | 2005 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 41dys |  | 4 | 0 | 4 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE66 Closure 1 SB NS Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 2006 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 41dys |  | 4 | 0 | 4 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE66Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2007 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 468 | 0 | 468 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2008 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2009 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2010 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2011 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 20 | 0 | 20 | 0 |  | Y |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2012 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 20 | 0 | 20 | 0 |  | Y |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2011 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/560 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2011 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2011 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 15 | 0 | 15 | 0 |  | Y |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2013 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 30 | 0 | 30 | 0 |  | Y |  | 4400M1/500 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2013 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 37 | 0 | 37 | 0 |  | Y |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2014 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 33 | 0 | 33 | 0 |  | Y |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2014 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 9 | 0 | 9 | 0 |  | Y |  | 4400M1/508 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2013 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 18 | 0 | 18 | 0 |  | Y |  | 4400M1/560 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2013 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 8 | 0 | 8 | 0 |  | Y |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2013 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 8 | 0 | 8 | 0 |  | Y |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2015 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 8 | 0 | 8 | 0 |  | Y |  | 4400M1/838 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2015 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 21 | 0 | 21 | 0 |  | Y |  | 4400M1/840 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2015 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 19 | 0 | 19 | 0 |  | Y |  | 4400M1/842 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2016 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/844 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2016 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4 | 0 | 4 | 0 |  | Y |  | 4400M1/846 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2016 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 10 | 0 | 10 | 0 |  | Y |  | 4400M1/881 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2016 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 18 | 0 | 18 | 0 |  | Y |  | 4400M1/884 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2017 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2018 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/881 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2018 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 8 | 0 | 8 | 0 |  | Y |  | 4400M1/884 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2019 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 4400M1/500 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2019 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 57 | 0 | 57 | 0 |  | Y |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2020 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 47 | 0 | 47 | 0 |  | Y |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2020 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400M1/508 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2019 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/560 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2019 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 14 | 0 | 14 | 0 |  | Y |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2019 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 35 | 0 | 35 | 0 |  | Y |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2021 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 77.19 | 0 | 77.19 | 0 |  | Y |  | 4400M1/500 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2021 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 199.84 | 0 | 199.84 | 0 |  | Y |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2022 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 203.64 | 0 | 203.64 | 0 |  | Y |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2022 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 58.13 | 0 | 58.13 | 0 |  | Y |  | 4400M1/508 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2021 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3.13 | 0 | 3.13 | 0 |  | Y |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2021 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 52.03 | 0 | 52.03 | 0 |  | Y |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2023 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 12.06 | 0 | 12.06 | 0 |  | Y |  | 4400M1/838 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2023 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 92.11 | 0 | 92.11 | 0 |  | Y |  | 4400M1/840 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2023 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 125.45 | 0 | 125.45 | 0 |  | Y |  | 4400M1/842 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2024 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 44.61 | 0 | 44.61 | 0 |  | Y |  | 4400M1/846 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2024 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 27.79 | 0 | 27.79 | 0 |  | Y |  | 4400M1/884 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2025 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 324 | 0 | 324 | 0 |  | Y |  | 4400M1/500 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2025 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 279 | 0 | 279 | 0 |  | Y |  | 4400M1/502 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2025 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1602 | 0 | 1602 | 0 |  | Y |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2026 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1143 | 0 | 1143 | 0 |  | Y |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2026 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 736 | 0 | 736 | 0 |  | Y |  | 4400M1/508 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2025 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 162 | 0 | 162 | 0 |  | Y |  | 4400M1/560 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2025 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 432 | 0 | 432 | 0 |  | Y |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2025 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 689 | 0 | 689 | 0 |  | Y |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2027 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 729 | 0 | 729 | 0 |  | Y |  | 4400M1/838 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2027 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1125 | 0 | 1125 | 0 |  | Y |  | 4400M1/840 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 2 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2027 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 960 | 0 | 960 | 0 |  | Y |  | 4400M1/842 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2028 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 978 | 0 | 978 | 0 |  | Y |  | 4400M1/844 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2028 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 283 | 0 | 283 | 0 |  | Y |  | 4400M1/846 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2028 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 689 | 0 | 689 | 0 |  | Y |  | 4400M1/881 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2028 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1211 | 0 | 1211 | 0 |  | Y |  | 4400M1/884 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE66 Closure 1 NB NS CGS 45078 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 2029 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 0 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3196 | 0 | 3196 | 0 |  | Y |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 2030 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 410 | 0 | 410 | 0 |  | Y |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 2 NB NS CGS 45078 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 2031 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 130 | 0 | 130 | 0 |  | Y |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS CGS 45078 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 2030 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 42 | 0 | 42 | 0 |  | Y |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE66 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 2032 | Sweeping - Paved non-running areas - Full Sweep 01 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 5309.875 | 0 | 5309.875 | 0 |  | Y |  |  | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE66 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2033 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 324 | 0 | 324 | 0 |  | Y |  | 4400M1/500 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE66 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2033 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 279 | 0 | 279 | 0 |  | Y |  | 4400M1/502 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE66 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2033 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 1602 | 0 | 1602 | 0 |  | Y |  | 4400M1/504 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE66 Closure 2 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2034 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 1143 | 0 | 1143 | 0 |  | Y |  | 4400M1/506 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE66 Closure 2 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2034 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 736 | 0 | 736 | 0 |  | Y |  | 4400M1/508 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE66 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2035 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 162 | 0 | 162 | 0 |  | Y |  | 4400M1/560 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE66 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2035 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 432 | 0 | 432 | 0 |  | Y |  | 4400M1/562 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE66 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2035 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 689 | 0 | 689 | 0 |  | Y |  | 4400M1/567 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE66 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2036 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 729 | 0 | 729 | 0 |  | Y |  | 4400M1/838 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE66 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2036 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1125 | 0 | 1125 | 0 |  | Y |  | 4400M1/840 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE66 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2036 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 960 | 0 | 960 | 0 |  | Y |  | 4400M1/842 | YNE66: M1 J34 North - 35 | YNE66 Closure 2 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE66 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2037 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 978 | 0 | 978 | 0 |  | Y |  | 4400M1/844 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE66 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2037 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 283 | 0 | 283 | 0 |  | Y |  | 4400M1/846 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE66 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2038 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 689 | 0 | 689 | 0 |  | Y |  | 4400M1/881 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE66 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2038 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1211 | 0 | 1211 | 0 |  | Y |  | 4400M1/884 | YNE66: M1 J34 North - 35 | YNE66 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE67 Closure 2 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2039 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 316.5137 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 59 | 41 | 18 | 0.69492 |  | N |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE67 Closure 2 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2040 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | NB | 70 | 0 | 70 | 0 |  | Y |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE67 Closure 2 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2041 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 19.2996 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 250 | 250 | 0 | 1 |  | N |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE67 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2042 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 32.4234 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 420 | 420 | 0 | 1 |  | N |  | 4400M1/832 | YNE67: M1 J35-35a | YNE67 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE67 Closure 2 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2043 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 29.3354 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 380 | 380 | 0 | 1 |  | N |  | 4400M1/834 | YNE67: M1 J35-35a | YNE67 Closure 2 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE67 Closure 2 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2043 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 60.4927 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 783.6 | 783.6 | 0 | 1 |  | N |  | 4400M1/836 | YNE67: M1 J35-35a | YNE67 Closure 2 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE67 Closure 2 NB NS Amey 45078 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2044 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 785.8827 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | Every 6 years |  |  | On ServiceNow
YNE67 Closure 2 NB NS Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 2045 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 580.06 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 25 | 22 | 3 | 0.88 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE67 Closure 2 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2046 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 107.8624 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 10 | 9 | 1 | 0.9 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE67 Closure 2 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2047 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 107.8624 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 10 | 9 | 1 | 0.9 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE67 Closure 2 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 2048 | CCTV Masts - Check mast breaking system | 575.2661 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 10 | 9 | 1 | 0.9 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE67 Closure 2 NB NS Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2049 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 237.2973 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 9 | 6 | 3 | 0.66667 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE67 Closure 2 NB NS Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2050 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 4 | 4 | 0 | 1 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE67 Closure Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 2051 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 8 | 0 | 8 | 0 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE67 Closure Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 2052 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 8 | 0 | 8 | 0 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE67 Closure Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 2053 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 8 | 0 | 8 | 0 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE67 Closure 2 NB NS Amey 45078 CCTV PTZ Cameras - Clean camera lens | 2054 | CCTV PTZ Cameras - Clean camera lens | 107.8624 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 10 | 9 | 1 | 0.9 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE67 Closure 2 NB NS Amey 45078 CCTV PTZ Cameras - Check camera functionality | 2055 | CCTV PTZ Cameras - Check camera functionality | 107.8624 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 10 | 9 | 1 | 0.9 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE67 Closure 2 NB NS Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 2056 | CCTV PTZ Cameras - Check data and power supplies | 107.8624 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 10 | 9 | 1 | 0.9 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE67 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2057 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 2520 | 0 | 2520 | 0 |  | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2058 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2059 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2060 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  |  |  |  | YNE67: M1 J35-35a | YNE67 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2061 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 15 | 0 | 15 | 0 |  | Y |  | 4400M1/512 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2062 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 15 | 0 | 15 | 0 |  | Y |  | 4400M1/570 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2062 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 551.2967 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 23 | 23 | 0 | 1 |  | Y |  | 4400M1/573 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45836085
YNE67 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2063 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 4 | 0 | 4 | 0 |  | Y |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2063 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 28 | 0 | 28 | 0 |  | Y |  | 4400M1/512 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2063 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 10 | 0 | 10 | 0 |  | Y |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2064 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 13 | 0 | 13 | 0 |  | Y |  | 4400M1/570 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2064 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 22 | 22 | 0 | 1 |  | Y |  | 4400M1/573 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45842308
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2065 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/832 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2066 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 31 | 0 | 31 | 0 |  | Y |  | 4400M1/834 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2066 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 7 | 0 | 7 | 0 |  | Y |  | 4400M1/836 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2065 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 13 | 13 | 0 | 1 |  | Y |  | 4400M1/875 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45842308
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2065 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/878 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2067 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 11 | 0 | 11 | 0 |  | Y |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2068 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  | Y |  | 4400M1/573 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45842449
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2069 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 77.9006 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 13 | 13 | 0 | 1 |  | Y |  | 4400M1/875 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45842449
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2069 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4 | 0 | 4 | 0 |  | Y |  | 4400M1/878 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2070 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 30 | 0 | 30 | 0 |  | Y |  | 4400M1/512 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2070 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2071 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 36 | 0 | 36 | 0 |  | Y |  | 4400M1/570 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2071 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 57 | 0 | 57 | 0 |  | Y |  | 4400M1/573 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2072 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2 | 0 | 2 | 0 |  | Y |  | 4400M1/875 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2072 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/878 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2073 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 26.82 | 0 | 26.82 | 0 |  | Y |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2073 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 81.21 | 0 | 81.21 | 0 |  | Y |  | 4400M1/512 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2073 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 98.12 | 0 | 98.12 | 0 |  | Y |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2074 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 10.49 | 0 | 10.49 | 0 |  | Y |  | 4400M1/570 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2074 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 88.33 | 0 | 88.33 | 0 |  | Y |  | 4400M1/573 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2075 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 39.3 | 0 | 39.3 | 0 |  | Y |  | 4400M1/832 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2076 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 321.65 | 0 | 321.65 | 0 |  | Y |  | 4400M1/834 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2076 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 60.6 | 0 | 60.6 | 0 |  | Y |  | 4400M1/836 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2075 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 28.7 | 0 | 28.7 | 0 |  | Y |  | 4400M1/875 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2075 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1.11 | 0 | 1.11 | 0 |  | Y |  | 4400M1/878 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2077 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 540 | 0 | 540 | 0 |  | Y |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2077 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 853 | 0 | 853 | 0 |  | Y |  | 4400M1/512 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2077 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1157 | 0 | 1157 | 0 |  | Y |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2078 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 492 | 0 | 492 | 0 |  | Y |  | 4400M1/570 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2078 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.9129 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1293 | 1293 | 0 | 1 |  | Y |  | 4400M1/573 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45837422
YNE67 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2079 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 540 | 0 | 540 | 0 |  | Y |  | 4400M1/832 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2080 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1371 | 0 | 1371 | 0 |  | Y |  | 4400M1/834 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2080 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 635 | 0 | 635 | 0 |  | Y |  | 4400M1/836 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2079 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 46.3623 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1624 | 1624 | 0 | 1 |  | Y |  | 4400M1/875 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45837422
YNE67 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2079 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 581 | 0 | 581 | 0 |  | Y |  | 4400M1/878 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE67 Closure 2 SB NS CGS 45078 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 2081 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 0 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 293 | 0 | 293 | 0 |  | Y |  | 4400M1/834 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE67 Closure 2 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 2082 | Sweeping - Paved non-running areas - Full Sweep 01 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 4441.4286 | 0 | 4441.4286 | 0 |  | Y |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE67 Closure 2 NB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2083 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | NB | 5128.5 | 0 | 5128.5 | 0 |  | Y |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE67 Closure 2 NB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2084 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 122.9272 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5128.5 | 5128.5 | 0 | 1 |  | N |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually
YNE67 Closure 2 NB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 2085 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 0 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | NB | 22529 | 0 | 22529 | 0 |  | Y |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE67 Closure 2 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2086 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | NB | 540 | 0 | 540 | 0 |  | Y |  | 4400M1/510 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE67 Closure 2 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2086 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | NB | 853 | 0 | 853 | 0 |  | Y |  | 4400M1/512 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE67 Closure 2 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2086 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | NB | 1157 | 0 | 1157 | 0 |  | Y |  | 4400M1/514 | YNE67: M1 J35-35a | YNE67 Closure 2 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE67 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2087 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 492 | 0 | 492 | 0 |  | Y |  | 4400M1/570 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE67 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2087 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 16.9182 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1293 | 1293 | 0 | 1 |  | Y |  | 4400M1/573 | YNE67: M1 J35-35a | YNE67 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52037951
YNE67 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2088 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 540 | 0 | 540 | 0 |  | Y |  | 4400M1/832 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE67 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2089 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1371 | 0 | 1371 | 0 |  | Y |  | 4400M1/834 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE67 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2089 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 635 | 0 | 635 | 0 |  | Y |  | 4400M1/836 | YNE67: M1 J35-35a | YNE67 Closure 2 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually
YNE67 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2090 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 21.2492 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1624 | 1624 | 0 | 1 |  | Y |  | 4400M1/875 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 52037951
YNE67 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2090 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 581 | 0 | 581 | 0 |  | Y |  | 4400M1/878 | YNE67: M1 J35-35a | YNE67 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections)
YNE68 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2091 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2493.5105 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | NB | 337 | 323 | 14 | 0.95846 |  | N |  | 4400M1/233 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route |  |  | 45833259
YNE68 Closure 1 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2092 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 370.5526 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 48 | 48 | 0 | 1 |  | N |  | 4400M1/516 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE68 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2091 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 0 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys | NB | 0 | 0 | 0 | 0 |  | Y |  | 4400M1/516 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE68 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2093 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2.316 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 30 | 30 | 0 | 1 |  | Y |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE68 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2094 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  | 0 | 0 | 0 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 6 years |  |  | On ServiceNow
YNE68 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 2095 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 131.8318 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 5 | 5 | 0 | 1 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE68 Closure 1 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2096 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 1 | 0 | 1 | 0 | 6/12 tech not in closure | N |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | ServiceNow
YNE68 Closure 1 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2097 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 1 | 0 | 1 | 0 | 6/12 tech not in closure | N |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | ServiceNow
YNE68 Closure 1 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 2098 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 1 | 0 | 1 | 0 | 6/12 tech not in closure | N |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | ServiceNow
YNE68 Closure 1 NB NS Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2099 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 79.0991 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE68 Closure 1 NB NS Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2100 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE68 Closure Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 2101 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE68 Closure Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 2102 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE68 Closure Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 2103 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE68 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2104 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 1838 | 0 | 1838 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2105 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2106 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2107 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  | 0 | 0 | 0 |  | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2108 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 2 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2109 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2 | 0 | 2 | 0 |  | Y |  | 4400M1/114 | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2110 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 8 | 0 | 8 | 0 |  | Y |  | 4400M1/115 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2110 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 7 | 0 | 7 | 0 |  | Y |  | 4400M1/150 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2111 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 11 | 0 | 11 | 0 |  | Y |  | 4400M1/232 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2111 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4400M1/233 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2111 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 13 | 0 | 13 | 0 |  | Y |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2111 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/516 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2110 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 6 | 0 | 6 | 0 |  | Y |  | 4400M1/830 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2112 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/150 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2113 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 8 | 0 | 8 | 0 |  | Y |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2114 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4400M1/150 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2115 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3 | 0 | 3 | 0 |  | Y |  | 4400M1/232 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2115 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 7 | 0 | 7 | 0 |  | Y |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2115 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 6 | 0 | 6 | 0 |  | Y |  | 4400M1/516 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2116 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 17.26 | 0 | 17.26 | 0 |  | Y |  | 4400M1/150 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2117 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 9.88 | 0 | 9.88 | 0 |  | Y |  | 4400M1/233 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2117 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 13.86 | 0 | 13.86 | 0 |  | Y |  | 4400M1/516 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2116 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 54.69 | 0 | 54.69 | 0 |  | Y |  | 4400M1/830 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 2 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2118 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 585 | 0 | 585 | 0 |  | Y |  | 4400M1/114 | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2119 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 383 | 0 | 383 | 0 |  | Y |  | 4400M1/115 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2119 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 555 | 0 | 555 | 0 |  | Y |  | 4400M1/150 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2120 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 445 | 0 | 445 | 0 |  | Y |  | 4400M1/232 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2120 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 510 | 0 | 510 | 0 |  | Y |  | 4400M1/233 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2120 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 470 | 0 | 470 | 0 |  | Y |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2120 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 960 | 0 | 960 | 0 |  | Y |  | 4400M1/516 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2119 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 976 | 0 | 976 | 0 |  | Y |  | 4400M1/830 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE68 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2121 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 82.1201 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 913.61 | 913.61 | 0 | 1 |  | N |  | 4400M1/232 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2121 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 26.4533 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 294.3 | 294.3 | 0 | 1 |  | N |  | 4400M1/233 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE68 Closure 2 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 2122 | Sweeping - Paved non-running areas - Full Sweep 01 | 0 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 3000.1667 | 0 | 3000.1667 | 0 |  | Y |  | 4400M1/114 | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE68 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2123 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1056 | 0 | 1056 | 0 |  | Y |  | 4400M1/114 | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE68 Closure 2 SB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2124 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 25.3117 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1056 | 1056 | 0 | 1 |  | N |  | 4400M1/114 | YNE68: M1 J35a-36 | YNE68 Closure 2 SB OS | Lane 3 & 4 Closure | 1 |  |  | Annually
YNE68 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 2125 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 0 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 8315 | 0 | 8315 | 0 |  | Y |  | 4400M1/114 | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE68 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2126 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 585 | 0 | 585 | 0 |  | Y |  | 4400M1/114 | YNE68: M1 J35a-36 | YNE68 Closure 2 SB NS | Lane 1 & 2 Closure | 1 | No |  | Annually |  |  | 45819905
YNE68 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2127 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 383 | 0 | 383 | 0 |  | Y |  | 4400M1/115 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | No |  | Annually |  |  | 45819905
YNE68 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2128 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 555 | 0 | 555 | 0 |  | Y |  | 4400M1/150 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) |  |  | 45819905
YNE68 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2129 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 17.7687 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-07 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | NB | 1358 | 1358 | 0 | 1 |  | N |  | 4400M1/232 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | No |  | Annually |  |  | 45819905
YNE68 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2129 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.533 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-07 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | NB | 805 | 805 | 0 | 1 |  | N |  | 4400M1/233 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | No |  | Annually |  |  | 45819905
YNE68 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2130 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 470 | 0 | 470 | 0 |  | Y |  | 4400M1/260 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | No |  | 2 times per year (ILM Certain Sections) |  |  | 45819905
YNE68 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2129 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.5611 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | 2023-12-07 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | NB | 960 | 960 | 0 | 1 |  | N |  | 4400M1/516 | YNE68: M1 J35a-36 | YNE68 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | No |  | Annually |  |  | 45819905
YNE68 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2127 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 976 | 0 | 976 | 0 |  | Y |  | 4400M1/830 | YNE68: M1 J35a-36 | YNE68 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | No |  | Annually |  |  | 45819905
YNE69 Closure 1 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2131 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 293.3542 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 38 | 38 | 0 | 1 |  | N |  | 4400M1/234 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 2 & 3 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE69 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2132 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 13 | 13 | 0 | 1 |  | N |  | 4400M1/234 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE69 Closure 1 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2131 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 316.5137 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 41 | 41 | 0 | 1 |  | N |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 2 & 3 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE69 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2132 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 486.3503 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 63 | 63 | 0 | 1 |  | N |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE69 Closure 1 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2131 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 138.9572 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 18 | 18 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 2 & 3 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE69 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2132 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 764.2648 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 99 | 99 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE69 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2132 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 470.9106 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 61 | 61 | 0 | 1 |  | N |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE69 Closure 1 SB NS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2133 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 1.2807 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 16.59 | 16.59 | 0 | 1 |  | N |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 2134 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 474.5946 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 18 | 18 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE69 Closure 1 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2135 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 1 | 0 | 1 | 0 | 7/12 closure cancelled due to sweeper breakdown. No lighting / tech resource | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | ServiceNow
YNE69 Closure 1 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2136 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 1 | 0 | 1 | 0 | 7/12 closure cancelled due to sweeper breakdown. No lighting / tech resource | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | ServiceNow
YNE69 Closure 1 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 2137 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 1 | 0 | 1 | 0 | 7/12 closure cancelled due to sweeper breakdown. No lighting / tech resource | N |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually |  |  | ServiceNow
YNE69 Closure Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2138 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 593.2432 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 15 | 15 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE69 Closure Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2139 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 12 | 12 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE69Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2140 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 161.6977 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 3373 | 3373 | 0 | 1 |  | N |  |  | YNE69: M1 J36-37 | YNE69Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2141 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2142 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2143 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE69: M1 J36-37 | YNE69 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 SB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2144 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 23.9694 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2145 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2146 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/238 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2145 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2146 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2147 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 9 | 9 | 0 | 1 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 2 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2147 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 55.1297 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 23 | 23 | 0 | 1 |  | N |  | 4400M1/109 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2148 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 12 | 12 | 0 | 1 |  | N |  | 4400M1/110 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2148 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 19 | 19 | 0 | 1 |  | N |  | 4400M1/111 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2148 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 57.5266 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 24 | 24 | 0 | 1 |  | N |  | 4400M1/112 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2148 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4400M1/113 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 2 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2147 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/148 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2148 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45.5419 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 19 | 19 | 0 | 1 |  | N |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 18 | 18 | 0 | 1 |  | N |  | 4400M1/234 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 20 | 20 | 0 | 1 |  | N |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 13 | 13 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2150 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76.7022 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 32 | 32 | 0 | 1 |  | N |  | 4400M1/238 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2150 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 13 | 13 | 0 | 1 |  | N |  | 4400M1/239 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2149 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2150 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64.7174 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 27 | 27 | 0 | 1 |  | N |  | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2151 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400M1/234 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2151 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2152 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 95.8777 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 16 | 16 | 0 | 1 |  | N |  | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2153 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2154 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/113 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2154 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2155 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/234 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2155 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2155 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 39.7238 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 9 | 9 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2155 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2156 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 66.2063 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 15 | 15 | 0 | 1 |  | N |  | 4400M1/238 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2156 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/239 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2155 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 52.9651 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 12 | 12 | 0 | 1 |  | N |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2156 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 39.7238 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 9 | 9 | 0 | 1 |  | N |  | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2157 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.37614 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 18.16 | 18.16 | 0 | 1 |  | N |  | 4400M1/110 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2157 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.45008 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 21.73 | 21.73 | 0 | 1 |  | N |  | 4400M1/111 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 2 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2158 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.4343 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 69.25 | 69.25 | 0 | 1 |  | N |  | 4400M1/148 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2157 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.14871 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 7.18 | 7.18 | 0 | 1 |  | N |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2159 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.24254 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 11.71 | 11.71 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2159 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.45236 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 21.84 | 21.84 | 0 | 1 |  | N |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2160 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.72369 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 34.94 | 34.94 | 0 | 1 |  | N |  | 4400M1/238 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2160 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.35066 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 16.93 | 16.93 | 0 | 1 |  | N |  | 4400M1/239 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2159 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.75248 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 36.33 | 36.33 | 0 | 1 |  | N |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2160 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.0932 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 52.78 | 52.78 | 0 | 1 |  | N |  | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2161 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.7163 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1146 | 1146 | 0 | 1 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 2 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2161 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 37.598 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1317 | 1317 | 0 | 1 |  | N |  | 4400M1/109 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2162 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.9846 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 665 | 665 | 0 | 1 |  | N |  | 4400M1/110 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2162 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.4316 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1101 | 1101 | 0 | 1 |  | N |  | 4400M1/111 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2162 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 33.8867 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1187 | 1187 | 0 | 1 |  | N |  | 4400M1/112 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2162 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.9291 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 593 | 593 | 0 | 1 |  | N |  | 4400M1/113 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 2 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2161 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.7456 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1112 | 1112 | 0 | 1 |  | N |  | 4400M1/148 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2162 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 15.9014 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 557 | 557 | 0 | 1 |  | N |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2163 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.5572 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 615 | 615 | 0 | 1 |  | N |  | 4400M1/234 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2163 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.6575 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1214 | 1214 | 0 | 1 |  | N |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2163 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 30.461 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1067 | 1067 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2163 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.2994 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 641 | 641 | 0 | 1 |  | N |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2164 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 43.4219 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1521 | 1521 | 0 | 1 |  | N |  | 4400M1/238 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2164 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.235 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 954 | 954 | 0 | 1 |  | N |  | 4400M1/239 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2163 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.4723 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 577 | 577 | 0 | 1 |  | N |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 2 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2164 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 26.1216 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 915 | 915 | 0 | 1 |  | N |  | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE69 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2165 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 221.0622 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2459.38 | 2459.38 | 0 | 1 |  | N |  | 4400M1/234 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2165 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 603.9243 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6718.83 | 6718.83 | 0 | 1 |  | N |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2165 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 517.6488 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5758.99 | 5758.99 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2165 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 132.9278 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1478.86 | 1478.86 | 0 | 1 |  | N |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2166 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 358.0169 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3983.04 | 3983.04 | 0 | 1 |  | N |  | 4400M1/238 | YNE69: M1 J36-37 | YNE69 Closure 2 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 1 NB NS CGS 45078 Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 2167 | Invasive Plant Species - Maintain Affected Property to control the spread or increase of instances of Invasive Weeds 1 | 39.7677 | 4.8.8 | A40084 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 576 | 576 | 0 | 1 |  | N |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE69 Closure 2 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 2168 | Sweeping - Paved non-running areas - Full Sweep 01 | 52.0928 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6994 | 6994 | 0 | 1 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2169 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 112.3806 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 4688.5 | 4688.5 | 0 | 1 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 2 SB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2170 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 112.3806 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 4688.5 | 4688.5 | 0 | 1 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB OS | Lane 2 & 3 Closure | 1 |  |  | Annually
YNE69 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 2171 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1229.0561 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 25638 | 25638 | 0 | 1 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2172 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.9948 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1146 | 1146 | 0 | 1 |  | N |  | 4400M1/108 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2172 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 17.2322 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1317 | 1317 | 0 | 1 |  | N |  | 4400M1/109 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2173 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.7012 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 665 | 665 | 0 | 1 |  | N |  | 4400M1/110 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2173 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.406 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1101 | 1101 | 0 | 1 |  | N |  | 4400M1/111 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2173 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 15.5313 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1187 | 1187 | 0 | 1 |  | N |  | 4400M1/112 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2173 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 7.7591 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 593 | 593 | 0 | 1 |  | N |  | 4400M1/113 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 2 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2174 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 14.5499 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1112 | 1112 | 0 | 1 |  | N |  | 4400M1/148 | YNE69: M1 J36-37 | YNE69 Closure 2 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Andy Reddy acknowledged FYI & uploaded
YNE69 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2175 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.288 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 557 | 557 | 0 | 1 |  | N |  | 4400M1/149 | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 284/5 | 275/3 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE69 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2176 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 40.2216 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3074 | 3074 | 0 | 1 |  | N |  | 4400M1/234 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE69 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2176 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 103.799 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 7933 | 7933 | 0 | 1 |  | N |  | 4400M1/235 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE69 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2176 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 89.3014 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6825 | 6825 | 0 | 1 |  | N |  | 4400M1/236 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE69 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2176 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 27.7391 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2120 | 2120 | 0 | 1 |  | N |  | 4400M1/237 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE69 Closure 2 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2177 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 72.0169 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5504 | 5504 | 0 | 1 |  | N |  | 4400M1/238 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE69 Closure 2 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2177 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.4826 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 954 | 954 | 0 | 1 |  | N |  | 4400M1/239 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE69 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2178 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.5497 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 577 | 577 | 0 | 1 |  | N |  | 4400M1/261 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE69 Closure 2 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2179 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 11.9723 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 915 | 915 | 0 | 1 |  | N |  | 4400M1/262 | YNE69: M1 J36-37 | YNE69 Closure 2 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE70 Closure 1 SB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2180 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 447.7511 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 58 | 58 | 0 | 1 |  | N |  | 4400M1/103 | YNE70: M1 J37-38 | YNE70 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE70 Closure 1 SB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2181 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 355.1129 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 46 | 46 | 0 | 1 |  | N |  | 4400M1/103 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE70 Closure 1 SB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2181 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 308.7939 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 40 | 40 | 0 | 1 |  | N |  | 4400M1/146 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE70 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2182 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 162.1168 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 21 | 21 | 0 | 1 |  | N |  | 4400M1/240 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2183 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 617.5877 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 80 | 80 | 0 | 1 |  | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE70 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2182 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 331.9534 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 43 | 43 | 0 | 1 |  | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2183 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 463.1908 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 60 | 60 | 0 | 1 |  | N |  | 4400M1/242 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE70 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2182 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 293.3542 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 38 | 38 | 0 | 1 |  | N |  | 4400M1/242 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2182 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 277.9145 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 36 | 36 | 0 | 1 |  | N |  | 4400M1/243 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2183 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 54.0389 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4400M1/264 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE70 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2182 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 154.3969 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 20 | 20 | 0 | 1 |  | N |  | 4400M1/264 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 SB NS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2184 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 99.691 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1291.36 | 1291.36 | 0 | 1 |  | N |  | 4400M1/106 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE70 Closure 1 NB NS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2185 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 6.1751 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 79.99 | 79.99 | 0 | 1 |  | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 3 times per year (ILM Entire Route) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2186 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 3.8553 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 49.94 | 49.94 | 0 | 1 |  | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE70 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 2187 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 131.8318 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 17 | 5 | 12 | 0.29412 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2188 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 11.9847 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 2 | 1 | 1 | 0.5 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 | Yes |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2189 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 11.9847 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 2 | 1 | 1 | 0.5 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 | Yes |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 2190 | CCTV Masts - Check mast breaking system | 63.9185 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 2 | 1 | 1 | 0.5 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 | Yes |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Vaisala 45078 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 2191 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 1 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2192 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 395.4955 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 15 | 10 | 5 | 0.66667 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2193 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 10 | 10 | 0 | 1 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Vaisala 45078 Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 2194 | Environmental Sensor Stations (ESS) - Test and calibrate sites pre-winter season and mid-winter season - 2 | 239.6942 | 4.6.5 | ART008 |  | 0 | Vaisala | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | 2 times per year | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 SB NS Amey 45078 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2195 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 392.9414 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | Every 6 years |  |  | On ServiceNow
YNE70 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Clean camera lens | 2196 | CCTV PTZ Cameras - Clean camera lens | 23.9694 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 3 | 2 | 1 | 0.66667 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 | Yes |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check camera functionality | 2197 | CCTV PTZ Cameras - Check camera functionality | 23.9694 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 3 | 2 | 1 | 0.66667 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 | Yes |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 2198 | CCTV PTZ Cameras - Check data and power supplies | 23.9694 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys |  | 3 | 2 | 1 | 0.66667 |  | N |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 | Yes |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2199 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 162.0333 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 3380 | 3380 | 0 | 1 |  | N |  |  | YNE70: M1 J37-38 | YNE70Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2200 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 2 & 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2201 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2202 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE70: M1 J37-38 | YNE70 Closure 1 SB OS | Lane 2 & 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2203 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2203 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/242 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2203 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 47.9388 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4400M1/263 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2203 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 71.9083 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/264 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2204 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/102 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2204 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 20 | 20 | 0 | 1 |  | N |  | 4400M1/103 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2204 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 15 | 15 | 0 | 1 |  | N |  | 4400M1/104 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2204 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52.7327 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 22 | 22 | 0 | 1 |  | N |  | 4400M1/105 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2204 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 88.6869 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 37 | 37 | 0 | 1 |  | N |  | 4400M1/106 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2204 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/107 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2204 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 8 | 8 | 0 | 1 |  | N |  | 4400M1/146 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2204 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 47.9388 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 20 | 20 | 0 | 1 |  | N |  | 4400M1/147 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2205 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400M1/240 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2205 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 25 | 25 | 0 | 1 |  | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2205 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 15 | 15 | 0 | 1 |  | N |  | 4400M1/242 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2205 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 8 | 8 | 0 | 1 |  | N |  | 4400M1/243 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2205 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 30 | 30 | 0 | 1 |  | N |  | 4400M1/244 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2205 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 9 | 9 | 0 | 1 |  | N |  | 4400M1/245 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2205 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 31.1602 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 13 | 13 | 0 | 1 |  | N |  | 4400M1/263 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2205 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 28.7633 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 12 | 12 | 0 | 1 |  | N |  | 4400M1/264 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2206 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 71.9083 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 12 | 12 | 0 | 1 |  | N |  | 4400M1/240 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2207 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/147 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/240 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 57.3788 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 13 | 13 | 0 | 1 |  | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 61.7926 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4400M1/242 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/243 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 48.5513 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4400M1/244 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4400M1/245 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/263 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2208 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 26.4825 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4400M1/264 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.26947 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 13.01 | 13.01 | 0 | 1 |  | N |  | 4400M1/105 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.2005 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 9.68 | 9.68 | 0 | 1 |  | N |  | 4400M1/106 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.2647 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 12.78 | 12.78 | 0 | 1 |  | N |  | 4400M1/107 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.50248 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 24.26 | 24.26 | 0 | 1 |  | N |  | 4400M1/146 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2209 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.93723 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 45.25 | 45.25 | 0 | 1 |  | N |  | 4400M1/147 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2210 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.2214 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 58.97 | 58.97 | 0 | 1 |  | N |  | 4400M1/263 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.4715 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 612 | 612 | 0 | 1 |  | N |  | 4400M1/102 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 38.5687 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1351 | 1351 | 0 | 1 |  | N |  | 4400M1/103 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.2709 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 640 | 640 | 0 | 1 |  | N |  | 4400M1/104 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.3427 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1238 | 1238 | 0 | 1 |  | N |  | 4400M1/105 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 49.0744 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1719 | 1719 | 0 | 1 |  | N |  | 4400M1/106 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.9536 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 769 | 769 | 0 | 1 |  | N |  | 4400M1/107 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.1583 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 566 | 566 | 0 | 1 |  | N |  | 4400M1/146 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2211 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 20.9544 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 734 | 734 | 0 | 1 |  | N |  | 4400M1/147 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE70 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2212 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.1518 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 846 | 846 | 0 | 1 |  | N |  | 4400M1/240 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2212 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 47.2759 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1656 | 1656 | 0 | 1 |  | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2212 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 35.3998 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1240 | 1240 | 0 | 1 |  | N |  | 4400M1/242 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2212 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 18.6134 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 652 | 652 | 0 | 1 |  | N |  | 4400M1/243 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2212 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 40.8525 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1431 | 1431 | 0 | 1 |  | N |  | 4400M1/244 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2212 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.5881 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 511 | 511 | 0 | 1 |  | N |  | 4400M1/245 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2212 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 22.3247 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 782 | 782 | 0 | 1 |  | N |  | 4400M1/263 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2212 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 13.2178 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 463 | 463 | 0 | 1 |  | N |  | 4400M1/264 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2213 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 866.0245 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 9634.77 | 9634.77 | 0 | 1 |  | N |  | 4400M1/242 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2213 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 203.9175 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2268.64 | 2268.64 | 0 | 1 |  | N |  | 4400M1/243 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2213 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 261.8576 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2913.24 | 2913.24 | 0 | 1 |  | N |  | 4400M1/244 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2213 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 172.7623 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1922.03 | 1922.03 | 0 | 1 |  | N |  | 4400M1/245 | YNE70: M1 J37-38 | YNE70 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE70 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 2214 | Sweeping - Paved non-running areas - Full Sweep 01 | 104.139 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 13981.75 | 13981.75 | 0 | 1 |  | N |  | 4400M1/102 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE70 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2215 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 289.5027 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 12078 | 12078 | 0 | 1 |  | N |  | 4400M1/102 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE70 Closure 1 SB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2216 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 289.5027 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 12078 | 12078 | 0 | 1 |  | N |  | 4400M1/102 | YNE70: M1 J37-38 | YNE70 Closure 1 SB OS | Lane 2 & 3 Closure | 1 |  |  | Annually
YNE70 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 2217 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 989.314 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 20637 | 20637 | 0 | 1 |  | N |  | 4400M1/102 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE70 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2218 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.0077 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 612 | 612 | 0 | 1 |  | N |  | 4400M1/102 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE70 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2218 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 17.6771 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1351 | 1351 | 0 | 1 |  | N |  | 4400M1/103 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE70 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2218 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.3741 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 640 | 640 | 0 | 1 |  | N |  | 4400M1/104 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE70 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2218 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.1986 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1238 | 1238 | 0 | 1 |  | N |  | 4400M1/105 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE70 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2218 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 22.4922 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1719 | 1719 | 0 | 1 |  | N |  | 4400M1/106 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE70 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2218 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 10.0619 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 769 | 769 | 0 | 1 |  | N |  | 4400M1/107 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE70 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2219 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.4058 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 566 | 566 | 0 | 1 |  | N |  | 4400M1/146 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE70 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2219 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 9.604 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 734 | 734 | 0 | 1 |  | N |  | 4400M1/147 | YNE70: M1 J37-38 | YNE70 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE70 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2220 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.0695 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 846 | 846 | 0 | 1 |  | N |  | 4400M1/240 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2220 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.6679 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1656 | 1656 | 0 | 1 |  | N |  | 4400M1/241 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2220 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 142.2935 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 10875 | 10875 | 0 | 1 |  | N |  | 4400M1/242 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2220 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 38.2066 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2920 | 2920 | 0 | 1 |  | N |  | 4400M1/243 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2220 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 56.8389 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4344 | 4344 | 0 | 1 |  | N |  | 4400M1/244 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2220 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 31.8345 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2433 | 2433 | 0 | 1 |  | N |  | 4400M1/245 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2221 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 10.232 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 782 | 782 | 0 | 1 |  | N |  | 4400M1/263 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE70 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2221 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.0581 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 463 | 463 | 0 | 1 |  | N |  | 4400M1/264 | YNE70: M1 J37-38 | YNE70 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 26.5.23 Uploaded Consent from Charles @ DBFO major.LA consents for diversion
YNE71 Closure 1 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2222 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 100.358 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 13 | 13 | 0 | 1 |  | N |  | 4700M1/1 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 2 & 3 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2223 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 200.716 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 26 | 26 | 0 | 1 |  | N |  | 4700M1/1 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure Amey 45078 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 2224 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 0 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE71 Closure 1 NB NS Amey 45078 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2225 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  | 0 | 0 | 0 | 0 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2226 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  | 0 | 0 | 0 | 0 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2227 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 392.9414 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 1 | 1 | 0 | 1 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Every 6 years | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 2228 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 131.8318 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 5 | 5 | 0 | 1 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2229 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2230 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 2231 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2232 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 316.3964 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 10 | 8 | 2 | 0.8 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2233 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 10 | 10 | 0 | 1 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 2234 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Every 5 years | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 2235 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 2236 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Clean camera lens | 2237 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check camera functionality | 2238 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 2239 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2240 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 169.2721 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 3531 | 3531 | 0 | 1 |  | N |  |  | YNE71: M1 J38-39 | YNE71 Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE71 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2241 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 2 & 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2242 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE71 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2243 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE71: M1 J38-39 | YNE71 Closure 1 SB OS | Lane 2 & 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 292/2" | 286/7" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2244 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 119.8471 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4700M1/24 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2245 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4400M1/101 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2246 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 9.5878 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4400M1/246 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2246 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 11 | 11 | 0 | 1 |  | N |  | 4700M1/1 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2246 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4700M1/11 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2246 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4700M1/12 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2245 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 7 | 7 | 0 | 1 |  | N |  | 4700M1/174 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2245 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 11 | 11 | 0 | 1 |  | N |  | 4700M1/176 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2245 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 16.7786 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 7 | 7 | 0 | 1 |  | N |  | 4700M1/178 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2245 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 43.145 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 18 | 18 | 0 | 1 |  |  |  | 4700M1/185 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2245 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 8 | 8 | 0 | 1 |  | N |  | 4700M1/187 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2246 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 15 | 15 | 0 | 1 |  | N |  | 4700M1/19 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2245 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 35.9541 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 15 | 15 | 0 | 1 |  | N |  | 4700M1/190 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2245 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 19.1755 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 8 | 8 | 0 | 1 |  | N |  | 4700M1/192 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2245 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 23.9694 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 10 | 10 | 0 | 1 |  | N |  | 4700M1/196 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2245 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26.3664 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 11 | 11 | 0 | 1 |  | N |  | 4700M1/198 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2246 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 33.5572 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 14 | 14 | 0 | 1 |  | N |  | 4700M1/22 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2246 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 25 | 25 | 0 | 1 |  | N |  | 4700M1/24 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2246 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 16 | 16 | 0 | 1 |  |  |  | 4700M1/25 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2246 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40.748 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 17 | 17 | 0 | 1 |  | N |  | 4700M1/6 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2246 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 4.7939 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4700M1/9 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2247 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4700M1/1 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2248 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4700M1/176 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2248 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4700M1/198 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2247 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4 | 4 | 0 | 1 |  | N |  | 4700M1/24 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2249 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4400M1/246 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2249 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 44.1376 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4700M1/1 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2249 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  |  |  | 4700M1/11 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2249 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2 | 2 | 0 | 1 |  | N |  | 4700M1/12 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2250 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/176 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2250 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/187 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2249 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 30.8963 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 7 | 7 | 0 | 1 |  | N |  | 4700M1/19 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2249 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4700M1/22 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2249 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 88.2751 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 20 | 20 | 0 | 1 |  | N |  | 4700M1/24 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2249 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4700M1/6 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2249 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4700M1/9 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2251 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.24088 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 11.63 | 11.63 | 0 | 1 |  |  |  | 4400M1/101 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2251 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.70422 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 34 | 34 | 0 | 1 |  |  |  | 4700M1/174 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2251 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.8227 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 88 | 88 | 0 | 1 |  |  |  | 4700M1/176 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE71 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2251 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.51035 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 24.64 | 24.64 | 0 | 1 |  |  |  | 4700M1/198 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2252 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.2048 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 58.17 | 58.17 | 0 | 1 |  |  |  | 4700M1/24 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2252 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.6777 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 81 | 81 | 0 | 1 |  |  |  | 4700M1/25 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.562 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 405 | 405 | 0 | 1 |  |  |  | 4400M1/101 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.819 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 414 | 414 | 0 | 1 |  |  |  | 4400M1/246 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.527 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 684 | 684 | 0 | 1 |  |  |  | 4700M1/1 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 31.4887 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1103 | 1103 | 0 | 1 |  |  |  | 4700M1/11 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 51.2726 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1796 | 1796 | 0 | 1 |  |  |  | 4700M1/12 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.0376 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 842 | 842 | 0 | 1 |  |  |  | 4700M1/174 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 24.4658 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 857 | 857 | 0 | 1 |  |  |  | 4700M1/176 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.1925 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 322 | 322 | 0 | 1 |  |  |  | 4700M1/178 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.2595 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1130 | 1130 | 0 | 1 |  |  |  | 4700M1/185 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.8394 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 765 | 765 | 0 | 1 |  |  |  | 4700M1/187 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.611 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 757 | 757 | 0 | 1 |  |  |  | 4700M1/19 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 47.1331 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1651 | 1651 | 0 | 1 |  |  |  | 4700M1/190 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.9576 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 594 | 594 | 0 | 1 |  |  |  | 4700M1/192 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.2741 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 500 | 500 | 0 | 1 |  |  |  | 4700M1/196 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 6.2235 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 218 | 218 | 0 | 1 |  |  |  | 4700M1/197 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2253 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 16.1297 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 565 | 565 | 0 | 1 |  |  |  | 4700M1/198 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 9.2782 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 325 | 325 | 0 | 1 |  |  |  | 4700M1/2 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 10.6485 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 373 | 373 | 0 | 1 |  |  |  | 4700M1/22 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 21.2113 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 743 | 743 | 0 | 1 |  |  |  | 4700M1/24 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 23.4095 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 820 | 820 | 0 | 1 |  |  |  | 4700M1/25 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 17.5286 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 614 | 614 | 0 | 1 |  |  |  | 4700M1/6 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2254 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 11.7619 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 412 | 412 | 0 | 1 |  |  |  | 4700M1/9 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2255 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 164.5872 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1831.08 | 1831.08 | 0 | 1 |  |  |  | 4400M1/246 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2256 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 86.1308 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 958.23 | 958.23 | 0 | 1 |  |  |  | 4700M1/185 | YNE71: M1 J38-39 | YNE71 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 292/2" | 286/7" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2255 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 788.6225 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 8773.65 | 8773.65 | 0 | 1 |  |  |  | 4700M1/19 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2255 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 349.4787 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3888.05 | 3888.05 | 0 | 1 |  |  |  | 4700M1/19 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2256 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 99.0851 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1102.35 | 1102.35 | 0 | 1 |  |  |  | 4700M1/190 | YNE71: M1 J38-39 | YNE71 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 292/2" | 286/7" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2255 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 128.9351 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1434.44 | 1434.44 | 0 | 1 |  |  |  | 4700M1/2 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2255 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 68.729 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 764.63 | 764.63 | 0 | 1 |  |  |  | 4700M1/22 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2255 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 41.7562 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 464.55 | 464.55 | 0 | 1 |  |  |  | 4700M1/25 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB OS CGS 45078 Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 2255 | Grass & Vegetation - Grass cut the central reserve 1 - ILM (activity requires litter picking by Amey resource) | 233.9311 | 4.8.5.3 | A40080 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2602.55 | 2602.55 | 0 | 1 |  |  |  | 4700M1/6 | YNE71: M1 J38-39 | YNE71 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 286/4" | 291/8" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 2257 | Sweeping - Paved non-running areas - Full Sweep 01 | 108.5894 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 14579.25 | 14579.25 | 0 | 1 |  |  |  | 4400M1/101 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2258 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 53.9192 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 2249.5 | 2249.5 | 0 | 1 |  |  |  | 4400M1/101 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE71 Closure 1 SB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2259 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 53.9192 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 2249.5 | 2249.5 | 0 | 1 |  |  |  | 4400M1/101 | YNE71: M1 J38-39 | YNE71 Closure 1 SB OS | Lane 2 & 3 Closure | 1 |  |  | Annually | 292/2" | 286/7" |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 2260 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 2225.7047 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 46428 | 46428 | 0 | 1 |  |  |  | 4400M1/101 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.2992 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 405 | 405 | 0 | 1 |  |  |  | 4400M1/101 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 29.3746 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 2245 | 2245 | 0 | 1 |  |  |  | 4400M1/246 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2263 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.9498 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 684 | 684 | 0 | 1 |  |  |  | 4700M1/1 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2263 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 14.4322 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1103 | 1103 | 0 | 1 |  |  |  | 4700M1/11 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 4 times per year (ILM Certain Sections) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 138.2896 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 10569 | 10569 | 0 | 1 |  |  |  | 4700M1/12 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 11.0171 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 842 | 842 | 0 | 1 |  |  |  | 4700M1/174 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2264 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 11.2134 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 857 | 857 | 0 | 1 |  |  |  | 4700M1/176 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 4.2132 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 322 | 322 | 0 | 1 |  |  |  | 4700M1/178 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 27.3203 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 2088 | 2088 | 0 | 1 |  |  |  | 4700M1/185 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2264 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 10.0096 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 765 | 765 | 0 | 1 |  |  |  | 4700M1/187 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 4 times per year (ILM Certain Sections)
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 60.7773 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4645 | 4645 | 0 | 1 |  |  |  | 4700M1/19 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 36.0215 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 2753 | 2753 | 0 | 1 |  |  |  | 4700M1/190 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2264 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.7722 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 594 | 594 | 0 | 1 |  |  |  | 4700M1/192 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 4 times per year (ILM Certain Sections)
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.5422 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 500 | 500 | 0 | 1 |  |  |  | 4700M1/196 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2261 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2.8524 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 218 | 218 | 0 | 1 |  |  |  | 4700M1/197 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE71 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2264 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 7.3927 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 565 | 565 | 0 | 1 |  |  |  | 4700M1/198 | YNE71: M1 J38-39 | YNE71 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections)
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 23.0156 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1759 | 1759 | 0 | 1 |  |  |  | 4700M1/2 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.877 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1137 | 1137 | 0 | 1 |  |  |  | 4700M1/22 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2263 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 9.7218 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 743 | 743 | 0 | 1 |  |  |  | 4700M1/24 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.8004 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1284 | 1284 | 0 | 1 |  |  |  | 4700M1/25 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2262 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 42.0796 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3216 | 3216 | 0 | 1 |  |  |  | 4700M1/6 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE71 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2263 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 5.3908 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 412 | 412 | 0 | 1 |  |  |  | 4700M1/9 | YNE71: M1 J38-39 | YNE71 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 4 times per year (ILM Certain Sections) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB OS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2265 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 424.5916 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 55 | 55 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually for ILM Sections Within the Route
YNE72 Closure 1 NB NS Enviroflow 45078 Gullies - Emptying / clear covers - Intelligence Led Maintenance | 2266 | Gullies - Emptying / clear covers - Intelligence Led Maintenance | 378.2725 | 4.3.1.1 | A40005 |  | 0 | Enviroflow | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 49 | 49 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually for ILM Sections Within the Route | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2267 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 31.6514 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 410 | 410 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE72 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2267 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 22.3876 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 290 | 290 | 0 | 1 |  | N |  | 4700M1/628 | YNE72: M1 J39-40 | YNE72 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE72 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2268 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 32.8093 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 425 | 425 | 0 | 1 |  | N |  | 4700M1/731 | YNE72: M1 J39-40 | YNE72 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE72 Closure Amey 45078 BC - Lamps (LED) for Illuminated Signs and Bollards | 2269 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE72 Closure 1 NB NS Amey 45078 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2270 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2271 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 1 | 0 | 1 | 0 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 2272 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 158.1982 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 35 | 6 | 29 | 0.17143 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2273 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 7 | 0 | 7 | 0 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2274 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 7 | 0 | 7 | 0 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 CCTV Masts - Check mast breaking system | 2275 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 7 | 0 | 7 | 0 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2276 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 8 | 0 | 8 | 0 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2277 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 2278 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 18 | 0 | 18 | 0 |  | Y |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Every 5 years | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 2279 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 18 | 0 | 18 | 0 |  | Y |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 2280 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 18 | 0 | 18 | 0 |  | Y |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Clean camera lens | 2281 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 7 | 0 | 7 | 0 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check camera functionality | 2282 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 7 | 0 | 7 | 0 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 2283 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | 2023-12-11 | 2023-12 | 2023-12-12 | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys |  | 7 | 0 | 7 | 0 |  | N |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually | 288/2 | 294/8 | On ServiceNow | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2284 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 115.9641 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2419 | 2419 | 0 | 1 |  | N |  |  | YNE72: M1 J39-40 | YNE72Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE72 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2285 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2286 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2287 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE72: M1 J39-40 | YNE72 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2288 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 119.8471 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4700M1/622 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2288 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 359.5413 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 15 | 15 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2288 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 119.8471 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4700M1/682 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2288 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 239.6942 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 10 | 10 | 0 | 1 |  | N |  | 4700M1/685 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 5 | 5 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71.9083 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 30 | 30 | 0 | 1 |  | N |  | 4700M1/622 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 95.8777 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 40 | 40 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 7.1908 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 3 | 3 | 0 | 1 |  | N |  | 4700M1/628 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 83.893 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 35 | 35 | 0 | 1 |  | N |  | 4700M1/682 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2289 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 25 | 25 | 0 | 1 |  | N |  | 4700M1/685 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2290 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 11.9847 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 5 | 5 | 0 | 1 |  | N |  | 4700M1/728 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2290 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 59.9236 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 25 | 25 | 0 | 1 |  | N |  | 4700M1/731 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2290 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 21.5725 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 9 | 9 | 0 | 1 |  | N |  | 4700M1/731 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2290 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 14.3817 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 6 | 6 | 0 | 1 |  | N |  | 4700M1/737 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2290 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38.3511 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 16 | 16 | 0 | 1 |  | N |  | 4700M1/779 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2290 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62.3205 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 26 | 26 | 0 | 1 |  | N |  | 4700M1/782 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2291 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 35.9541 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6 | 6 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2292 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23.9694 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 4 | 4 | 0 | 1 |  | N |  | 4700M1/779 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2293 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2293 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 150.0677 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 34 | 34 | 0 | 1 |  | N |  | 4700M1/622 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2293 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 260.4116 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 59 | 59 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2293 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 119.1714 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 27 | 27 | 0 | 1 |  | N |  | 4700M1/682 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2293 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 136.8264 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 31 | 31 | 0 | 1 |  | N |  | 4700M1/685 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2294 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/734 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2294 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1 | 1 | 0 | 1 |  | N |  | 4700M1/779 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2295 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.092998 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 4.49 | 4.49 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2295 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.48425 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 23.38 | 23.38 | 0 | 1 |  | N |  | 4700M1/622 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2295 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.75952 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 36.67 | 36.67 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2295 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 1.8695 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 90.26 | 90.26 | 0 | 1 |  | N |  | 4700M1/682 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2295 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.34051 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 16.44 | 16.44 | 0 | 1 |  | N |  | 4700M1/685 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2296 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.68164 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 32.91 | 32.91 | 0 | 1 |  | N |  | 4700M1/731 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2296 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 17.1291 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 827 | 827 | 0 | 1 |  | N |  | 4700M1/779 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2296 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2.2701 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 109.6 | 109.6 | 0 | 1 |  | N |  | 4700M1/782 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4128 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 680 | 680 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 28.6624 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1004 | 1004 | 0 | 1 |  | N |  | 4700M1/622 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 45.877 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1607 | 1607 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.9593 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 524 | 524 | 0 | 1 |  | N |  | 4700M1/628 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 19.4128 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 680 | 680 | 0 | 1 |  | N |  | 4700M1/682 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2297 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 14.0743 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 493 | 493 | 0 | 1 |  | N |  | 4700M1/685 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2298 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 27.7774 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 973 | 973 | 0 | 1 |  | N |  | 4700M1/728 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2298 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 32.1168 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1125 | 1125 | 0 | 1 |  | N |  | 4700M1/731 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2298 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 12.2472 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 429 | 429 | 0 | 1 |  | N |  | 4700M1/734 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2298 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 36.0564 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1263 | 1263 | 0 | 1 |  | N |  | 4700M1/737 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2298 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 25.9503 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 909 | 909 | 0 | 1 |  | N |  | 4700M1/779 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2298 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 34.315 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1202 | 1202 | 0 | 1 |  | N |  | 4700M1/782 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 2299 | Sweeping - Paved non-running areas - Full Sweep 01 | 76.4522 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 10264.5 | 10264.5 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2300 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 357.7197 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 14924 | 14924 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2301 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 357.7197 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 14924 | 14924 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually
YNE72 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 2302 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 1276.6115 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 26630 | 26630 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2303 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 8.8974 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 680 | 680 | 0 | 1 |  | N |  | 4700M1/619 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2303 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 13.1368 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1004 | 1004 | 0 | 1 |  | N |  | 4700M1/622 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2303 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 21.0267 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 1607 | 1607 | 0 | 1 |  | N |  | 4700M1/625 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2303 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 6.8563 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 524 | 524 | 0 | 1 |  | N |  | 4700M1/628 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2304 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 8.8974 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 680 | 680 | 0 | 1 |  | N |  | 4700M1/682 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2304 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 6.4506 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 493 | 493 | 0 | 1 |  | N |  | 4700M1/685 | YNE72: M1 J39-40 | YNE72 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 288/2 | 294/8 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE72 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2305 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 12.7312 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 973 | 973 | 0 | 1 |  | N |  | 4700M1/728 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2305 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 14.72 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1125 | 1125 | 0 | 1 |  | N |  | 4700M1/731 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2305 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 5.6132 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 429 | 429 | 0 | 1 |  | N |  | 4700M1/734 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2305 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 16.5257 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1263 | 1263 | 0 | 1 |  | N |  | 4700M1/737 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2306 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 11.8938 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 909 | 909 | 0 | 1 |  | N |  | 4700M1/779 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE72 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2306 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 15.7275 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | SB | 1202 | 1202 | 0 | 1 |  | N |  | 4700M1/782 | YNE72: M1 J39-40 | YNE72 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE73 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2307 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1200 | 0 | 1200 | 0 |  | Y |  | 4700M1/634 | YNE73: M1 J40-41 | YNE73 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE73 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2307 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1230 | 0 | 1230 | 0 |  | Y |  | 4700M1/637 | YNE73: M1 J40-41 | YNE73 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE73 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2307 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 350 | 0 | 350 | 0 |  | Y |  | 4700M1/641 | YNE73: M1 J40-41 | YNE73 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE73 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2308 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 395 | 0 | 395 | 0 |  | Y |  | 4700M1/716 | YNE73: M1 J40-41 | YNE73 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE73 Closure Amey 45078 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 2309 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 0 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE73 Closure Amey 45078 BC - Lamps (LED) for Illuminated Signs and Bollards | 2310 | BC - Lamps (LED) for Illuminated Signs and Bollards | 0 | 4.5.8 | A40043 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE73 Closure Amey 45078 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2311 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Amey 45078 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2312 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Amey 45078 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2313 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 785.8827 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Every 6 years |  |  | On ServiceNow
YNE73 Closure Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 2314 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1450.1501 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 55 | 55 | 0 | 1 |  | N |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2315 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 95.8777 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 8 | 8 | 0 | 1 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2316 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 95.8777 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 8 | 8 | 0 | 1 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Amey 45078 CCTV Masts - Check mast breaking system | 2317 | CCTV Masts - Check mast breaking system | 511.3477 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 8 | 8 | 0 | 1 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2318 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 672.3423 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 17 | 17 | 0 | 1 |  | N |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2319 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 2 | 2 | 0 | 1 |  | N |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE73 Closure Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 2320 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 14 | 0 | 14 | 0 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE73 Closure Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 2321 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 14 | 0 | 14 | 0 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 2322 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 14 | 0 | 14 | 0 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Amey 45078 CCTV PTZ Cameras - Clean camera lens | 2323 | CCTV PTZ Cameras - Clean camera lens | 95.8777 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 8 | 8 | 0 | 1 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Amey 45078 CCTV PTZ Cameras - Check camera functionality | 2324 | CCTV PTZ Cameras - Check camera functionality | 95.8777 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 8 | 8 | 0 | 1 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 2325 | CCTV PTZ Cameras - Check data and power supplies | 95.8777 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 8 | 8 | 0 | 1 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE73 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2326 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 2250 | 0 | 2250 | 0 |  | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2327 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2328 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2329 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE73: M1 J40-41 | YNE73 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2330 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 12 | 0 | 12 | 0 |  | Y |  | 4700M1/634 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2330 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 9 | 0 | 9 | 0 |  | Y |  | 4700M1/637 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2330 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4700M1/688 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2330 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 11 | 0 | 11 | 0 |  | Y |  | 4700M1/691 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2331 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4700M1/722 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2332 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2332 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 42 | 0 | 42 | 0 |  | Y |  | 4700M1/634 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2332 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 33 | 0 | 33 | 0 |  | Y |  | 4700M1/637 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2332 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 7 | 0 | 7 | 0 |  | Y |  | 4700M1/641 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2332 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 50 | 0 | 50 | 0 |  | Y |  | 4700M1/688 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2332 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 48 | 0 | 48 | 0 |  | Y |  | 4700M1/691 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2333 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 6 | 0 | 6 | 0 |  | Y |  | 4700M1/716 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2333 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 20 | 0 | 20 | 0 |  | Y |  | 4700M1/719 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2333 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 25 | 0 | 25 | 0 |  | Y |  | 4700M1/722 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2333 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4700M1/725 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2333 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 35 | 0 | 35 | 0 |  | Y |  | 4700M1/773 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2333 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 21 | 0 | 21 | 0 |  | Y |  | 4700M1/776 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2334 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 16 | 0 | 16 | 0 |  | Y |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2334 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 8 | 0 | 8 | 0 |  | Y |  | 4700M1/688 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2334 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 10 | 0 | 10 | 0 |  | Y |  | 4700M1/691 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2335 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4 | 0 | 4 | 0 |  | Y |  | 4700M1/719 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2335 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 6 | 0 | 6 | 0 |  | Y |  | 4700M1/773 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2335 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2 | 0 | 2 | 0 |  | Y |  | 4700M1/776 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2336 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 53 | 0 | 53 | 0 |  | Y |  | 4700M1/634 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2336 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 47 | 0 | 47 | 0 |  | Y |  | 4700M1/637 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2336 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 2 | 0 | 2 | 0 |  | Y |  | 4700M1/641 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2336 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 22 | 0 | 22 | 0 |  | Y |  | 4700M1/688 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2336 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 37 | 0 | 37 | 0 |  | Y |  | 4700M1/691 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2337 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2 | 0 | 2 | 0 |  | Y |  | 4700M1/719 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2337 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4700M1/722 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2337 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4700M1/773 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2337 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2 | 0 | 2 | 0 |  | Y |  | 4700M1/776 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2338 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 6152 | 0 | 6152 | 0 |  | Y |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2338 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 224.4 | 0 | 224.4 | 0 |  | Y |  | 4700M1/637 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2338 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 21.41 | 0 | 21.41 | 0 |  | Y |  | 4700M1/641 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2338 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1845 | 0 | 1845 | 0 |  | Y |  | 4700M1/688 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2339 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 8.41 | 0 | 8.41 | 0 |  | Y |  | 4700M1/716 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2339 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 572.7 | 0 | 572.7 | 0 |  | Y |  | 4700M1/722 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2339 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 89.46 | 0 | 89.46 | 0 |  | Y |  | 4700M1/725 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2339 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 247.84 | 0 | 247.84 | 0 |  | Y |  | 4700M1/776 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE73 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2340 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 729 | 0 | 729 | 0 |  | Y |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2340 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1251 | 0 | 1251 | 0 |  | Y |  | 4700M1/634 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2340 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1159 | 0 | 1159 | 0 |  | Y |  | 4700M1/637 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2340 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 590 | 0 | 590 | 0 |  | Y |  | 4700M1/641 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2340 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 666 | 0 | 666 | 0 |  | Y |  | 4700M1/688 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2340 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 526 | 0 | 526 | 0 |  | Y |  | 4700M1/691 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2341 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 951 | 0 | 951 | 0 |  | Y |  | 4700M1/716 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2341 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 788 | 0 | 788 | 0 |  | Y |  | 4700M1/719 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2341 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1274 | 0 | 1274 | 0 |  | Y |  | 4700M1/722 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2341 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 671 | 0 | 671 | 0 |  | Y |  | 4700M1/725 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2341 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 896 | 0 | 896 | 0 |  | Y |  | 4700M1/773 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2341 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 626 | 0 | 626 | 0 |  | Y |  | 4700M1/776 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE73 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 2342 | Sweeping - Paved non-running areas - Full Sweep 01 | 86.1944 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 11572.5 | 11572.5 | 0 | 1 |  | Y |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE73 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2343 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 5885.5 | 0 | 5885.5 | 0 |  | Y |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE73 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2343 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 5885.5 | 0 | 5885.5 | 0 |  | Y |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 3 & 4 Closure | 1 |  |  | Annually
YNE73 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 2344 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 0 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 22002 | 0 | 22002 | 0 |  | Y |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE73 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2345 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 729 | 0 | 729 | 0 |  | Y |  | 4700M1/631 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820148
YNE73 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2345 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 1251 | 0 | 1251 | 0 |  | Y |  | 4700M1/634 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820148
YNE73 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2345 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 1159 | 0 | 1159 | 0 |  | Y |  | 4700M1/637 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820148
YNE73 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2345 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | NB | 590 | 0 | 590 | 0 |  | Y |  | 4700M1/641 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820148
YNE73 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2346 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 666 | 0 | 666 | 0 |  | Y |  | 4700M1/688 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820148
YNE73 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2346 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 526 | 0 | 526 | 0 |  | Y |  | 4700M1/691 | YNE73: M1 J40-41 | YNE73 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820148
YNE73 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2347 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 951 | 0 | 951 | 0 |  | Y |  | 4700M1/716 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820148
YNE73 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2347 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 788 | 0 | 788 | 0 |  | Y |  | 4700M1/719 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820148
YNE73 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2347 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 1274 | 0 | 1274 | 0 |  | Y |  | 4700M1/722 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820148
YNE73 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2347 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning |  |  |  | 2023-06-01 | 2023-07-31 | 2024-02-29 | Subject to share with scheme works and clash management | 43dys | SB | 671 | 0 | 671 | 0 |  | Y |  | 4700M1/725 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820148
YNE73 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2348 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 896 | 0 | 896 | 0 |  | Y |  | 4700M1/773 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820148
YNE73 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2348 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 626 | 0 | 626 | 0 |  | Y |  | 4700M1/776 | YNE73: M1 J40-41 | YNE73 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820148
YNE74 Closure 1 NB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2349 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 764.96 | 0 | 764.96 | 0 |  | Y |  | 4700M1/650 | YNE74: M1 J41-42 | YNE74 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE74 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2350 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 274.29 | 0 | 274.29 | 0 |  | Y |  | 4700M1/703 | YNE74: M1 J41-42 | YNE74 Closure 1 SB OS | Lane 2 & 3 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE74 Closure 1 SB OS Amey 45078 LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 2350 | LDS - Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) 1 - ILM | 0 | 4.3.2.3 | A40009 |  | 0 | Amey | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1244.79 | 0 | 1244.79 | 0 |  | Y |  | 4700M1/707 | YNE74: M1 J41-42 | YNE74 Closure 1 SB OS | Lane 2 & 3 Closure | 1 |  |  | 3 times per year (ILM Entire Route)
YNE74 Closure Amey 45078 BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 2351 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 0 | 4.5.1 | A40036 |  | 0 | Amey | 1300 - Lighting | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | Every 2 years
YNE74 Closure Amey 45078 Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 2352 | Electrical supplies, components and distribution cables - Inspection and Test network in accordance with BS7671 | 0 | 4.6.12.1 | ART027 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 5 | 0 | 5 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | Every 6 years |  |  | On ServiceNow
YNE74 Closure Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 2353 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 1054.6546 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 40 | 40 | 0 | 1 |  | N |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE74 Closure Amey 45078 CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 2354 | CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings | 0 | 4.6.2.1 | ART005A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 5 | 0 | 5 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE74 Closure Amey 45078 CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 2355 | CCTV Masts - Greasing of winch assembly to manufacturers recommendations | 0 | 4.6.2.2 | ART005B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 5 | 0 | 5 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE74 Closure Amey 45078 CCTV Masts - Check mast breaking system | 2356 | CCTV Masts - Check mast breaking system | 0 | 4.6.2.3 | ART005C |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 5 | 0 | 5 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE74 Closure Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2357 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 355.9459 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 9 | 9 | 0 | 1 |  | N |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE74 Closure Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2358 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys |  | 5 | 5 | 0 | 1 |  | N |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE74 Closure Amey 45078 APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 2359 | APTR Telephones - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.3 | ART006 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 126dys |  | 1 | 0 | 1 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE74 Closure Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 2360 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 14 | 0 | 14 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE74 Closure Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 2361 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 14 | 0 | 14 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE74 Closure Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 2362 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Pending confirmation of redundancy of this asset | 41dys |  | 14 | 0 | 14 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE74 Closure Amey 45078 CCTV PTZ Cameras - Clean camera lens | 2363 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 5 | 0 | 5 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE74 Closure Amey 45078 CCTV PTZ Cameras - Check camera functionality | 2364 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 5 | 0 | 5 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE74 Closure Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 2365 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 5 | 0 | 5 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE74 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2366 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys |  | 1638 | 0 | 1638 | 0 |  | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2367 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2368 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2369 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | No assets | 43dys |  |  |  | 0 | 0 |  |  |  |  | YNE74: M1 J41-42 | YNE74 Closure 1 SB OS | Lane 3 & 4 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2370 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 10 | 0 | 10 | 0 |  | Y |  | 4700M1/647 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2370 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 9 | 0 | 9 | 0 |  | Y |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2370 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 5 | 0 | 5 | 0 |  | Y |  | 4700M1/696 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2371 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2 | 0 | 2 | 0 |  | Y |  | 4700M1/707 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2372 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 6 | 0 | 6 | 0 |  | Y |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2372 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 25 | 0 | 25 | 0 |  | Y |  | 4700M1/647 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2372 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 12 | 0 | 12 | 0 |  | Y |  | 4700M1/650 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2372 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4700M1/653 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2372 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 35 | 0 | 35 | 0 |  | Y |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2372 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 14 | 0 | 14 | 0 |  | Y |  | 4700M1/696 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2372 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 9 | 0 | 9 | 0 |  | Y |  | 4700M1/697 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2372 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4700M1/699 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 3 | 0 | 3 | 0 |  | Y |  | 4700M1/703 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 14 | 0 | 14 | 0 |  | Y |  | 4700M1/707 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 17 | 0 | 17 | 0 |  | Y |  | 4700M1/710 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 7 | 0 | 7 | 0 |  | Y |  | 4700M1/713 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 25 | 0 | 25 | 0 |  | Y |  | 4700M1/762 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4700M1/764 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 20 | 0 | 20 | 0 |  | Y |  | 4700M1/767 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2373 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 21 | 0 | 21 | 0 |  | Y |  | 4700M1/770 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2374 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 20 | 0 | 20 | 0 |  | Y |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2374 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 10 | 0 | 10 | 0 |  | Y |  | 4700M1/647 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2374 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 6 | 0 | 6 | 0 |  | Y |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2374 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 12 | 0 | 12 | 0 |  | Y |  | 4700M1/696 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2374 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 16 | 0 | 16 | 0 |  | Y |  | 4700M1/697 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2375 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 8 | 0 | 8 | 0 |  | Y |  | 4700M1/710 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2375 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 2 | 0 | 2 | 0 |  | Y |  | 4700M1/713 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2375 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 8 | 0 | 8 | 0 |  | Y |  | 4700M1/762 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2375 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 6 | 0 | 6 | 0 |  | Y |  | 4700M1/764 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2375 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 12 | 0 | 12 | 0 |  | Y |  | 4700M1/767 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2375 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4 | 0 | 4 | 0 |  | Y |  | 4700M1/770 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2376 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 31 | 0 | 31 | 0 |  | Y |  | 4700M1/647 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2376 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 1 | 0 | 1 | 0 |  | Y |  | 4700M1/650 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2376 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 38 | 0 | 38 | 0 |  | Y |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2376 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 27 | 0 | 27 | 0 |  | Y |  | 4700M1/696 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2377 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 5 | 0 | 5 | 0 |  | Y |  | 4700M1/707 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2377 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 1 | 0 | 1 | 0 |  | Y |  | 4700M1/710 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2377 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4 | 0 | 4 | 0 |  | Y |  | 4700M1/767 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2377 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 4 | 0 | 4 | 0 |  | Y |  | 4700M1/770 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2378 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 9.47 | 0 | 9.47 | 0 |  | Y |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2378 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 21.8 | 0 | 21.8 | 0 |  | Y |  | 4700M1/650 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2378 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 26.84 | 0 | 26.84 | 0 |  | Y |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE74 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2379 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 540 | 0 | 540 | 0 |  | Y |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2379 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 827 | 0 | 827 | 0 |  | Y |  | 4700M1/647 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2379 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 734 | 0 | 734 | 0 |  | Y |  | 4700M1/650 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2379 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 134 | 0 | 134 | 0 |  | Y |  | 4700M1/653 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2379 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 473 | 0 | 473 | 0 |  | Y |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2379 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 470 | 0 | 470 | 0 |  | Y |  | 4700M1/696 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2379 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 154 | 0 | 154 | 0 |  | Y |  | 4700M1/697 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 NB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2379 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 56 | 0 | 56 | 0 |  | Y |  | 4700M1/699 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep)
YNE74 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2380 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 139 | 0 | 139 | 0 |  | Y |  | 4700M1/703 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2380 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 934 | 0 | 934 | 0 |  | Y |  | 4700M1/707 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2380 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 603 | 0 | 603 | 0 |  | Y |  | 4700M1/710 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2380 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 564 | 0 | 564 | 0 |  | Y |  | 4700M1/713 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2380 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 47 | 0 | 47 | 0 |  | Y |  | 4700M1/760 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2380 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 628 | 0 | 628 | 0 |  | Y |  | 4700M1/762 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2380 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 149 | 0 | 149 | 0 |  | Y |  | 4700M1/764 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2380 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 709 | 0 | 709 | 0 |  | Y |  | 4700M1/767 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS CGS 45078 Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 2380 | Grass & Vegetation - Undertake 2m wide Swathe to Nearside Verges | 0 | 4.8.5.2 | A40079 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 527 | 0 | 527 | 0 |  | Y |  | 4700M1/770 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 |  |  | Annually (Apr - Sep) | 300/6 116/8 M62 | 291/7 299/7 M1 |  | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 NB NS Amey 45078 Sweeping - Paved non-running areas - Full Sweep 01 | 2381 | Sweeping - Paved non-running areas - Full Sweep 01 | 50.4467 | 4.9.2 | A40095 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Complete | Complete | Complete | 2023-06-01 | 2023-07-31 | Complete |  | 43dys | NB | 6773 | 6773 | 0 | 1 |  |  |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | 2 times per year
YNE74 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2382 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3837.5 | 0 | 3837.5 | 0 |  | Y |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE74 Closure 1 NB OS Amey 45078 Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 2383 | Litter Picking - Grade A to Carriageway, paved verges and paved central reservations of motorways and APTRs | 0 | 4.9.3 | A40096 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 3837.5 | 0 | 3837.5 | 0 |  | Y |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB OS | Lane 3 & 4 Closure | 1 |  |  | Annually
YNE74 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 2384 | Litter Picking - Grade A to Motorway and APTR roundabouts and lay-bys, approach and slip roads | 0 | 4.9.4 | A40097 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 22250 | 0 | 22250 | 0 |  | Y |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 |  |  | Annually
YNE74 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2385 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 540 | 0 | 540 | 0 |  | Y |  | 4700M1/644 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820149
YNE74 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2385 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 827 | 0 | 827 | 0 |  | Y |  | 4700M1/647 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820149
YNE74 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2385 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 734 | 0 | 734 | 0 |  | Y |  | 4700M1/650 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820149
YNE74 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2385 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 134 | 0 | 134 | 0 |  | Y |  | 4700M1/653 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually |  |  | 45820149
YNE74 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2386 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 473 | 0 | 473 | 0 |  | Y |  | 4700M1/694 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820149
YNE74 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2386 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 470 | 0 | 470 | 0 |  | Y |  | 4700M1/696 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820149
YNE74 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2386 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 154 | 0 | 154 | 0 |  | Y |  | 4700M1/697 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820149
YNE74 Closure 1 NB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2386 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | NB | 56 | 0 | 56 | 0 |  | Y |  | 4700M1/699 | YNE74: M1 J41-42 | YNE74 Closure 1 NB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) |  |  | 45820149
YNE74 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2387 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2023-12-15 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | SB | 139 | 0 | 139 | 0 |  | Y |  | 4700M1/703 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 300/6 116/8 M62 | 291/7 299/7 M1 | 45820149 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2387 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2023-12-15 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | SB | 934 | 0 | 934 | 0 |  | Y |  | 4700M1/707 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 300/6 116/8 M62 | 291/7 299/7 M1 | 45820149 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2387 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2023-12-15 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | SB | 603 | 0 | 603 | 0 |  | Y |  | 4700M1/710 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 300/6 116/8 M62 | 291/7 299/7 M1 | 45820149 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 2387 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | 2023-12-14 | 2023-12 | 2023-12-15 | 2023-06-01 | 2023-07-31 | 2023-12-31 |  | 43dys | SB | 564 | 0 | 564 | 0 |  | Y |  | 4700M1/713 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | Annually | 300/6 116/8 M62 | 291/7 299/7 M1 | 45820149 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2388 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 47 | 0 | 47 | 0 |  | Y |  | 4700M1/760 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45820149 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2388 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 628 | 0 | 628 | 0 |  | Y |  | 4700M1/762 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45820149 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2388 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 149 | 0 | 149 | 0 |  | Y |  | 4700M1/764 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45820149 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2388 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 709 | 0 | 709 | 0 |  | Y |  | 4700M1/767 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45820149 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE74 Closure 1 SB NS Amey 45078 Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 2388 | Litter Picking - Grade A to Verges, non-paved central reservations and Amenity Areas 1 - ILM | 0 | 4.9.5 | A40098 |  | 0 | Amey | 4000 - Sweeping and Cleaning | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-07-31 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 43dys | SB | 527 | 0 | 527 | 0 |  | Y |  | 4700M1/770 | YNE74: M1 J41-42 | YNE74 Closure 1 SB NS | Lane 1 & 2 Closure | 1 | Yes |  | 2 times per year (ILM Certain Sections) | 300/6 116/8 M62 | 291/7 299/7 M1 | 45820149 | 20:00 | 6:00 | Night Shift | Approved | Paul Please add to your spreadsheet for you to review this booking the end of November
YNE90 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2389 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys |  | 1146 | 0 | 1146 | 0 |  | Y |  |  | YNE90: M180 Ings - J1 | YNE90 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE90 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2390 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2391 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE90 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2392 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE90 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2393 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000M180/101 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2393 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 4 | 0 | 4 | 0 |  | Y |  | 2000M180/104 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2394 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | CW | 10 | 0 | 10 | 0 |  | Y |  | 2000M180/105 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2394 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 3 | 0 | 3 | 0 |  | Y |  | 2000M180/109 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2393 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 3 | 0 | 3 | 0 |  | Y |  | 2000M180/110 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2394 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 4 | 0 | 4 | 0 |  | Y |  | 2000M180/111 | YNE90: M180 Ings - J1 | YNE90 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 283/3M18 SB J5 Exit Slip | 2/5 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2393 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 5 | 0 | 5 | 0 |  | Y |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE90 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2395 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 12.1 | 0 | 12.1 | 0 |  | Y |  | 2000M180/112 | YNE90: M180 Ings - J1 | YNE90 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/7 | 0/0 |  | 20:00 | 6:00 | Night Shift | Approved | 0
YNE91 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2396 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys |  | 4303 | 0 | 4303 | 0 |  | Y |  |  | YNE91: M180 J1-2 | YNE91 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2397 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2398 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2399 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE91: M180 J1-2 | YNE91 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2400 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 1 | 1 | 0 | 1 |  | Y |  | 2000M180/107 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2401 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 6 | 0 | 6 | 0 |  | Y |  | 2000M180/108 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2400 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 2 | 2 | 0 | 1 |  | Y |  | 2000M180/113 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2400 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 1 | 1 | 0 | 1 |  | Y |  | 2000M180/114 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2402 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 2 | 0 | 2 | 0 |  | Y |  | 2000M180/115 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2403 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 1 | 0 | 1 | 0 |  | Y |  | 2000M180/116 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 2 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2402 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000M180/117 | YNE91: M180 J1-2 | YNE91 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2401 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000M180/118 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2403 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 2 | 0 | 2 | 0 |  | Y |  | 2000M180/121 | YNE91: M180 J1-2 | YNE91 Closure 2 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2400 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 1 | 1 | 0 | 1 |  | Y |  | 2000M180/124 | YNE91: M180 J1-2 | YNE91 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) | 2/3 | 10/5 |  | 20:00 | 6:00 | Night Shift | Approved | Please note 24/7 hardshoulder in place 7/0 7/4
YNE91 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2401 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 1 | 0 | 1 | 0 |  | Y |  | 2000M180/125 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE91 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2404 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 23.22 | 0 | 23.22 | 0 |  | Y |  | 2000M180/108 | YNE91: M180 J1-2 | YNE91 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2405 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys |  | 2605 | 0 | 2605 | 0 |  | N |  |  | YNE92: M180 J2-3 | YNE92 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2406 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 | 1/9: not mentioned on night report |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2407 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 EB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2408 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE92: M180 J2-3 | YNE92 Closure 1 WB OS | Lane 3 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2409 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 3 | 0 | 3 | 0 |  | N |  | 2000M180/126 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2410 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2000M180/127 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2410 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/132 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2410 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/135 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2410 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 8.8275 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 2 | 2 | 0 | 1 |  | N |  | 2000M180/136 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2409 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 2 | 0 | 2 | 0 |  | N |  | 2000M180/139 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 & 2 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2409 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 3 | 0 | 3 | 0 |  | N |  | 2000M180/141 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 & 2 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2410 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/156 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2409 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 2 | 0 | 2 | 0 |  | N |  | 2000M180/159 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2410 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/163 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2410 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 3 | 3 | 0 | 1 |  | N |  | 2000M180/184 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2409 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 5 | 0 | 5 | 0 |  | N |  | 2000M180/191 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 & 2 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2411 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 24.3 | 0 | 24.3 | 0 |  | N |  | 2000M180/126 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2411 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 17.3 | 0 | 17.3 | 0 |  | N |  | 2000M180/129 | YNE92: M180 J2-3 | YNE92 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2412 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.5961 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 28.78 | 28.78 | 0 | 1 |  | N |  | 2000M180/132 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE92 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2412 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0.33057 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 15.96 | 15.96 | 0 | 1 |  | N |  | 2000M180/184 | YNE92: M180 J2-3 | YNE92 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2413 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys |  | 4519 | 0 | 4519 | 0 |  | N |  |  | YNE93: M180 J3-4 | YNE93 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2414 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2415 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2416 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE93: M180 J3-4 | YNE93 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2417 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 2 | 0 | 2 | 0 |  | N |  | 2000M180/147 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2418 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 2 | 0 | 2 | 0 |  | N |  | 2000M180/149 | YNE93: M180 J3-4 | YNE93 Closure 2 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 2 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2419 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 1 | 1 | 0 | 1 |  | N |  | 2000M180/150 | YNE93: M180 J3-4 | YNE93 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept) |  |  | 45819313
YNE93 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2420 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 3 | 0 | 3 | 0 |  | N |  | 2000M180/154 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2420 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 2 | 0 | 2 | 0 |  | N |  | 2000M180/157 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2421 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 1 | 0 | 1 | 0 |  | N |  | 2000M180/158 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2417 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 2 | 0 | 2 | 0 |  | N |  | 2000M180/162 | YNE93: M180 J3-4 | YNE93 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2421 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 4 | 0 | 4 | 0 |  | N |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2422 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 5.83 | 0 | 5.83 | 0 |  | N |  | 2000M180/154 | YNE93: M180 J3-4 | YNE93 Closure 3 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2423 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 11.51 | 0 | 11.51 | 0 |  | N |  | 2000M180/181 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE93 Closure 1 WB NS CGS 45078 Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 2424 | Injurious Weeds - Maintain Affected Property to control the spread or increase of instances of Injurious Weeds 1 ILM | 0 | 4.8.7 | A40083 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 1367 | 0 | 1367 | 0 |  | N |  | 2000M180/164 | YNE93: M180 J3-4 | YNE93 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2425 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 229.0997 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys |  | 4779 | 4779 | 0 | 1 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2426 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2427 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 EB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2428 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE94: M180 J4-5 | YNE94 Closure 1 WB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2429 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 6 | 0 | 6 | 0 |  |  |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2430 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 1 | 0 | 1 | 0 |  |  |  | 2000M180/168 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2429 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 3 | 0 | 3 | 0 |  |  |  | 2000M180/170 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2431 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 1 | 0 | 1 | 0 |  |  |  | 2000M180/173 | YNE94: M180 J4-5 | YNE94 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 2 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2432 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 4.4138 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 1 | 1 | 0 | 1 |  |  |  | 2000M180/174 | YNE94: M180 J4-5 | YNE94 Closure 2 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2433 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 3 | 0 | 3 | 0 |  |  |  | 2000M180/176 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 2 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2433 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 4 | 0 | 4 | 0 |  |  |  | 2000M180/179 | YNE94: M180 J4-5 | YNE94 Closure 2 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2434 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 13.2413 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 3 | 3 | 0 | 1 |  |  |  | 2000M180/182 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 3 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2434 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 22.0688 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 5 | 5 | 0 | 1 |  |  |  | 2000M180/185 | YNE94: M180 J4-5 | YNE94 Closure 3 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2429 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 7 | 0 | 7 | 0 |  |  |  | 2000M180/188 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2430 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 1 | 0 | 1 | 0 |  |  |  | 2000M180/190 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 4 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2435 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 3 | 0 | 3 | 0 |  |  |  | 2000M180/195 | YNE94: M180 J4-5 | YNE94 Closure 4 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2436 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 31.44 | 0 | 31.44 | 0 |  |  |  | 2000M180/166 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2437 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 20.08 | 0 | 20.08 | 0 |  |  |  | 2000M180/168 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 EB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2436 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | EB | 197.4 | 0 | 197.4 | 0 |  |  |  | 2000M180/188 | YNE94: M180 J4-5 | YNE94 Closure 1 EB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE94 Closure 1 WB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2437 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | WB | 41.19 | 0 | 41.19 | 0 |  |  |  | 2000M180/190 | YNE94: M180 J4-5 | YNE94 Closure 1 WB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2438 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys |  | 1968 | 0 | 1968 | 0 |  | N |  |  | YNE95: M181 | YNE95 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2439 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 NB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2440 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2441 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE95: M181 | YNE95 Closure 1 SB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2442 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | NB | 1 | 0 | 1 | 0 |  | N |  | 2000M181/131 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2442 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | NB | 8 | 0 | 8 | 0 |  | N |  | 2000M181/135 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2442 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | NB | 1 | 0 | 1 | 0 |  | N |  | 2000M181/142 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2442 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | NB | 7 | 0 | 7 | 0 |  | N |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2443 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | NB | 24.67 | 0 | 24.67 | 0 |  | N |  | 2000M181/145 | YNE95: M181 | YNE95 Closure 1 NB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE95 Closure 1 SB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2444 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Intervention missed / partially complete due to plant breakdown / incomplete activities due to time constraints. No further roadspace planned this financial year following assessment of outstanding works | 22dys | SB | 17.04 | 0 | 17.04 | 0 |  | N |  | 2000M181/150 | YNE95: M181 | YNE95 Closure 1 SB NS | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE100 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2445 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2.1127 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 51 | 51 | 0 | 1 |  |  |  | 2000A160/210 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure 1 CW OS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2446 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 44.9458 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | CW | 1085 | 1085 | 0 | 1 |  |  |  | 2000A160/215 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure 1 CW OS | Lane 2 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE100 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2445 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 27.0918 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 654 | 654 | 0 | 1 |  |  |  | 2000A160/325 | YNE100: A160 Brocklesby - Habrough | YNE100 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2447 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 275.6197 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 6653.51 | 6653.51 | 0 | 1 |  |  |  | 2000A160/220 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2447 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 14.567 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 351.65 | 351.65 | 0 | 1 |  |  |  | 2000A160/223 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2447 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 9.6578 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 233.14 | 233.14 | 0 | 1 |  |  |  | 2000A160/227 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2447 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 16.1407 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 389.64 | 389.64 | 0 | 1 |  |  |  | 2000A160/230 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2447 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 95.3949 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | EB | 2302.85 | 2302.85 | 0 | 1 |  |  |  | 2000A160/235 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure 1 CW NS CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2448 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 75.3515 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | CW | 1819 | 1819 | 0 | 1 |  |  |  | 2000A160/240 | YNE101: A160 Habrough - Manby | YNE101 Closure 1 CW NS | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2447 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 380.413 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 9183.24 | 9183.24 | 0 | 1 |  |  |  | 2000A160/305 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2447 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 139.1514 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 3359.14 | 3359.14 | 0 | 1 |  |  |  | 2000A160/310 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2447 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 36.0109 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 869.31 | 869.31 | 0 | 1 |  |  |  | 2000A160/313 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2447 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 4.9573 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 119.67 | 119.67 | 0 | 1 |  |  |  | 2000A160/315 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE101 Closure CGS 45078 Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 2447 | Grass & Vegetation - Cutting of Amenity grass areas, including gates way features, Village Verge & Landscape Features 2 | 74.1792 | 4.8.5.1 | A40078 |  | 0 | CGS | 3000 - Landscape and Ecology | Complete | Complete | Complete | 2023-06-01 | 2023-06-30 | Complete |  | 22dys | WB | 1790.7 | 1790.7 | 0 | 1 |  |  |  | 2000A160/320 | YNE101: A160 Habrough - Manby | YNE101 Closure | Lane 1 Closure | 2 |  |  | 6 times per year (Mar - Oct)
YNE102 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2449 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 923 | 0 | 923 | 0 | Unable to complete due to ongoing Wentbridge and Ferrybridge works | Y |  |  | YNE102: A162 Ferrybridge | YNE102 Closure | Lane 1 Closure | 1 | No |  | ILM 2 times per year (Apr - Sept)
YNE102 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2450 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE102: A162 Ferrybridge | YNE102 Closure 1 NB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE102 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2451 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB NS | Lane 1 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept) | [5 empty] | Day Shift
YNE102 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2452 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  |  |  | 0 | 0 |  |  |  |  | YNE102: A162 Ferrybridge | YNE102 Closure 1 SB OS | Lane 2 Closure | N/A |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 NB OS Bettamix 45078 VRS - Check all Road Restraint System - ILM | 2453 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 928 | 0 | 928 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45819388
YNE104 Closure 1 NB NS Bettamix 45078 VRS - Check all Road Restraint System - ILM | 2454 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 937 | 0 | 937 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/11 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM Every 2 years |  |  | 45819388
YNE104 Closure 1 NB OS Bettamix 45078 VRS - Check all Road Restraint System - ILM | 2453 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 936 | 0 | 936 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/11 | YNE104: A631 Tinsley | YNE104 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45819388
YNE104 Closure 1 SB OS Bettamix 45078 VRS - Check all Road Restraint System - ILM | 2455 | VRS - Check all Road Restraint System - ILM | 0 | 4.2.1 | A40001 |  | 0 | Bettamix | 0400 - Road Restraint Systems | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 891 | 0 | 891 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM Every 2 years |  |  | 45819388
YNE104 Closure 2 CW OS CGS 45078 Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 2456 | Filter drains - Weed spray along Filter Drain and Combined carrier and Filter drain | 0 | 4.3.11.2 | A40020 |  | 0 | CGS | 0500 - Drainage & Service Ducts | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 288 | 0 | 288 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW OS | Lane 2 Closure | 1 |  |  | Every 2 years (May - Sept)
YNE104 Closure Vaisala 45078 Meteorological sites - Clean fog sensors | 2457 | Meteorological sites - Clean fog sensors | 0 | 4.6.6 | ART009 |  | 0 | Vaisala | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 1 | 0 | 1 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE104 Closure Infratec 45078 Remotely operated temporary traffic management signs - Change batteries | 2458 | Remotely operated temporary traffic management signs - Change batteries | 0 | 4.6.8.1 | ART013 |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 1 | 0 | 1 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 & 2 Closure | 1 |  |  | Every 5 years |  |  | On ServiceNow
YNE104 Closure Infratec 45078 Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 2459 | Remotely operated temporary traffic management signs - Inspect and clean battery connectors | 0 | 4.6.8.2 | ART014A |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 1 | 0 | 1 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE104 Closure Infratec 45078 Remotely operated temporary traffic management signs - Clean sign face | 2460 | Remotely operated temporary traffic management signs - Clean sign face | 0 | 4.6.8.3 | ART014B |  | 0 | Infratec | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 1 | 0 | 1 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 & 2 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE104 Closure Amey 45078 Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 2461 | Midas outstations and detectors - Optimisation of MIDAS detectors in accordance with MCH 2584 [Ref 11.N] | 0 | 4.6.9 | ART030 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 1 | 0 | 1 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE104 Closure Amey 45078 Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 2462 | Road Traffic Signals (RAG) - Check alignment and condition of site and operation of any rotating tactile devices | 0 | 4.6.10.1 | ART023A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 4 | 0 | 4 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE104 Closure Amey 45078 Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 2463 | Road Traffic Signals (RAG) - Inspection and test in accordance with TD 101 [Ref 43.N] | 0 | 4.6.10.2 | ART023B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 4 | 0 | 4 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE104 Closure Amey 45078 Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 2464 | Electrical supplies, components and distribution cables - RCD operation and visual inspection of cable terminations | 0 | 4.6.12.2 | ART028 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 4 | 0 | 4 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE104 Closure Amey 45078 Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 2465 | Emergency Roadside Telephone (ERT) - Clean telephone internally and externally - Intelligence Led Maintenance | 0 | 4.6.4 | ART007 |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 2 | 0 | 2 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 1 |  |  | ILM Annual Network Wide |  |  | On ServiceNow
YNE104 Closure Amey 45078 CCTV PTZ Cameras - Clean camera lens | 2466 | CCTV PTZ Cameras - Clean camera lens | 0 | 4.6.13.1 | ART029A |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 1 | 0 | 1 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE104 Closure Amey 45078 CCTV PTZ Cameras - Check camera functionality | 2467 | CCTV PTZ Cameras - Check camera functionality | 0 | 4.6.13.2 | ART029B |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 1 | 0 | 1 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE104 Closure Amey 45078 CCTV PTZ Cameras - Check data and power supplies | 2468 | CCTV PTZ Cameras - Check data and power supplies | 0 | 4.6.13.3 | ART029C |  | 0 | Amey | 1500 - Roadside Technology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 1 | 0 | 1 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 1 |  |  | Annually |  |  | On ServiceNow
YNE104 Closure CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2469 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys |  | 831 | 0 | 831 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2470 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  | 0 | 0 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 NB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2471 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  | 0 | 0 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure 1 NB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 SB OS CGS 45078 Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 2472 | Grass and vegetation - Maintain and preserve sight lines & stopping distance, Junc,curves, bends & Central Reserves 1 | 0 | 4.8.3.1 | A40072 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | No assets | 22dys |  |  | 0 | 0 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure 1 SB OS | Lane 2 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 2 CW NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2473 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 7 | 0 | 7 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE104 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2474 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 3 | 0 | 3 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45817472
YNE104 Closure 3 CW NS CGS 45078 Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2475 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 0 | 4.8.3.2 | A40073 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 3 | 0 | 3 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE104 Closure 2 CW NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2476 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 117 | 0 | 117 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE104 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2477 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 6 | 0 | 6 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45818261
YNE104 Closure 1 NB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2477 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 3 | 0 | 3 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/11 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45818261
YNE104 Closure 1 SB NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2478 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 5 | 0 | 5 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45818261
YNE104 Closure 3 CW NS CGS 45078 Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2479 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 0 | 4.8.3.3 | A40074 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 74 | 0 | 74 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE104 Closure 2 CW NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2480 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 14 | 0 | 14 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE104 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2481 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 10 | 0 | 10 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45819027
YNE104 Closure 1 NB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2481 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 2 | 0 | 2 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/11 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45819027
YNE104 Closure 1 SB NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2482 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | SB | 10 | 0 | 10 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/12 | YNE104: A631 Tinsley | YNE104 Closure 1 SB NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep) |  |  | 45819027
YNE104 Closure 3 CW NS CGS 45078 Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2483 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 0 | 4.8.4.1 | A40075 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 12 | 0 | 12 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 1 |  |  | Annually (Apr - Sep)
YNE104 Closure 2 CW NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2484 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 17 | 0 | 17 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2485 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 22 | 0 | 22 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45819000
YNE104 Closure 3 CW NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 2486 | Grass and vegetation - Remove obstructions & Maintain safe access to feeder pillars and technology equipment 1 - ILM | 0 | 4.8.4.2 | A40076 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 10 | 0 | 10 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/3 | YNE104: A631 Tinsley | YNE104 Closure 3 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 2 CW NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2487 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | CW | 888.43 | 0 | 888.43 | 0 | Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/1 | YNE104: A631 Tinsley | YNE104 Closure 2 CW NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept)
YNE104 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2488 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 1468.31 | 0 | 1468.31 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/10 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45818684
YNE104 Closure 1 NB NS CGS 45078 Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 2488 | Grass and vegetation - Remove obstructions & Maintain safe access to footways, footpaths, bridleways, cycle tracks 1-ILM | 0 | 4.8.4.3 | A40077 |  | 0 | CGS | 3000 - Landscape and Ecology | Removed from Rebaselined SP | Removed from Rebaselined SP | Removed from Rebaselined SP | 2023-06-01 | 2023-06-30 | N/A | Unable to access due to scheme works. Roadspace not available within 2023/24. | 22dys | NB | 23.26 | 0 | 23.26 | 0 | 5/9 TM not on Rbt so no assets in closure due to scheme conflicts restricting access. Unable to access due to conflicting TM arrangements; share oppurtunities identified and agreed for July | Y |  | 4400A631/11 | YNE104: A631 Tinsley | YNE104 Closure 1 NB NS | Lane 1 Closure | 1 |  |  | ILM 2 times per year (Apr - Sept) |  |  | 45818684