## Sheet1
Highways England Confirmation of Task Order
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties Redactions made under FOIA 2000 exemptions sec 40: personal info and sec 43: commercial.
Supplier: | PB
Project Title: | Contract Management 11
Contract Ref. | 114/2/1391/5 | CPA No.: | Redacted |  | BPA No.: | Redacted
PIN Description: | SE Contract Management | Sub Pin: | Redacted |  | PIN No.: | Redacted
HE Reference: | SE 84 15/16PB | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 1.12 | Consultant Contact: |  |  | Redacted
Start & End Date: | 01/10/2015 - 28/02/2016 | CTO Authorisation No. |  |  | Redacted
Task Overview
Background Task Overview and Expected Outcomes For a period of 5 months between 01th October 2015 - 28th February 2016 1. Attendance by project coordinator, PM or appropriate nominated representative at monthly meetings 2. Monthly progress report - 3 days before meetings 3. Monthly financial forecasts on accordance to Highways England timestable 4. Programme monitoring 5. Monthly invoicing
Task Objectives and Milestones
1. Attendance by project coordinator, PM or appropriate nominated representative at monthly meetings 2. Monthly progress report - 3 days before meetings 3. Monthly financial forecasts on accordance to Highways England timestable 4. Programme monitoring 5. Monthly invoicing
Task Outcomes
Expected project outcomes 2 / 3 working days before meeting Monthly financial information on last working day of the month Draft CTO to be loaded on TAPE within 2 working days of the
Project Risk and Management
Project Risk and Management 1 - Task set up and Administration 2 - Inception 3 - Verification 4 - Technical Assessment: Not all information provided at project outset 5 - Reporting 6 - Finalising 7 - Close down: Delay in task being closed causes delay to the review of KPIs are delayed there is a risk they will not accurately reflect task performance. Mileage will be charged at the higher rate of Redacted per mile.
Project Title: | Contract Management 11 |  |  |  | HE Reference: | SE 84 15/16PB
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Lump Sum
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 84 15/16PB | Redacted | Redacted |  | 2015-09-23 | Redacted | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | Redacted
Carry over Amount from previous financial year |  |  |  |  | Redacted
Previously Invoiced Amount |  |  |  |  | Redacted
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | Redacted
Total Project Fee Estimate |  |  |  |  | Redacted
Name | Grade | Hours |  | Hourly Rate | (£)
Hayward, Emma | Principal Planner / Engineer | Redacted | @ | Redacted | Redacted
Shiu, Caz | Senior Technician | Redacted | @ | Redacted | Redacted
Stoneman, Andrew | Director | Redacted | @ | Redacted | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
Date Produced: | 2015-09-30 |  | Works Total |  | Redacted
Confidential and commercially sensitive information which shall not be disclosed to third parties |  |  |  |  | Redacted
|  |  | Sub Total |  | Redacted
|  |  | Expenses |  | Redacted
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | Redacted