Call-Off Schedule 20 (Call-Off Specification)

This Schedule sets out the characteristics of the Deliverables that the Supplier will be required to make to the Buyers under this Call-Off Contract

Bid Pack

Attachment 3 – Statement of Requirements

Contract Reference: CCLL24A05 Provision of EVI Support Service – Legal Support

PURPOSE

  - CCS is developing a support service for buyers seeking to procure Electric Vehicle Infrastructure (EVI) via an open tender concession contract under the Procurement Act 2023. This will be taken forwards in two phases. Through the service, customers will be able to draw on CCS commercial expertise alongside robust templates, legal documents, social value advice and other support to leverage private sector investment in EVI.

  - The scope of this contract covers provision of legal and consultancy services to review and develop ‘customisable’ tender documents, schedules, guidance and advice. These relate to the procurement of public electric vehicle charging infrastructure through a concession contract by local authorities and other public sector bodies.

  - Many (but not all) of the anticipated documents exist in draft form, including an example of terms and conditions that with some adaptation may be appropriate to use in a configurable tender pack. Some of the documentation may require modifying or adapting depending on the intended use case for the charging infrastructure (on-street or off-street). Full details are outlined in the requirements section below.

  - The contract duration and maximum contract value for phase 1 will be set out in the awarded contract (and identified as a maximum committed cost for phase 1). The contract will also provide scope to undertake additional related services as part of phase 2 should CCS request these (up to the maximum overall contract value). Phase 2 is subject to subsequent internal CCS approval. There is no obligation on CCS to request phase 2 activity.

  - Suppliers should provide full details related to the delivery of phase 1, answering in full the assessment questions. The scope and deliverables for any additional services under Phase 2 will be agreed between both parties prior to the additional activity commencing.

  - The output from Phase 1 will enable CCS to own and host a set of customisable tender documents and supporting guidance reflecting best practice. These are intended to significantly reduce resource and legal costs that would otherwise be incurred by the public sector in the deployment of EVI.

# BACKGROUND TO THE BUYER

  - Crown Commercial Service (CCS) is an executive agency and trading fund of the Cabinet Office of the UK Government. CCS is responsible for managing the procurement of common goods and services, increasing savings for the taxpayer by centralising buying requirements, and leading on procurement policy on behalf of the government.

  - CCS plays an important role helping the UK public sector save money when buying common goods and services. We are the biggest public procurement organisation in the UK. We use our commercial expertise to help buyers in central government and across the public and third sectors to purchase everything from locum doctors and laptops to police cars and electricity.

# OVERVIEW OF REQUIREMENT

  - The supplier will review and contribute to documentation that forms part of a CCS EVI support service aimed at public sector organisations seeking to implement EVI concession contracts via an open tender route.

  - The support service (to be developed by CCS) will provide route to market support offering:

  - A simpler, accessible procurement process for customers

  - Reduced lead time - through configurable templates, pre-written terms, and guidance

  - Value to the public sector - with guidance on futureproofing and end-of-life recycling and positive local impact

  - In preparation for the Phase 1 work outlined in this statement of Requirements, CCS will work with a stakeholder group including The Department for Transport, Cenex and PA Consulting (referred to as the Procurement Forum) to create draft documentation for review. Limited engagement and discussion by the supplier with representatives from the procurement forum may be required during this activity.

# DEFINITONS

| Expression or Acronym | Definition |
| --- | --- |
| EVI | means Electric Vehicle Charging Infrastructure. |
| DfT | means Department for Transport. |
| OZEV | means Office for Zero Emission Vehicles. |
| LEVI Fund | means Local Electric Vehicle Infrastructure Fund - a government grant fund for local authorities to help fund deployment of on street EVI |

# SCOPE OF REQUIRMENT

## CCS is seeking support to review and finalise a ‘customisable’ concession contract tender pack and guidance suitable for use by public sector bodies to procure on and off street public charging infrastructure. This must be compliant with procurement rules (including PA2023 and relevant regulations applicable to concession contracts).

## The scope of the contract covers provision of qualified expert staff (legal services). Suppliers should provide full details regarding the delivery of Phase 1 activities and provide day rates for undertaking phase 2 activity where this is agreed between the supplier and CCS

## The phase 1 activity will require expert knowledge of the EVI sector and procurement law as applied to concession contracts. Knowledge of the Procurement Act 2023 and related regulations is also important.

  - For the avoidance of doubt, the output and IPR from phase 1 will be owned by CCS and made available to the public sector to inform and support open tender concession contracts. Future use of the documentation to procure EVI will be at the buyers’ risk and they will be advised to seek their own legal advice to ensure the final tender documents are suitable for the specific requirements being sought.

## Additional activity (Phase 2) is at the discretion of CCS and will be limited to advice and guidance related to the support service.

# THE REQUIREMENT

## Bidders should provide full details regarding the delivery of Phase 1 activities. These include:

    - initial advice on the outline and structure of tender pack for an open tender concession contract for on-street EV charging, reflecting on best practice.

    - a review of and updates to a draft ‘customisable’ concession contract tender pack and the development of related guidance. The draft tender documents will be made available by CCS (in collaboration with the procurement forum). The task may include the development of new schedules or annexes.

    - making drafting changes and recommendations related to:

      - compliance with relevant procurement rules. This will include the current procurement regulations (for any procurement undertaken before February 2025) and necessary changes to reflect implementation of the Procurement Act 2023.

      - alignment, where applicable, with DfT requirements related to EV infrastructure (as outlined in LEVI grant funding documentation).

      - detail potential legal risks with use of the configurable tender pack and related guidance by public bodies and set out options to mitigate risks.

      - the terminology, to ensure clarity and precision in language. In particular to reflect the desire to use plain English in contract terms.

      - improvements based on legal precedent and best practice

    - provide concise, high level process driven guidance to assist public bodies looking to undertake a concession based procurement for EVI. Include advice on tailoring the customisable contract pack to the buyer’s requirements.

    - conduct a review to ensure other related regulatory and statutory measures applicable to EV Infrastructure requirements (from site survey, connection and installation to operation and decommissioning) are covered in the contract provisions and guidance. This should reflect the whole life-cycle of an EVI contract.

    - comment briefly on an approach to deliver social value, sustainability, ethical sourcing and accessibility features within the configurable tender pack.

    - Make recommendations on structuring the tender pack so that it aligns with and simplifies a procurement delivered through the Jaegar e-sourcing portal.

  - Within Phase 1 provision should be made for an online stakeholder presentation to explain any recommendations and to answer questions.

  - Funding of up to a maximum of £90,000 has been approved for the delivery of phase 1 over an expected duration of up to ten (10) weeks. The price and timescale proposed by bidders for delivery of phase 1 should reflect the maximum approved funding and the expected timescale.

  - Suppliers are required to confirm their intent to support phase 2, if requested by CCS following phase 1, and to provide rate card information relevant and applicable to the additional activity (under Phase 2). Please set out any discounts on lot 1 rates. Any future request to undertake phase 2 activity is at the discretion of CCS and will be limited to advice and guidance on a range of topics including but not limited to:

## the process of assessing a supplier’s financial standing and capability ahead of an open procurement to further reduce the pressure on buyers.

## developing added value features, for example, on new accessibility standards for chargepoint sites or provisions that enhance sustainability or social value.

## improving and refining the tender pack and associated guidance including for new EVI use cases such as workplace or fleet charging

    - the management of EVI concession contracts

  - The option to undertake additional and related services to support phase 2 activity is provided in the overall contract duration and value. The overarching contract value has been set at a maximum value of £Redacted under FOIA section 43, Commercial Interests (for both Phase 1 and the optional Phase 2) with a maximum contract duration of 12 months to complete Phase 2 if this is requested following completion of phase 1. Any additional services (beyond Phase 1) will be subject to internal CCS financial and policy approval.

  - Depending on the nature of the activity undertaken in phase 2, the successful supplier may be required to establish an ethical wall between the support /delivery team and the wider organisation.

# KEY MILESTONES AND DELIVERABLES

# The following Contract milestones/deliverables shall apply:

| Milestone/Deliverable | Description | Timeframe or Delivery Date |
| --- | --- | --- |
| Project Initiation | Kick Off - Review of proposed project plan and reporting arrangements (including clarifications to be agreed with CCS). Initial documentation provided to the supplier by CCS | Within 1 week of contract award |
| Feedback on structure | Provide initial views and suggestions on the outline and structure of the configurable Invitation to Tender pack | Within week 2 of Contract Award |
| Initial draft tender documents | Complete initial changes and make recommendations to documents provided by CCS and make available (in draft) additional or updated documents, schedules and annexes as appropriate | Within week 4 of Contract Award |
| Interim review | Progress review and online presentation to stakeholders (CCS and Procurement Forum) | Within week 5 of Contract Award |
| Initial guidance | Supplier to draft initial high-level process driven guidance and supporting guidance on completing the tender pack. Provide outputs from a review of relevant standards and legislation. | Within week 6 of Contract Award |
| Final review and delivery of revised documents guidance | Complete drafting changes, development of additional schedules and or clauses identified as necessary following the feedback session, and process guidance. Documents to be provided in word and PDF format, and suitable for hosting and viewing on-line. This will include a core ITT document set compliant with the current legislation and a full set based on the implementation of the procurement act 2023. Two iteration rounds will be supported before the documents are finalised. IPR (including rights to publish and disseminate information) related to the draft and final reports will be assigned to Crown Commercial Service.. | Within week 10 of Contract Award |

# MANAGEMENT INFORMATION/REPORTING

  - The Provider will report to the CCS Technology Category - Transport Technology Strategy Lead on a weekly basis to review progress against the agreed Engagement and Delivery Plan. This shall include but not limited to:

    - Progress against key milestones

    - Identified risk to delivery

  - Updates will be required on an as-needed basis within standard working hours.

  - The Provider will work with CCS to agree a template for reporting

# VOLUMES

## Not Applicable

# CONTINUOUS IMPROVEMENT

## Changes to the way in which the Services are to be delivered must be brought to the Buyer’s attention and agreed prior to any changes being implemented.

# SUSTAINABILITY / SOCIAL VALUE

## Crown Commercial Service have determined that the following theme is relevant and proportionate to this Statement of Requirements:

## Wellbeing – Improve health and wellbeing in the workforce: Demonstrate action to support health and wellbeing, including physical and mental health, in the contract workforce.

## Procurement Policy Note (PPN) 6/20 – Taking Account of Social Value in the Award of Central Government Contracts. ‘Social value should be explicitly evaluated in all central government procurement, where the requirements are related and proportionate to the subject-matter of the contract, rather than just ‘considered’.

## PPN 06/20 guidance documents can be found at: https://www.gov.uk/government/publications/procurement-policy-note-0620-taking-account-of-social-value-in-the-award-of-central-government-contracts .

  - ‘Social Value for Commercial Success’ an e-learning course accessed through the Government Commercial College that can be found via the ‘Social Value Mandatory eLearning’ link. It takes less than one hour to complete and will help you to better understand what social value is, why it is important and how to implement it.

# QUALITY

  - Industry best practice and standards relating to data collection, statistics, analysis and reporting should be adhered to where appropriate in the analysis and outputs related to this work.

# PRICE

  - Prices has been submitted via the e-Sourcing Suite Attachment 4 – Price Schedule excluding VAT and including all other expenses relating to Contract delivery.

  - Price will be evaluated against delivery of the requirements covered by Phase 1 (fixed maximum price proposed in bid). Suppliers will also include their rate card, including any discounts against the Lot 1 Framework rates to be utilised if Phase 2 of the contract is used.

# STAFF AND CUSTOMER SERVICE

## The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

## The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

## The Supplier shall ensure that staff understand the Buyer’s vision and objectives and will provide excellent customer service to the Buyer throughout the duration of the Contract.

# SERVICE LEVELS AND PERFORMANCE

## The Buyer will measure the quality of the Supplier’s delivery by:

| KPI/SLA | Service Area | KPI/SLA description | Target |
| --- | --- | --- | --- |
| ## 1 | ## Timeliness | ## Weekly updates provided via email. Staff available for a weekly call to discuss progress against plan. | ## 100% delivery of email updates and availability for weekly call. |
| ## 2 | ## Timeliness | ## Deliverables completed by delivery date unless agreed by CCS in advance – measured by submission of reports or updates by target delivery date | ## 100% of deliverables completed by target delivery date |
| ## 3 | ## Quality | ## Progress with Phase 1 requirements align with goals and objectives for Phase 1 – supplier to demonstrate alignment with goals and objectives in weekly reports | ## Demonstrated alignment at weekly calls |
| ## 4 | ## Quality | ## Advice and data is accurate, complete (as far as best endeavours permit) and consistently applied in the outputs. | ## No significant concerns raised in peer review or in discussions with procurement forum stakeholders |
| ## 5 | ## Effectiveness | ## Number of touchpoints across procurement forum is sufficient to capture and reflect aims of this exercise | ## At least two touchpoints with wider procurement forum stakeholders |
| ## 6 | ## Additional work | ## Where appropriate (requested by CCS) the KPIs may also be applicable to additional work under the contract. |  |

# SECURITY AND CONFIDENTIALITY REQUIREMENTS

## The Supplier shall keep in confidence any confidential or commercially sensitive Information disclosed to it by CCS and not disclose that Information to any person without the written consent.

## IPR arising from this activity (including rights to publish and disseminate information) and related to the draft and final documents will be assigned to Crown Commercial Service.

# PAYMENT AND INVOICING

## Payment can only be made following satisfactory delivery of pre-agreed certified products and deliverables.

## Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

## Invoices should be submitted to: Redacted under FOIA section 40, Personal Information

# CONTRACT MANAGEMENT

## Attendance at Contract Review meetings shall be at the Supplier’s own expense.

# LOCATION

## The location of the Services will be carried out at the suppliers own base location