## Sheet1
Highways Agency Confirmation of Task Order
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | JMP
Project Title: | Shropshire/Telford/Herefordshire Area Based Support (1/10/15-31/12/15)
Contract Ref. | 0 | CPA No.: | Redacted |  | BPA No.: | Redacted
PIN Description: | Development Planning | Sub Pin: | Redacted |  | PIN No.: | Redacted
HA Reference: | WM 42 15/16JMP | HA Ordering Officer: |  |  | Redacted
Consultant Ref: | X101002 | Consultant Contact: |  |  | Redacted
Start & End Date: | 01/10/2015 - 31/12/2015 | CTO Authorisation No.
Task Overview
Highways England supports the economy through the provision of a safe and reliable strategic road network (SRN), which allows for the efficient movement of people and goods. A well-functioning strategic road network enables growth by providing for safe and reliable journeys. This can help reduce business costs by providing certainty, improving access to markets, enabling competition, improving labour mobility, enabling economies of scale, and helping attract inward investment. However, development proposed in Local Plans or through planning applications has the potential to adversely impact on the SRN. It is therefore imperative that Highways England engages efficiently and effectively with local authorities and developers to ensure that growth can be delivered in a manner consistent with Highways England’s objectives. In order to ensure effective engagement with the planning system, Highways England requires JMP to provide further support across the West Midlands. This is necessary owing to an increased workload within the Asset Development Team on Route Strategies, Super Pinch Points and a significant increase in the renewal schemes identification and design requirements. This increased support is related specifically to Spatial Planning activities (Development Management Planning (DP) and Spatial Planning (SP)) and Highways England has proposed a new approach as set out below for delivery of DP and SP support across the current five operationally defined areas in the West Midlands comprising Shropshire/Telford/Herefordshire, Stoke/Staffordshire, Worcestershire, Warwickshire/Coventry and the Motorway Box. This task relates specifically to delivery of DP and SP support in Shropshire/Telford/Herefordshire. JMP will provide DP and SP support to the Shropshire/Telford/Herefordshire Asset Managers delivering the following services: • Review of consultations on Local Plans and associated documentation including Infrastructure Delivery Plans and the Community Infrastructure Levy; • Direct technical planning support to the development management process; • Advice on and attendance at meetings; • Provision of technical and organisational support to stakeholder liaison meetings; and • Monitor consultation deadlines, in line with the 21 day deadline for responses. As part of the above, support will include advice such as third party telephone and email exchanges, and assistance in relation to any matters not otherwise covered by defined Contract Management or Studies tasks. (Note: Studies and Contract Management work will be subject to approval through separate CTOs as agreed with project sponsors). Under this approach, Asset Managers will review each case as it is received and determine the level of support they require. The Asset Manager will contact JMP to discuss and agree the nature of tasks required and the timescales. It is anticipated that the Asset Manager may seek to delegate as much as possible to JMP, subject to their wider priorities. It is very important that the Asset Managers and JMP work closely to ensure the tasks are identified and agreed in good time to ensure their delivery.
Task Objectives and Milestones
JMP will provide draft letters and written advice/responses where necessary for all appropriate requests with Asset Managers having only to carry out a short check for accuracy, appropriateness of response and tone before sending onwards. JMP will also provide direct liaison with the ASC, consultants, developers and local authorities. To facilitate the direct liaison JMP will contact/meet with the appropriate organisations and individuals involved in development and spatial planning. This activity will help to build relationships and supplement JMP’s knowledge of the area in relation to the SRN (to ensure JMP has the same knowledge base as the Asset Manager). During the ‘transition’ period, as JMP takes on more of Highways England’s development and spatial planning activities, JMP will make use of any un-allocated time within this CTO to strengthen/build the internal and external relationships and knowledge base. At all times, JMP will ensure that Highways England's reputation of supporting economic development is at least maintained, if not improved upon. JMP will track individual tasks undertaken through this CTO and will provide a summary of activity carried out against this CTO in conjunction with monthly invoices. This information will be provided in a form agreed with Highways England. Tasks involving less than one hour time input will not be separately recorded.
Task Outcomes
In providing the services referred to above, JMP will provide support and advice under this CTO through a range of means as discussed with Highways England sponsors including: • Face to face and telephone communication; • Provision of Reports/Technical Notes/Discussion Notes, letters and forms; • Emails and other forms of electronic communication; • Provision of plans/tabulations/diagrams/photographs/presentations/videos etc; • Provision of model outputs (including outputs produced from separate CTOs); • Attendance at meetings/working groups/workshops as required; • Provision of a monthly Shropshire/Telford/Herefordshire Task List spreadsheet. Individual tasks undertaken as part of this CTO will be submitted (unless in exceptional circumstances) to JMP by email to Redacted JMP will include these tasks on the JMP Task List with agreed deadlines where appropriate and JMP will monitor delivery of each task. Key JMP team members will be supported by other team members as necessary. To minimise project risk it is expected that the Asset Manager will identify the task in good time to enable JMP to provide the appropriate resources to complete the task within the defined timescale and achieve the 21 day deadline for responses to planning applications/consultations.
Project Risk and Management
Task management will include liaison with the task sponsor, setting up the task in TAPE and initial KPI scoring. The KPI for cost will not be relevant to this task and will be scored as 10. Costs incurred on the task will be billed to Highways England on a monthly basis and will reflect the actual costs incurred by JMP. JMP will monitor task costs and will advise Highways England should it appear that the task budget could be exceeded. The task costs in the CTO will not identify expenses in advance. All expenses related to the task will be sought in line with the Travel and Subsistence v2 document which forms part of JMP’s contract with Highways England. Time/Cost input will be set out in the CTO within TAPE for a range of JMP team members expected to work on the task during the month based on an assessment of forecast costs taking into account previous expenditure and anticipated work pressures. Project Director: Redacted
Project Title: | Shropshire/Telford/Herefordshire Area Based Support (1/10/15-31/12/15) |  |  |  | HA Reference: | WM 42 15/16JMP
HA Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Target Cost
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HA Sponsor
WM 42 15/16JMP | Redacted | Redacted |  |  | Redacted | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | Redacted
Carry over Amount from previous financial year |  |  |  |  | Redacted
Previously Invoiced Amount |  |  |  |  | Redacted
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | Redacted
Total Project Fee Estimate |  |  |  |  | Redacted
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
Redacted | Redacted | Redacted | @ | Redacted | Redacted
|  |  | @ |  | Redacted
|  |  | @ |  | Redacted
Date Produced: | 2015-09-14 |  | Works Total |  | Redacted
Confidential and commercially sensitive information which shall not be disclosed to third parties |  |  |  |  | Redacted
|  |  | Sub Total |  | Redacted
|  |  | Expenses |  | Redacted
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | Redacted