## Schedule of Work
MCA - SCHEDULE OF WORKS
Site Address: |  | Ravenscar
Station Road YO13 0LX
Project Type: |  | Minor Works Improvement
Tenderers for the above contract should complete the tables below, indicating what they would charge for each required element. Prices must: • Be stated in Pounds Sterling; • Include all other charges and overheads associated with the element being priced.
|  | General Works, Site conditions and Prelims : | Tender: £ | Comments
Notes
** | R&D Asbestos Survey to be supplied prior to commencement of any works.
** | Existing main power supply and fuse board to be reviewed. Any improvements must be advised at tender stage and detailed to the client in advance.
1 | General conditions temporary siteworks & Preliminaries
1.01 | No storage will be provided on site all materials and waste are to be removed from site as they occur
1.02 | Allow for all skips and storage containers as necessary , including all licenses for their location the client takes no responsibility for any materials, plant or equipment stored or left on site
1.03 | Toilet facilities will be available on site no canteen facilities will be available contractors are to make allowances for as necessary
1.04 | All public footpaths, highways and fire routes as part of the site and property are to be kept clear of all obstructions and debris at all time. All access and scaffolding should not obstruct the above at any time
1.05 | Allow for the supply of temporary fire fighting equipment, first aid equipment, hard hats, PPE and signage to comply with HSE regulations
1.06 | Allow for standard insurance during the works
1.07 | All electrical work and installation to be undertaken by an NICEIC Approved contractor to current regulations
1.08 | All work carried out must comply with current building regulations
2 | Strip out
2.01 | Remove all timber stud walls and doors as indicated on attached plan set aside office door for reuse later make good walls removed ready for decoration
2.02 | Make good ceiling and wall where timber studs removed
2.03 | Remove shower base and door complete include for terminating water and power supplies
2.04 | Remove ceramic tiles from shower area make good walls ready for decoration
2.05 | Remove floor coverings to Main office, shower area and kitchen area NB Toilet flooring to remain as existing
2.06 | Remove all electrical sockets, lighting and heaters not required in new layout
2.07 | Remove all kitchen base units including sink, under sink heater, cap off all services
3 | Building work remedial works
3.01 | Cut out plaster to outer wall as indicated on plan to install 300mm flat lateral straps from wall plate to solid brick work fixed using stainless steel screws make good plasterwork ready for redecoration
4 | Refurbishment works
4.01 | Install 75mm x 50mm studwork to form return wall as per plan covered with single 12.5 plaster boards both side tape and filled finished ready to receive decorations
4.02 | Install saved door and frame in new location as indicated on plan
4.03 | Install the following kitchen units from the Howden Glendevon gloss white range. 1 x 1000 drawer line sink base unit, 1 x 500 x 4 drawer unit, 1 x 1000 wall unit, 28mm bullnosed black laminated worktop with connection bolts, joint compound, included for all end panels, plinths, cornice and brushed steel effect handles
4.04 | Provide space for free standing fridge as per plan
4.05 | Install inset sink with pillar lever taps & wastes. Allow for connecting to existing under sink water heater and wastes pipes in toilet
4.06 | Install 3 x twin sockets above work surface, 1 x single socket outlet below work surface for fridge connected to a neon fused spur above work surface
4.07 | Provide and install 2 x 1000kw wall mounted heaters with thermostatic controls
4.08 | Install 3 x twin socket outlets with USB ports in white trunking as indicated on plan
4.09 | Allow to alter emergency lighting to suit new layout
4.01 | Allow to install Metro bevelled tiles to splash back between the worktop and wall cupboards, included for chrome trims. all tiling to be finished to a good quality. Tile colour white. Grout colour grey.
4.11 | Prepare and decorate all new and previously painted walls and ceilings. Using 1 undercoat and 2 top coat of Dulux Trade matt Emulsion Paint walls magnolia ceilings white
4.12 | Prepare and decorate all new and previously painted timber surfaces with 1 coat undercoat and 2 top coats white gloss
4.13 | Supply and install Milliken carpet tiles Ref; light trails colour Titanium to all areas on first floor except toilet allow for all door naps and finishing strips between carpet and Altro flooring to kitchen area
4.14 | Supply and fit Altro Reliance 25 safety flooring to area shown on plan by kitchen area mastic sealant all perimeter
5 | Completion
5.01 | On completion of electrical works, provide NICEIC electrical test cert for all new installations
5.02 | On completion of work allow to undertake an emergency lighting/ fire alarm discharge test in line with NICEIC guidelines and provide certification to demonstrate that all emergency lights / alarms are operational and compliant.
5.03 | On completion Contractor to undertake deep clean of working areas and leave the premises clean and tidy, free from dirt, dust and any builders waste and plant.
6 | Preliminaries & Overheads
6.01 | Prelims
6.02 | Overheads
| TENDER TOTAL |  | 0
| VAT |  | 0 | 20%
| TOTAL INCLUSIVE OF VAT |  | 0
The nominated Procurement Manager is:
Finance & Contracts
Bay 3/19 – Spring Place
105 Commercial Road
Southampton
SO15 1EG
Tel:- 020 381 72328
Email: - Contracts@mcga.gov.uk
Signed:
in the capacity of:
duly authorised to sign tenders for and on behalf of :
Postal Address:
Telephone No:
Email:
Date: