## CDRL Annex E Documents
2. CDRL detailed description
CDRL Number | Title | Document Content Requirements | Purpose | SOR Reference | T&Cs Reference | Applicable Codes and Standards | First submission to the Authority | Frequency of Submission | Submission Deadline | Medium of delivery
1 | Monthly Report | 1.1. In addition to the requirements of DEFCON 604, the report shall include clear summaries of: 1.1.1 Any issues arising impacting upon the performance of this Contract and proposed, inter alia, mitigation and resolution action to be taken 1.1.2 An explanation where performance is either below satisfactory (including any scores other than green identified in the BSC) or otherwise not in accordance with the contractor forecast of performance 1.1.3 Commercial issues 1.1.4 Supply chain status and performance 1.1.5 Provided as discrete attachments to the report each month: (Information Redacted) | Performance reporting | Serial Number 12.2 & 12.3 (WBS 12.0 ) | DEFCON 604 |  | N/A | Information Redacted | 5 business days prior to the last business day of every month (except where subsumed by the Annual Report) | Electronic copy in a single Microsoft Power Point format including embedded Microsoft Excel and PDF documents as required. Delivery shall be via the shared working environment.
2 | Finance Report | 2.1. The report shall detail as a minimum finance data by Authority Equipment showing payment and performance retention (if any), spend to date, forward commitment, forward predicted load, uncommitted and spend on risk. The Finance reporting structure shall be in accordance with Appendix 1. Note: Reporting WBS updated for Period 2 2.2. (Information Redacted) 2.3 The finance reports shall include variances statements against the 12-month forecast baseline. The Finance reporting structure shall be in accordance with Appendix 1. 2.4. The report shall include forecast payment profiles for Tasking however is to be identified separately to the core spend. 2.5 The Contractor shall retain the Finance Report information and supporting financial records in accordance with DEFCON 609. | Performance reporting | Serial Number 12.2 & 12.3 (WBS 12.0 ) |  |  | N/A | Information Redacted | As part of the monthly report and the Annual Progress Report. | Microsoft Excel. Delivery shall be via the shared working environment. Also to be delivered to the customer alongside the monthly report via email in a compressed file.
3 | Operational Damage Register | 3.1. In addition to the requirements of Clause 8.2.10 of the Special Conditions, the register shall include, but not be limited to, each of the following as headers: 3.1.1. Reference number 3.1.2. Date of occurrence 3.1.3. Date added to register, 3.1.4. Authority Equipment affected, 3.1.5. Platform involved 3.1.6. Description of event 3.1.7. Reason for defining as Operational Damage 3.1.8. Rectification scope of work 3.1.9 Sentencing status (e.g. pending, accepted or rejected) 3.1.10 Relevent Completion Date 3.1.11 Actual Completion Date 3.1.12 OD Rectification Costs 3.1.13 Remaining uncommitted Operational Damage Limit of Liability | Record of any Operational Damage occurrences | Serial Number 17.2 & (WBS 17.0) | Clause 6.11 8.2 of the Special Conditions |  | N/A | Information Redacted | As part of the monthly report and the Annual Progress Report. | Microsoft Excel. Delivery shall be via the shared working environment. Also to be delivered to the customer alongside the monthly report via email in a compressed file.
4 | Task Register | 4.1. In addition to the requirements of Clause 9.1 of the Special Conditions, the register shall detail: 4.1.1 which Tasks are approved, planned, cancelled or withdrawn; 4.1.2 which Authority Equipment(s) the Task relates to; 4.1.3 brief description of the work; 4.1.4 price; 4.1.5 original due date, any and all changes agreed to the due date, expected completion date, actual completion date; 4.1.6 current status/progress achieved; and 4.2. The register shall also contain appropriate hyperlinks to supporting documentation such as the TAF (inclusive of both the originally version authorised by the Authority as well as any amendments thereto agreed by the Parties). | Record of any ad-hoc task | Serial Number 12.2 & 12.3 (WBS 12.0 ) | Clause 7 9.1 of the Special Conditions |  | N/A | Information Redacted | As part of the monthly report and the Annual Progress Report. | Microsoft Excel. Delivery shall be via the shared working environment. Also to be delivered to the customer alongside the monthly report via email in a compressed file.
5 | Balanced Scorecard (BSC) | 5.1. The BSC shall: 5.1.1 detail the month by month record of the Contractor’s performance against the Performance Levels to date. 5.1.2 forecast performance for the next 3 months following the reporting month such to be clearly indicated as a forecast. | Performance reporting | Serial Number 12.2 & 12.3 (WBS 12.0 ) | Clause 11 13 of the Special Conditions |  | N/A | Information Redacted | As part of the monthly report and the Annual Progress Report. | Microsoft Excel. Delivery shall be via the shared working environment. Also to be delivered to the customer alongside the monthly report via email in a compressed file.
6 | Contractor Stocked Inventory (CSI) account | 6.1. A CSI account for all sites to be produced inclusive of all stock held by the Contractor on the CSI accounts at any Contractor sites including those locations within Authority establishments. | Asset accounting | Serial Number 7.1 (WBS 7.0 ) | - |  | N/A | Information Redacted | As part of the monthly report and the Annual Progress Report. | Microsoft Excel. Delivery shall be via the shared working environment. Also to be delivered to the customer alongside the monthly report via email in a compressed file.
7 | Critical items list | Information Redacted | Inventory management and supply risk | Serial Number 8.7 (WBS 8.0 ) | - |  | N/A | Information Redacted | As part of the monthly report and the Annual Progress Report. | Microsoft Excel. Delivery shall be via the shared working environment. Also to be delivered to the customer alongside the monthly report via email in a compressed file.
8 | Annual Progress Report | 8.1. In addition to the requirements of DEFCON 604, the report shall contain an overview of the preceding year, issues for action and a forecast of activity for the following year including a summary of the achievements against the performance indicators in the preceding period, overall progress of the Contract, financial statements, trends, the status of assets, obsolescence, operational damage, highlight any significant changes made to the (Information Redacted) and any other issues arising. 8.2. Attachments will be provided for the following: (Information Redacted) 8.3. The annual report shall subsume the monthly report for that month. | Performance reporting | Serial Number 12.4 (WBS 12.0 ) | DEFCON 604, DEFCON 620, Clause 6.12 of the Special Conditions, Clause 7.9 of the Special Conditions, Clause 11 of the Special Conditions |  | N/A | Information Redacted | 5 business days prior to the last business day falling in April each year of the Contract Term, save for the final year of the Contract in which case delivery shall be made 5 business days prior to the last business day falling in the month following contract end date. | Electronic copy in a single Microsoft Word or Powerpoint format including embedded Microsoft Excel and PDF documents as required. Delivery shall be via the shared working environment.
9 | Disposal Declaration Report | 9.1. A Report to optimise the Authority’s stock holdings and reduce overstock. 9.2 Format shall be in accordance with the Authority’s Inventory Analyser spreadsheet issued to the Contractor. 9.3 The Report shall include (Information Redacted) 9.4 The Report shall include (Information Redacted) | Inventory disposals activity to optimise the Authority’s stock holdings and reduce overstock. | Serial Number 9.3 (WBS 9.0) | - |  | N/A | Information Redacted | To be provided 12 months from Contract Effective Date and thereafter 5 business days prior to the last business day falling in January each year of the Contract Term. | Electronic copy in a single Microsoft Excel format which is embedded in the Annual Progress Report (reference CDRL 8).
10 | Establishment List (E List) | 10.1 The review process shall include consideration of all sections A to H detailed as follows: A - First fit items and built in spares B - Maintenance spares C - Test and tuning spares D - Diagnostics E - [Section removed] F - Jigs, tools and gauges G - Special to Type Test Equipment H - Deployment spares | Inventory management and configuration control | Serial Number 5.1 WBS 5.0) | DEFCON 16 |  | N/A | Information Redacted | E-list status to be provided at Contract award and as required thereafter. Annual status to be provided 12 months from cotract award and annulally thereafter. Individual E-Lists to be provided 20 working days following identification/notification of requirement to update. | Electronic copy of E List to be provided via Shared Working Environment,
11 | Obsolescence Management Plan | 11.1. The Obsolescence Management Plan shall as a minimum include: (Information Redacted) | Equipment through-life management | Serial Number 10.1 & 10.2 (WBS 10.0) | DEFCON 606, Clause 24 of the Special Conditions | (Information Redacted) | With Thales Bid (draft version) | Information Redacted | To be provided on the Contract Effective Date and to thereafter be maintained by the Contractor, and to include any changes as instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. To be provided 6 months prior to the end of the Contract Term. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
12 | Obsolescence Equipment Plan | 12.1. The Obsolescence Equipment Plan shall at a minimum include: (Information Redacted) | Equipment through-life management | Serial Number 101.1 & 10.2 (WBS 10.0) | DEFCON 606, Clause 24 of the Special Conditions | (Information Redacted) | N/A | Information Redacted | To be provided within two months of the Contract Effective Date and to thereafter be maintained by the Contractor, and to include any changes as instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. To be provided 6 months prior to the end of the Contract Term. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
13 | Not Used |  | Equipment through-life management | Serial Number 10.6 (WBS 10.0) | DEFCON 606, Clause 24 of the Special Conditions | BS EN 62402:2007
14 | Document Control Plan | 14.1 The documentation plan shall detail how the Deliverable Documents shall be maintained in accordance with this Annex E. The plan shall at a minimum cover each of the following documents: 14.1.1 Configuration Management Plan 14.1.2 Obsolescence Management Plan 14.1.3 Acquisition Management Plan 14.1.4 Annual Disposal Plan 14.1.5 Communications & Information Management Plan 14.1.6 Business Continuity Management Plan 14.1.7 Deliverable Quality Plan 14.1.8 Risk Management Plan 14.1.9 Asset Management Plan 14.1.10 Service Management Plan | Information management and control | Serial Number 13.7 (WBS 13.0) | - | - | N/A | Information Redacted | Within 4 months of the Contract Effective Date and to thereafter be maintained by the Contractor, and to include any changes as instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
15 | Exit Plan | 15.1 The Exit Management Plan shall be delivered in accordance with Annex S. | Exit Management | Annex S |  |  | N/A | Information Redacted | 12 months after Contract Effective Date. | Electronic copy in a single Microsoft Word format. Delivery shall be via the shared working environment.
16 | Service Management Plan | 16.1 The Service Management Plan shall at a minimum provide a summary of the Services to be performed and include the following: (Information Redacted) | Service delivery assurance | Serial Number 13.12 (WBS 13.0) | - |  | With Thales Bid (draft version) |  | To be provided on the Contract Effective Date and to thereafter be maintained by the Contractor, and to include any changes as instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
17 | Quality Management Plan | 17.1. The Quality Management Plan shall: 17.1.1 specify the activities, processes, plans, resources and responsibilities to be applied by the Contractor to ensure that all Contract quality requirements are fulfilled 17.1.2 detail effective and efficient business management controls, the allocation of roles, responsibilities and competence of delivery team staff with all aspects of Quality inclusive of clear methods of communication and reporting requirements operated and the quality related activities the Contractor and its Sub-Contractors shall 17.1.3 identify in sufficient detail all critical Sub-Contractors and the Contractor shall certify that all such Sub-Contractors have produced and maintained quality plans which have been reviewed and assessed as adequate by the Contractor and such Sub-Contractors maintain a quality management system which has been assessed and certified to a standard consistent with Clause 23.2 of the Special Conditions 17.1.4 analyse requirements under the Contract 17.1.5 demonstrate provision is in place to meet such requirements by means of processes, plans and joint work instructions 17.1.6 validate process compliance and effectiveness 17.1.7 ensure the quality of Contractor Deliverables 17.18 ensure data collection, analysis, sentencing and improvement 17.19 demonstrate efficient and affective supplier assessment, validation and monitoring. | Quality assurance | Serial Number 13.11 (WBS 13.0) | DEFCON 602A, Clause 23 of the Special Conditions | Information Redacted | N/A | Information Redacted | Within three month of the Contract Effective Date, and thereafter to be maintained by the Contractor, and to include any changes as instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
18 | Asset Management Plan | 18.1 The Asset Management Plan shall: (Information Redacted) | To safeguard the Authority’s assets held by the contractor. | Serial Number 7.1 (WBS 7.0) | DEFCON 611, DEFCON 694, Clause 43 of the Special Conditions | Information Redacted | With Thales Bid (draft version) | Information Redacted | To be provided on the Contract Effective Date and to thereafter to be maintained by the Contractor and an updated version to be supplied to the Authority 5 business days prior to the last business day falling in March each year. | Electronic copy in a single Microsoft Word format. Delivery shall be via the shared working environment.
19 | Safety and Environmental Management Statement (SEMS) | 19.1. The Safety and Environmental Management Statement shall define the method of compliance with the safety and environmental requirements specified by the Authority in support of the requirements of the prevailing Safety & Environmental Management Plan (SEMP) as provided by the Authority. At a minimum it shall detail the following: (Information Redacted) | Safety management | Serial Number 13.18 (WBS 13.0) | - | Information Redacted | N/A | Information Redacted | Within 2 months of the Contract Effective Date, and to be maintained by the Contractor throughout the contract term. To include any changes as instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
20 | Acquisition Management Plan | 20.1. The Acquisition Management Plan shall include: 20.1.1 an overview of the Contractor's organisation for execution of the Contract and outline management processes, including details of all Sub-Contractors with their risk factor for ceasing to trade or withdraw from the market 20.1.2 an overview of the supplier selection criteria used for Sub-Contractors 20.1.3 Supply chain management procedures and processes operated for the following events : 20.1.3.1 Supplier ceasing trading 20.1.3.2 Supplier financial stability 20.1.3.3 Supplier having issues with ability to supply 20.1.4 Detail shall be provided for configuration control of assets 20.1.5 demonstration of an effective process for ensuring value for money from suppliers. | Management information of the supply chain controls and processes | Serial Number 13.13 (WBS 13.0) | Clause 50 of the Special Conditions, Clause 51 of the Special Conditions | - | N/A | Information Redacted | To be provided on the Contract Effective Date and to thereafter be maintained by the Contractor, and to include any changes as instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. | Electronic copy in a single Microsoft Word. Delivery shall be via the shared working environment.
21 | Configuration Management Plan | Information Redacted | Configuration management | Serial Number 15.1 (WBS 15.0) | DEFCON 502, DEFCON 606, Clause 24.8 of the Special Conditions, Clause 43.12 of the Special Conditions | Information Redacted | N/A | Information Redacted | To be provided within one month Contract Effective Date and to thereafter be maintained by the Contractor, and to include any changes as instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
22 | Not Used
23 | Minutes and Agendas | Minutes 23.1. All minutes shall include at a minimum: 23.1.1 Subject heading. This shall set out the general purpose of the meeting, its location and date 23.1.2 Present. After the subject heading, a list of the people at the meeting by name and job title, prefaced by the word ‘Present’ shall be included. Listing the Chairman first and the Secretary last, regardless of their ranks or grades, annotated ‘Chairman’ and ‘Sec’ after their job title in a separate column. All others present shall be listed in descending order of rank or grade, along with their job title, and their committee or working group or meeting title when appropriate 23.1.3 In attendance. A record of any subject matter experts or other persons invited to meetings exclusivley for the purpose of either providing specialist advice or to represent a higher authority. Such details to be listed after those ‘Present’, prefaced by the entry ‘In attendance’ 23.1.4 Representatives. Detail of any persons in attendance as a representative of someone else who was due to attend, but could not. Listing such representatives details within the list of those present, and specifiying the name and job title of the person they are representing 23.1.5 Attendance for part of a meeting. A record of people who do not attend the whole meeting, recording the items for which they were present, either exclusion i.e. ‘(not for Item 1)’ or by inclusion i.e. ‘(Items 2 and 3 only)’ 23.1.6 Apologies. A record of any person who cannot attend a meeting, and is not represented, such details to be listed prefaced by ‘Apologies’ 23.1.7 Items. A record each item under a group heading, copied directly from the agenda. Below the item heading, separate paragraphs shall be used to summarise the statement of the issue, the relevant discussion and the decisions. Each item shall be structured as ‘a minute’ seperated into 3 parts, as as follows: 23.1.7.1 State the issue. An outline of the issue to be resolved by stating the issue in such a manner as the reader who was not at the meeting can understand the record of the discussion without referring to other documents 23.1.7.2 Record the discussion. A summary of the discussion relevant to the issue and decision(s). 23.1.7.3 Detail the decision(s). All decisions to be recorded in clear and precise terms including rationale for the decision(s), confirmation of who was authorised to take the decision(s), and confirmation for each decision what action(s) will be taken including by when, where and how, with clear linkage to relevant Actions Summary serial. 23.1.8 Signature block. This shall provide confirmation of the completeness and accuracy of the minutes and constitute authority to release by the Contractor. 23.1.9 Endorsement block. This shall be used to confirm (or otherwise) ratification of the minutes by the Authority. 23.1.10 Distribution list. Detail all persons issued with a copy of the minutes. 23.1.11 Actions Summary. Shall be provided in a table format and detail: 23.1.11.1 All actions from preceding meetings where the meeting concerned is one of a series (such actions presented consistent with 23.1.11.2 and 23.1.11.3 below) 23.1.11.2 Link to associated recorded decision 23.1.11.3 the actions and timetables for lead personnel with the information presented under the following headings: 23.1.11.3.1 Unique Serial 23.1.11.3.2 Item (or subject or decision, as appropriate) 23.1.11.3.3 Description of Action (including where and how) 23.1.11.3.4 Action lead (including confirmation of their organisation and job role) 23.1.11.3.5 Date action raised 23.1.11.3.6 Original Due Date 23.1.11.3.7 Estimated Completion Date 23.1.11.3.8 Actual Completion or Cancellation Date 23.1.11.3.9 Status (i.e. Open, Completed, Suspended, Cancelled) 23.1.11.3.10 Related actions (including any dependencies on other actions) 23.1.11.3.11 Notes to include explanation for any delayed completion of actions per the original due date or basis for suspension or cancellation 23.1.12 Protective marking. Where all items require an equal protective marking, the protective marking pursuant to DEFCON 659A and DEFCON 660 shall be identified only at the top and bottom of each page, and such marking repeated on the reverse of the final page of a hard-copy document. If the markings for items vary, the protective marking of individual Items shall be indicated [in brackets] on the same line as the item heading. The highest protective marking shall be utilised as the overall marking for the minutes. 23.2 All minutes shall be accurate, brief and logically arranged, and written using an impersonal style in reported speech. The minutes shall record all significant and limited to that amount of detail necessary for a reader who was not at the meeting to understand the reasons for the decisions. Agendas 23.3 Where the Contractor is instructed by the Authority to generate an Agenda this shall at a minimum include: 23.3.1 Subject heading which states the general purpose of the meeting, together with the location, room, time and date 23.3.2 Body which contains a list of the items for discussion arranged in a logical order including against each item a brief meaningful summary of the topic, and show who (if will lead the discussion and the time allotted for discussion. When the meeting is one of a regular series, the first 2 items shall include ‘Minutes of last meeting’ and 'Matters arising from last meeting’ 23.3.3 ‘Any other business’ (or any variation thereof) shall not be included as an accepted element of any agenda and all substantive matters for discussion shall be specifcied as an item consistent with 23.3.2 above 23.3.4 A list of attendees shall be recorded consistent with 23.1.2 and 23.1.3, as well as (where such is known in advance) 23.1.4 and 23.1.5 | Standard method of audit trail and records of decisions | Serial Number 2.5 (WBS 2.0) | Defcon 642 | - |  | Information Redacted | Minutes Draft Minutes shall be produced and issued to the Authority within 10 business days of the meeting. Final Minutes shall be issued by the Contractor to the Authority within a further 5 business days of receipt by the Contractor of confirmation of the Authority's agreement with the content of the Draft minutes. Agendas Draft Agendas shall be produced and issued to the Authority within 2 business days of receipt by the Contractor of such instruction by the Authority (and in any case a minimum of 2 business days prior to the associated meeting). Final Agendas shall be issued by the Contractor to the Authority within a further 2 business days of receipt by the Contractor of confirmation of the Authority's agreement with the content of the Draft Agendas (and in any case a minimum of 1 business day prior to the associated meeting) . | Electronic copy in a single Microsoft Word. Delivery shall be via email to all required attendees and interested parties. Record to also be held on the shared working environment.
N/A
24 | Provisioning Template Form | 24.1. The provisioning template shall be completed for all Repair and Spares orders raised each month. Price information shall be provided for all New Manufacture orders via the Provisioning template. | Inventory management and National Audit Office audit | Serial Number 7.12 (WBS 7.0) | - | - |  | Information Redacted | At time of placement of new manufacture and repair orders | Electronic copy provided in Microsoft Excel format. Delivery shall be via the shared working environment.
25 | Risk Register | 25.1. The Risk Register shall identify and assess all risks associated with execution of the Contract including meeting all Performance Levels and shall contain the following as a minimum for each risk: 25.1.1 ID Number – A unique identifier for the risk compirsed of a sequential risk number followed by requirement number) 25.1.2 Risk Owner 25.1.3 Short Risk Title 25.1.4 Risk Cause 25.1.5 Risk Event 25.1.6 Risk Consequence 25.1.7 Risk Background 25.1.8 Type of Risk (e.g. ( Technical, Political, Commercial etc) 25.1.9 Trigger Date 25.1.10 Expiry Date 25.1.11 Risk Assessment (pre-mitigation): 25.1.11.1 probability of risk occurring (%) 25.1.11.2 explanation of probability score 25.1.11.3 performance impact (High/Medium/Low) 25.1.11.4 performance impact Statement quantifying the potential impact 25.1.11.5 cost impact (High/Medium/Low) 25.1.11.6 cost Impact statement quantifying the potential costs using three point estimates 25.1.11.7 time impact (High/Medium/Low) 25.1.11.8 time Impact statement quantifying the potential impact. 25.1.12 Type of Mitigation Action (i.e. tolerate, treat, transfer, terminate) 25.1.13 Description of Mitigation Action(s) including timetable for implementation and justification for selecting those Mitigation Actions, and recording a summary of any alternatives considered but dismissed (including the basis for dismissal) 25.1.14 Relevant assumptions and basis of estimate 25.1.15 Relevant dependencies 25.1.16 Risk Assessment (post-mitigation): 25.1.16.1 probability of residual risk occurring (%) 25.1.16.2 explanation of probability score allocated to residual risk 25.1.16.3 performance impact of the residual risk (High/Medium/Low) 25.1.16.4 explanation of performance impact score allocated to residual risk 25.1.16.5 cost impact of the residual risk (High/Medium/Low) 25.1.16.6 explanation of cost impact rating allocated to residual risk 25.1.16.7 time impact (High/Medium/Low) 25.1.16.8 explanation of time impact rating allocated to residual risk 25.1.17 Identification of any associated or knock-on risks 25.1.18 Fallback options if risk mitigation is unsuccessful 25.1.19 Date risk raised 25.1.20 Status (Open/Closed) 25.1.21 Date last reviewed and updated comments. | Risk identification, control and mitigation | Serial Number 13.16 (WBS 13.0) | Clause 31 of the Special Conditions | - | With Thales Bid (draft version) | Information Redacted | As part of the monthly report and the Annual Progress Report. | Electronic copy provided in Microsoft Excel format. Delivery shall be via the shared working environment.
26 | Risks, Issues and Opportunities Management Plan | 26.1. The Risks, Issues and Opportunities Management Plan shall include the following as a minimum: (Information Redacted) | Risk management controls, processes and responsibilities | Serial Number 13.15 (WBS 13.0) | Clause 31 of the Special Conditions |  | With Thales Bid (draft version) | Information Redacted | To be provided within three months of the Contract Effective Date and to thereafter be maintained by the Contractor, and to include any changes as instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
27 | Equipment Supportability Matrix | 27.1 The Equipment Supportability Matrix (ESM) (Annex A5) shall: (Information Redacted) | Equipment support definition | Serial Number 13.22 (WBS 13.0) |  |  | N/A | Information Redacted | Contract Award Date, and thereafter to be maintained by the Contractor, with updates provided within 30 business days of any proposed changes to the support solution (either made by the Contractor or the Authority) | Electronic copy provided in Microsoft Excel format as per template. Delivery shall be via the shared working environment.
28 | Through Life Management Plan | 28.1 The Through Life Management Plan (TLMP) shall document the specific measures and processes the Contractor shall use to manage the Authority Equipment support levels defined in the ESM (CDRL 27) aligned to the relevant Out of Service Dates (OSDs) specified therein. The structure of the through life management plan shall be as follows: 28.1.2 Executive summary 28.1.2 Mission and objectives - defining the project objectives and parameters. 28.1.3 Stakeholders - stakeholder analysis 28.1.4 Strategies - defining the strategies for achieving the mission and objectives 28.1.5 Plans and processes – describing how strategies will be implemented to align with the relevant OSDs. 28.1.6 Resources 28.1.7 Costs 28.1.8 Evaluation of success - defining any proposed benefits and criteria on which success will be evaluated 28.1.9 References to technical and support documentation 28.1.10 Details of any planned/undertaken technology refreshes | Identifies specific measures and processes used to manage the Equipment | Serial Number 13.19 (WBS 13.0). |  |  | N/A | Information Redacted | Contract Effective Date and thereafter to be maintained by the Contractor, and to include any changes arising from updates to CDRL 11, 12 & 13 or as otherwise instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, annual updates shall be provided from the date of first issue. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
29 | Sonar 2093 Towed Body tracker schedule | 29.1 (Information Redacted) | S2093 Towed Body asset management and availability forecasting | Serial Number 13.14 (WBS 13.0) |  |  | N/A | Information Redacted | As part of the monthly report and the Annual Progress Report. | PDF. Delivery shall be via the shared working environment. Also to be delivered to the customer alongside the monthly report via email in a compressed file.
30 | Not Used
31 | Business Continuity Management Plan | 31.1 The Business Continuity Management Plan shall meet the requirements of Clause 47 of the Special Conditions | Supply chain management and risk mitigation | Serial Number 13.3 (WBS 13.0) | Clause 47 of the Special Conditions |  | N/A | Information Redacted | To be provided within 3 months of Contract Award. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
32 | Communications and Information Management Plan | 32.1 The Communications and Information Management Plan shall set out: 32.1.1 the means of communication including the computer systems, infrastructure, networks, business process and rules applied by the Contractor to enable effective, timely and accurate communications 32.1.2 the training and support arrangements delivered and maintained by the Contractor (e.g. for Contractor provided collaborative working environments). 32.1.3 the governance, assurance and compliance operated by the Contractor in the execution of its obligations under the Contract including the requirement for electronic information sharing. | Details of communication/information systems | Serial Number 13.17 (WBS 13.0 – Other Deliverables) |  |  | N/A | Information Redacted | Within 4 months of the Contract Effective Date, and thereafter to be maintained by the Contractor, and to include any changes instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
33 | Extraordinary Reports | 33.1 As agreed at request of the report by the Authority. | Reporting | Serial Number 13.20 (WBS 13.0) | - | As may be specified at request of the report by the Authority. | N/A | Information Redacted | As agreed at request of the report by the Authority. | As agreed at request of the report by the Authority.
34 | Miscellaneous Reporting | 34.1 All other reports prescribed under the Special Conditions and General Conditions as well as the Annexes to the Contract. This includes but is not limited to; (Information Redacted) | Reporting | - | General Conditions, Special Conditions, Annexes to the Contract | Annex D refers | N/A | Information Redacted | As prescribed in the associated General Conditions, Special Conditions or Annexes to the Contract or as may be otherwise instructed by the Authority. | As prescribed in the associated General Conditions, Special Conditions or Annexes to the Contract or as may be otherwise instructed by the Authority.
35 | Integrated Support Plan | Information Redacted | Service delivery assurance | Serial Number 1.11 (WBS 1.0) |  |  | With Thales Bid (draft version) | Information Redacted | Contract Award Date, and thereafter to be maintained by the Contractor, and to include any changes instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
36 | Operational Defect Summary | 36.1 A weekly summary of all open (outstanding) Operational Defects reported on the relevant Defect Reporting Management system. Content to be listed within this document following agreement between the Contractor and the Authority. Defect reporting systems to be updated by the Contractor by a predetermined day of each week. | Service delivery assurance | Serial Number 2.2 (WBS 2.0) |  |  | N/A | Information Redacted | Last working day of the Contract Award week. Weekly thereafter | Microsoft Excel. Delivery shall be via the shared working environment.
37 | Master Equipment Briefing Sheet | 37.1 Submitted by the Authority when an agreed number of Op Defs are raised, and it is identified that there is a risk of an equipment not meeting the SOR-mandated availability requirement. Contractor to provide a response within the timeframes agreed. | Service delivery assurance | Serial Number 2.2 (WBS 2.0) |  |  | N/A | Information Redacted | Within 10 Business Days of receipt from the Authority | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
38 | S2022 Status Report | 38.1 Monthly summary of all open (outstanding) Shortcoming Reports reported on the relevant management reporting system . Content to be listed within this document following agreement between the Contractor and the Authority. Reporting systems to be updated by the Contractor by a predetermined day of each week. | Service delivery assurance | Serial Number 2.5 (WBS 2.0) |  |  | N/A | Information Redacted | As part of the monthly report and the Annual Progress Report. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
39 | Not Used
40 | Reliability and Maintainability Case Report | 40.1 The R&M Case Report, produced in accordance with (Information Redacted), shall provide evidence of the suitability of the proposed solution, based on past or current use. | Service delivery assurance | Serial Number 3.2 (WBS 3.0) |  |  | N/A | Information Redacted | Agreed only to be supplied in the case of major re-design | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
41 | Not Used |  | Service delivery assurance | Serial Number 3.3 (WBS 3.0)
42 |  | Intentional Blank
43 |  | Intentional Blank
44 | Not Used
45 | Not Used
46 | Not Used
47 | Not Used
48 | Inventory Modelling Data | 48.1 When a need is identified to introduce inventory, modelling data shall be supplied to allow the Authority to peer review proposed inventory levels. 48.2 Modelling data required may vary between systems supported and actual inventory to be modelled. Modelling data shall be provided as requested by the Authority in accordance with the M-SET ILSP, Table 8.2. If there is no data or text requirement, the contractor will enter ‘NOT APPLICABLE’ and justify the reasons. | Service delivery assurance | Serial Number 7.3 (WBS 7.0) |  |  | With Thales bid (draft version) | Information Redacted | As part of the bid and when new equipment is introduced into scope. | Electronically, in a format that is compatible with the Authority's modelling systems or Microsoft Excel.
49 |  | Intentional Blank
50 | Initial Provisioning Specification List | 50.1 | Supply chain management and risk mitigation | Serial Number 7.19 (WBS 7.0) |  |  | N/A | Information Redacted | As part of the bid only | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
51 | Not Used
52 | Intentional Blank
53 | Software Support Plan | 53.1 SwSP describes in detail the support of the software engineering and programmable elements activities. SwSP includes but not limited to ( If there is no data or text requirement, the contractor will enter ‘NOT APPLICABLE’ and justify the reasons): (Information Redacted) | Service delivery assurance | Serial Number 11.1 (WBS 11.0) |  |  | With Thales bid (draft version) | Information Redacted | Within 4 months of the Contract Effective Date, and thereafter to be maintained by the Contractor, and to include any changes instructed by the Authority acting reasonably. The Contractor shall update the document as required within 20 business days of becoming aware of any required changes or being so instructed by the Authority. As a minimum, the Contractor shall confirm the document’s status and report on any changes implemented or pending at the Annual Progress Review Meeting. | Electronic copy provided in Microsoft Word format. Delivery shall be via the shared working environment.
54 | Information System Inputs | 54.1 Information System data inputs for all systems listed within the M-SET SOR, Serial (Information Redacted) 54.2 Information system inputs to be provided for all listed systems in service at the time of Contract Award and any replacement systems introduced throughout the contract duration | Service delivery assurance | Serial Number 13.2 (WBS 13.0) |  |  | N/A | Information Redacted | Within 10 Business days of notifying the Authoirty of a new or changed inventory need. Within 10 Business Days of a request from the Authority. | Data provided in a format that is compatible to the relevant Information System.
55 | Not Used
56 | Not Used
57 | Not Used
58 | Not Used
59 | Not Used
60 | Not Used
61 | Not Used
Note: applicable to all CDRLs | Copyright notices | The recipient is warned that this document should be handled in accordance with the HM Government Security Classification indicated throughout. The copyright in this document is the property of Thales UK Limited. The document is supplied by Thales UK Limited on the express terms that it is to be treated in confidence and that it may not be copied, used or disclosed to others for any purpose except as authorised in writing by Thales UK Limited or in accordance with the rights granted in respect thereof to the UK MOD under UK MOD Contract Number MCS/1001. Any person, other than the authorised holder, who finds or otherwise obtains possession of this document, should post it, together with their name and address, to The Intellectual Property Department, Thales UK Ltd, 350 Longwater Avenue, Green Park, Reading RG2 6GF. Postage will be refunded.
Any copyright notice applied to any Deliverable Documentation in accordance with the rights afforded under this Contract shall in all cases acknowledge the Authority's rights under this Contract. Where the Contractor fails to do so the Authority reserves the right at its sole discretion to reject such documentation on these grounds alone.