## Q&A log
Q. No | Question | Answer
1 | Where we are to provide new concrete slabs, can you please provide a specification and construction detail. | Please respond with a common sense approach based upon your expert knowledge.
2 | Item 3.27/2 – please provide a specification | Please respond with a common sense approach based upon your expert knowledge.
3 | Armsby (2): Does it really require concrete? We could just rebuild the toppled sections back onto the undisturbed base stone? | We shall discuss in detail the need or otherwise for concrete when intimate investigations are carried out on each of the monuments. The idea is to start at the top of the list and work through each and everyone identifying, in conjunction with the successful tenderer, what needs to be done and how best to achieve this. There is a finite budget and when this has been expended the work to the remainder of the list may well have to be forfeited at this time.
4 | Bond (3): Again we query the use of concrete and suggest that it could be just rebuilt and the ledger levelled. | The expertise of the successful tenderer will help determine the levels and type of intervention necessary for each monument. The responses should reflect the most appropriate options for repair/refurbishment but also cover the demand as it stands.
5 | Bond (3): We would also question to construction of new concrete kerbs | Again, the expertise of the successful tenderer will help determine the levels and type of intervention necessary for each monument. The responses should reflect the most appropriate options for repair/refurbishment but also cover the demand as it stands.
6 | Crisp (5): The schedule shows the wrong photo sheet. This is just a point of info, as it shows the correct photos afterwards. | Obviously, concentrate only on the correct photographs.
7 | Fitch (6): There is an unknown quantity of mosaic replacement due to dirt and soil | Please provide a square metre rate for replacement.
8 | Fitch (6): The schedule says poured concrete but the pier is bedded on the ledger | So note this, cost this and price accordingly to what you, as the expert contractor might do more appropriately, please.
9 | Mellon (7): The schedule says to dismantle the superstructure only, but why pour footing around the remaining lower section of monument without dismantling? | Respond in a similar manor to the above (Fitch response) suggestion, please.
10 | Mellon (7): The schedule says to remove base slab, but we would question how this is possible without dismantling the entire monument? Says superstructure only down the column bases. | As previously suggested.
11 | Pettitt (9): Again we would question the necessity for concrete. | As previously suggested.
12 | Yorke (12): There is no surviving stained glass | There is a very small amount of surviving glass.
13 | Yorke (12): Further clarification requested for new permanent support structure – design, material | Please respond with a common sense approach based upon your expert knowledge.
14 | Yorke (12): The schedule says to prop, but there is propping already present | Please respond with a common sense approach based upon your expert knowledge.
15 | Yorke (12): We suggest that galvanising the steel bars is an unnecessary item. Another option is to decorate and refix with SS fixings | Please respond with a common sense approach based upon your expert knowledge.
16 | Yorke (12): Similarly, we would suggest the doorframe be treated, redecorated and refixed with SS fixings. If metalwork isn’t embedded, then best practice is to keep and protect | Please respond with a common sense approach based upon your expert knowledge.
17 | Yorke (12): Could you please confirm what is meant by cover moulds – hood mouldings? | Please respond with a common sense approach based upon your expert knowledge.
18 | Yorke (12): There is currently no door | Please respond with a common sense approach based upon your expert knowledge. | `
19 | Bill (13): The door has no frame to repair as it sits on pintels | Please respond with a common sense approach based upon your expert knowledge.
20 | Bill (13):Roof stones suggested at 3500 x 2000 x 250 – we would query these dims | Please respond with a common sense approach based upon your expert knowledge.
21 | Bill (13):We suggest that corner stones should be repaired/pieced in rather than replaced | Please respond with a common sense approach based upon your expert knowledge.
22 | Cave (14): Could you please clarify the underpinning requirement | Please respond with a common sense approach based upon your expert knowledge.
23 | Chaplin (15): There is an unknown quant for infilling | Please respond with a common sense approach based upon your expert knowledge.
24 | Fletcher (17): Roof panels 1000 x 1500 x 250? We have assumed 25mm is meant. Please clarify quants. | Please respond with a common sense approach based upon your expert knowledge.
25 | Fletcher (17): Further clarification requested for installation of new screen to replace mesh – design, material | Please respond with a common sense approach based upon your expert knowledge.
26 | Leyland (19): Is this work just to the railings and railing stones? Not the floor surrounding the monument? | Most likely yes.
27 | Mcdonald (20): Perimeter kerbing all seems fine, possibly doesn’t need taking up and relaying on concrete footings. | Good.
28 | Mcdonald (20): Angel wings both have missing sections, are these sections still with us or lost? | One wing is in storage.
29 | Mcdonald (20): Lower glazed panel is missing | Please price for an appropriate replacement.
30 | Meyrick (21): We couldn’t see any broken roof stones | Please reflect this in your response.
31 | Meyrick (21): Please clarify what was meant by Kerb | Please respond with a common sense approach based upon your expert knowledge.
32 | Pankhurst (23): There is a large tree root which would need cutting back otherwise any new works would soon be disturbed again | No tree roots will be cut back as this will cause irreparable damage to the focal avenue; there are alternative methods of repair to be discussed. Please respond with a common sense approach based upon your expert knowledge.
33 | Rendle (24): The schedule says to replace piers where missing, but they all seem to be present | Please respond with a common sense approach based upon your expert knowledge.
34 | Wade (25): We request further clarification on what is meant by wires | Please respond with a common sense approach based upon your expert knowledge.
35 | Coombe (27) not on the pricing schedule – is this correct? | This will be repaired and paid for by others outside this contractual arrangement.