## Sheet1
Highways Agency Confirmation of Task Order Redactions made under FOIA 2000 exemptions sec 40: personal info and sec 43: commercial.
Supplier: | JMP |  |  |  | 23082.31
Project Title: | M66_A56 Study - Modelling
Contract Ref. | 114/2/1391/4 | CPA No.: | Redacted | BPA No.: | Redacted
PIN Description: | Redacted | Sub Pin: | Redacted | PIN No.: | Redacted
HA Reference: | NW 29 15/16 JMP | Start and End Date : 03/07/2015 - 06/11/2015 |  | 11/04/2012 - 30/04/2012
Task Overview and Expected Outcomes
This is a modelling task, the task will comprise of the following five Milestones: • Milestone 1 – Method Statement; • Milestone 2 – Scoping & Feasibility; • Milestone 3 – Data Collection and Baseline Conditions; • Milestone 4 – Model Development; and • Milestone 5 – Reporting and Meetings. The team has been identified based upon those who have previously worked on tasks on the M66/A56 as this will ensure they have an appreciation of the flows and traffic movements around the M66/A56 and local area. The study area will include A56/M66 corridor, from Junction 8 of the M65 in the north to M60 Junction 18 in the south. Two separate models are proposed to cover key sections of the study area. These include Highways England network along the M66 (between M60 J18 slip roads and M66 Junction 1 slip roads). and A56 around Edenfield/Haslingdon (between A56 off-slip at M66 and A56/Grane Road). This would include all Highways England network, slip roads and junctions onto the local network (subject to available data).
Task Objectives and Milestones
Milestone One – Method Statement A method statement (provided here) sets out the key elements of the task and will be submitted (electronically) to the Highways England Project Sponsor for general agreement prior to the task being entered into TAPE. The time associated with the method statement is to understand and interpret the task brief with due regard to the expected project outcome. Task Overview and Expected Outcomes The work will involve developing two Base Year micro-simulation models of key parts of the SRN within the agreed study area. This will include: • Model 1: M66 – between M60 J18 and M66 Junction 1; and • Model 2: A56 Edenfield/Haslingdon – between M66 and A56/Grane Road. The following table includes an allocation of time for a risk review to be undertaken by the lead consultants. Milestone Two – Scoping and Feasibility The scoping and feasibility stage of the project will be used to give a clear indication of the study objectives providing an opportunity for the confirmation of the model extent and requirements. To ensure this, AECOM will conduct an inception meeting with Highways England to discuss the requirements of the proposed micro-simulation model. The associated ‘M66 - A56 Baseline Study’ task order (W524008) will provide the necessary scoping of the wider study. This will identify the extent of the study area, key available data, baseline conditions and identifications of future committed and proposed schemes which could affect future traffic flows on the M66/A56 corridor. Milestone Three – Data Collection and Baseline Conditions To support the proposed model, appropriate existing local data will be obtained and used to inform the model, these will include: • Link flow data from the HATRIS database including TRADS data; • Local link flows/turning counts for local approach roads to the M66/A56 from HFAS and local authorities (during baseline study a lack of available junction data was identified); • Congestion data requested from DfT will be used to inform vehicle speeds on the M66/A56; and • Junctions operating under signal control will be identified and appropriate data requested from GMUTC/BBMM/Local Authorities. No existing strategic models cover in detail the study areas, as a result it is likely that some data collection would be recommended to provide a suitable level of data to inform model development. This is likely to include a range of data including turning counts and ANPR surveys. It is understood that data collection would be undertaken separate to this task order, with the need to include sub-consultants to undertake these surveys. The scope of data collection would be discussed and agreed separately with Highways England prior to undertaking further model development. Milestone Four – Model Development The brief sets out the aim of developing micro-simulation models using an appropriate modelling package. AECOM consider VISSIM an appropriate tool for the size of the stated study areas (M66 between M60 J18 slip roads and M66 Junction 1 slip roads & A56 Edenfield/Haslingdon). Appropriate mapping will be included to ensure that the model accurately represents appropriate lane widths, merges and diverge layouts. As appropriate signal data will be obtained from GM-UTC or BBMM and incorporated within the model, with VIS-VAP techniques being adopted for variable signal timings as appropriate. Once the network is constructed, network speed information, vehicle types and vehicle compositions will be added to the network. Upon completion of the network construction, matrices will be developed from existing traffic routings obtained from the data collection and baseline review. Also incorporating any additional data from the additional surveys identified in Milestone 3. As appropriate, traffic flows will be aligned to a 2015 base year. The model will be assigned and calibrated/validated for AM and PM peak periods for the 2015 base year. To support the identification of potential network issues, a single future year forecast scenario will be created. The derivation of this future year model will be based on the changes in traffic flows between base year and future year. The traffic flows associated with this test will be based on outputs from associated tools such as NTEM forecasts. The outputs of this future year scenario will be useful to understand the potential forecasted issues on the M66/A56 network. Milestone Five – Reporting & Meetings AECOM will produce a study report documenting the model development and calibration/validation of the model against DMRB criteria. This will include the details of the supply model. The report will also include details of the issues identified on the network during the review of the future year scenario test. In addition to the inception meeting discussed in milestone two, a further results meeting with Highways England will be undertaken to present the resultant VISSIM model, providing a run through of its capabilities. It is envisaged this meeting will also provide an opportunity to discuss future uses of the model, include likely do minimum and do something test which could be undertaken using the model as part as further task orders.
Expected Project Outcomes
Expected Project Outcomes Two 2015 base year VISSIM models will be prepared covering: • M66 - Junction 1 to 3 (between M66 off-slips at Simister to M66 Junction 1 off-slips); and • A56 – Edenfield / Haslingdon (between A56/M66 and A56/Grane Road). In addition, a modelling report will be produced detailing the model development and calibration/validation to provide a baseline model for future year forecasting and scheme testing.
Project Risk and Management
Project Risk and Management Any delay in approving the task order could result in delays to the preparation of the outputs. Also, any delays in receiving data to inform the model or any gaps in data could delay or limit the capabilities of the micro-simulation model. The task assumes data collection to inform the modelling, the collection of this supplementary data could affect the timescales and requirement for additional information to inform the modelling.
HA Project Sponsor | Sign: |  | Print Name: |  | Date:
Management Approver: | Sign: |  | Print Name: |  | Date:
Contractual Approval: | Sign: |  | Print Name: |  | Date: