Arts Council England Invitation to Tender

Title: Random Acts Network Centres programme evaluation

Reference number: ART011-0070

Deadline for receipt of tender proposals: 12 noon on 12th October 2015

- Background

- The Arts Council

- Arts Council England champions, develops and invests in artistic and cultural experiences that enrich people's lives. We support a range of activities across the arts, museums and libraries - from theatre to digital art, reading to dance, music to literature, and crafts to collections.

- Great art and culture inspires us, brings us together and teaches us about ourselves and the world around us. In short, it makes life better. Between 2011 and 2015, we have invested £1.4 billion of public money from government and an estimated £0.85 billion from the National Lottery to help create these experiences for as many people as possible across the country.

Section 1: Introduction

Arts Council England is seeking a service provider to deliver an evaluation of the Random Acts Network Centres programme. This invitation to tender specifies the requirements for the provision of the evaluation.

The following details are outlined in this document:

- The service to be provided

- The information to be provided by tenderers

- The terms of business relating to the award of any contract

- The timetable for the tendering programme

The Random Acts Network Centres programme

The Arts Council is committed to supporting entry points for emerging young talent into the arts and creative industries. We recognise the importance of creative and digital skills to the economy and are working to ensure young, diverse people have opportunities to develop these skills in tandem – both in and out of school.  As part of our Creative Media policy we are committed to working in partnership with the wider creative media industries to extend the impact of our work, and broker opportunities for new talent and audiences.

The Random Acts Network Centres project sees us continue our successful partnership with Channel 4. Random Acts is Channel 4's short-form arts strand which showcases ‘bold expressions of creativity’ through films ranging in duration from 90 seconds to three minutes. The Arts Council has invested in the programme since its launch in 2011.

In 2015, Channel 4 and the Arts Council are collaborating on a re-launch of Random Acts with a new focus on identifying, supporting and showcasing new diverse young talent. Over the 3-year period 2015-18, the Arts Council will commit £3 million of Lottery funding to fund five new Random Acts Network Centres. Each will act as a talent development and commissioning centre for 16- to 24-year-olds. Each will lead a partnership comprising a range of arts, education and TV production organisations to form a ‘network’ within each Arts Council area.

The five networks will deliver a 3-year programme of activity including education, training and production support to collectively facilitate the creation of 120 high quality short films per year (24 films per network per year) designed for distribution on Channel 4 platforms.

Each network will work together to nurture emerging talent, help to develop ideas for short films from 16- to 24-year-olds, and provide a platform for young talent to gain exposure and pursue wider development opportunities. The Network Centre will be the designated lead organisation responsible for the administration, leadership and performance of the network.

Following an open application process, the following organisations were selected to lead the Random Acts Network Centre for each of the five Arts Council areas: ICA, London; Screen South, the South East; Calling the Shots, the South West; Rural Media Company, the Midlands; Tyneside Cinema, the North. Four of the five centres began their work in March 2015; Tyneside Cinema was appointed later and began in July 2015.

An external broadcast and production advisor, Maddy Allen, Head of Production at Keo Films, has been appointed by the Arts Council to provide expert support to the Network Centres during the first year of their operation, until March 2016.

Programme aims

The Arts Council and Channel 4 have jointly identified the following key outcomes to be achieved collectively by the Network Centres by the end of March 2018:

- 360 new high quality short films from across England created by 16- to 24-year-olds, with first- and second-year participants continuing to develop their work and ideas following their Random Acts commissions

- At least 360 16- to 24-year-olds have gained high quality support through educational, training and creative development opportunities

- Diverse new 16- to 24-year-old talent has been found, nurtured and given a platform for exposure

- High quality contemporary arts and cultural activity is made accessible to audiences, including on Channel 4 television and online platforms

- Data is gathered from the project that provides knowledge of the target audience and the role of arts and culture in their lives, and evaluation from the project is shared with the wider arts and cultural sector

In terms of activity, by March 2018, Random Acts networks are expected to:

- Discover, showcase and promote diverse young talent

- Increase the profile and reach of arts films and creative work by 16- to 24-year-olds, including to large, diverse Channel 4 audiences

- Provide training, advice and mentoring to support and enable young talent and a two-way knowledge exchange between the arts sector and young people

- Share information and learning from the project in relation to young people, talent development and young audiences with wider arts and cultural sector to improve knowledge and understanding

- Encourage new, innovative and sustainable partnerships between the arts, education and creative media industries

The key outputs expected of the Network Centres are:

- A programme of talent development that supports the development of the target audience (16- to 24-year-olds), encourages exposure to arts and cultural activity and provides opportunities for further progression

- An agreed number and range of appropriate training opportunities for new talent from the target age range (to be negotiated as part of their funding agreement)

- 24 short films of broadcast quality per year.

Random Acts Network Centres activity will contribute to the Arts Council’s Creative media policy and to its 10-year strategy, Great art and culture for everyone. The following success measures are relevant to Goal 5 of the strategy

- More children and young people have the opportunity to experience the richness of the arts, museums and libraries

- More children and young people receive a high-quality cultural education in and out of school

- Arts organisations, museums and libraries are delivering high-quality arts and cultural experiences for children and young people

In addition the project supports Goals 1 and 2 of the strategy, namely:

- Artists, arts organisations, museums and libraries are delivering artistic work, and cultural experiences that represent the height of ambition, talent, and skill (1.1)

- The work produced by arts organisations and museums, and services provided by libraries, reflects the diversity of contemporary England (1.3)

- More people have the opportunity to experience and participate in great art, museums and libraries (2.1)

- The number and range of people experiencing great art, museums and libraries has increased (2.2)

Equality and diversity has been systematically considered in relation to the Random Acts Network Centres programme. An Equality Analysis has been produced by the Arts Council and the commitment to reaching and working with diverse participants was an important consideration in the selection of Network Centres. A detailed analysis of the extent to which this commitment has been delivered is expected within the evaluation. It is anticipated that the evaluation reporting will include case studies that exemplify good practice in relation to diversity.

Duration of Contract

The period of the contract is from 1 November 2015 until 30 April 2018.

Procurement and Project Timeline

The indicative timetable for the project is:

| Activity | Date (all 2015) |
| --- | --- |
| Issue ITT | 28 September |
| Deadline for clarification questions | 5 October |
| Deadline for receipt of tender proposals | 12 noon on 12 October |
| Initial review of tenders and scoring | 19 October |
| Possible clarification meetings | 22/23 October |
| Moderate/Finalise scores and identify preferred bidder | 26 October |
| Contract award | 28 October |
| Pre Contract Inception meeting | 30 October |
| Contract commencement | 1 November |

Section 2: Specification requirements

Evaluation purpose and questions

Our aim in commissioning an evaluation is to identify:

- The impact of the investment against the specified programme aims and outcomes

- Learning and insights from the programme that can be captured summarised and disseminated to inform and benefit comparable activities in the wider arts and culture sector

- Analysis and reporting of a formative nature that can help the national Random Acts network to evolve to more effectively meet programme aims and objectives over the lifetime of the project

- Summative information and analysis that can help the Arts Council understand what was successful about the programme and what were the barriers and issues that might have hindered it from achieving even more.

The Network Centres will already, to varying degrees have developed their own monitoring, reporting and evaluation approaches at a local, project level. A key and immediate priority for this programme level evaluation will be to audit what evaluation activities and data collection protocols and practices have been initiated to date by each of the Network Centres and to develop a consistent framework for future (and if necessary retrospective) data collection that can be adopted by each centre in order to provide a consistent set of information that can be aggregated, analysed and interpreted at a programme level. The appointed evaluator will need quickly to build a positive relationship with the Network Centres, and with Channel 4. The programme evaluator will be expected to develop a methodology and collaborative way of working that helps to support and add value to the activities of the individual network centres.

As part of its Memorandum of Understanding (MoU) with the Arts Council, Channel 4 has committed to ‘providing data and evaluation’, such as Omniture reporting on volumes of visitors to any Random Acts content hosted on Channel 4 platforms and overall number of VOD views on other platforms that the content is available on e.g. Sky. Full details on the ways in which Channel 4’s Audience Technology and Insight team can support the Arts Council’s evaluation activities are included in a schedule to the MoU, which will be made available to the successful tenderer.

Research Questions

An evaluation of the programme aims and impacts:

- To what extent and how has the Random Acts Network Centres programme achieved the aims and outcomes specified for the programme

- What have been the key impacts of the programme

Learning and policy development

- What have been the key challenges and successes for the Network Centres, the partners and young people that they worked with, and for Arts Council England and Channel 4?

- What are the lessons learned for both the sector and for Arts Council England?

Methodology

We would like this evaluation to provide a balance of findings in terms of breadth across the programme, and depth to highlight and explore key issues in greater detail. We therefore require a mixed method approach and would like bidders to propose a research methodology that they believe will best meet the aims of the brief. This may include methods such as a document review, surveys with all or a sample of the programme’s recipients, strategies for collecting and analysing participant and audience data, including from Channel 4, and interviews and/or focus groups with people connected to, or benefiting from, the programme and its activities. An important element of the programme evaluation will be the development of a framework to enable the individual network centres to capture essential information, such as the demographic profile of participants, in a consistent way. We would welcome as part of the tender proactive proposals for how learning captured through the evaluative process can be disseminated to benefit the wider arts sector.

Outputs

The following outputs will be required:

- A research methodology and data framework which all five Network Centres can sign up and contribute to; and which draws on audience data and insights captured by Channel 4

- Annual reports in April 2016 and April 2017. It is anticipated that these will be formative and might: summarise progress and achievements of the Network Centres; highlight areas and issues for improvement or review; develop exemplary case studies

- A draft final report in March 2018

- A final written report in April 2018. This will be summative and will record and analyse the achievements of the programme as a whole

- A set of research data, to be stored in a readily accessible electronic format such as Excel

All reports to include appendices as agreed between Arts Council England and the contractor. The contents and structure of the report to be agreed in advance of writing and all reports to be supplied in both hard copy and electronic format. The final report should adhere to the Arts Council’s accessibility and formatting guidance.

The results will be published on our website. We may prepare or commission summary reports and other materials for subsequent wider distribution.

Key Deliverables                                      Due Date

| Agreed research methodology and data framework | December 2015 |
| --- | --- |
| First annual report | April 2016 |
| Second annual report | April 2017 |
| Final programme evaluation report | April 2018 |

Useful weblinks

http://randomacts.channel4.com/

http://www.artscouncil.org.uk/media/uploads/pdf/creative_media_policy_final.pdf

http://www.artscouncil.org.uk/media/uploads/Great_art_and_culture_for_everyone.pdf

http://www.artscouncil.org.uk/media/uploads/Random_Acts_Network_Centre_North_Guidance_for_applicants.pdf  (example of guidance given to all applicants)

http://callingtheshots.co.uk/random-acts/

https://www.tynesidecinema.co.uk/learn/random-acts

http://www.ruralmedia.co.uk/Random-Acts.aspx

https://www.ica.org.uk/blog/ica-designated-random-acts-network-centre-london

http://www.screensouth.org/content.aspx?page=34

- Please refer to our brand guidelines

Escalation Procedures

In the event of a major problem, a list of contacts will be required to manage any problem to a successful conclusion.

Account Management

In performing the services required under this contract the supplier will report to Paul Glinkowski, Senior Manager Creative Media. Please specify in your proposal the named individual who will be responsible for the account management of this contract on behalf of your organisation.

The programme of work will be overseen and guided by Paul Glinkowski, with assistance from Vivienne Niblett, Senior Officer, Policy & Research (Evaluation). The project may also be supported by a small steering group comprising a mixture of Arts Council staff and representatives from the Network Centres.

Management reporting/review meetings

Review meetings will happen at least quarterly throughout the duration of the contract. Regular update phone calls with the Arts Council lead officer will be scheduled approximately every two weeks.

Pricing/Budget

The budget available for this project is in the range of £60,000 and £100,000 inclusive of VAT and all travel and other expenses. Bids which exceed £100,000 inclusive of VAT and all expenses will be excluded from this procurement exercise as being unaffordable. Value for money is a key element of the evaluation criteria.

Payment Structure and billing requirements

A contract will be awarded for the length of the project. Arts Council England will pay on receipt of each deliverable.

You must indicate any subcontractors you are proposing to use in delivering the services.

Evaluation criteria

You are required to respond to ALL of the criteria below.  To assist our evaluation of your tender submission, please ensure you clearly cross-refer your responses to the assigned numbers. Any relevant supporting tender documentation must also be clearly identifiable by a criteria number.

| Pass Fail Criterion 1 | PASS/FAIL |
| --- | --- |
| The Arts Council requires the service provider to have and provide evidence of a minimum of 3 years’ experience in successfully delivering similar services including: - the design and delivery of mixed methods research - complex programme-level evaluations - high level skills in report writing and in the framing and dissemination of research findings and learning in a range of formats for a range of audiences Please provide evidence of 3 years’ experience of undertaking similar projects successfully and contact details for references to demonstrate this. (Word limit – 500 words) |  |
| Pass Fail Criterion 2 |  |
| The Bidder’s total Fixed and Firm Costs do not exceed £100,000 inclusive of VAT and all expenses. Bidders whose costs exceed this amount will be excluded from further consideration in the tender process. |  |

If you pass all of the pass/fail criteria set out above, we will evaluate your tender response using the quality and price criteria which are set out below.

- Quality criteria (70 marks available)

- The table below gives the criteria that will be used to evaluate the quality of the tender proposals received.

|  | Criteria | Weighting |
| --- | --- | --- |
| 1 | Demonstrate your understanding of the brief and set out your detailed proposals for delivering against our requirements to time and to budget. In your response you should set out (by reference to previous relevant experience) why your methodology is suitable for this contract. | 35% |
| 2 | Demonstrate your experience of successfully delivering similar services and producing similar research outcomes, e.g. provide examples of two previous evaluation reports you have been commissioned to produce, with contact details for references. | 20% |
| 3 | Detail the relevant experience of your proposed delivery team by providing CVs. | 10% |
| 4 | Detail your quality assurance procedures and identify the risks to successful delivery and your plans to mitigate them. | 5% |

Each criterion will be scored using the methodology in the table below.

| # 0 | # Very Poor | # No response or partial response and poor evidence provided in support of it. Does not give Arts Council confidence in the ability of the Bidder to deliver the Contract and/or our requirements are not met in most respects. |
| --- | --- | --- |
| # 1 | # Weak | # Response is supported by a weak standard of evidence in some areas giving rise to concern about the ability of the Bidder to deliver the Contract and/or our requirements are not met in some respects. |
| # 2 | # Satisfactory | # Response is satisfactory and supported by a satisfactory standard of evidence. Gives Arts Council confidence in the ability of the bidder to deliver the contract, meets the requirements in most respects. |
| # 3 | # Good | # Response is comprehensive and supported by good standard of evidence. Gives Arts Council a high level confidence in the ability of the Bidder to deliver the contract and meets Arts Council requirements. |
| # 4 | # Very Good | # Response is comprehensive and supported by a very good standard of evidence meeting Arts Council requirements and may exceed them in some respects. Gives Arts Council a very good level of confidence in the ability of the Bidder to deliver the contract. |
| # 5 | # Exceptional | # Response is very comprehensive and supported by a high standard of evidence. Gives Arts Council a very high level of confidence in the ability of the Bidder to deliver the contract. May exceed Arts Council requirements in several respects. |

- Price criteria (30 marks)

30 marks will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your fixed and firm total costs figure including VAT and expenses will be used to score this question.

For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced bidder gets 30% (full marks) for price and the second placed bidder gets 27.6% and so on. (8/100 x 30 = 2.4 marks; 30 – 2.4 = 27.6 marks)

The bidder with the highest score when the quality and price marks are added up will be the preferred bidder.

Schedule of Charges

VAT is chargeable on the services to be provided and this will be taken into account in the overall cost of this procurement contract.

Bidders shall complete the schedule of charges Table A below estimating the number of days and travel and subsistence costs associated with their bid. The total fixed price will be inclusive of VAT and inclusive of expenses and all costs to be incurred.

|  |  |  | Role Description and Day Rate |  |  | Total Days | Total Firm & Fixed Price shall not exceed (£) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TABLE A: |  |  | e.g. Project Manager/ Director [name individual] | e.g. Researcher [name individual] | Other [name individual] |  |  |
|  |  |  | e.g. £500 | e.g. £300 | e.g. £200 |  |  |
| Research team fees |  |  | Quantity |  |  |  |  |
| e.g. Project initiation meeting |  |  | e.g. 0.5 | 0.5 |  | 1 | 400 |
| Production of Framework |  |  |  |  |  |  |  |
| Annual Reports |  |  |  |  |  |  |  |
| Quarterly Meetings |  |  |  |  |  |  |  |
| Final Programme Evaluation Report |  |  |  |  |  |  |  |
| Please include any other deliverables you are proposing to meet our requirements in section 3. |  |  |  |  |  |  |  |
| Travel and subsistence |  |  |  |  |  |  |  |
| Other (non-staff) costs – Please specify |  |  |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |  |  |
| Sub-total |  |  |  |  |  |  | £ |
| VAT |  |  |  |  |  |  |  |
| Total Fixed Price including VAT and expenses shall not exceed (n.b. this figure will be used for the purposes of allocating your score for the price criterion) Please note: bids that exceed £100,000 for all the services (including VAT and expenses) will be excluded from this tender process as unaffordable. |  |  |  |  |  |  | £ |

Notes:

Arts Council England reserves the right to reject abnormally low tenders.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

Section 2: Instructions to tenderers

Please submit your tender offer in accordance with all of the instructions, requirements and specifications set out in the enclosed documentation.

You must treat these documents and any further information provided by Arts Council England as confidential at all times and only disclose them if necessary to prepare a compliant response to the tender.

Nothing in the enclosed documentation or appendixes, or any other communication made between Arts Council England and any other party, can be considered a contract or agreement at this stage.

Compliance

Arts Council England reserves the right to disqualify or reduce the evaluation score of any tenderers who do not fully comply with the requirements in the tender documentation, in particular the closing time and date.

If you propose alternative goods or services for consideration, you must clearly mark these as non-compliant. Arts Council England reserves the right to reject any proposals with non-compliant alternatives. Tenders that are received are not automatically accepted.

The Arts Council’s standard terms and conditions for services will form part of the contract to be awarded. These can be downloaded and reviewed from our website: http://www.artscouncil.org.uk/media/uploads/pdf/

There are terms and Contract_for_Services_over_10K and those for Contracts for Services below £10k. You should review the terms applicable to this tender.

The Arts Council may also require further terms to be included in the contract that are specific to the successful supplier‘s application.. The Preferred Supplier will not be permitted to enter into any negotiations on the terms of the Contract. Any attempt to negotiate amendments will breach the terms of this ITT and will result in the Preferred Supplier being excluded from the tender process. In such circumstances Arts Council England reserves the right to invite the next highest scoring Bidder to enter into the Contract.

Please note that Arts Council England are required to publish online the final awarded contract and any associated documentation. If you have any concerns about the future publication of sensitive information you should raise these within your tender proposal, highlighting which areas within your proposal you consider may be subject to exemption, and subsequent redaction, in line with the provisions of the Freedom of Information Act 2000 (FOIA). More information about FOIA can be found at www.ico.gov.uk.

Validity of offer

Please note that by submitting a tender response for consideration you are confirming that, as an officer for the company/organisation that you represent, you have read and understood the tender documents and that your offer to Arts Council England is open for acceptance for 60 days from the tender closing date.

Tendering

Arts Council England reserves the right, in its absolute discretion, to cancel or suspend this tender process at any time and for any reason. If we need to do this we will notify you in writing as soon as reasonably practicably.

Arts Council England is not responsible, and will not pay for any expenses or losses you incur during, but not limited to, the tender preparation, site visits, or clarification meetings.

Information and questions

If you need us to clarify the documentation or if you have further questions regarding the tender process, write to the lead officer quoting the tender reference number. We will try to respond to reasonable requests for further information within the timescale of the tender.

Arts Council England reserves the right to advise all other tenderers of material questions and the answers supplied without disclosing the source of the enquiry. These will be issued via the Contracts Finder website ((https://online.contractsfinder.businesslink.gov.uk/) if the contract value is estimated to be above £10k including VAT. It is the bidder’s responsibility to check the website regularly for any clarifications.

Return of Tender

You must complete and submit your tender response by email to procurement@artscouncil.org.uk before the tender response deadline of 12 noon on 12 October 2015.

If you are experiencing any problems submitting your document online, please contact the Delta helpdesk at helpdesk@delta-esourcing.com or call 0845 270 7050 for further assistance.

Any tender delivered after the closing date and time for any reason may be discounted.

The Arts Council is not responsible if all or part of your tender is not received.

Post-tender clarifications

Arts Council England reserves the right to conduct post-tender clarifications with one or more tenderers depending on the closeness of a bidder’s score to the highest scoring bidder. Arts Council England reserves the right to ask you to attend a post-tender clarification meeting.