## Sheet1
CLARIFICATION LOG
Tender: | Solar Panel and Battery Storage
Tender Reference: | NZ199
Published Date: | 2024-04-03
Version number: | 0.1
Number | Clarification | Response | Reply date
1 | Are we limited to using a hybrid inverter? It would be far more practical and cost efficient to use one or two larger "main" inverters connected to AC battery chargers. | No - not limited. If you believe that you have a better solution - please detail this and explain why and clearly indicate the cost. | 2024-04-03
2 | on 6.2, item c, you ask for the inclusion of a structural report to confirm roof load capacity at submission of the tender? | We are happy to have a structural report from the winning bidder. | 2024-04-03
3 | With reference to the above tender, are we able to part cover some of the Skylights as we do not seem to be able to install a104kW system without doing so. | three skylights on the central north section can be covered. | 2024-04-08
4 | Also is there room to manoeuvre a scissor lift on the workshop floor to be able to install netting. | There is no internal room for using a scissor lift. | 2024-04-08
5 | Are the currently installed solar panels staying? | Yes these were installed in 2011 and are staying in place. They use 4 inverters currently - 2 x Solis and 2 x Fronius. | 2024-04-08
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: jackie@jackiegeorge.co.uk