## Sheet1
Highways England Confirmation of Task Order
Redacted under Section 40 and Section 43 of the FOI Act (2000)
Supplier: | AECOM | Fee Request for this CTO |  | 12578.32
Project Title: | A421/A5 Junctions Study – A421/A428 Marsh Leys Traffic Surveys
Contract Ref. | 0 | CPA No.: | Redacted | BPA No.: | Redacted
PIN Description: | ODE Spatial Planning 19-20 | Sub Pin: | 3 Other SP | PIN No.: | Redacted
HE Reference: | EE 20 19/20AECOM | Start and End Date : |  | 09/05/2019 - 05/07/2019
Task Overview and Expected Outcomes
AECOM have been asked by Highways England to undertake a study of A421 and A5 junctions, to determine its current and future operation. The following A421/A5 junctions are to be surveyed: - A421/A428 Marsh Leys junction; - A421/A6; - A5/A509 H5 Portway and adjacent A509/V6 Grafton Street Roundabout; and - A5/V6 Grafton Street. This study will comprise of a number of stages; survey data collection, base model (LinSig/ARCADY) and forecast model preparation. This sub-task of the study includes the commissioning and overseeing of the traffic surveys that are required to build the base model for the A421/A428 Marsh Leys junction. These surveys could also inform forthcoming merge/diverge assessments. The types of surveys that will be included are: • Link Counts (10 days); • Turning Counts (3 Days); • Queue Data (3 Days); and • Saturation Flow Data (3 Days). For turning counts and queue data the survey period will be collected over a period of three week days. Link count data will be collected for a 2 x 5 weekday periods. The surveys will be used to determine the demand flow at the junction, the turning counts and saturation flows for direct entry to the model, whereas the queue length surveys will be used to determine how well the base model represents the existing operation of the junction and to make adjustments to the model where necessary, before it is taken forward to the forecasting stage. The fee proposal also incorporates a site visit to the junctions on one of the days of the survey.
Task Objectives and Milestones
The objective of this task is to obtain traffic survey data for A421/A428 Junction and the associated mainline and slip roads. This survey data will then be used within the ‘A421/A5 Junctions Study’ which will identify the future operation of the junction.
Expected Project Outcomes
The provision from the appointed survey company of the raw and processed survey data for use within the ‘A421/A5 Junctions Study’.
Project Risk and Management
In order to conduct the survey on neutral days/month, the timescales to implement the survey has become limited. If there is a delay in the commissioning of the work then this could impact the ability of the full survey specification to take place. The surveys need to take place either side of half term week, i.e. 20th May to 24th May and 3rd June to 7th June. The tight timescales may also produce delays, if permissions with Bedford Borough Council or HE to install survey equipment are stalled. There are limited safe locations to install cameras along the on/offslips which could make it difficult to accurately measure queue lengths and in some cases may produce gaps in the queue data. AECOM will work with the survey company to locate the cameras in the most effective, safe place to ensure the best data possible is captured, however if a safe place cannot be identified there may be some gaps in the data. In AECOM’s preliminary assessment of the site it is considered that this risk is low. There is a risk that at the time of the surveys non typical events could occur which could make the data collected unsuitable for building a traffic model that represents a typical AM/PM peak hour. The events could for example include adverse weather, collisions, unusual levels of congestion, non-typical or special events. There is a risk of delays on the A421 or adjacent routes which could affect the free flow of traffic through the junction that is not attributed to the capacity of the junction, but due to congestion downstream of the junction. To minimise these risks AECOM has proposed to record three days of turning counts and queue data, plus 10 weekdays of link count data. There is however still a risk that typical flow conditions may not be captured within the survey periods.
HE Project Sponsor | Sign: |  | Print Name: |  | Date:
Management Approver: | Sign: |  | Print Name: |  | Date:
Contractual Approval: | Sign: |  | Print Name: |  | Date: