## Contents (hidden)
Contents
#REF! |  |  |  | 3
#REF! |  |  |  | 4
#REF! |  |  |  | 5
#REF! |  |  |  | 6
#REF! |  |  |  | 7
Quality check
Rev | Status | Prepared by | Checked by | Date | Issued to | Company | Transmission | Date
XX | Lore pseudo | Name | Name | XX/XX/XXXX | Name | Name | Name | XX/XX/XXXX
XX | Lore pseudo | Name | Name | XX/XX/XXXX | Name | Name | Name | XX/XX/XXXX
XX | Lore pseudo | Name | Name | XX/XX/XXXX | Name | Name | Name | XX/XX/XXXX
XX | Lore pseudo | Name | Name | XX/XX/XXXX | Name | Name | Name | XX/XX/XXXX
XX | Lore pseudo | Name | Name | XX/XX/XXXX | Name | Name | Name | XX/XX/XXXX
XX | Lore pseudo | Name | Name | XX/XX/XXXX | Name | Name | Name | XX/XX/XXXX
© Turner & Townsend Project Management Limited. This document is expressly provided to and solely for the use of [insert client name] on the [insert project name and takes into account their particular instructions and requirements. It must not be made available or copied or otherwise quoted or referred to in whole or in part in any way, including orally, to any other party without our express written permission and we accept no liability of whatsoever nature for any use by any other party.

## Risk Register
Client's Risk Log | [5 empty] | Tenderer's Mitigation
Risk ID | Title | Category | Description (There is a Risk that…) | Cause (As a result of…) | Effect (Which will result in…) | Mitigation
1 | Material Availability | Construction | Availability of critical / specified material to complete the works. | Materials cannot be procured within the appropriate timescales due to market pressures (demand and supply). | Delays to programme; cost increases, impact on quality of final product if substitutes used.
2 | Supply Chain Security | Procurement and contract | Contractor unable to secure supply chain. Integrator supply chain goes into administration, Integrator goes into administration. | Delayed appointments limiting available supply chain to contract with, scope changes, difficult market conditions, poor financial condition of sub-Constructor. | Unable to deliver project to time/quality and increase risk, possible logistical issues with local supply chain in Japan.
3 | Material Prices | Funding and budget | Materials (Japan & International) become unaffordable. | Adverse price fluctuation in materials (concrete, steel, aggregates) and services / exchange rates due to increased demand, limited supply and pressures. | Delay to programme and increased cost. Fundamental re-design to avoid expensive materials. Most notably related to structural design and finishes.
4 | Expo Approval Process | Schedule & Programme | Delays to schedule due to potentially lengthy approval process. | Expo approval process timeframes are lengthy, congested approvals process as pavilions submit at similar times, onerous requirements to satisfy Expo. | Impact on overall delivery of project if timescales affect planned delivery schedule.
5 | Buildability of Creative Concept | Construction | Contractor deviates from creative vision due to design buildability issues. | Design buildability not sufficiently developed at early stage, costly design, complexity of design cannot be built in programme or to budget. | Delays on site, increase in cost and reduction in quality, programme delays.
6 | Equipment Availability | Construction | Availability of specified equipment such as cranes, piling rigs, etc. | Equipment cannot be procured within the appropriate timescales due to market pressures (demand and supply). | Delays to programme; cost increases, impact on quality of works if substitutes used.
7 | Operatives Availability | Construction | Availability of sufficient operatives to complete the works. | Operatives cannot be procured within the appropriate timescales due to market pressures (demand and supply). | Delays to programme; cost increases, impact on quality of works if substitutes used.
8 | Site Ground Conditions | Construction | There is the discovery of unexpected (poor) ground conditions resulting in the construction excavation and foundation duration taking longer than anticipated, delaying the programme | The ground conditions and site location, geotechnical findings, ground / soil has only recently achieved settlement duration and is unstable / weak. The site is Oceanfront, and the water table is higher than expected. Insufficient time allocated for Ground Conditions surveys. | Cost impact, constructability, delays on site, increase in costs, health and safety impact, additional works required to sea water/ ground water, programme delays, change in design and change in construction methodology.
9 | Complexity of Supply Chain | Management and governance | Complex supply chain is difficult to manage and prevents timely progress. | Over complication of contract strategy and appropriate allocation of responsibilities by Integrator. Bespoke suppliers or trades are difficult to manage in line with Client and Expo requirements. | Cost increases, programme delays, management complexity.
10 | Site Logistics (Access and Usage) | Construction | Contractor identifies issues with the site access and egress routes, Contractor's Site Logistics/Traffic Management Plan coordination is insufficient, and there is no availability of space for the laydown of materials. | Proposed access/egress strategy is not suitable for the transportation of materials and goods. The traffic management plan is not developed appropriately at the right stage of the programme and there is insufficient communication in place. UK Pavillion land cannot be used for material storage, or otherwise, until design is approved by Expo and local permits in place. | Delays on site, increased costs, health and safety implications, delays to the programme, theft, vandalism.
11 | Environmental Discoveries | Environment, Sustainability and Net Zero | Environmental discoveries prevent construction progress, i.e. there is the presence of hazardous materials / waste on site, Discovery of animal nesting, or the presence of ecological habitats and protected species. | The discovery of an unknown quantity and quality of hazardous materials present on the site, and the possible disturbance of these materials during construction, Local ecological conditions. | Delays on site, and as a result to the programme, cost increases.

## _master (hidden)
Title