| Key Procurement Activities | Dates |
| --- | --- |
| Despatch of the OJEU Contract Notice | 29/06/2018 |
| Deadline for Bidders’ clarification questions relating to the Selection Questionnaire ("SQ") | 16/07/2018 at 5pm |
| Deadline for submission of completed SQs | 30/07/2018 at Midday |
| Shortlist identified for Invitation to Submit Initial Tenders (“ISIT”) | 16/08/2018 |
| Unsuccessful Bidders notified | 17/08/2018 |
| Final version of the ISIT document issued to Bidders shortlisted following completion of the SQ phase | 17/08/2018 |
| Deadline for clarification questions relating to ISIT | 31/08/2018 5pm |
| Initial Tender return date and time | 11/09/2018 at Midday |
| Clarification and Evaluation (ISIT) | 12/09/2018 to 24/09/2018 |
| Shortlist identified for Invitation to Submit Detailed Tenders (“ISDT”) | 24/09/2018 |
| Unsuccessful Bidders notified | 25/09/2018 |
| ISDT document issued to Bidders shortlisted following completion of the ISIT phase | 25/09/2018 |
| Pre-ISDT submission negotiation meetings commence | 01/10/2018 |
| Deadline for clarification questions relating to ISDT | 17/10/2018 at 5pm |
| Detailed Tender return date and time | 26/10/2018 at Midday |
| Post-ISDT submission negotiation meetings commence | 05/11/2018 |
| Negotiation concluded and shortlist identified for Invitation to Submit Final Tender ("ISFT") | 15/11/2018 |
| ISFT document issued to Bidders shortlisted following completion of the ISDT phase | 16/11/2018 |
| Deadline for clarification questions relating to ISFT | 20/11/2018 at 5pm |
| Final Tender return date and time | 26/11/2018 at Midday |
| Clarification and evaluation of final tenders | 27/11/2018 to 19/12/2018 |
| Winning Bidder Selected | 19/12/2018 |
| Notification to unsuccessful Bidders and winning Bidder | 20/12/2018 |
| End of mandatory standstill period | 31/12/2018 |
| Contract awarded | 02/01/2019 |
| Contract signature by | 09/01/2019 |
| Transition services commence | 14/01/2019 |
| Operational services commence | TBA |