## EVP Programme Plan
Timescales (2020-21)
Task ID | Task Description | Activity Owner | Start Date | End Date | % Complete | Status | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | Comments
1 | Mature Schedule of Requirement (SoR) and confirm requirement. | IH / KB
2 | Develop Procurment Strategy and Commercial Strategy | RB /AW
3 | Develop Advert, Invitation to Tender (ITT) and Scoring Methodology | IH /RB
4 | Secure Funding Approval (BC) | KB
5 | Publish Advert and ITT under Open Procedure of PCR 2015 | RB |  |  |  |  | 2020-07-31
6 | ITT Response Date | All | [5 empty] | 2020-08-31
7 | ITT Evaluation Period
8 | Tender Evaluation Period (TEP) and down selection
9 | Mandatory Standstill Period (10 calendar days)
10 | Contract Award | [9 empty] | 2020-11-16
11 | Contract Start-Up Meeting
12 | Contract Management Activities
13 | Invoke Contractual Option to Extend Contract

## EVP Scoring Criteria
Score | Criteria
0 | No Answer –Nil or inadequate response. Fails to demonstrate an ability to meet the requirement.
1 | Poor –The response addresses some of the elements of the requirement but does not fully detail or explain how the requirement will be fulfilled.
2 | Satisfactory –The response addresses some of the elements of the requirement but requires much more detail or explanation how the requirement will be fulfilled.
3 | Good - The response addresses the majority of the elements of the requirement but requires some more detail or explain how the requirement will be fulfilled.
4 | Very good - The response addresses all elements of the requirement, demonstrates a very good understanding of the requirement and provides details and explanations of how the requirement will be fulfilled.
5 | Excellent - The response is comprehensive, unambiguous and demonstrates a thorough understanding of requirement and provides excellent details and explanations of how the requirement will be met in full.

## EVP Technical Scoring
In addition to answering the questions below, all Bidders must submit a proposal of how they will deliver the EVP Statement of Requirement (SoR). |  |  |  |  | Bidder Name
Number | Question | Word Count | Score | Weighting | Score | Notes
1 | The bidder will describe how they will design and develop the DE&S Recruitment Marketing Strategy and provide examples of how this would be implemented. The bidder will describe how they will assist DE&S in establishing stronger relationships with potential candidates through social media and how they will assit in building DE&S’ employment brand in a targeted way. | 1000 | 0 - 5 | 30% | 0
2 | The bidder will describe how they promote and ensure diversity within ethnicity, social mobility and gender groups when developing and delivering recruitment campaigns for organisations similar to DE&S. | 1000 | 0 - 5 | 10% | 0
3 | The bidder will describe their previous experience and specialist skills in Recruitment Marketing and Advertising and will provide demonstrable examples of their track record and examples of successes. | 1000 | 0 - 5 | 20% | 0
4 | The bidder will describe how innovation will be used to deliver the solution and identify the routes to markets that will be utilised. | 1000 | 0 - 5 | 10% | 0
5 | The bidder will detail how they will provide clear, accurate, reliable reporting to DE&S whilst monitoring and demonstrating Return on Investment (RofI) for the routes to market and attraction tools | 1000 | 0-5 | 10% | 0
6 | The Bidder shall provide details of any awards it has won within the past 1year, such as RAD's,In House Recruitment Awards and Employer Brand Management Awards etc... | 500 | 0 - 5 | 5% | 0
|  |  | Total Bid Score Q1-6 (out of 30) |  | 0
7 | Presentation / Scenario - please do not respond to this. Important Note: You will be invited to the Presentation/Scenario if you're successful and achieve a minimum score of 3 (total 2.4) against Questions 1 - 5. Bidders can only achieve a score of 0 or 5 for Question 6 in line with the Technical Evaluation Criteria in the ITT. | N/A | 0 - 5 | 15% | 0
|  |  | Total Bid Score Q7 (out of 5) |  | 0
|  |  | Total Overall Bid Score (out of 35) |  | 0
Note: In order for the Tender to be deemed Technically Compliant, the minimum score of 3 required against each Technical Evaluation Criterion for Questions 1-5 must be met as a minimum. If the scoring falls below the Minimum Scoring Required on one or more of the Technical Evaluation Criteria, the Tender will be deemed Technically Non-Compliant.

## EVP Technical Scoring Original
In addition to answering the questions below, all Bidders must submit a proposal of how they will deliver the EVP Statement of Requirement (SoR). |  |  |  |  | Bidder Name
Number | Question | Word Count | Score | Weighting | Score | Notes
1 | The bidder will describe how they will design and develop the DE&S Recruitment Marketing Strategy and provide examples of how this would be implemented. The bidder will describe how they will assist DE&S in establishing stronger relationships with potential candidates through social media and how they will assit in building DE&S’ employment brand in a targeted way. | 1000 | 0 - 5 | 30% | 5
2 | The bidder will describe how they promote and ensure diversity within ethnicity, social mobility and gender groups when developing and delivering recruitment campaigns for organisations similar to DE&S. | 1000 | 0 - 5 | 10% | 5
3 | The bidder will describe their previous experience and specialist skills in Recruitment Marketing and Advertising and will provide demonstrable examples of their track record and examples of successes. | 1000 | 0 - 5 | 20% | 5
4 | The bidder will describe how innovation will be used to deliver the solution and identify the routes to markets that will be utilised. | 1000 | 0 - 5 | 10% | 5
5 | The bidder will detail how they will provide clear, accurate, reliable reporting to DE&S whilst monitoring and demonstrating Return on Investment (RofI) for the routes to market and attraction tools | 1000 | 0-5 | 10% | 5
6 | The Bidder shall provide details of any awards it has won within the past 1year, such as RAD's,In House Recruitment Awards and Employer Brand Management Awards etc... | 500 | 0 - 5 | 5% | 5
7 | Presentation / Scenario - please do not respond to this. Important Note: You will be invited to the Presentation/Scenario if you're successful and achieve a minimum score of 3 (total 15) against Questions 1 - 5. Bidders can only achieve a score of 0 or 5 for Question 6 in line with the Technical Evaluation Criteria in the ITT. | N/A | 0 - 5 | 15% | 5
|  |  | Total Bid Score (out of 35) |  | 5
|  |  | Percentage Score |  | 100%