Providing support for implementation and compliance building in UK Overseas Territories on articles 8, 11 and 13 of the FCTC

Programme specification 2017

| Date | June 2017 |
| --- | --- |
| Version | 1 |

- Purpose

  - This document set outs Public Health England’s specification for providing support for implementation and compliance building for articles 8, 11 and 13 of the Framework Convention on Tobacco Control (FCTC) in UK Overseas Territories (UKOT).

- Background

  - The FCTC represents a legally binding blueprint for governments to implement evidence-base tobacco control policies.  The UK is highly compliant with the Framework Convention Tobacco Control (FCTC) however UK ratification of the Convention left OTs in an anomalous position. This programme is funded to assist interested OT administrations in implementation of the FCTC. No separate ratification of the convention is required. In high level discussions with OT heads of government, there is enthusiasm among most UKOTs to implement the FCTC.

  - There is a range of resources available that could help UKOTs to develop appropriate regulations and legislation and provide support for overcoming barriers to become compliant with articles 8, 11 and 13.

- Context

  - Support for implementation and compliance building will include, but is not limited to, the assembly of a resource library. Additional support will be commission in the course of the year reflecting emerging needs within UKOTs.

- Purpose of the support for implementation and compliance building

  - To advise PHE and UKOTs on communications related to regulatory implementation and compliance building

  - To collate existing regulations and legislation related to articles 8, 11 and 13 of the FCTC.

  - To identify and collate regulations and legislation which are particularly relevant for UKOTs population size, administrative processes and capacity.

  - To identify and collate resources that can help overcome barriers to successful implementation of articles 8, 11 and 13, for example support for countering tobacco industry interference.

  - To provide additional support for implementation and compliance building

- Quality assurance and governance requirements

  - The successful provider will have an extensive track record in supporting lower and middle income countries and territories to implement the FCTC.

  - The successful provider is expected to demonstrate strong understanding of articles 5.3, 8, 11 and 13 of the FCTC.

  - The successful provider will have an extensive track record in implementing the FCTC in the UK and a strong understanding of how this can relate to UKOTs.

  - The successful provider will have a strong track record of supporting policy and regulatory implementation in tobacco control at a local, national and international level.

  - The successful provider will be expected to present a plan for the programme at the outset.

  - A project oversight group will be established to include a nominee from PHE.

- Delivery timescale

  - To complete and deliver a programme of implementation support and compliance building by 31st March 2018.

- Contract period

  - The contract is for the 2017/2018 implementation support and compliance building only.

  - The successful candidate will be invited to bid for subsequent projects.

- Bid evaluation criteria

  - Bids will be evaluated based on the following criteria:

    - Value for money of overall programme.

    - Expertise and experience in regulatory implementation of the FCTC.

    - Ability to provide implementation support and compliance building as set out in section 4.

    - Ability to meet quality assurance and governance requirements set out in section 5.

    - Compliance with PHE required delivery date(s) of goods/service.

    - Feasibility and achievability of programme.

    - Acceptance of PHE terms and conditions.

- Contact point(s)

  - It is expected that the successful provider will appoint a suitably qualified project manager who will be the main point of contact with PHE.

  - The key contact point at PHE will be Martin Dockrell (Tobacco Control Lead) or his designate. The PHE tobacco control team will be available for telephone or face-to-face advice at agreed points throughout the project lifetime.

- Costs

  - Providers responding to this tender will be required to give a detailed breakdown of their costs. Please note that applicants will need to demonstrate value for money.

  - The overall contract value will be up to £70,000 in the first year on a draw down basis.

  - At the end of the contracted period (March 2018) a minimum value of £10,000 will be awarded as a retention fee.