## Cover
UK - OFFICIAL SENSITIVE
Propulsion Demonstrator ITN: 710871451 : Master Dependencies and Assumptions List (MDAL)
Document Author ¦ Approver : Steve Hyde, Nik Khanna
©2024 Reaction Engines Proprietary Information
Document History
Revision | Date of Issue | Reason for Issue | Notes / Comments |  | Approver | Signature
1 | 2024-05-28 | Master AED issued with proposal | Shall be finalised 1 month after contract award.
2 | 2024-07-08 | Updated to reflect fixed price contract | Shall be finalised 1 month after contract award.
This document is subject to the following Export Control Information
Country |  | Export Classification |  | Date
UK |  | ML22a relating to ML10d |  | 2024-05-28
UK - OFFICIAL SENSITIVE

## Overview & Intructions
Key | Discriptor | Programme
Assumptions | A entry which provides clarity and context to the outputs of the contract. (In Scope) | Financial
Exclusions | A entry which provides a statement of clarity to what is not delivered or out of scope to an obgliation to subject entry (out of Scope) | Technical
Dependencies | An event or action which is required in order to achieve a stated outcome.

## Programme AEDs
| ©2024 Reaction Engines Proprietary Information |  |  | UK OFFICIAL SENSITIVE
UID | AED Category | Assumption/Exclusion/Dependency | AED Title | AED Description | Impact & Implications
001 | Financial | Assumption | Firm Price | The proposal is on a firm price basis, the deliverables stated within the technical proposal are the desired outcomes as identified at the time of the proposal. | REL will endeavour to deliver outcomes stated within the SoW.
002 | Financial | Dependency | Firm Price - Consumption of the LoL | It is assumed that to deliver the technical outputs specified within the SoW the Authority shall maintain approval to cover the budgetary maximum price, as specified within the contract, throughout the contract period. | Any changes to the available budget may have an adverse effect on the company's ability to deliver outcomes.
003 | Financial | Assumption | Firm Price - Budgetary Pricing | All costs stated within the financial and contractual proposal are on a firm price basis; REL is responsible for managing the outcome cost for delivering these requirements within the proposal. | REL has introduced a number of management processes within the delivery of the contract to monitor, report and action any variance identified.
004 | Financial | Assumption | Contract Structure | It is assumed that the contract shall not be classified as a QDC throughout the contract period. | Changes to the contracting structure may have an adverse costing effect due to the additional obligations associated with the reporting and management of QDC contracts.
005 | Programme | Assumption | Reporting Outcomes | It is assumed that the reporting methods and requirements developed in delivery of this Contract shall be on a minimal basis, reflecting information generated for internal use. | Any additional reporting requirements from those proposed may have a costing impact, requiring more PM effortt.
006 | Programme | Assumption | Quarterly Progress Review Attendance | It is assumed the Authority shall, in the attendance of the quarterly progress review, have SQEP representatives who have the necessary delegated Authority to accept necessary decision within the review, such as change requests. | Failure to provide SQEP and delegated authority representatives may impact SOR delivery.
007 | Programme | Assumption | Programme Classification | It is assumed that the classification of the Programme shall be no higher than Official-Sensitive, except for elements specifically connected with missions or use cases, as detailed in the Security Aspects letter. Furthermore, all component hardware assets are classified no higher than OFFICIAL, with the exception of the Pre-Cooler brazed modules which are classified OFFICIAL-SENSITIVE. | Classification of the Programme at higher than Official-Sensitive will occur additional costs associated with the higher level of security and data protection required.
008 | Programme | Assumption | Operational Analysis | As requested by the RCO, NG shall provide Operational Analysis in full in accordance with the NG white paper submitted to MOD, ref AS_DSEA_00401 | REL will sub-contract the Operational Analysis to NG using the available white paper as a basis for the detailed work to be completed
009 | Programme | Assumption | Airframer cost estimates | Scaled Composites Airframe programme and costings are sufficiently accurate and comprehensive for the airframe portion of this package | REL do not intend to seek further updates for airframe level cost and programme beyond those already available from Scaled Composites
010 | Programme | Assumption | Core Engine and Turbomachinery modules | Turbomachinery capability can be acquired via REL supply chain/partnering | REL strategy is to fill propulsion capability gaps associated with the core engine and other turbomachinery modules through execution of a supply chain/partnering strategy that will be determined during this phase (Pivot Planning)
011 | Programme | Assumption | Airframer prime role | REL will not prime airframe beyond this phase | RCO need to satisfy internal MOD scrutineers that air vehicle and sub system cost estimates other than the propulsion system are suitable and comprehensive for the purpose for which they are provided
012 | Programme | Exclusion | ITAR | Technology/artefacts under ITAR control are excluded from the scope of the contract | As a TAA is not in place, any technology knowledge or requirement that is under ITAR control will be excluded from this proposal
013 | Programme | Exclusion | Payload deployment capability | Payload deployment capability was not considered in the previous NG/Scaled Composites work and will not be included as part of this work package | Any cost, programme or technical input to the MOD business case concerning payload deployment will need to be provided by RCO/DSTL
014 | Programme | Exclusion | Operational System Airframe Development | Airframe development roadmap and costing will only be to a Y plane demonstrator, any parallel or subsequent development leading to an operational system will be excluded, for example payload deployment capability | Consideration will need to be given by the RCO to any parallel work needed to achieve the RCO aspiration timeline to Operational System readiness and for incorporation of resultant work packages into the RCO business case for future phases of work
015 | Programme | Dependency | DSTL input to Operational analysis | DSTL shall provide all the necessary inputs to NG for the Operational analysis | REL rely on DSTL to collate and input concept information into the Operational Analysis based on the previously issued propulsion system data
016 | Programme | Exclusion | Operational Analysis Acceptance | TAA will not be available to enable REL to approve the quality of the NG Operational Analysis(OA) deliverables | RCO will receive OA artefacts directly from NG and will be responsible for sign-off
017 | Programme | Dependency | MoD Industrial strategy for HVX | MoD Industrial strategy limitations will need to be shared with REL to ensure any proposed roadmap will be compliant with it | Proposed roadmap, supply chain, partnering etc could be in conflict with MoD industrial strategy and not acceptable if this information is not shared at the start of the contract
018 | Programme | Dependency | MoD UK Sovereignty requirements | MoD UK Sovereignty requirements will need to be shared with REL to ensure any proposed roadmap will be compliant with it | Proposed roadmap, supply chain, partnering etc could be in conflict with MoD industrial staragy and not acceptable if this information is not shared at the start of the contract
019 | Programme | Dependency | Transition point to Acquisition Programme (trigger event(s)) | Transition point to Acquisition Programme major events should be communicated to build into the roadmap | Any major events/inputs to inform a potential transition to an Acquisition programme should be communicated to enable them to be built into roadmaps and planning
020 | Programme | Exclusion | Airframe technology maturation detail via Government to Government where required (as no TAA in place) | Airframe technology maturation will have to be passed via Government to Government where required (as no TAA in place) | REL will not be able to be involved in any Airframe technology details under ITAR control so these will be excluded from the deliverables. The RCO will have to obtain this information directly from government to government discussions.