## Sheet1
Highways England Confirmation of Task Order |  |  |  |  | Redacted under Section 40 and Section 43 of the FOI Act (2000)
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | Atkins
Project Title: | M20 Lorry Area Brock (Interim) Project - Task Order No.3
Contract Ref. | Redacted | CPA No.: | Redacted |  | BPA No.: | Redacted
PIN Description: | M20 Op Stack Interim Solution | Sub Pin: | Redacted |  | PIN No.: | Redacted
HE Reference: | SE 3 18/19ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | Redacted | Consultant Contact: |  |  | Redacted
Start & End Date: | 20/04/2018 - 31/05/2018 | CTO Authorisation No.
Task Overview
1. Preparation of technical notes and attendance at PSCRG meetings. 2. Production of Safety Plan and undertaking of Road Safety Audit and associated reporting. 3. Design work to include: Preparation of DfS; Statutory Service Requirements; Geotechnical Assessments, Road Restraint Systems; As Built drawings; Structures assessments; Pavement repairs; Drainage; 4. Production of PCF products including: Combined Modelling and Appraisal (ComMA) report; Equality Impact Assessment (EqIA) screening; Health and Safety; Environmental including Environmental Assessment Plan, Report and Screening; SAR / TAR. GIR/GDR amongst others. Refer to the latest Stage Management Plan which includes the agreed PCF products for Atkins to generate. (Redacted email sent on 16/03/18) 5. HE Project Manager Redacted maintains a ‘Works Brief’ document which was the 1st revision was sent on 16/11/17, most recently updated on 26/03/17 (Update 5). This document and the associated email communication form part of the formal instruction of works/ from HE to Atkins. 6. It's noted that this CTO covers time on Task Order 3 activities from start of March 2018. However it also subsumes time from the start of February 2018 from Task 2 where we have agreed with Atkins that additional costs accounted will be reflected in this CTO under Task Order 3. 7. Atkins will undertake Principal Designer role.
Task Objectives and Milestones
• To prepare PCF Products for SGAR 3-5 meeting on 9th May 2018 • To support Highways England in finalising Environment Screening submissions (RoD/NoD) • To prepare staged release of permanent works design information for RRS, whitelining and typical details for pavement repair and drainage protection commencing end of May 2018 • To provide BIM governance information by end of October 2019
Task Outcomes
To support scheme delivery ready for March 2019
Project Risk and Management
Risks • Changing Scope and political influences affect delivery milestone of March 2019 Management • Framework Contract management – Redacted • Framework Task management – Redacted • Project Manager – Redacted • Programme Management – Redacted • Project Director - Redacted. Note that for the purpose of delivering the requirement of this bespoke task, it draws on specialist technical input; therefore to facilitate this we propose to charge Redacted at non-rate capped Redacted per hour.
Project Title: | M20 Lorry Area Brock (Interim) Project - Task Order No.3 |  |  |  | HE Reference: | SE 3 18/19ATK
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 3 18/19ATK | 502250.36 | 0 |  |  | 502250.36 | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 502250.36
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 502250.36
Total Project Fee Estimate |  |  |  |  | 502250.36
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted | Director | 132 | @ | Redacted | Redacted
M20 (Director) | Director | 1405 | @ | Redacted | Redacted
M20 (Associate Director) | Associate Director | 892 | @ | Redacted | Redacted
M20 (Principal Planner/Engineer) | Principal Planner / Engineer | 1437 | @ | Redacted | Redacted
M20 (Senior Planner/Engineer) | Senior Planner/Engineer | 1850 | @ | Redacted | Redacted
M20 (Planner/Engineer) | Planner/ Engineer | 166 | @ | Redacted | Redacted
M20 (Assistant Planner/Engineer) | Assistant Planner/ Engineer | 940 | @ | Redacted | Redacted
M20 (Senior Technician) | Senior Technician | 378 | @ | Redacted | Redacted
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2018-04-18 |  | Works Total |  | 502250.36
Confidential and commercially sensitive information which shall not be disclosed to third parties
|  |  | Sub Total |  | 502250.36
|  |  | Expenses |  | 15000
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 517250.36