## Sheet1
CLARIFICATION LOG
Tender: | Tender for Professional Services - Kerrier Way Green Gateway, Camborne
Tender Reference:
Published Date: | 2023-03-01
Version number: | 0.3
Number | Clarification | Response | Reply date
1 | Please can you advise what is your proposed RIBA Stage 5 Construction & RIBA Stage 6 Handover periods, (so that we can attach to our proposed RIBA Stage 3: Developed Design and 4: Technical Design periods) respectively? | The programme for the delivery phases of the project will be agreed as the developed designs take shape. The Council's only current restrictions on timescales are goverened by the Town Deal funding for the project, which must be spent by the end of the 2025/26 financial year. We envisage the project to be complete by December 2024, but this is only for Camborne Town Council resource management planning. | 2023-03-27
2 | The tender information suggests that the project will be delivered through a number of design and build contracts. Is this a project requirement? Considering the nature of works, it may be preferable to deliver the works though a main traditional contractor with design and build elements included as subcontracts within that contract. Would the client be open to discussions on delivery of this nature? | Absolutely. We will gladly work with the principal designer to agree the most practical and affordable delivery model for the project | 2023-04-26
3 | We assume that the client will be paying the planning fees (and any other associated fees) - is this the case? | Yes CTC will be paying the planning fees, but it is expected that all associated preparation costs are included in the tender price | 2023-04-26
4 | The planning application will require arboricultural and ecology surveys so we assume we should include these elements in our scope - please confirm that these services are not allowed for elsewhere? | These should be included as indicated above | 2023-04-26
5 | Section 8.2 in the selection questionnaire (H&S management) asks for experience acting as principal contractor role, we assume this should be principal designer role? | Sorry, yes Principal Designer | 2023-04-26
Clarifications will be published against the Contract Notice on Find a Tender and Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: