## Clarification Log
WP10 - Hydraulic System Replacement Projects - Clarification Questions and Answers Log
Q. No. | Question | Response | Date issued
1 | Door cylinder, does it have Viton seals | The supplier can specify the most suitable seal for their solution. Please note that the cylinders will be exposed to fumigant every 6 months which takes place in at high humidity. | 2024-12-05
2 | Noted that we need an enclosure on our power unit to control the power unit electrically, how do they want to interface our enclosure with the site controls ie what provision do we need to make for that. | Currently, the hydraulic system actuators are controlled directly from the incinerator control panel rather than a dedicated controller for the hydraulic system. To simplify the project, the intention would be for the new hydraulic system to be controlled in the same way as the existing. | 2024-12-05
3 | Does the power unit need duty and standby pump motor sets for resilience | Yes, duty and standby pump motor sets are required. | 2024-12-05
4 | Do you want the manual retraction of the of the Ram for the loading system, to be done Hydraulically or with Mechanical intervention | The supplier is to consider if the hydraulic ram system can be upgraded to include a manual override such that the ram can be inserted/extracted manually if the hydraulic system fails. If this is not possible determine if a secondary independent ram system can be installed. The concern is that the current layout requires hydraulic power to withdraw the ram from the combustion chamber. | 2024-12-05
5 | Does the additional service of lifting the service door above the multistage cylinder need to be a permanent install on the new pack. | The service door is to be permanently hard piped as part of the works. It must be noted that the loading lid has to be opened first as there is an overlap onto the service door. | 2024-12-05
6 | What is the current oil type used on site | Current oil is Hydraulic Oil ISO 32. Supplier to specify the type of hydraulic oil suitable for their system. | 2024-12-05
7 | Do we need to allow the cost for the oil within the specification | Yes | 2024-12-05
8 | How are the cylinders fumigated prior to leaving site for repair, ie do they need to be fully stripped on site? | As part of the tender please can the supplier add a line item to for the existing cylinders to be fully stripped and de-greased within ISO 11. The site will disinfect and fumigate the cylinders before passing to the supplier for overhauling and retesting. The disinfection and fumigation period is typically overnight. | 2024-12-05
9 | Can you supply photographs of the multistage cylinder in situ | Photos are attached | 2024-12-05
10 | Is there any drawings of the multi stage cylinder and its fixings into its housing | The only document available is the O&M included in in the tender and can be sent to suppliers once they have completed the confidentiality agreement. | 2024-12-05
11 | Do hose ends have to be stainless steel | The supplier should select a material which is suitable for their hydraulic system and can be exposed to fumigant every 6 months which takes place in at high humidity. | 2024-12-05
12 | Does the new pipework need to be stainless steel | The supplier should select a material which is suitable for their hydraulic system and can be exposed to fumigant every 6 months which takes place in at high humidity. | 2024-12-05
13 | The scope of works mentions disposal of the existing hydraulic equipment, but during our survey on site, the engineer that came in with us said we can leave it there for them to dispose of, please confirm if this is required . | Disposal of the existing hydraulic system should be part of the tender (see ITT) | 2024-12-05
14 | The engineer in question lives next door to a garden containing Pigs . He does not interact with them and does not go into their property. Is there a risk of exposure to the pigs from being within a certain distance if he is in his garden, and should any additional precaution be required in his case ? | As the Engineer does not live on the same property as the pigs, he is fine to visit site and work within SAPO4 contained areas and then to enter his own garden. The risk of exposure of the pigs to a pathogen from within the contained areas is very low due to the controls that are in place. In our training for those working within containment, we ask staff to keep a distance of 10m from susceptible animals when they are walking across footpaths, so if the engineer was at all concerned, he could implement this, although there is no requirement to. Please see Quarantine Requirements attached | 2024-12-05
15 | 1. Does the hydraulic system components need to be stainless steel material ie the hydraulic tank, Steel Hard Lines and associated fittings, as it was mentioned about washing the area down after use | The supplier should select a material which is suitable for their hydraulic system and can be exposed to fumigant every 6 months which takes place in at high humidity. | 2024-12-05
16 | 2. Is there 110V sockets available onsite for the pump to removal oil from hyd tank. | This can be arranged during the works. | 2024-12-05
17 | Confirm weight limit and LOLA certs for use of current ceiling crane | SWL, Max load is 1000KG. next inspection date is 15/05/2025. Certificate attached. | 2024-12-05
18 | It was discussed on phonecall that we could provide our own clothing for use once on the clean zone side could you confirm the levels of protective clothing which can be used during installation, if this can be cleaned also. Shower process during shutdown | The building will be fumigated prior to the works starting, however the showering out procedures stay in place throughout the works. Any clothing taken into ISO 11 will not able to be brought out again. Tools can be taken in, however it needs to be confirmed that they can be fumigated out again - the majority of general tools are able to be fumigated. The supplier can wear any clothing inside ISO 11 and are free to select the clothing and safety PPE in line with their RAMS. | 2024-12-05
19 | Can we have a copy of the Site layout plan and a drawing of incinerator plant, room and the building where the incinerator sits | Please see attached drawings | 2024-12-05
20 | Confirm hard pipes are acceptable with no hoses used | As per URS in tender pack - Needs to be hard piped system up to the actuator/cylinder. Then suitable connection to allow for vibrations. | 2024-12-05
21 | What sensors are used on the main push cylinder | Since the hydraulic system is fully controlled by the incinerator control panel, it is expected that sensors currently in use will remain in place. Supplier to clarify further if needed. | 2024-12-05
22 | Is there a hydraulic schematic drawing | An O&M is available in the tender package upon agreement to confidentiality agreement. | 2024-12-05
23 | Access to the company building the new control panel to discuss how the plc will communicate with the hydraulic system | Currently, the hydraulic system actuators are controlled directly from the incinerator control panel rather than a dedicated controller for the hydraulic system. To simplify the project, the intention would be for the new hydraulic system to be controlled in the same way as the existing. | 2024-12-05
24 | Is there a way to Site the HPU beside incinerator and pipe through the wall on the "safe side" for ease of future maintenance | Currently, the entire hydraulic system is located within the bio-contained space and does not exit this space. The supplier is free to propose alternative options - please be aware that the this will result in a hydraulic system which crosses the bio-containment barrier. Such a design would need to be reviewed via a HAZOP and will likely require guarantees from the supplier that there is no possibility for the oil transferring between the two areas to be exposed to the environment within the Incinerator Loading Hall (i.e. where the current hydraulic system is located.) | 2024-12-05
25 | What collars need to be used around the pipe | The supplier can specify the most suitable collars for their solution. Please note that the cylinders will be exposed to fumigant every 6 months which takes place in at high humidity. | 2024-12-05
26 | Is there a list of current approved subcontractors | The supplier is able to use their own sub-contractors provided their sub-contractors work under the same quality, safety and environmental policies as the supplier. The supplier will take full responsibility of their own sub-contractors. | 2024-12-05
27 | How will; the cylinders be cleaned before shipping for refurb, and how long will this process take | As part of the tender please can the supplier add a line item to for the existing cylinders to be fully stripped and de-greased within ISO 11. The site will disinfect and fumigate the cylinders before passing to the supplier for overhauling and retesting. The disinfection and fumigation period is typically overnight. | 2024-12-05
28 | where can we locate a CDM site office? Project will have to be run in 2 phases; strip out and installation. CDM site will be removed between the 2 phases | As part of this tender, the supplier is not required to allow for CDM Construction Site costs, unless they deem it necessary. It is proposed that during the shutdown where these works take place, there will be a CDM site set up for the suppliers use, should they need this. If all works are taking place within the ISO 11 building, then no CDM requirements will be needed as all works will be carried out in line with The Pirbright Institute's Safe Systems of Works. | 2024-12-05
29 | Length of shutdown may not allow for cylinders to be refurbished. Therefore we advise to Quote for new | Please can the suppliers provide an optional line item cost for replacing the existing cylinders with new. This can be considered as part of the tender. | 2024-12-05
30 | HPU needs to be bunded | The supplier is to propose the full solution based on their expertise and experience. | 2024-12-05
31 | Manual override system – duty standby with generator to run if power fails. | Yes, duty and standby pump motor sets are required for the hydraulic system. The building has it own UPS and generators, so no allowance has to be made for a dedicated generator for the hydraulics. The supplier is to consider if the hydraulic ram system can be upgraded to include a manual override such that the ram can be inserted/extracted manually if the hydraulic system fails. If this is not possible determine if a secondary independent ram system can be installed. The concern is that the current layout requires hydraulic power to withdraw the ram from the combustion chamber. | 2024-12-05
32 | Mobile Scaffolding we can use can we get certified prior works through Pirbright, as mentioned approved Scaffolding company list you already have - easier to use them to get over the line and the RAMs will get approved easier because of previous works | Please can the suppliers add a provisional cost for scaffolding in their tender. There is a local company which has experience of working in ISO11 and this can be discussed closer to the time of the works. | 2024-12-05
33 | Can we utilise existing ladders onsite | Yes, there are ladders and step ladders inside ISO11 which can be used for the works. | 2024-12-05
34 | Can we use bump caps as mentioned on call, also assume all of our pre delivered PPE will need to be written off and disposed of at the end of the project | The supplier is to use PPE as specified in their RAMS for the works. Bump caps can be used provided the supplier risk assessment allows for this. | 2024-12-05