STATEMENT OF SERVICE REQUIREMENT FOR

THE PROVISION OF A TECHNICAL WRITER TO ASSIST IN THE REWRITE AND PUBLICATION OF THE NATIONAL OBJECTIVES, REQUIREMENTS AND MODEL STANDARDS DOCUMENT

1		BACKGROUND TO THE PROJECT

1.1	Delivery of revisions to NORMS has always been part of the process of achieving the 	overall regulatory intent to promote industry ownership and responsibility for security. 	With DECC we have agreed a timetable for review and development, and aim to 	deliver a revised document called NORMS 2 for their approval in summer 2016.  This 	has been agreed at, and progress is routinely discussed at the ONR Board Security 	Committee and the DECC CNS Programme Board.  It is a key element of the 	2015/16 Programme Plan (and will be in the subsequent year as well).

1.2	NORMS 2 seeks to drive improvements in dutyholders’ assurance regimes and 	encourage greater ownership, responsibility and accountability for delivering effective 	security. The NORMS 2 development process will also exploit opportunities to bolster 	the regulatory framework for cyber security and pursue further harmonisation with 	safety standards and processes. This is consistent with ONR priorities and strategy, 	annual plan commitments and in line with Government policy.

1.3	The employment of a technical writer to deliver high-quality document final drafts 	suitable for final ONR checks and onward delivery to DECC (for Secretary of State 	approval) and to industry (as part of Regulatory Impact Assessment development) by 	March 2016 de-risks the chances delayed/non delivery due to ONR staff being 	diverted to reactive activities, whilst introducing skill-sets not available within ONR.

1.4	ONR intend NORMS 2 to be a world-class document that is accessible to 	dutyholders, Government, other stakeholders, and (to as large an extent as possible) 	the public.

2	SCOPE OF THE SERVICES REQUIRED

2.1	The programme of work is anticipated to run from July to December 2015 and 	comprises of the following elements:

2.1.1	Production of Prewrite

The current NORMS document consists of eight chapters across 279 pages. It has 	been developed iteratively and become difficult to use due to correlated information 	pertaining to a specific element being distributed throughout the chapters rather than 	collocated. A new four-tiered structure has been designed for NORMS 2 consisting of 	a Unifying purpose statement at Tier 1, supported by ten High-Level Objectives 	(HLOs) that were determined following extensive stakeholder engagement. In order 	to produce a NORMS 2 prewrite it is necessary to deconstruct the current NORMS 	content (which sites within Tier 3 – Regulatory Requirements and Tier 4 – Technical 	Guidance) and remap it against the new HLOs. Furthermore, NORMS is supplemented by two additional documents titled the Civil Nuclear Personnel Security Standard and the Civil Nuclear Information Security Standard. It is also necessary to deconstruct these documents and incorporate them within the new NORMS 2 structure.

2.1.2	Workshop Facilitation

A series (up to five) of stakeholder workshops will be held following distribution of the 	prewrite. The intended outcomes of the workshops are to secure support and acquire 	opinions on suitable content for the first draft. The contract involves working in a 	facilitate role by encouraging participant contribution, recording proceedings and 	generating a post-workshop brief with consolidated output.

2.1.3	Technical Authoring of First Draft

  - Gap Analysis – A full gap analysis will need to be undertaken of the 	prewrite to ensure adequate population of the HLOs

  - Identification and incorporation of suitable Tier 3 & 4 content cognisant 	of workshop output and relevant extant publications such as ONR 	Technical Inspection and Assessment guides.

  - Refinement of content – The content of the prewrite will need 	extensive refinement to ensure consistency, coherence and eliminate 	repetition.

  - Presentation of first draft to be completed by 31 December 2015.

2.2	Copies of the NORMS document can be provided to Bidders via an encrypted cd 	upon request by emailing procurement@hse.gsi.gov.uk stating “T2756 – NORMS 	Request" in the subject header.

2.3	The programme of work will include prewrite, workshop facilitation and technical 	authoring.

2.4	The expected outcome is a complete first draft of the NORMS 2 document that 	incorporates the consolidated views of all stakeholders, meets government 	expectations and provides part of a fit for purpose regulatory framework that 	underpins the transformation of security regulation of the civil nuclear industry.

2.5	The final document should conform to the plain English and ONR style guides.

2.6	Although unlikely, the establishment of the new Government may impact on delivery of the NORMS 2 project.

3		OBJECTIVES

3.1	The primary outcome of the project is to produce a first draft of NORMS 2. This will 	require assistance in workshop facilitation through ensuring delegate views are 	recorded, consolidated and incorporated within the first draft NORMS 2, where 	appropriate.

3.2	The contractor should note that the overall objective of NORMS 2 is to support the 	wider paradigm shift of civil nuclear security. The success criteria for NORMS 2 	implementation is defined by industry transformation in terms of, inter alia, 	leadership, competence management and internal assurance; and, designing 	effective security solutions that:

- Add value through integration with business processes

- Encourage innovation and staff involvement

- Reduce regulatory burden

3.3	The contractor should further note that the NORMS 2 project seeks to maximise 	benefit though:

- Achieving closer alignment of approach with safety regulation

- Refreshing and modernising the regulatory framework, particularly in respect of cyber security

- Improving openness and transparency of security regulation

4	CONSTRAINTS

4.1	Working arrangements

- The contract will be managed and reported upon in line with the agreed 	delivery schedule agreed by the ONR Board Security Committee and the 	DECC CNS Programme Board.

- In-programme contract management will be provided by the Deputy 	Programme 	Director.  Day-to-day activity will be coordinated by the ONR 	CNS Policy Band 2.

- Work will be completed using the ONR electronic data management system 	(TRIM) to ensure that document audit and retention requirements are fulfilled.

- A contract risk register will be maintained and overseen under in-programme 	management structures.

- Clear expectations for delivery milestones and quality assurance will be 	provided for 	within the contract, and will be discussed during the project 	initiation meeting.

4.2	Security considerations

- The successful contractor will be provided (if necessary) with IT equipment to 	enable secure communication at OFFICIAL-SENSITIVE and all relevant 	documentation such as the extant NORMS.

- The successful contractor will be required to hold a Baseline Personal 	Security Standard clearance.

5	SUBMISSION OF TENDERS

5.1	To submit a compliant proposal in response to this specification Bidders must :

- Clearly address all aspects of the specification (including scope, objectives and constraints);

- Provide a description of the Technical Support Contractor team’s appropriate experience to undertake this work package, and how it will go about the task;

- Provide CVs of the key staff proposed. It is anticipated that the work will principally be undertaken by a very small number of high calibre and experienced individuals with appropriate technical support, management oversight and quality assurance applied;

- Provide 2 references where they have delivered similar services for other clients.

Contracts for the supply of services should have been performed during the past three years. (The customer contact should be prepared to speak to ONR to confirm the accuracy of the information provided).

- Provide an anticipated cost and spend profile for the services

- Provide confirmation of availability of the key staff for the period of proposal;

- Provide the names and contact details of the Project and Contract Managers proposed for this task;

- Identify the anticipated engagement with ONR, including any progress meetings..

6	EVALUATION

6.1	Tenders will be evaluated across three stages of the procurement process, as detailed in the Instructions to Bidders document, comprising of :

- Compliance;

- Quality;

- Value for Money.

The Evaluation Criteria and scoring mechanism is outlined in Schedule B.