12 February 2018

# Dear Bidders,

Request for Quotation: PRJ 612 Healthy Living Ambassadors Training Wave 2

I am writing to you on behalf of Haringey CCG. We currently have a requirement for Healthy Living Ambassadors Training Wave 2, the details of which are set out in the Annex A to this RFQ letter.

We need our chosen supplier to commence the work in the week commencing 7th March 2018 and finish the work on or before November 30th 2018.

Please note the attached (Annex B) NHS Terms and Conditions for the Supply of Services will apply to any contract awarded as a result of this quotation exercise.

If you are interested in quoting for this requirement, please reply with a ‘bid response document’ to the following email box nelcsu.clinical-procurement@nhs.net by 12:00 noon on the 23rd February 2018 with the following information:

- Full name and address of supplier, our reference number and your contact details;

- Details of services to be supplied including details in response to the requirements set out in the Annex A / the evaluation criteria to this letter and a referee (preferably public sector);

- Expected delivery / start / finish date, and a project time table;

- Total price excluding VAT (Annex C);

- Confirmation of acceptance of the terms and conditions of contract (Annex B);

- Annex D – Conflict of Interest Declaration.

Procurement Timeline

| # | Description of the Event | Start Date | Deadline |
| --- | --- | --- | --- |
| 1. | Request for Quotation Issued | 12/02/2018 | 12/02/2018 |
| 2. | Deadline for Clarification Questions | 12/02/2018 | 20/02/2018 |
| 3. | Deadline for submission of quotations | 23/02/2018 | 23/02/2018 |
| 4. | Evaluation of Quotations | Week commencing 26/02/2018 |  |
| 5. | Approval of Contract Award Recommendation | Week commencing 26/02/2018 |  |
| 6. | Notification of outcome of quotation exercise to successful and unsuccessful bidders | Week ending 02/03/2018 |  |
| 7. | Mobilisation | Week commencing 05/03/2018 |  |
| 8 | Contract Commencement Date | 7/30/2018 | 7/30/2018 |

The CCG is seeking quotations from a number of suppliers. The following criteria will apply to the selection of the successful supplier:

| # | Evaluation Criteria |  | Weight |
| --- | --- | --- | --- |
| 1 | Proposed Approach |  | 70% |
|  | 1.1 | Clear Methodology for the delivery of this specification. | 15% |
|  | 1.2 | Capacity to undertake the work in the timelines required - project plan to cover the timescale is requested. | 10% |
|  | 1.3 | Please detail your experience and capability in the area of prevention and leadership training programmes and leadership, including CVs for the team. | 15% |
|  | 1.4 | Please detail your approach to engagement with NHS providers and HLP co-design. | 15% |
|  | 1.5 | Please detail your approach to evaluation and quality of reporting. | 15% |
| 2 | Price (Any quotations exceeding the financial envelope will be disqualified) |  | 30% |
|  | Proposed Approach + Price |  | 100% |

Evaluation scoring criteria:

| Score |  | Definition |
| --- | --- | --- |
| 0 | Non-compliant | No response or partial response and poor evidence provided in support of it. Does not give the commissioner confidence in the ability of the Bidder to deliver the Contract. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Minor reservations | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Compliant | Response is comprehensive and supported by good standard of evidence. Gives the commissioner confidence in the ability of the Bidder to deliver the contract. Meets the Commissioner’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the Commissioner a high level of confidence in the ability of the Bidder to deliver the contract. Exceeds the commissioner’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the Commissioner a very high level of confidence the ability of the Bidder to deliver the contract. Exceeds the Commissioner’s requirements in most respects. |

The Quotation must be submitted in a PDF format, with pricing submitted in a separate file (or submit one priced and one unpriced bid).  Quotations received after the above date and time may not be considered.

It would be appreciated if you could advise, within 3 days of receiving this RFQ, if you intend to submit a bid or your reasons for not submitting a bid.

If the panel feels at any point that there is not sufficient evidence to score a bidder on any evaluation point then they may, at their discretion, seek clarification from any and all bidders. Bidder clarifications will at all times take account of the commercial confidence of bidders.

If a bidder scores a ‘0’ on any sub-section then they may be eliminated at the discretion of the panel, dependent on how service critical the panel deems that sub-section to be. If a bidder scores ‘0’ on an entire section of the evaluation, the bidder will be automatically eliminated from any further evaluation.

The pass-mark for the qualitative evaluation (Questions 1.1 – 1.7) element is 50%. If a bidder does not attain this score overall then their bid will be rejected. This process ensures that NEL Commissioning Support Unit and Haringey CCG attain a minimum acceptable service quality. Following submission of bids, a moderation / evaluation meeting may be held. Following the moderation meeting, Haringey CCG and NELCSU may invite the bidders scoring over 50% to a post bid submission clarification meeting to establish confidence in the Evaluation Panel that you will be able to deliver what you have stated.

In the event of a tie (where two or more top scoring Bidders had the same total weighted score including both quality and price), the CCG will select from amongst those Bidders, the submission of the Bidder with the highest weighted score for the price section.

Your response must be valid for acceptance for 90 days from the deadline for receipt of quotations. Your response constitutes an offer and if Haringey CCG accepts that offer then a legally binding contract will exist between us.

Respondents accept that the Haringey CCG is subject to the Freedom of Information Act and government transparency obligations which may require Haringey CCG to disclose information received from you to third parties.

This RFQ letter and your response do not give rise to any contractual obligation or liability unless and until such time as Haringey CCG issues a letter referencing this Request for a Quotation with a signed contract and a valid Purchase Order number accepting your quotation. Haringey CCG does not make any commitment to purchase and shall have no liability for your costs in responding to this Request for a Quotation.

## Canvassing and contacts

Bidders shall not in connection with this Procurement:

- Offer any inducement, fee or reward to any officer or employee of NELCSU or Haringey CCG or any person acting as an advisor to NELCSU or Haringey CCG in connection with this Procurement

- Do anything which would constitute a breach of the Prevention of Corruption Acts 1889-1916

- Canvass any of the persons referred to above in connection with the Procurement

No attempt should be made to contact NELCSU or Haringey CCG staff, except the Project Team, or to contact NELCSU / Haringey CCG or NELCSU / Haringey CCG advisers or other NHS/DoH bodies as part of the procurement process. Any enquiries made to persons other than the NEL Commissioning Support Unit Project Team will be regarded as prima facie evidence of canvassing.

## Conflicts of interest

In order to ensure a fair and competitive procurement process, Haringey CCG requires that all actual or potential conflicts of interest that a potential bidder may have are identified and resolved to the satisfaction of the CCG.

Potential Applicants should notify the CCG of any actual or potential conflicts of interest in their response to the RFQ. If the potential bidder becomes aware of an actual or potential conflict of interest following submission of the application it should immediately notify the CCG by completing the Conflict of Interest form (see Annex D) for this procurement. Such notifications should provide details of the actual or potential conflict of interest.

If, following consultation with the potential bidder or bidders, such actual or potential conflict(s) are not resolved to the satisfaction of the CCG, Haringey CCG reserves the right to exclude at any time any potential Applicants(s) from the Procurement process should any actual or potential conflict(s) of interest be found by the CCG to confer an unfair competitive advantage on one or more potential bidder(s), or otherwise to undermine a fair procurement process.

Examples of potential conflicts of interest are (without limitation) as follows:

A Bidding organisation, or any person employed or engaged by or otherwise connected with a Bidding organisation, is currently carrying out any work for the CCG, NHS England and/or the Department of Health (DH), or has done so within the last six (6) months;

A Bidding organisation is providing services for more than one Potential Bidder, in respect of this Procurement.

The ‘Conflict of Interest Declaration’, provided in Annex D, must be completed by an authorised signatory, in his / her own name, on behalf of the Bidding organisation and attached in response to this section of this RFQ.

The CCG should be immediately notified, in the event that any actual or potential conflict of interest comes to a potential Bidder’s attention at any time following the submission of the potential Bidder’s ‘Conflicts of Interest Declaration’ and bid documents.

If you have any queries about this letter or the requirement, please contact the under signed at nelcsu.clinical-procurement@nhs.net.

If you are unable to meet this requirement or are otherwise not intending to provide a quote, I would be grateful if you could let me know as soon as possible.

Yours sincerely,

Cristina Marcus

Procurement Officer

NEL Commissioning Support Unit

Second floor,

1 Lower Marsh,

London

SE1 7NT

Annex A

Specification

For

Healthy Living Ambassadors training wave 2

## Introduction:

Healthy London Partnership (HLP) is funded by the NHS in London (Clinical Commissioning Groups and NHS England) to deliver better health and care for all Londoners. Our partners include the Mayor of London, Greater London Authority, Public Health England, London Councils and Health Education England.

HLP’s Prevention Programme is leading a system approach for workplace health in London. Our programme aims to support organisations to:
-Engage in health and wellbeing for staff across all levels

-Identify and embed workplace health as ‘business as usual’

-Increase impact and capacity of staff to improve workplace culture and behaviour

-Evaluate what works and inform sustainable impact

-Create communities of practice

The Prevention programme supports delivery of the NHS Five Year Forward View, challenging the NHS to become a better employer by supporting the health of its frontline staff.

The NHS workforce faces a significant health and wellbeing challenge. Of the 1.2m staff employed, it is estimated 400,000 are overweight and 300,000 are obese. Musculoskeletal and mental health issues make up the main reasons for absenteeism and presenteeism within the system.  A reduction in sickness absence by 0.1% across the NHS could save £34,941,722 - the full time equivalent of 1,364 staff. (source: NHS Employers)

## The aims within the Mayor’s Better Health for All Londoners Strategy also sit alongside the Prevention Programme. Other related work includes ThriveLDN which is a citywide movement to improve the mental health and wellbeing of all Londoners, supported by the Mayor and led by the London Health Board.

## Objective

Healthy Living Ambassadors 2018

We are now looking to take learning from a first wave (detailed in Section 3- Context below) and deliver a second wave of training which will:

-Extend the offer to new NHS organisations and partners

-Improve the training offer and materials

-Evaluate the model for growth at scale

-Build and evidence to evaluate return on investment

-Build and support work to date to upon it to increase impact where ambassadors are already in place

Healthy Living Ambassadors act as leaders and role models to colleagues sharing their passion, supporting colleagues and contribute to a healthy culture and working practice.

They act as a positive resource informing staff of appropriate ways to access services, information, tools and techniques to support wellbeing at work. They can be from any grade across the organisation and similarly are able to work across all levels from senior to frontline to take collective action in the workplace.

The project links directly to other workstreams, including an engagement pilot with General Practice, a ‘Healthy Living Week’ campaign in September, Mental Health training and a Workplace Health evaluation project.

Anticipated benefits

- Improved skills, experience and responsibility on local workplace health and wellbeing issues

- Increased recognition from senior leadership that workplace wellbeing is fundamental to productivity, service delivery  and, ultimately, patient experience. One measure could be from senior/exec  feedback from bite-sized training.

- Learning and evaluation regarding effectiveness of staff engagement model for shaping workplace health

- Contribution towards the developing evidence base on what works to promote health and wellbeing at work

- Increased productivity, reduced sickness absence, improved staff retention, increased staff satisfaction / voice / engagement, capacity and capability building.

## Context

Healthy Living Ambassadors 2017 Summary

In Summer/Autumn 2017 we co-designed and delivered wave 1 training to CCGs, Trusts and other NHS organisations. The content of these modules is grounded in recognised, evidence-based research and study.

Run over 2 sessions of around 3-4 hours, it included modules on:

- Healthy eating

- Physical activity

- Smoking cessation

- Good mental health (e.g. stress management)

- General wellbeing

- Leadership, engagement and communication

Inclusion of Making Every Contact Count (MECC) content was suggested to participating organisations at the lead-in stage.

The outputs have been:

-198 staff trained across 11 organisations in total

-15 executives trained in a ‘bite size’ module

-The formation of a connected group of organisations.

- A suite of training materials

## Proposed Area of Considerations

As well as some organisations who have expressed an interest, we would also like to reach outer boroughs, primary care and non-NHS SMEs.

The training could be delivered by a single provider with additional support for the community of practice/networking elements being delivered by an additional provider/subcontractor.

## Deliverables

The successful provider would:

1. Support wave 1 organisations

- Identify, deliver support offer to organisations in already in place via 1-2-1s, group session or electronic platform

- Comms planning

2. Refine model and materials for wave 2

Co-design with HLP including:

- Theory of change, leadership element

- Comms and marketing materials to HLP branding specification including. model, theoretical approach & user / organisational journey

- Pre-training materials for organisations e.g. E-flyer,poster, top tips, ideas for activities

- Photographs / video and short testimonials of participants for use in HLP comms

- Resource list

3. Deliver training programme including:

- Up to 10 organisations / 2-300 staff. Providers will need to indicate what is feasible within the financial envelope and may need to be negotiated in relation to the balance of activities within the delivery model.

- Individual organisation needs analysis and engagement

- Record baseline data health and wellbeing activity of organisations prior to commencement

- Organisation onboarding and support

- executive bite-size module

- Train the trainer module

- Support and coordination with organisation contact(s)

- Gathering of photos, case studies and video from training sessions

4.Evaluation

- Evaluate and report on all of sections 1-3 including lead-in and post-training focus groups

- Analysis of data post training (3, 6 and 9 months), and gathering of feedback from cohorts trained

- Final and interim programme reports

- Evaluate organisation level needs and long term benefits

- Breakdown and comparison of data of wave 1 and wave 2

- Host celebration event for ambassadors wave 1 & 2

5.Programme management and reporting

- Regular updates including fortnightly catch ups

- Stage review and monitoring of agreed milestones

- Monthly status reports

- Risk and issues updates

The successful bidder will be able to demonstrate:

Expertise

- A strong track record of engagement and training at all staff levels, including senior leadership teams

- A strong understanding of the current evidence base for improving workplace health and wellbeing and those at risk of poor health in the workplace

Working

- Evidence of working creatively, collaboratively and proactively with end users, commissioners, providers and London partners to design and deliver successful projects

- Expertise and experience in developing workplace health plans from a bottom-up approach as well as from a senior/executive perspective

- Excellent skills in producing valid and reliable feedback in various formats from events and focus groups

- Strong and demonstrable project management skills

Production

- Evidence of ability to deliver engaging, energising, motivating and incentivising material

- A strong track record in thematic report writing and data/feedback analysis

- Understanding how to execute successful workplace health plans

- Good evaluation skills or experience in evaluation change in a ‘system’ environment

We are also looking for providers to produce training sessions that encourage competition, are fun and will encourage attendees to spread awareness on health and wellbeing.

## Governance

The project will be managed by Nathan Winch, Healthy London Partnership, and overseen by Sarah Bowker, Implementation lead. Jemma Gilbert is the overall lead for Prevention at HLP. Scoring of bids will be administered by Nathan, Sarah and one member of Prevention TBC.

## Proposed Timetable

Lead-in: Feb-April

- Successful bidder feedback / negotiation session

- Stakeholder kick off meeting. This will look at the successful bidders’ project plan, design, agree initial risks and issues, comms requirements.

- Development of elements / methodology codesigned with staff

- Produce prototype of training and resources

- Prevention Board - Workplace Health update

Delivery Apr-July

- Evaluation/baseline assessment of each cohort within each organisation

- Delivery of bite-sized training for executive/senior staff– up to 30 people

- Delivery of training for staff across mix of roles/bands– up to 200 people – N.B Split of staff across all bands vital.

- 2 train the trainer coaching and network sessions for wave 1 or wave 2 delegates, numbers tbc

- Provision of ambassador marketing material eg posters/oyster holder/pens

Analysis - July

- Analysis of participants and feedback of first training sessions

- Analysis of participants and feedback of second training sessions

- Mid point evaluation report

- End point evaluation report

Reporting & Presentation - Sept

- Focus Group Report, including suggestions for improvements for future training

- Fortnightly status updates with Project Manager

- Monthly reporting

- Quarterly reporting for HLP Prevention Board

- Regular update of risks and issues register

- Debrief and post-delivery Focus Group

- Final report and evaluation

- Post training celebration event

Annex B

Terms and Conditions for the Supply of Services

Annex C

Financial Submissions

Financial Envelope - The financial envelope available for this work is within the range of £40 – 50,000. Any quotation exceeding the financial envelop will not be considered.

1.1	Providers are required to submit a comprehensive pricing schedule covering all costs involved with satisfying the Customer need, covering (but not restricted to) the following points:

- A full breakdown of staff costs which includes a fixed daily charge (exclusive of VAT) for each individual who is engaged in delivery of this contract. Providers are required to state how many days will be required for each individual as a separate line.

- Clearly outline the use of non-staff including consultants, contractors, sub-contractors, temps involved in the above breakdown

- Detail any other necessary costs which will be required (e.g. marketing, translation, management fee, overheads, cost of providing any materials etc.)

- The price submitted must be the total cost of the delivery of the service

- All charges must be provided in GBP and must be exclusive of VAT.

1.2	The charges must be inclusive of any and all additional charges which may apply. Contracting Authority will not accept any additional costs which are not declared.

1.3	The commercial scoring will be based on the total contract value

1.4	Providers are required to complete and submit the pricing schedule as part of their submission

| Breakdown of all Cost | Cost (£) |
| --- | --- |
| Breakdown of all costs |  |
| Management/co-ordination costs (specify staff role) |  |
| Service Delivery (specify with staff roles) |  |
| Operational Costs |  |
| Venue, Postage, Printing & Stationery, Telephone, Mobile Phones, Hire of equipment, etc. |  |
| If the work is to be broken down into specific sections, cost out each section separately. |  |
| Total |  |

The lowest price (within affordability limits) will be awarded the maximum score for price with other bidders awarded score in proportion to the lowest priced using the following formula:

Score = Lowest Tender Price x 30 (maximum score/mark available ). Other/Higher Tender Price.

All costs must be inclusive of travel and related expenses to the Base location. An estimate of the overall costs for expenses must be submitted to enable comparison of bids on an equal basis.

All prices exclude VAT.

If submitting your proposal as a pdf document, please submit your prices in a separate file.

Haringey CCG is requesting that bidders submit a breakdown of total cost for all the work / services as detailed in the Service Specification.

The lowest price (within affordability limits) will be awarded the maximum score for price with other bidders aggregated against that.  Quotations exceeding the financial will be awarded 0 score and disqualified from the process.

# ANNEX D

Declaration of conflict of interests

(Bidders/Contractors)

Project Name: PRJ 612 Healthy Living Ambassadors Training Wave 2

NHS Haringey CCG Bidders/potential contractors/service providers’ declaration form: financial and other interests

This form is required to be completed in accordance with the CCG’s Constitution, and s140 of the NHS Act 2006 (as amended by the Health and Social Care Act 2012) and the NHS (Procurement, Patient Choice and Competition) (No2) Regulations 2013 and related guidance

Notes:

- All potential bidders/contractors/service providers, including sub-contractors, members of a consortium, advisers or other associated parties (Relevant Organisation) are required to identify any potential conflicts of interest that could arise if the Relevant Organisation were to take part in any procurement process and/or provide services under, or otherwise enter into any contract with, the CCG, or with NHS England in circumstances where the CCG is jointly commissioning the service with, or acting under a delegation from, NHS England.

- Any changes to interests declared either during the procurement process or during the term of any contract subsequently entered into by the Relevant Organisation and the CCG must be notified by completing a new declaration form and submitting it to the CCG.

- Relevant Organisations completing this declaration form must provide sufficient detail of each interest so that the CCG, NHS England and also a member of the public would be able to understand clearly the sort of financial or other interest the person concerned has and the circumstances in which a conflict of interest with the business or running of the CCG or NHS England (including the award of a contract) might arise.

- If in doubt as to whether a conflict of interests could arise, a declaration of the interest should be made.

Interests that must be declared (whether such interests are those of the Relevant Person themselves or of a family member, close friend or other acquaintance of the Relevant Person), include the following:

- the Relevant Organisation or any person employed or engaged by or otherwise connected with a Relevant Organisation (Relevant Person) has provided or is providing services or other work for the CCG or NHS England;

- a Relevant Organisation or Relevant Person is providing services or other work for any other potential bidder in respect of this project or procurement process;

- the Relevant Organisation or any Relevant Person has any other connection with the CCG or NHS England, whether personal or professional, which the public could perceive may impair or otherwise influence the CCG’s or any of its members’ or employees’ judgements, decisions or actions.

Declarations:

| Name of Relevant Organisation: |  |
| --- | --- |
| Interests |  |
| Type of Interest | Details |
| Provision of services or other work for the CCG or NHS England |  |
| Provision of services or other work for any other potential bidder in respect of this project or procurement process |  |
| Any other connection with the CCG or NHS England, whether personal or professional, which the public could perceive may impair or otherwise influence the CCG’s or any of its members’ or employees’ judgements, decisions or actions |  |

| Name of Relevant Person | [complete for all Relevant Persons] |  |
| --- | --- | --- |
| Interests |  |  |
| Type of Interest | Details | Personal interest or that of a family member, close friend or other acquaintance? |
| Provision of services or other work for the CCG or NHS England |  |  |
| Provision of services or other work for any other potential bidder in respect of this project or procurement process |  |  |
| Any other connection with the CCG or NHS England, whether personal or professional, which the public could perceive may impair or otherwise influence the CCG’s or any of its members’ or employees’ judgements, decisions or actions |  |  |

Form Completion

| I declare that to the best of my knowledge and belief, the above information is complete and correct. I undertake to update as necessary the information. I understand that the information will be used in the evaluation process to assess my organisation’s suitability to be included in the tender evaluation process, and that giving false information may result in my organisation being disqualified from the process, at this or whatever stage it becomes known to the Commissioners. |  |
| --- | --- |
| Signed: |  |
| Name: |  |
| Position: |  |
| Bidder: |  |
| Date: |  |