|  |  |  |  |
| --- | --- | --- | --- |
| WEEK | Activity | Expected Duration | Comment |
| Week-1 - 0 | Mobilisation | 1 week | REDACTED |
| Week 1 (assume 26th October 2020) | Prepare PEP in draft | 2 weeks | REDACTED |
| Kick-off meeting | 1 day | REDACTED |
| Orientation of core team | 1 day | REDACTED |
| Review existing site information | 1 week | REDACTED |
| Week 2 | Site visits and information gatheringEstablish the Multi-criteria decision analysis to support site selection | 2 weeks | REDACTED |
| Week 3 | Report back possible locations | 1 day | REDACTED |
| Week 3 | Prepare massing / sketches | 3 weeks | REDACTED |
| Week 4 | Design work continues |   | REDACTED |
| Week 5 | Commencement of cost estimates | 1 week | REDACTED |
| Week 6 (week commencing 7th December 2020) Week 6 | Present site options with construction cost estimates applied | 1 day | REDACTED |

**Deliverables – Redacted version**

|  |  |  |  |
| --- | --- | --- | --- |
|  |   |   |  |
|   | Arcadis to price second | Target 1 week |  |
|   | phase |   | REDACTED |