## Meeting Schedule
Project PETREL Meeting Schedule |  |  |  |  | Schedule 5 to Contract No: SSP/00192
Title | Frequency/location | Date | Chair | Required Attendees |  | Terms of Reference
Start Up Meeting | One-Off/ MoD Abbey Wood | Within 1 wk of Contract Award | PETREL Project Manager | PETREL Technical Manager PETREL Commercial Manager PETREL Requirements Manager PETREL Quality Manager PETREL Risk Manager PETREL Safety Manager PETREL Support Manager PETREL Project Controller Contractor Project Manager Contractor Technical Manager Contractor Commercial Manager Contractor Requirements Manager Contractor Quality Manager Contractor Risk Manager Contractor Safety Manager Contractor Support Manager |  | To agree terms of engagement post contract award.
Progress Reviews | Monthly/ UK venue to be agreed with the Authority | TBC | PETREL Project Manager | PETREL Technical Manager PETREL Commercial Manager PETREL Requirements Manager PETREL Quality Manager PETREL Risk Manager PETREL Safety Manager PETREL Support Manager PETREL Project Controller Contractor Project Manager Contractor Technical Manager Contractor Commercial Manager Contractor Requirements Manager Contractor Quality Manager Contractor Risk Manager Contractor Safety Manager Contractor Support Manager |  | The Objective of the Progress Review is to review project performance through assessment of production status, project schedule, risk, safety, quality and technical issues
Quality Management Review | Monthly/MoD Abbey Wood or Contractors Premises as required | TBC | PETREL Quality Manager | PETREL Quality Manager Contractor Quality Manager |  | Quality Performace Review
Safety Panel Part 2 Mtg | One-Off/ MoD Abbey Wood | TBC | PETREL Project Manager | DCC Programme Leader Survivability Team Leader PETREL Safety Manager PETREL Project Manager MOD Stakeholders as required Contractor Project Manager Contractor Technical Manager Contractor Safety Manager |  | Review the Final Safety Case Part 2 and associated documentation (Hazard log)
Interim Design Acceptance (IDA) | MoD Abbey Wood | TBC | PETREL Project Manager | PETREL Technical Manager PETREL Commercial Manager PETREL Requirements Manager PETREL Quality Manager PETREL Risk Manager PETREL Safety Manager PETREL Support Manager PETREL Project Controller Contractor Project Manager Contractor Technical Manager Contractor Commercial Manager Contractor Requirements Manager Contractor Quality Manager Contractor Risk Manager Contractor Safety Manager Contractor Support Manager |  | Interim Design Acceptance
Final Design Acceptance (FDA) | MoD Abbey Wood | TBC | PETREL Project Manager | PETREL Technical Manager PETREL Commercial Manager PETREL Requirements Manager PETREL Quality Manager PETREL Risk Manager PETREL Safety Manager PETREL Support Manager PETREL Project Controller Contractor Project Manager Contractor Technical Manager Contractor Commercial Manager Contractor Requirements Manager Contractor Quality Manager Contractor Risk Manager Contractor Safety Manager Contractor Support Manager |  | Final Design Acceptance
PM Support Meetings | Quarterly from Delivery of Tranche 1 / UK Venue to be agreed with the Authority | TBC | PETREL Support Manager | PETREL Project Manager PETREL Commercial Manager PETREK Requirements Manager PETREK Quality Manager Contractor Project Manager Contractor Commercial Manager Contractor Requirements Manager Contractor Support Manager |  | To deliver the PETREL Support Solution