## Sheet1
Highways Agency Confirmation of Task Order Redactions made under FOIA 2000 exemptions sec 40: personal info and sec 43: commercial.
Supplier: | AECOM | Fee Request for this CTO |  | 25050.92
Project Title: | A120 Braintree to Marks Tey Corridor Feasibility Study - Option Generation & Sifting
Contract Ref. | Redacted | CPA No.: | Redacted | BPA No.: | Redacted
PIN Description: | Redacted | Sub Pin: | Redacted | PIN No.: | Redacted
HA Reference: | EE 92 15/16AECOM | Start and End Date : |  | 30/09/2015 - 15/01/2016
Task Overview and Expected Outcomes
Option generation for the challenges listed in the initial List of Challenges; Initial sifting using the Early Assessment Sifting Tool (EAST); Attend sifting workshop with Client and key stakeholder(s); Document findings of workshop; Produce initial Option Assessment Report (OAR); Identify better performing options and confirm shortlist with Client.
Task Objectives and Milestones
• A ‘long list’ and a ‘short list’ of Options; • Drawings illustrating the Options considered; • Hosting and attendance at an Option Sifting Workshop; • An Option Assessment Report.
Expected Project Outcomes
To identify and sift Options for the improvement of the corridor.
Project Risk and Management
The timescales for the data collection and analysis are dependent upon the availability of data collection specialists. Current indications are that they could deploy quickly, however, this could change and has the potential to affect the programme.
HA Project Sponsor | Sign: |  | Print Name: |  | Date:
Management Approver: | Sign: |  | Print Name: |  | Date:
Contractual Approval: | Sign: |  | Print Name: |  | Date: