STATEMENT OF SERVICE REQUIREMENT FOR THE PROVISION OF TECHNICAL SUPPORT ON EXTERNAL HAZARDS ASSESSMENT OF THE HINKLEY POINT C (HPC) SAFETY DOCUMENTATION TO SUPPORT PERMISSIONING OF CONSTRUCTION ACTIVITIES – STAGE 4

1	BACKGROUND TO THE PROJECT

1.1	The overall external hazards assessment of the Hinkley Point C (HPC) safety documentation to support permissioning of construction activities is covered by an assessment plan [1] covering the period from the First Nuclear Safety Concrete (FNSC) to Nuclear Island Concrete (NIC) permissioning points, itself based on an earlier scope of work [2]. This scope splits the work in to four stages, of which Stages 1, 2 and 3 are now complete [3], [4], [5]. This scope of work covers Stage 4 and provides additional information relevant to Stage 4. The intent at this stage is to tender only for Task T1, A tender for tasks T2 & T3 will be sought subsequently, on the basis of information developed in T1.

1.2	The permissioning date for Nuclear Island Concrete (NIC) has been defined and this has driven out the delivery dates for ONR’s assessment work to support permissioning decisions; these are in the Table below. ONR has decided that because of the quantity of construction work between the FNSC and NIC permissioning points, an additional permissioning point, called Pumping Station (PS), will be implemented; this is also included in the table below. The safety submission to be provided by NNB GenCo to support their request to proceed beyond these permissioning points consists of:

- PS: Pre-Construction Safety Report 3 (PCSR3) + Secondary Hold Point Report (SHPR),

- NIC: PCSR3 + Nuclear Island Report (NICR).

1.3	Stage 4 work is therefore sub-divided into Stage 4a and 4b to reflect this.

1.4	PCSR3 is currently at Freeze 3 [6] and includes chapters that were submitted as supporting documents for the FNSC permissioning point that were assessed at Stage 3.There are many supporting documents that are relevant to Stage 4 work, see Table 1. PCSR3 replaces PCSR2012 [7] and is now to be considered as the overall safety case for HPC construction.

1.5	Consideration of seismic hazard will not form part of this work, even though it formed a significant part of Stages 1-3 work. Consideration of seismic hazard issues has progressed to the point where it is now better placed in the Civil Engineering workstream. However, Task T1 recognises that ABSC are well placed to provide support to this workstream in an advisory capacity on these issues, and an allowance for this should be made in the tender.

1.6	The table below gives dates for important relevant reports and permissions, and planned dates known at this time for future reports and permissions. This indicates the overall timeline of the project.

| ONR Sampling rationale |  |  | Stage 1 |
| --- | --- | --- | --- |
|  | ABSC Deliverable [3] | 23/5/14 |  |
| First Non-Permissioning Convergence Point |  |  | Stage 2 |
|  | ONR Assessment Report [8] | Mar. 2014 |  |
|  | ABSC Deliverable [4] | 5/6/15 |  |
| First Nuclear Safety Concrete |  |  | Stage 3 |
|  | ONR Assessment Reports [9] | Oct. 2016 |  |
|  | ABSC Deliverable [5] | 2/12/16 |  |
|  | ONR Assessment Reports – Addendum [10] | 10/2/17 |  |
|  | CONSENT granted for FNSC | 6/3/17 |  |
| Pumping Station |  |  | Stage 4a |
|  | PCSR 3 Freeze 3 | Dec. 2016 |  |
|  | ONR Assessment Report PCSR 3 - DRAFT | 31/5/17 |  |
|  | SHPR | 31/5/17 |  |
|  | PCSR 3 FINAL | 31/7/17 |  |
|  | TSC Deliverable 1 | 15/7/17 |  |
|  | ONR Assessment Report PCSR 3 - FINAL | 31/8/17 |  |
|  | ONR Assessment Report PS - DRAFT | 30/9/17 |  |
|  | TSC Deliverable 2 | 30/11/17 |  |
|  | AGREEMENT granted for PS | Nov. 17 |  |
|  | ONR Assessment Report PS - FINAL | 20/12/17 |  |
| Nuclear Island Concrete |  |  | Stage 4b |
|  | NICR | 31/5/18 |  |
|  | TSC Deliverable 3 | 31/5/18 |  |
|  | ONR Assessment Report | 30/6/18 |  |
|  | CONSENT granted for NIC | Nov. 18 |  |

Table 1: Scope and delivery dates for ONR assessment of HPC Pumping Station and Nuclear Island Concrete Permissioning Hold Points

- SCOPE OF THE SERVICES REQUIRED

2.1	An initial list of documents upon which to scope the Stage 4 work is captured in Table 2. The work involves assessing the relevant parts of PCSR 3, SHPR and NICR and related documents listed in Table 2. Tables 3 and 4 provide details of other reports that have been available to ONR. These tables are for information purposes only.

2.2	Substantial work has already been completed at Stage 2 and 3 on assessing HPC PCSR2012 and relevant parts of PCSR 3. A list of outstanding findings, recommendations etc., arising out of Stage 3 assessment work but requiring resolution in Stage 4 has been prepared [11]; this list has been passed to NNB GenCo for their comment in respect of issues that remain open/closed, or need further work by them. Most of these issues arose out of earlier TSC work [5]. You should consider this in forming a judgement of remaining work to be undertaken in task T1.

2.3	You should familiarise yourself with this work because Stage 4 work is intended to build on previous work. In particular, there are a number of outstanding actions captured in the ABSC Stage 3 report [5] that will need resolving for Stage 4.

2.4	Given that external hazards analysis and safety case supporting technical work occurs early in the new build construction process, the intent at this late stage is to sample in to the submitted documentation to:

a) identify any gaps/additional relevant material since the previous submission for FNSC,

b) close down the outstanding issues arising from earlier work as efficiently as possible and

c) sift all this in light of its nuclear safety significance and determine a sampling approach that focusses on issues of significance.

2.5	The scope covers the entirety of Stage 4 work, but initially, a limit of liability price is sought only for Task T1, on the basis that T2 and T3 will depend on the information provided by T1.

## 3	OBJECTIVES

3.1	You are requested to provide a proposal for suitably qualified and experienced persons (SQEPs) to undertake the assessment work as described above for Stage 4 according to the scope of work defined above by:

- Assessment of the HPC safety case submissions and additional documentation described herein, from an external hazards perspective.

- Where technical inadequacies are identified, to provide recommendations for further work by NNB GenCo.

## 3.2	Tasks

T1	Preliminary work to consolidate Stage 3 work in to a set of sub-tasks under T2 and T3. The objective is to establish, in consultation with the Project Officer, the work needed to efficiently close out the issues identified in [11] and identify additional assessment work on any relevant new material presented since the submission for FNSC, based on a strategy of sampling according to potential nuclear safety significance. Deliverable D1.

In addition, provide advice on seismic hazard issues relevant to HPC for the duration of Stage 4 work.

Deliverables

D1	Short note and commentary on Ref. [11] identifying assessment remaining work, and list of sub-tasks under T2 and T3.

T2	Stage 4a: Assess the HPC submission and additional documentation in light of the findings and recommendations made in the ONR Assessment Report for FNSC [9] and supporting ABSC deliverable report [5]. Interface with other team members, other ONR specialists and EDF-NNB staff as required. Deliverables D1 & D2.

Provide support to the Project Officer to interface with the rest of the external hazards team and to assist in face-to-face meetings with the Licensee. Assume:

- Three (3) 1-day meeting with NNB GenCo at their Bristol HQ.

- Three (3) 1-day meetings with other ONR inspectors and team members at ONR Redgrave Court, Bootle

Deliverables

D2	Report of work undertaken at Stage 4a to support the Project Officer in preparing the ONR Assessment Report PCSR 3 - FINAL.

D3	Report of work undertaken at Stage 4a to support the Project Officer in preparing the ONR Assessment Report PS - FINAL.

T3	Stage 4b: Assess the HPC submission and additional documentation in light of the findings and recommendations made in the ONR Assessment and ABSC deliverable reports for FNSC, taking account of progress made on NIC issues during Stage 4a. Interface with other team members, other ONR specialists and NNB GenCo staff as required. Deliverable D3.

Provide support to the Project Officer to interface with the rest of the external hazards team and to assist in face-to-face meetings with the Licensee. Assume:

- Three (3) 1-day meeting with NNB GenCo at their Bristol HQ.

- Three (3) 1-day meetings with other ONR inspectors and team members at ONR Redgrave Court, Bootle

Deliverables

D4	Report of work undertaken at Stage 4b to support the Project Officer in preparing the ONR Assessment Report NIC - FINAL.

- CONSTRAINTS

4.1	Tasks and deliverables to be completed by the dates below:

- Deliverable D1 – As soon as practicable following contract initiation – by discussion with the Project Officer.

- Deliverable D2 – 15/7/17

- Deliverable D3 – 30/11/17

- Deliverable D4 – 31/5/18

## 4.2		Conflicts of Interest

Any conflicts of interest to be advised by completion and submission of the Potential Conflicts of Interest Declaration Form, attached at Schedule C.

## 5	SUBMISSION OF TENDERS

5.1	To submit a compliant proposal in response to this specification Bidders must:

- Clearly address all aspects of the specification (including objectives, scope and constraints);

- Provide details of the project team members, including grades and rates and short curriculum vitae (CV) summarising relevant experience;

- Explain how the aims and scope of the work are to be addressed, and the proposed approach. This should include:

- Identification of the required tasks with the number of days required for each task and timescales, including details of who will undertake each of the tasks; and

- Experience of the project team relevant to each of the tasks. This should include a brief description of examples of the work undertaken by the individual that provides evidence of adequate experience to undertake the assigned task.

- Identify the anticipated engagement with ONR, including any progress meetings;

- Include a project plan and timetable covering each of the proposed tasks;

- Provide a detailed breakdown of all proposed costs associated with this work;

- Provide a schedule of invoices and forecast of invoice values.

6	CONTRACT MANAGEMENT

6.1	ONR will require to be kept updated about progress and delivery of the required work via monthly meetings, by telephone, and a contract start-up meeting at ONR’s offices at Bootle. Subsequent progress meeting should be arranged with the ONR Project Office and can be held at ONR’s office in Bootle, or the contractor’s premises.

7	REFERENCES

| [1] | ONR, Hinkley Point C – Topic Stream B7 – External Hazards – Assessment Plan up to Nuclear Island Concrete, Rev. 0, March 2017 (TRIM ref: 2017/156160). |
| --- | --- |
| [2] | ONR, Scope of Work – External Hazards Assessment of Hinkley Point C Safety Documentation, Rev. 1, June 2015 (TRIM ref: 2015/218367) |
| [3] | ABS Consulting, Screening of Supporting Documents for Review of External Hazard Withstand Claimed in the Hinkley Point C Pre-Construction Safety Report 2012, Report 3163927-R-01 Issue 1, May 2014 (TRIM ref: 2014/262789). |
| [4] | ABS Consulting, External Hazards Assessment of Hinkley Point C Safety Documentation, Report 3163927-R-02 Issue 1, June 2015 (TRIM ref: 2015/252507). |
| [5] | ABS Consulting, External Hazards Assessment of Construction Safety Justification Documentation for the Technical Galleries at Hinkley Point C, Report 3163927-R-04 Issue 1, December 2016 (TRIM ref: 2016/474669) |
| [6] | NNB GenCo, Hinkley Point C PCSR3 Freeze 3, September 2015 (TRIM ref: 2015/335499) |
| [7] | NNB GenCo, Hinkley Point C PCSR2012, December 2012 (TRIM ref: 2013/23292) |
| [8] | ONR Assessment Report, First Project Convergence Point at Hinkley Point C - Progress Report for Work Stream B7 External Hazards, ONR-CNRP-PR-14-039 Rev. 0, December 2014 (TRIM ref: 2014/423694) |
| [9] | ONR Assessment Report, NNB GenCo – External Hazards Assessment of CSJ-01, ONR-NR-AR-002 Rev. 0, October 2016 (TRIM ref: 2016/105827) |
| [10] | ONR Assessment Report, External Hazards Assessment to Inform Consent to Commence Construction of Hinkley Point C – Addendum Report, ONR-NR-AR-16-066 Rev. 0, February 2017 (TRIM ref: 2016/468599) |
| [11] | NNB GenCo, ONR Workstream B7 Items Register_ NNB Response 04.05.17, May 2017 (TRIM ref: 2017/180719) |

Table 2 – Document Selection for Assessment at Stage 4

| TITLE | DOCUMENT NUMBER | REVISION NUMBER AND DATE | TRIM REF |
| --- | --- | --- | --- |
| HPC PCSR3: Chapter 2 – Site Characteristics and Layout, Sub-Chapter 2.1 – Site Description And Data | HPC-NNBOSL-U0-000-RES-000086 | Version 4 15/12/2016 | 2016/500497 |
| PCSR3: Chapter 2 – Site Characteristics and Layout, Sub-Chapter 2.2 – Plot Plan | HPC-NNBOSL-U0-000-RES-000087 | Version 2 04/11/2016 | 2016/465114 |
| HPC PCSR3: Chapter 13 – Hazards Protection, Sub-Chapter 13.1 – External Hazards Protection | HPC-NNBOSL-U0-000-RES-000205 | Version 2 21/12/2016 | 2016/503284 |
| HPC PCSR3: Chapter 13 – Hazards Protection, Sub-Chapter 13.3 – Basic Design Hazard Protection Schedule | HPC-NNBOSL-U0-000-RES-000206 | Version 2 11/11/2016 | 2016/495168 |
| Support for Answering ONR/HSL Questions on Rainfall, Air Temperature and Sea Temperature | HPC-EDFRAD-XX-000-PAP-100003 | Revision 1.0 22/09/2016 | 2016/479229 |
| Response to Queries Raised in Review of the HPC Accidental Aircraft Crash Assessment | NNB GenCo letter ONR-HPC-20828N | Version 1.0 22/06/2016 | 2016/253768 |
| Request for Closure of Issue 2060: Licensee’s Philosophy for Treatment of Beyond Design Basis External Hazards | ONR-NR-HPC-20793N | Version 1.0 17/08/2016 | 2016/327928 |
| Pumping Station Secondary Hold Point Report | HPC-NNBOSL-U1-HPA-REP-100000 | Revision A | TBC – awaiting submission |
| Synthesis on the Risk of Frazil Ice Formation at Hinkley Point C, | UKX-SEPTEN-XX-ALL-NOT-200097 | Revision A | TBC – awaiting submission |
| Verification of the adequacy between HPC heat sink safety and operating cases and sea levels' return periods | HPC-CNEPEX-U0-HP7-NOT-200041 | Revision C | TBC – awaiting submission |
| Application of the Joint Probability Method to the HPC Case Study for the Estimation of Low Sea Level | HPC-ETGCXX-U9-ALL-REP-000323 | Revision B | TBC – awaiting submission |
| Hinkley Point: definition of the Extreme Low Water Level to be considered | ENITSF100006 | Revision D | TBC – awaiting submission |
| Synthesis report for functional & operational requirements and mitigation means for relevant low flow conditions | HPC-CNEPEX-U0-HP7-NOT-200177 | Revision C | TBC – awaiting submission (Rev B - 2016/222532) |
| Justification of hazards taken in consideration for pumping station BDHPS | HPC-ETSEEX-AU-HPX-NOT-001209 | Revision B | 2016/457986 |
| Basic Design Hazard Protection Schedule & FSA - External flooding - Pumping station | HPC-ETSIMX-AU-HPX-NOT-001210, or, HPC-ETSEEX-AU-HPX-NOT-001210 | Revision A | TBC – awaiting submission |
| Functional Safety analysis supporting the basic design hazard protection schedule related to the extreme air temperature in HP | HPC-CNEPEX-AU-HP7-STR-200553 | Revision A | TBC – awaiting submission |
| Functional Safety Analysis supporting the Basic Design Hazard Protection Schedule to the hazard fauna, Flora and Anthropogenic Clogging | HPC-ETFCTX-AU-ALL-NOT-000026 | Revision A | TBC – awaiting submission |
| Functional Safety Analysis supporting the Basic Design Hazard Protection Schedule to the hazard Extreme Low Water Level (ELWL) Marine Works and Pumping Station (HP) | HPC-ETFCTX-AU-HPX-NOT-001238 | Revision A | TBC – awaiting submission |
| Functional Safety Analysis supporting the Basic Design Hazard Protection Schedule to the hazard hydrocarbons | HPC-ETFCTX-AU-HPX-NOT-001239 | Revision A | TBC – awaiting submission |
| Functional Safety Analysis supporting the Basic Design Hazard Protection Schedule to the hazard silting | HPC-ETFCTX-AU-HPX-NOT-001241 | Revision A | TBC – awaiting submission |
| Basic Design Hazard Protection Schedule & FSA - APC and induced shock event - Heat Sink | HPC-ETGCXX-AU-HPX-NOT-001224 | Revision A | TBC – awaiting submission |
| Basic Design Hazard Protection Schedule & FSA - Extreme climatic conditions (tornado, snow and wind, wind generated missiles) – Pumping station | HPC-ETGCXX-AU-HPX-NOT-001225 | Revision A | TBC – awaiting submission |
| Synthesis note for the hazard silting | HPC-CNEPEX-U1-ALL-NOT-201398 | Revision A | TBC – awaiting submission |
| Credibility of the More Onerous Clogging Event for the CFI drum Screens | HPC-CNEPEX-U9-CFI-NOT-201334 | Revision A | TBC – awaiting submission |
| Nuclear Island Basic Design Hazard Protection Schedule: Extreme Climatic Conditions | UKX-ECESNX-XX-ALL-NOT-001252 | Revision A | TBC – awaiting submission |
| Nuclear Island Concrete Hold Point Report | Document assumed by ONR based on similar deliverables for previous hold points | - | - |
| Justification of hazards taken in consideration for Nuclear Island | Document assumed by ONR based on similar deliverables for previous hold points | - | - |
| Nuclear Island Basic Design Hazard Protection Schedule: External Flooding | HPC-ECESNX-XX-ALL-NOT-001237 | Revision A | TBC – awaiting submission |
| UK - Beyond Design Methodologies for External hazards excluding earthquake | UKX-CNENXX-XX-000-TQY-200436 | Revision A | TBC – awaiting submission |
| UK EPR - Beyond Design Basis External Hazards - Doctrine | UKX-SEPTEN-AU-ALL-STU-200205 | Revision B | TBC – awaiting submission |
| NNB Letter: Response to finding 9 of ONR workstream B7 – external hazards – CSJ-01 assessment report | NNB-209-RIO-001455 | Version 1.0 22/02/2017 | 2017/76491 |
| NNB Letter: Response to ONR Issues on HPC Construction Safety Justification CSJ-01 | NNB-209-RIO-001351 ONR-HPC-20882N | Version 2.0 06/12/2016 | 2016/477755 |

Table 3 – Documents made available to ONR and listed for information

| TITLE | DOCUMENT NUMBER | REVISION NUMBER AND DATE | TRIM REF |
| --- | --- | --- | --- |
| HPC PCSR3: Chapter 13 – Hazards Protection, Sub-Chapter 13.2 – Internal Hazards Protection | HPC-NNBOSL-U0-000-RES-000141 | Version 2.0 08/11/2016 | 2016/495167 |
| HPC PCSR3: CHAPTER 23 – Response to Fukushima, Sub-Chapter 23.0 – Safety Approach for UK EPR (HPC Safety Requirements) | HPC-NNBOSL-U0-000-RES- 000222 | Version 2.0 26/10/2016 | 2016/465109 |
| HPC PCSR3: CHAPTER 23 – Response to Fukushima Foreword | HPC-NNBOSL-U0-000-RES- 000165 | Version 2.0 31/10/2016 | 2016/465115 |
| HPC PCSR3: Chapter 23 – Response to Fukushima Sub-Chapter 23.1 – Fukushima Safety Features and Design Enhancements | HPC-NNBOSL-U0-000-RES-000223 | Version 1.0 01/11/2016 | 2016/465110 |
| HPC PCSR3: Chapter 23 – Response to Fukushima, Sub-Chapter 23.2 – SEG System Description | HPC-NNBOSL-U0-000-RES-000225 | Version 1.0 15/11/2016 | 2016/475290 |
| PCSR3: Chapter 23 – Response to Fukushima, Sub-Chapter 23.3 – Safety Assessment | HPC-NNBOSL-U0-000-RES-000224 | Version 2.0 15/11/2016 | 2016/465111 |
| PCSR3: Chapter 23 – Response to Fukushima Sub-Chapter 23.4 – Enhancements to the Emergency Arrangements following Fukushima | HPC-NNBOSL-U0-000-RES-000226 | Version 2.0 01/11/2016 | 2016/465113 |
| CC023 interim closure | Email from S. Turner to P. Ford | - | 2016/470921 |
| Email - Ryan Atkins to P. Ford, FW: Updated External Hazards Engagement Plan | Email | - | 2017/95393 |
| List of Engagement References_v4 | List of references relevant to PCSR3 supplied by NNB GenCo to ONR | - | 2017/95565 |
| Email from S. Turner to P. Ford, FW: Draft MED for pumping station | Email | - | 2017/95630 |
| Synthesis note of set-back-wall studies | HPC-ETGCXX-AU-000-NOT-001213 | Revision A | TBC – awaiting submission |
| Hinkley Point C Sea Protection - Final Study Report | HPC-GEN410-U0-SWP-RET-000007 | Revision B 14/08/2015 | 2015/394972 |
| Email from R. Atkins to P. Ford, RE: Documentation regarding the coastal flooding hazard at HPC and the removal of the set back wall | Email | - | Hardcopy only |
| Email from T. McNulty to P. Ford et al., HPC Site Layout Plan | Email | - | Hardcopy only |
| Functional Safety Analysis supporting the Basic Design Hazard Protection Schedule to the hazard frazil/icing | HPC-ETFCTX-AU-HPX-NOT-001240 | Revision A | TBC – awaiting submission |
| HPC Intake and Outfall Heads ALARP and BAT Review | HPC-NNBOSL-U9-HPT-RET-100000 | Version 1 15/06/2015 | 2015/379745 Email attachment |
| UK EPR – Identification of Systems to be Considered in the Hazard Studies and Consequences When Lost – CI-BOP Scope, Revision A | HPC-ETSEEX-AU-ALL-NOT-000047 | Revision A 18/12/2014 | 2015/234423 |
| Basic Design Hazard Protection Schedule & FSA - Internal flooding, HELB and Surge event in the forebay (Swell) - Pumping Station and Forebay, Revision B | HPC-ETSIMX-AU-HPX-NOT-001238 | Revision B 03/11/2015 | 2016/100972 |
| Functional analysis for safety and process requirements of HPL galleries, Revision A | HPC-CNEPEX-U9-HPL-NOT-200487 | Revision A 14/04/2016 | 2016/356631 |
| Guideline for verification of the water supply of ESWS and UCWS EPR pumps | UKX-SEPTEN-AU-ALL-STU-000599 | Revision B | TBC – awaiting submission |
| Basic Design Hazard Protection Schedule & FSA – Aircraft Impact – Nuclear Island | Document assumed by ONR based on similar deliverables for previous hold points | - | - |
| Guidance for the development of Hazard Protection Schedules at the Basic Design stage of HPC Project | HPC-ECESNX-XX-ALL-NOT-000268 | Revision A 09/09/2014 | 2016/375828 |
| Assessment of Hazard Building pairs to be addressed through a Basic Design Hazard Protection Schedule on CNEN scope | HPC-CNENX-XX-AU-ALL-NOT-201375 | Revision A 20/10/2016 | 2016/457990 |
| Application of Basic Design Hazard Protection Schedule Guidance to NNB Scope Buildings | HPC-NNBOSL-U0-ALL-REP-000001 | Version 1.0 28/08/2015 | 2016/471611 |
| Hazard Protection Schedule for HHE, HUC, HBX (and HBP) | HPC-GEN371-U0-ALL-RES-100000 | Version 1.1 07/08/2015 | 2016/384647 |
| Basic Design Hazard Protection Schedule & CFSA – extreme climatic conditions (extreme wind, tornado) – HOR | HPC-CNEPEX-U9-HOR-NOT-200525 | Revision A | TBC – awaiting submission |
| EPR UK - HPC - Design Quality Plan related to Basic Design Hazard Protection Schedule (BDHPS) activities performed by SNE/AGS on CNEN scope | HPC-ECESNX-AU-ALL-NOT-000265 | Revision D 22/06/2016 | 2016/335367 |
| Resolution Plan for [AF-UKEPR-CE-057] | UKX-ECEIGX-XX-ALL-REP-001227 | Revision A 15/12/2016 | 2017/118394 |
| EPR UK - HPC - Design Quality Plan related to hazard studies performed by CNEPE for CI&BOP scope | HPC-CNEPEX-AU-ALL-NOT-200112 | Revision C 30/06/2016 | 2017/118397 |
| HPC project – Design Quality Plan for External Hazards | HPC-ECEIGX-XX-ALL-NOT-000511 | Revision C 15/09/2016 | 2017/118399 |
| Aircraft impact risk frequencies considered for LOOP, LUHS and PSA level 3 releases. | UKX-SEPTEN-AU-ALL-NOT-200310 | Revision B | TBC – awaiting submission |
| Nuclear Island Basic Design Hazard Protection Schedule: External Explosion | UKX-ECESNX-XX-ALL-NOT-001253 | Revision A | TBC – awaiting submission |
| Combined & Consequential Hazards | UKX-SEPTEN-AU-ALL-NOT-200265 | Revision A | TBC – awaiting submission |
| HPC - Unit 1 and Unit 2 - Identification of potential lightning strikes on NI buildings | HPC-CNENXX-AU-ALL-NOT-201339 | Revision A | TBC – awaiting submission |
| AF-CC-23.04 – BDHPS for NI raft consent - Batch 4 - Lightning and EMI | HPC-ECESNX-XX-ALL-NOT-001239 | Revision A | TBC – awaiting submission |
| AF-CC-23.04 – BDHPS for NI raft consent - Batch 4 - External Missiles | HPC-CNENXX-XX-ALL-NOT-201669 | Revision A | TBC – awaiting submission |

Table 4 – Documents forming part of the Seismic Assessment, which now sits within the Civil Engineering workstream B6

| TITLE | DOCUMENT NUMBER | REVISION NUMBER AND DATE | TRIM REF |
| --- | --- | --- | --- |
| Nuclear Island Basic Hazard Protection Schedule: Earthquake, | UKX-CNENXX-XX-ALL-NOT-001249 | Revision A 29/02/2016 | 2016/231155 |
| E-mail to R Atkins, HPC early feedback on PSHA and certain other seismic issues | Email | - | 2016/209027 |
| HPC Seismic Design Basis Document | HPC-NNBOSL-XX-000-REP-100246 | Version 1.0 21/10/2016 | 2016/467772 |
| HPC Interim Beyond Design Basis Seismic Justification For Systems and Components | HPC-3RDREG-U0-000-ANA-100000 | Version 1.0 27/09/16 | 2016/467777 |
| Basic Design Hazard Protection Schedule & FSA - Earthquake and seismic event - Pumping station | HPC-ETGCXX-AU-HPX-NOT-001223 | Revision B | TBC – awaiting submission |
| Basic Design Hazard Protection Schedule & CFSA – Earthquake and induced effects – HCA | HPC-CNEPEX-AU-HCA-NOT-200363 | Revision A 27/04/2016 | 2016/457991 |
| UK EPR – Hinkley Point: liquefaction and earthquake induced settlements | HPC-EDTGGX-XX-000-RET-000529 | Revision A 29/11/2013 | 2016/467786 |

Reference should be made to [1] for details of the overall assessment project scope for the HPC project, ONR’s method of engagement with it, and background explanation.