## Front Cover
Specification of Works:
External Repair and Refurbishment Works
At:
25 Market Place, Southwold, IP18 6ED
On behalf of:
Southwold Town Council
Ref:
2108021
Version:
B
Date:
2nd November 2022
Prepared by
North & Hawkins Ltd
15 Chestnut Drive
Wymondham
NR18 9SB
Tel: 01603 397055
www.northandhawkins.co.uk

## Preliminaries
1 | SECTION 1 – PRELIMINARIES/GENERAL CONDITIONS | Cost (£)
1.01 | Contract Parties
1.02 | Employer:
Southwold Town Council
1.03 | Contractor:
TBC
1.04 | Contractual Matters
i. It is intended that these preparatory works will be contracted by way of a JCT Minor Works with Contractor Design 2016. All Contract Terms apply.
ii. Base Date: Not applicable
iii. CDM Planning Period: 2 weeks
iv. Date for Commencement / Completion of Works:
Commencement: Spring 2023.
Completion: within 6 weeks of commencement.
v. Liquidated Damages: £100 per week
vi. Rectification Period: 6 months
vii. Retention Percentages: 95% interim Valuations, 97.5% after Practical Completion.
viii. Adjudication clauses apply. Arbitration clauses do not apply
ix. Insurances: Clause 5.4C applies - Employer arranges composite cover for the Works and for the existing structures. The Contractor shall maintain a Contractors All Risk Policy of not less than £1,000,000. The Contractor must provide evidence of suitable current Contractors All Risks, Public Liability and Employer’s Liability insurance cover to a minimum level of £5 million. The Employer will insure the building.
x. Contractors Design Portion:
1.Leadwork detailing to Lead Sheet Association design guide.
In respect of performance specified items, it is the contractor’s duty to check the integrity of the item advised in contract documents or notify the CA where this is not checked.
1.05 | Restrictions and Requirements
- No smoking will be permitted within any part of the building.
- No burning will be permitted on site.
- No trespass of workmen, plant or materials onto or over adjoining owner’s property.
- The Contractor will be responsible for security of the building and all fixed or unfixed contents during the contract period.
- The Contractor will be responsible for the stability of the building at all times - provide all necessary temporary works and supports.
- The Contractor will be responsible for safe isolation, protection and termination of all mechanical & electrical services prior, during and after the works.
- No noisy work is to be undertaken outside normal working hours.
The site must be kept clean and tidy at all times. Do not allow rubbish, dirt or debris to spread off site.
At the end of the contract the buildings and grounds must be left in ‘as found’ condition. Clear away all equipment, rubbish & debris.
Comply with all relevant road traffic and parking legislation at all times.
All work to gas services must be undertaken by a qualified Gas Safe Register registered fitter. The Contractor will be responsible for the provision of safe access equipment.
All electrical works to be completed by a register NICEIC electrician. All necessary certification to be provided on completion of the Works.
1.06 | Health & Safety
The relevant sections of the CDM Regulations 2015 apply. The project will not be notifiable. Submit method statements and risk assessments at pre-start meeting stage.
The Contractor must take all due precautions when drilling or opening up previously enclosed areas.
Asbestos - An asbestos survey has been commissioned and will be provided to the contractor. For pricing the specification, assume no asbestos is present.
All normal Health & Safety practices must be applied and enforced, including (but not limited to):
Personal Protective Equipment
Working at heights
Isolation of services
Preventing falls
Preventing objects dropping from height
Working in enclosed areas
Control of dust
Control of noise
Vibration injuries
Manoeuvring vehicles and plant
Lifting & carrying heavy items
Structural Collapse
Hygiene & disease control
Fire Prevention
Social Distancing
COVID-19
COSSH Regulations
The Contractor must take due regard to other occupiers in the adjacent buildings and providing adequate warning and protection from the works at all times.
The Contractor is required to provide WC and welfare facilities however due to site constraints, as there is no site space, this will comprise of making local arrangements.
Works are to adhere to local tier grades and government guidelines to meet safe working conditions of operatives and residents.
1.07 | General
The Contractor is to allow for all foreseeable preliminary items including welfare, hoarding and scaffolding/access.
The Contractor may use existing utility services where installed however no undertaking is provided that these are suitable for the Contractors use.
Adequate full time supervision must be provided at all times and a responsible person must be designated and present throughout working hours.
The Contractor must fully comply with all relevant legislation, codes and byelaws.
1.08 | Accommodation
The Contractor is permitted use of the building within agreed areas, for the provision of site accommodation providing shelter (likely top floor store room).
There is limited public highway parking available.
1.09 | Attendance
The Contractor is to allow for all necessary attendance and builder’s work on all trades/sub-Contractors to facilitate the works.
1.1 | Scaffolding/High Level Access
The Contractor shall provide and install all necessary scaffolding hoists, ladders, staging, tackle, tarpaulins etc., and alter or adapt them during the works and maintain same and keep in good order. Scaffolding shall comply with British Standard 5974:2010 and British Standard EN 12811:1 and all subsequent British Standards.
All scaffolding etc. shall be erected and maintained where necessary to include use by all sub-contractors. All scaffolding shall be erected in accordance with current Codes of Practice and in compliance with the Construction (Design and Management) Regulations 2015. All necessary watching and lighting shall be provided. All scaffolding shall be dismantled on completion of the works and carted away from the site.
CDM Note: Ensure scaffolding and scaffold towers are inspected before use and every 7 days.
1.11 | Extent of Works
External: • Refurbishment and redecoration of cast iron gutters and downpipes, with replacement of an existing downpipe and gutter. • Replacement of failing lead-style sheeting and detailing with new lead work over customer entrance and timber shop front windows • Removal of existing cement fillet detail/coating and installation of lead soakers and flashing to parapet wall adjoining the neighbouring shop, ‘Joules’. • Removal of render to both front facing elevations, replace with suitable lime-based render. • Timber resin repairs to external joinery, including first floor windows and shop front windows • External redecoration of joinery. • Following completion of external works, making good the damaged plaster to the affected storeroom at first floor level only. Internal: - Rubbing down friable plaster within first floor store room below new lead flashings and corrdior. - Re-plaster rubbed down areas with lime plaster.
1.12 | All dimensions, sizes and areas are to be checked on site prior to the commencement of works or ordering of materials and the CA is to be advised of any discrepancies. Dimensions quoted in this specification and accompanying documents are for information only and are not to be used for construction. On no account will the Employer be held responsible or liable for extras or omissions.
1.13 | Where particular materials, products or manufacturers are specified, equivalents may be used, provided the prior consent and approval of CA has been obtained.
1.14 | The Contractor is to clearly establish the extent of the works required to complete them satisfactorily. All queries must be raised during the tender period, as no claim for additional items will be considered once the contract has been awarded.
1.15 | The drawings to accompany this specification are:
TN RS196 - 001 - Existing Ground Floor Plan TN RS196 - 002 - Proposed Elevations TN RS196 - 003 - Existing Second Floor Plan TN RS196 - 005 - Existing Elevations TN RS196 - 007 - Proposed Elevations Lead Details
Total - Preliminaries (Carry Forward to Summary Page)

## Scope of Work
2 | SECTION 2 - SCOPE OF WORK, EXTERNAL REFURBISHMENT | Cost (£)
2.1 | GENERALLY
2.1.1 | The unit will be occupied throughout the project.
2.1.2 | Asbestos R&D survey will be provided by the client in due course, however, it is to be assumed that there is no asbestos present for pricing purposes. Assume no asbestos is present.
2.1.3 | Site Set-up: Ensure protection of services and other items that could be damaged during completion of works. Costs for all necessary making good should be included in the individual work items whether or not to make good is specifically referred to. Damage to existing surfaces is also to be made good.
2.1.4 | Storage: Allow for all necessary site storage as well as removal and disposal of all debris and waste.
2.1.5 | Scaffold & Other Access Provisions: Supply, erect and maintain as necessary to carry out the works suitable full access scaffold, access towers, toe-boards, ladders or other access equipment suitable for use by all specified trades and sub trades to all levels of the specified elevations. Clean the scaffold area, as the scaffolding is dropped, and clear all away on completion. All scaffold in accordance with preliminaries and TG-20.
2.1.6 | Allow for complete scaffolding to front facing elevation on 1-3 East Street and side elevation fronting 25 Market Place (Elevations A and B on the tender drawings).
2.2 | RE-RENDERING WORKS
2.2.1 | Remove Existing Render: Carefully hack off/remove existing render to both elevations (Elevation A and B according to tender drawing TN RS196-005) using hand percussion tools at a shallow angle to the wall in order to remove render without damage to the timber frame. The substrate beneath is brick infill.
2.2.2 | Provisional Sum: Once the render is removed, the condition of the bricks will be seen. Include a provisional sum of £5,000 to repair/stabilise and infill parts that have fallen into disrepair. | 5000
2.2.3 | Provisional Sum: Allow provisional sum of £5,000 for spliced timber / epoxy resin repairs to the timber frame following removal of the existing render. Allow for inspecting ends of first floor ceiling joists for decay/damage due to potential dry/wet rot. If dampness is found then this will require drying out period first and the building fabric to be assessed. | 5000
2.2.4 | Reinforcement: Supply and fit Type 95s Stainless Steel Expanded Metal Lath (EML) to the timber frame and brick substrate across all areas being rendered. This is then to have the first base coat applied to it.
2.2.5 | New Lime Render to Elevation A and B; Three Part System: Allow to apply The Lime Centre Ultra Render or equivalent approved for base coats and Lux Render or equivalent approved for the finish coat. The render is to be applied in 3no coats. The base coat is applied onto EML as specified elsewhere. After applying the first base coat, The Lime Centre Fibre Mesh (9mm x 10mm) is applied into the render ready for the second base coat onto this mesh and this comes in 1000mm x 50m rolls. This is to be applied over all areas being re-rendered and embedded into the first basecoat by applying in 2 passes with the mesh trowelled in between passes. Fibre mesh overlaps at no less than 100mm. The mesh can be doubled up at corners, around openings with pieces being trowelled with plaster against the surface before application of the basecoat and further mesh. Each coat must be scratched to give a good mechanical key before further coats are applied. Dampen down the surface prior to coating. Ensure it is thinner than the first. Key the final coat of Ultra whilst still green with a nail or devil float before applying the topcoat of Lux. The base coat is to be applied in 2no coats. The top coat is to use The Lime Centre Lux Render. This is to be applied to a straight, keyed, flat, dampened surface in a number of passes each approximately 1-2mm thick, up to a maximum of 4mm. Each pass or layer of Lux should be applied while the first pass of Lux is still damp but has had time to “pull in”. The second Ultra coat may be applied after the previous has adequately cured, usually 2-4 days. Apply Lux once the Ultra base coats have had sufficient time to cure. Usually 4 -7 days. Adherence to the data and guidance sheets must be adhered too. Contractor to allow for all necessary scaffolding throughout, to ensure access to relevant areas and protection to areas below (pedestrianised street).
2.3 | TIMBER REPAIRS TO EXTERNAL JOINERY
2.3.1 | Provisional Sum: Allow the sum of £5,000.00 (Five thousand pounds) for timber care epoxy resin repairs to external timber joinery including doors, windows, shop front, barge boards, and other decorative timber elements/details). Allow for small and large resin repairs and scarfing of timber sections where necessary. Allow for inspection by the CA once safe access is possible. All repairs to be instructed by the CA. | 5000
2.4 | NEW LEADWORK
2.4.1 | Allow to remove existing lead-style sheeting from the overhanging shop frontage and front entrance located on Elevation A on the drawing TN RS196-005. Allow to replace with new lead covering in accordance with Lead Sheet Association Guidelines. Allow to form a welted edge detail around the perimeter edges. Rolls of lead detail are to be joined using a mop-stick or flat rolled joint.
2.4.2 | Externally, to Elevation A on drawing TN RS196-005, left hand side where the pitched roof meets the adjoining building (occupied by Joules Clothing), raise scaffolding and roof pitch access to the length of the sloping roof meeting the adjacent gable wall. Works are not required to the opposite slope to the rear elevation.
2.4.3 | Allow to remove the existing mortar flaunching formed over the brick gable parapet detail. Allow inspection by CA. Allow to cut into Party Wall to install new code 4 lead stepped soakers and cover flashing detail to Elevation A on drawing TN RS196-005 - Proposed Elevations. Drawing Lead Details is indicative and the contractor is responsible for the final design.
2.4.4 | All new lead work is to be protected with 2no. coats of high quality BLM patination oil, to be applied in accordance with the manufacturer's best practice guidance. Oil to be applied as work proceeds, and application should be complete before the end of each working day.
2.5 | EXTERNAL REDECORATION WORKS
2.5.1 | New Lime Wash Paint to Render: Allow to apply Graphenstone primer and GCS Exterior paint in the colour Arctic or equivalent approved on newly rendered elevations (Elevation A and B on drawing TN RS196-005) including the area underneath the barge boards at the apex of the gable. This is to be applied according to the manufactures data sheet. The drying time between coats is 2-4 hours and 24 hours for total drying time. Apply 3no coats.
2.5.2 | Redecorate Existing Joinery: Allow to properly prepare for and redecorate all presently or previously painted timber surfaces on the exterior of the buildings to the specified elevations including doors, windows, shop front, barge boards, and other decorative timber elements/details. Redecorate joinery to Elevations A and B on drawing TN RS196-005 only. Remove all defective paint to timber, including redundant metal fixings back to a sound base, and prepare by priming, sealing and additional undercoating prior to general redecoration. Allow filling to the surface to leave a smooth surface ready for decoration. Allow to prime and redecorate with Crown Trade paint, minimum 3no coats. Following striking of the scaffolding, clean the elevation once complete.
2.5.3 | Redecorate Existing Rainwater Goods: Allow for all the existing cast iron gutters and downpipes will undergo light refurbishment involving rubbing down of any damaged paintwork and removal of rust before being primed and redecorated using suitable oil-based smooth, gloss, white metal paint (Hammerite or equal approved) to match the existing colour scheme. Allow for all uPVC gutters are to be deep cleaned, rubbed down lightly to create a key, and painted with 1no coat of white paint. The paint used is to be uPVC White Aluminium 9006 PNT - 1K uPVC Acrylic Window and Door Paint or equivalent approved.
2.6 | RAINWATER GOODS
2.6.1 | Replacement of Gutter and Downpipe: Carefully take down one small length of gutter to the corner of East Street and Market Place as highlighted on the tender drawing TN RS196-007 - Proposed Elevations. Replace existing gutter and new wider downpipe. Decorate before attaching. Allow to remove existing gutter and replace with Half Rounded Cast Iron Gutter. This comes as 1829mm (L) x 115mm (W) and built to BS460. However, the length of gutter required is 1200mm. Also, allow to replace the downpipe and connect new wider downpipe to newly formed connection. Size1829mm (L) x 65mm (ID). This is to be built to BS460.
2.6.2 | Decorate New Gutter and Downpipe: Allow to decorate the new cast iron gutter and downpipe as specified elsewhere.
2.6.3 | Rear elevation: allow to modify height of existing uPVC gutter run to create suitable gradient for rainwater flow into the existing hopper. Please see tender drawing TN RS196-005.
2.6.4 | Cleaning: Allow to clear and clean internally and externally all remaining uPVC gutters and downpipes of any debris and leave good working order. Test upon completion.
2.7 | INTERNAL WORKS
2.7.1 | Tenant to remove all chattels and belongings present from the Store Room 2 (see drawing TN RS196-002) to allow full access. | Note
2.7.2 | Rubbing Down Existing Friable Plaster: Allow to carefully and locally rub down blown plaster on the North East corner of the Store Room 2 and the wall along the corridor next to Store 3 (see drawing TN RS196-002) to sound plaster. Make sure not to damage the plaster underneath. For pricing purposes, allow to rub down 25m2 of plaster. Cart away all arisings.
2.7.3 | Re-Plaster Elevations: Allow to re-plaster all rubbed down areas of the walls with The Lime Centre The Heritage Range Putty Plaster or equivalent approved. This is to be applied in three coats. After rubbing down, the scratch coat is not necessary. The float coat is a Heritage Putty Plaster which is of a medium course (3mm sand) and does not require animal hair to be added to this layer. This layer is 8mm thick. The finish coat is to be applied on top of this and has a fine finish. This coat is 3mm deep.
2.8 | CONTINGENCY SUM
2.8.1 | Allow £3,000.00 as a contingency which is to be expended at direction of CA. | 3000
Total - Scope of Work (Carry Forward to Summary Page)
Other Costs not to be carried to Tender Sum
A | Contractors Preliminaries per week for valid extensions of time, to cover weekly costs, overheads, profit, insurances. Do not include one off set up . Site dismantling costs.
B | Contractors percentage on cost for:-
Bi | Specialist sub contractors
Bii | Materials
Biii | Plant
C | Labour Rates
Ci | Skilled Labour
Cii | Labour (mates)
Ciii | M&E engineers
Civ | Decorator

## Summary Page
SUMMARY PAGE | Cost (£)
Preliminaries
Scope of Work
Other costs
Total (To Form of Tender)

## Form of Tender
Form of Tender
*I/We: ..................................................
carrying on business at:
…………………………………………………………………………………….
having examined the specification and manufacturers recommendations and literature, hereby tender and undertake to execute and complete the whole of the said Works in conformity with the aforementioned documentation for the sum of:
£………………………………………………………… ……(in figures)
……………………………………………………………………(in words)
exclusive of VAT (or such other sum as may be ascertained in accordance with the Conditions of Contract).
Should My/Our tender be accepted, and if requested by the Employer, I/We agree to enter into the Articles of Agreement. Unless and until such an agreement is executed this Form of Tender and the acceptance hereof shall constitute a binding contract between us.
I/We agree that the insertion by me/us of any conditions qualifying this tender or any unauthorised alteration to any of the tender documents may cause the tender to be rejected and confirm that I/We have not inserted any conditions qualifying this tender or made any unauthorised alteration to any of the tender documents.
I/We certify that the details of this tender have not been communicated to any other person or adjusted in accordance with any agreement or arrangement with any other person, firm or company.
I/We also certify that I/We am/are not a party to a scheme or arrangement under which any other tenderer was reimbursed any part of his/her tender cost.
I/We confirm that the above sum includes all Provisional Sums and all Contingencies and agree that this tender shall remain open for acceptance by you and shall not be withdrawn for a period of 10 weeks from the closing date for return of tenders.
I/We understand that you are not bound to accept the lowest or any tender you may receive, and you will not pay any expenses incurred by us in connection with the preparation and submission of this tender.
I/We hereby warrant and undertake to you in the terms set out in the Instructions to Tenders.
I/We certify that this is a bona fide Tender.
I/We undertake to complete and deliver the whole of the Works comprised in the Contract within 6 weeks from the Date of Possession.
Contractor's Representative's Signature:
(Print Name in Full): ............................................
Position in Company/Firm (must be a director or secretary or another person authorised by the company to sign *):
...............................................................................
Name of Company/Firm:
..............................................................................................................
Address:
.....................................................................................................................................
…………………………………………………………………..............................…………
…………………………………………………………………..............................…………
Tel. No(s): ......................................................
Email Contact: .................................................
Date .................................

## Designers RA
Risk Classification
Likelihood: Remote = 1; Possible = 2; Probable = 3
Severity: Minor = 1; Serious = 2; Severe / Fatal = 3
Risk rating: 1, 2 = Low; 3 - 5 = Medium; 6 - 9 = High
Project: Tea point refurbishment |  |  | Address: 25 Market Place, Southwold, IP18 6ED |  |  |  | File No. 2108021 |  | Date: Jan 2022
Project Element: All |  |  | Designer: TN
Ref | Activity Element | Significant potential hazards | Population at risk | Risk classification |  |  | Design action to be taken to reduce risk | Design action |  | Reduced risk factor | Future action
|  |  |  | Likelihood | Severity | Rating |  | By | Date
1 | Scaffold set-up and striking. | Injury to public from scaffold erection and striking | Public | 1 | 2 | 2 | Licence for works and follow local authority permit requirements. Barrier area as scaffolding works progresses. Likely need to close pavement. | MS | 2022-06-15 | 2 | Ensure scaffold erected in accordance with best practive / TG20.
2 | Working at height | Fall from height. Trips | Operatives | 2 | 3 | 6 | Top lift of scaffold to be fully boarded to allow safe movement of materials and prevent falls. | MS | 2022-06-15 | 3 | Ensure scaffold erected in accordance with best practive / TG20.
5 | Decorations | Exposure to lead containing materials (LCM). | Operatives | 2 | 3 | 6 | Require contractor to test redecoration areas with 3M LeadCheck swads and report any positive results. Test 10% of windows and to each wall / ceiling surface type. | MS | 2021-09-13 | 1 | Monitor contractor testing and record results.
MS
2021-09-13