Order Schedule 20 (Order Specification)

This Schedule sets out the characteristics of the Deliverables that the Supplier will be required to make to the Buyers under this Order Contract

### Research Specification: Understanding our Customers - Quantitative Research Defined Term Agreement

CCS Research & Insights DPS (RM6126)

Specification

July 2024

Contents

1.	Introduction	3

2.	Context	3

3.	Research Audiences	4

4.	Methodology	5

5.	Timetable	6

6.	Length of Contract	7

7.	Outputs	7

8.	Quality and Risk Management	8

9.	Expertise and Capability	9

10.	Project Management and Contract Administration	10

11.	Research Cost Model: Research Scenarios and Rate cards	11

Annex A Statement of Work Form	14

## Introduction

  - HM Revenue & Customs (HMRC) invites Suppliers from the Research & Insights DPS (RM6126) to submit tenders for a Defined Term Agreement (DTA) under which they may be required to undertake a range of small and medium-sized quantitative research projects. These will be aimed at understanding HMRC customers and their response to HMRC activity.

  - HMRC intends for this contract to be in place by September 2024, and to run for four years.

  - HMRC intends to appoint one Supplier to deliver research commissioned via the DTA contract. The DTA contract will make use of a range of quantitative research methods outlined and costed within the rate card provided by the appointed Supplier with their tender.

  - The successful Supplier will be ‘on standby’ for any insight needs raised by HMRC which fit the nature of this DTA contract (i.e., small and medium-sized quantitative research on HMRC customers).

  - Once needs arise for HMRC to use the DTA contract, the Supplier shall be prepared to deliver this alongside their existing work, sometimes at short notice (a minimum of two weeks) and to tight deadlines (final findings within two months of the set-up meeting).

  - HMRC will maintain the overall management of the projects that are commissioned through the DTA.

## Context

  - HMRC’s vision is to be a trusted, modern tax and customs department. To deliver this vision we have set ourselves 5 strategic objectives:

    - Collect the right tax and pay out the right financial support

    - Make it easy to get tax right and hard to bend or break the rules

    - Maintain taxpayers’ consent through fair treatment and protect society from harm

    - Make HMRC a great place to work

    - Support wider government economic aims through a resilient, agile tax administration system

  - The Customer Understanding and Behaviour team (CUB; formerly Behaviour, Insight and Research (BIR)) supports HMRC to achieve these objectives by building an evidence base for understanding customers through externally commissioned research. We specifically focus on evidence for understanding and improving customer experience, and use the evidence base to inform HMRC decision-making to improve HMRC operations.

  - HMRC’s needs will emerge and evolve over the contract period. Below are examples of the kind of research projects we expect will be commissioned under this contract. Research to provide a better understanding of:

- Customers’ views and experiences of HMRC services that they have used, including online services such as Self Assessment.

- Customer barriers to using some of HMRC’s services

- Customer understanding of guidance, services or policies which HMRC may introduce

- Customers’ response to HMRC communications to understand their views and actions that they would take on receiving communications

- The specific experience and views of different segments which may include:

  - Socio-demographic segments (such as pensioners or young people)

  - Behavioural segments (such as existing HMRC Individual and SME segmentations)

  - Life-event segments (such as “those new to work” or “dealing with bereavement”)

- The support we provide to Tax Agents (e.g., accountants)

- The experience and views of businesses in complying with HMRC requirements

  - The DTA will be one of CUB’s vehicles to externally commission research. It will replace an existing quantitative DTA expiring this summer and meet continued demand for external research to support important and imminent HMRC business decisions. Specifically, the DTA’s purpose is to deliver small and medium-sized quantitative research projects, including some that require rapid turnaround (final findings within two months of the set-up meeting).

  - Small and medium-sized quantitative projects are defined as having a maximum cost of up to approximately £80,000 and delivering research that may include online surveys, CATI or other research methodologies.

## Research Audiences

  - Research projects commissioned under this contract will focus on all three of HMRC’s main customer groups which include:

- Individual customers, such as PAYE customers, Self Assessment customers, and Tax Credit claimants

- Small, medium and large businesses (from full range of industrial sectors and turnover bands)

- Agents, such as accountants, bookkeepers, and customs intermediaries.

  - Within these main groups are a variety of subgroups, some of which are harder to recruit due to low incidence, the sensitivity of some topics of research, or because they are part of a customer subgroup who are particularly time poor. Examples of such subgroups are wealthy customers, vulnerable customers, customers in debt, and businesses in some industrial sectors.

  - While HMRC anticipates being able to provide customer data for use as sampling frames for some research projects, the Supplier shall be required, upon instruction, to source participants from independent data sets, for example from third-party mailing lists or using approaches such as random digit dialling. The Supplier shall have the necessary capacity, either in-house or via the use of sub-contractors, to access external sampling sources or free-find. The Supplier shall also have the capacity to recruit samples where HMRC set socio-demographic or other segmentation parameters for recruitment (for example by HMRC customer group: Self-Assessment customers, customers eligible for tax credits, etc.).

  - The Supplier shall utilise proven approaches to maximise recruitment success rate for hard-to-reach groups and subgroups.

## Methodology

  - The Supplier shall have the capability to deliver a range of different types of quantitative research as determined by each project’s requirements when commissioned from the contract. Below is a list of types of quantitative research methods and analysis that the Supplier may be required to deliver:

- Omnibus surveys

- Online surveys, including push to web

- Panels

- CAWI, CAPI, CATI

- Questionnaire design

- AI survey and analysis tools (e.g., for open questions)

- Descriptive statistics

- Advanced statistical techniques and modelling

  - HMRC envisage that most requirements will dictate the use of omnibus or other surveys using short questionnaires (5-20 minutes) and using online self-completing or telephone interviewing methods, but other types of numeric data or survey results may also be required. The Supplier shall have the necessary expertise, capability and capacity to deliver this if required.

  - Omnibus surveys and panels can take various approaches. The Supplier must provide details of all omnibus surveys or panels they will use for this DTA, including benefits and limitations of each.

  - All findings are required to be sufficiently robust. For example, for all random probability research we would request suppliers aim for a confidence interval of around +/- 3 percentage points at the 95% level for results at the total sample level. This is a guide, and we will accept bids with differing levels of accuracy as long as the approach is fully justified and any trade-offs are set out clearly.

  - HMRC requires the Supplier to provide appropriate interpretation and conclusions as part of the analysis they conduct. Analytical findings must be accompanied by a narrative that captures patterns across all analyses conducted and that directly speaks to research objectives and questions.

  - Suppliers must fully justify their approaches and recruitment strategy. For example, bidders must explain how they will reduce order bias if using an omnibus approach and ensure that sample bias is mitigated if utilising panels.

## Timetable

  - The timeline provided below is indicative of the timelines expected by HMRC for a research project. Suppliers are required to demonstrate in their tenders that they will be able to complete the research within the below timelines or sooner, unless a revised timescale is agreed between the two parties during the project commissioning process. Timelines should be adjusted to account for multiple fieldwork waves as necessary.

| Activity | Date |
| --- | --- |
| Discussions between HMRC and the contractor | Week 1 |
| HMRC provides research brief | Week 2 |
| Supplier provides research proposal | Week 3 |
| Statement of Work signed and call-off project commences | Week 4 |
| Development of research materials & opt-out | Week 5 to 8 |
| Fieldwork | Week 9 to 12 |
| Analysis and reporting | Week 13 to 15 |
| Presentation of findings | Week 16 |
| Finalising written report, outputs signed off, project closes | Week 17 to 20 |

  - Project timelines and milestones will be agreed for each project commissioned under this contract. The Supplier shall deliver the milestone activity by the agreed timescales unless otherwise agreed by the two parties in writing.

  - Suppliers must include an illustrative project plan and time schedule for each of the example scenarios outlined in Annex H that identifies the main tasks and key milestones that will be used to monitor progress, indicating clearly where HMRC is expected to contribute.

## Length of Contract

  - The DTA contract will run for a four-year period.

  - The DTA final date by which all projects must be delivered will be the termination date of the contract.

  - HMRC reserves the right to include, within each called-off project, break clauses as necessary to review progress and decide whether or not to proceed with subsequent phases of the project. The two parties will agree at the outset of commissioning a project if there will be any payments due as a result of cancelling a project. Any costs agreed will be proportionate.

## Outputs

  - The exact deliverables required for each project will be agreed between the two parties during the commissioning stage. As a minimum, HMRC anticipate requiring the following outputs for most, if not all, research projects commissioned under this contract:

  - Draft copies of all key documents, such as survey scripts, presentation charts, topline and final reports provided to HMRC. These are to be submitted in sufficient time to the HMRC project manager for comments to be incorporated and for our approval to be given for the final version. Specific deadlines will be agreed with the HMRC team managing it.

  - All summaries, reports, data outputs (e.g., tables and graphs) should be provided in an electronic format, compatible with Microsoft Office applications. All reports should be concise (approximately 8-10 pages) and written in plain English. They shall be of a high (publishable) standard, in line with the GOV.UK style guide and accessibility requirements, making them suitable for online publication. HMRC expects all drafts to be complete, to have been proof-read before delivery and for data in the drafts to have been quality assured. HMRC may arrange for any final reports produced to be peer-reviewed, either in-house or externally.

  - Raw quantitative data shall be provided in a format compatible with Excel, SPSS and any other formats agreed with HMRC, alongside syntax for any derived variables.

  - Delivery of PowerPoint presentations (approximately 25-30 slides) on key findings plus Q&A session to a group of HMRC officials – this will typically take place online, but HMRC may ask for face to face.

  - There may be additional outputs required which will be agreed with the agency at the point of commissioning each project.

  - The Supplier shall provide translations for research participants in Welsh and/or provide Welsh language versions of requested research tools or outputs if requested by HMRC.

  - The Supplier shall ensure they have the necessary capability and capacity to deliver the indicative outputs stated within section 7.1 for each project.

  - Contractors are also reminded that any research reports to be published on www.gov.uk must meet the accessibility requirements for public sector bodies’ publications: https://www.gov.uk/guidance/accessibility-requirements-for-public-sector-websites-and-apps#accessibility-standards

## Quality and Risk Management

  - The Supplier shall hold professional accreditations and quality standards relevant to the delivery of quantitative research.

  - Suppliers must include a quality control plan with their proposal, which must demonstrate their internal procedures to assure quality control. This must include details of:

  - How quality of delivery will be maintained throughout the length of the DTA;

  - How quality will be consistently achieved across a range of projects;

  - How you propose to incorporate feedback from HMRC on any quality issues into any ongoing and future call-off projects.

  - The quality control plan must specifically address monitoring of recruitment and interviewer performance, securing reliable data from respondents, ensuring high standards in data analysis and ensuring final outputs meet HMRC’s needs. The quality control plan must also specifically address the maintenance of any panels used.

  - Proposals must also include an assessment of the key risks to this project. This must identify the most significant risks to successful completion of the programme of work, assess the degree of risk (likelihood and impact), and set out strategies for minimising these risks and managing the consequences if problems occur. A risk register template is at Annex G. Key risks arising from this DTA may include:

  - Ensuring capability and capacity to resource projects through the call-off process at short notice;

  - Managing tight project timelines;

  - Hard-to-reach or difficult recruitments (e.g., low response rate), potentially leading to compromises in data quality and/or research coverage;

  - Fieldwork slippage owing to real-world events (e.g., delays to getting research materials agreed);

  - Sensitivity of subject matter.

## Expertise and Capability

  - HMRC acknowledges that considerable resources are required for the successful delivery of this contract and its call-off projects to time and to sufficiently high standards. It is possible that agencies invited to tender have the skills and ability within their organisation to undertake all or part of this research but do not have sufficient resources required to successfully deliver the whole research requirement. We therefore encourage agencies to collaborate with other suppliers if required and where relevant to ensure that they are fully capable of undertaking this work.

  - HMRC is seeking suppliers who can demonstrate that their proposed research delivery team has:

  - Relevant qualifications/training/methodological specialisms;

  - Experience recruiting from specific participant groups as set out in section 3;

  - Experience with quantitative methods as set out in section 4;

  - Experience delivering the outputs as set out in section 7;

  - Experience researching taxation topics.

  - Proposals must summarise the skills and expertise relevant to this requirement that members of staff bring to the team and clearly identify the DTA programme manager and individual project managers and include their CVs as an annex. Each CV must not exceed two pages.

  - The proposal must also specify details of which parts (if any) of the project will be sub-contracted, the name of the sub-contractor who will work on the project, their experience of related research, and their responsibilities within the project. If it is proposed to sub-contract any of the work, the same details as those provided by the Supplier should be given about the qualifications, experience and responsibilities of sub-contractor staff involved along with a description of their respective roles and the management arrangements put in place. Ultimately, the successful Supplier will be held to account for the performance of any sub-contractor and needs to demonstrate their confidence to successfully manage sub-contractors. This should also be considered for any joint submissions, as the second contractor will be treated as a sub-contractor.

## Project Management and Contract Administration

  - Both HMRC and the appointed Supplier will each nominate a member of staff to be the main DTA point of contact (the programme manager) for the duration of the agreement. Both programme managers will maintain a close working relationship throughout the contract to identify and implement opportunities for innovation and/or improvement.

  - Individual projects called-off from this DTA will be overseen by various project managers within HMRC’s analytical function. These project managers will lead on all day-to-day aspects of the project on behalf of HMRC.

  - It is expected that the appointed Supplier will nominate project managers to lead on the day-to-day management of called-off projects. The Supplier’s project manager must work closely with the HMRC project manager and through them, with internal customers within HMRC throughout the duration of the project. The HMRC project manager must be kept informed of progress and be involved in key decisions. Proposed changes in project staffing (at all levels) or deviations from the agreed work programme must be discussed and agreed with the project manager in advance.

  - The award of this DTA contract does not guarantee a minimum amount of work during the contract period. However, in order to maximise the value of the contract to HMRC and to the Supplier, regular review meetings between HMRC and the Supplier’s programme managers on a six-monthly basis or as required and between HMRC and the appointed supplier’s project managers in relation to specific projects called-off the DTA will be held throughout the length of the contract. This is to ensure that quality standards are met and contract management is optimal for both HMRC and the appointed Supplier.

  - Whilst we anticipate using this DTA for discrete quantitative research projects, we do not commit to exclusively using this contract for these purposes and reserve the right to choose to commission such work through other means and with other Suppliers as we see fit.

## Research Cost Model: Research Scenarios and Rate cards

  - The contract value for the four-year period will be up to £499,000 (excluding VAT) (anticipating an annual average value of up to £125,000 per year). This maximum contract value and annual average spend is not guaranteed as the total spend will depend on the number, nature and value of the projects called-off the DTA.

  - Individual call-off projects will have a spend of up to around £80,000, though this could be more for specific evidence requirements. Suppliers are asked to submit costings for the example scenarios set out in Annex H according to the guide of up to £80,000 per project.

  - HMRC reserves the right to not consider for award any tenders where the example scenario costings are in excess of £80,000 per project.

  - The Supplier shall adhere to the costing assumptions outlined in the costing model for any project called-off from the DTA contract.

  - Costs will be fixed throughout the duration of the contract.

  - The Supplier may request a review into the prices included within Call-Off Schedule 5 Pricing Details where they can evidence to HMRC that there has been an increase in the Consumer Price Index (CPI).

  - HMRC will review the evidence submitted by the Supplier and will either approve or reject the request. The decision to approve or reject the request will be based solely on whether HMRC agrees that the criteria specified within Clause 26 of the Core Terms has been met. HMRC will not unreasonably withhold approval to a request under Clause 26 of the Core Terms.

  - Where a price review request is accepted and the Supplier requests a price amendment during the review, the Supplier will be required to demonstrate that any new proposed prices constitute good value as defined within DPS Order Schedule 16 - Benchmarking. The cost to compile evidence for a price review shall be borne solely by the Supplier.

  - The Parties agree that any agreed changes required to this Contract identified in the price review will be implemented at the direction of the Relevant Authority in accordance with Clause 24 of the Core Terms (Changing the contract).

  - The Supplier will not be permitted to request a price review within 12 months of the service go-live date. The Supplier will not be permitted to request a price review within 12 months of a previous price review where HMRC subsequently agrees to price amendments.

  - Any price increases agreed between the two parties must not exceed the rates submitted by the Supplier at framework level. Any price increases as a percentage of the original pricing must also not exceed the percentage increase to CPI.

  - Cost criteria for the DTA contract will be evaluated through three research project scenarios provided at Annex H, which Suppliers should provide cost breakdowns for.

  - Suppliers must include indicative scenario costings and a rate card in their tender.

  - For each of the research scenarios listed in Annex H, you must provide:

  - an itemised cost sheet using the template in Annex E, based on the pricing/rates that would be the agreed contract charges (provided separately from the main proposal);

  - within the main proposal, up to two pages maximum per scenario summarising your methodological approach (including pros and cons of your chosen approach and trade-offs) and your understanding of the research context, any sensitivities, risks and mitigation plans;

  - within the main proposal, a short timetable showing how long it would take to deliver outputs from each of the research scenarios, assuming HMRC are able to sign off the proposal and any fieldwork material within two weeks of receiving them and how much time would be allocated to each scenario project by which levels of staff (e.g. Director, Senior Researcher, Junior Researcher).

The indicative costed scenarios will be used to evaluate the costs.

  - Tenderers will also be required to complete a rate card as part of the procurement exercise. This rate card will be used to cost any subsequent project called-off the DTA contract. The rate card is included at Annex E.

  - The unit costs/rates provided in the indicative costed scenarios must be the same as the unit costs / rates provided in the rate card. HMRC reserves the right to clarify or exclude a tenderer if they submit an indicative costed scenario with unit costs / rates different to those included within their rate card.

  - For the avoidance of doubt, the unit costs/rates provided in the rate card must be the total cost of delivering that activity/service, inclusive of all third-party costs.

  - Costs provided should be exclusive of VAT.

## Annex A Statement of Work Form

This Statement of Work is issued under and in accordance with the Contract entered into between the parties dated 30/09/2024.

| Project Overview |  |
| --- | --- |
| Project Start Date |  |
| Project End Date |  |
| Deliverables |  |
| Project Plan |  |
| Total Cost |  |
| Payment Milestones |  |
| Additional Clauses |  |

Signed by on behalf of the Supplier:

Name:

Role:

Signature:

Date Signed:

Signed by on behalf of the Customer:

Name:

Role:

Signature:

Date Signed: