Council Of The Isles Of Scilly Museum and Cultural Centre Part 2 - Project Description 09 August 2023

Version: 1.0 Status: DRAFT

Project Description

| Project Name | Isles of Scilly – Museum and Cultural Centre |
| --- | --- |
| Scope of Work | Extensive refurbishment and renovation of existing Town Hall and new extensions to create a new museum and cultural centre. |
| Employer | Council of the Isles Of Scilly |
| Site Address | Town Hall, St Marys, Isles of Scilly, TR21 0PZ |
| Employer Contact | Keith Grossett – Council Of The Isles Of Scilly |
| Programme (Construction) | March 2024 – March 2025 |
| Current Forecast Cost | £4.6m (excluding contractor preliminaries, overhead and profit, design fees, contingency, inflation and VAT) |
| Form of Procurement | Traditional - 2 Stage |
| Stage 1 Tender Return | 20/09/2023 |
| Contractor Selection due | 04/10/2023 |
| Stage 2 Tender Return | 19/01/2024 |
| Start on Site | 01/04/2024 |
| Anticipated Completion | 31/03/2025 |

Professional Team

The Employer’s Consultant Team comprises:

- Project Director – Neil Richardson

- Project Manager – David Clarke Associates

- Architect – Purcell

- Structural Engineer – Fenton Holloway

- Quantity Surveyor – Currie & Brown

- Principal Designer – Purcell

## Procurement Route

This is to be a Construct Only contract, with Pre-Construction advice from the selected Contractor. The proposed form of contract will be JCT SBCXQ 2016 with contractor design elements.

The Contract will include some element of Contractor’s Design which are being confirmed during RIBA Stage 4.

## Project Information

Current design, scope and programme details are included in the Tender Documents at Appendix A (Specification – Appendix A).

A strategic programme is being updated, as well as the Risk Register. The Contractor is required to focus on post contract programme and overall project risks.

## Programme

Key dates are:

- Contractor Appointment (commencement of Stage 2)	 04/10/2023

- Agree Contract Sum					 19/02/2024

- Construction Start Date				 01/04/2024

- Construction Completion		 		 31/03/2025

## Risk Register

A Risk Register is currently being updated, however some of the key risks are noted below:

Working in a listed building

Working in a remote location

Party wall requirements with neighbours

Funding deadlines