Council Of The Isles Of Scilly Museum and Cultural Centre Part 3 - Duties Of The Contractor 09 August 2023

Version: 1.0 Status: Draft

Duties of the Contractor

Contractor Pre Construction Duties & Outputs

Project Planning and Management

With reference to the Employer’s brief, prepare a Contractor’s Project Execution Plan (PEP) to cover RIBA stage 4, detailing all key Contractor deliverables. This will include input by the Contractor into the design process (reviewing the design information to ensure completeness for the purposes of pricing and construction, specialist services sub-contractor input to determine design completeness and outstanding information particularly in relation to the location, nature and state of existing services installations) to work with the Client’s design team to develop and complete an affordable design for Stage 2 tender.  The execution plan should address:

- Overall project programme and strategy

- Design review and critical analysis

- Procurement and supply chain management

- Cost planning, cost control and package management

- Meetings structure and purpose

- Value and risk management

- Sustainability

- Access and operational requirements during construction

Following consultation with the Professional team, prepare the preconstruction and construction programmes clearly identifying as a minimum the critical path, leads times and key milestones. Programmes should be presented as a Gant chart using Microsoft Project or similar.

Prepare in agreement with the Professional team, drawing and information release schedules giving dates for release of information from the design team for both procurement and construction purposes.

Advise on the provision and layout of site facilities and services to be provided or secured by the Contractor.

Submit monthly reports to the Project Manager / Contract Administrator, highlighting progress, achievements, critical issues and proposals for managing them.

Actively participate in the value management and value engineering process to ensure that all project delivery and financial objectives are achieved or exceeded.

Design

Advise on buildability in relation to the proposed design and the practical implications of proposed drawings and specifications including programming and sequencing of work. Identify potential problems / risk areas associated with demolition and the on-going maintenance and use of the building. Identify where value may be added during works. Comment on Health and Safety aspects of the design.

Advise on access to the site including limitations and access within the confines of the site. Comment on the practical issues associated with the following:

- Access to site/ working areas

- Temporary on site storage and efficient compound layout

Advise on and agree with the Professional team construction methods, building systems and equipment and the selection, availability and price of materials and goods (in relation to the temporary works).

Review the demolition scope and design, and determine, review, and seek to eliminate or mitigate areas of risk due to:

- incomplete design

- uncertainty over existing structures; assist the consultants in removing such risks by establishing the nature of existing structures to ensure the design is complete

- ensuring services are maintained to neighbouring areas

- programme, including procurement

Contractor Design Responsibilities

Identify any Contractor design required prior to contract award and agree associated design fees and order dates and manage the design process and integration of all Contractor Designed Portions (CDP). This should include but is not limited to all temporary works.

Tenderers should note that the current list of identified Contractor design elements may be subject to change during the Stage 2 tender period as the design develops and is finalised; tenderers should recognise this, and this should not preclude other elements of the scheme becoming Contractor design elements during the stage 2 tender period.

Cost Management

Work with the Employers QS to develop a cost plan based on BCIS elements cost format. The Contractor shall propose sub-contract procurement packages (where necessary) which shall be fully reconciled with allowances made within the cost plan.  Cost Plans may include rates based on £/m2 or Element Unit Quantities as agreed with Employers QS. Agree and notify consent to the cost plan and the total thereof to the Contract Administrator / Project manager.

Lead the negotiations with sub-contractors and suppliers to assist with achieving costs within the agreed project funding.

Agree any required adjustments to preliminaries costs (which should only be applicable to justifiable changes to the project that reasonably incur additional cost and could not have been accounted for at the Stage 1 Tender) for the project with the Employer’s QS.

Procurement

Advise on the whole supply chain procurement strategy and requirements. Ensure the entire scope is included with no gaps at the package interfaces.

Advise the Employer’s Professional team on the breakdown of the Project into suitable work packages for Subcontracts.

Consult with the Employer’s Professional team and initiate the preparation of sub-contractors and supplier lists for tendering, investigate and report on their capabilities and financial standing.  The Contractor shall obtain a minimum of three competitive quotes for any work he intends sub-contract unless agreed otherwise with the Employer.

Agree final tender lists with the Professional team.

Assist in preparing tender documents; prepare enquiry documents including subcontract terms, agree attendances with Employer’s Professional team and invite tenders in accordance with agreed tender lists.

Evaluate tenders from sub-contractors and suppliers; provide detailed tender reports and make recommendations thereon. This shall include a full reconciliation of each sub-contract package together with both technical and commercial recommendations.

The Pre-Construction Fee is to exclude all tendering costs which are to be recovered through Main Contractor Overheads.

Meetings

Attend such meetings as are agreed with the Project Manager as necessary in provision of the pre-contract services.

Risk Management

In consultation with the Project Manager, identify, take ownership, mitigate, and report on project risks prior to contract award.

The project risk registers should encapsulate all project risks and while it may include health & safety or construction risks it should not be wholly focused on these.

At contract award take ownership of the risks allocated to the Contractor and fully participate in the updating of the Project Risk Register.

Health & Safety

All statutory health & Safety requirements will remain unchanged by this agreement, and for the avoidance of doubt this includes the obligations and duties of all parties to comply with the Construction (Design and Management) Regulations 2015.