## Table (hidden)
Package | Site | Lift Site | No. Bags | Flying Start Date | Finish Date | Traffic Management Required
1 | Alport | Snake Summit | 3586 | 2018-10-15 | 2019-03-17 | TBC with Helicopter Company
2 | Derwent and Howden | Salter's Brook | 900 | 2018-10-04 | 2018-03-17 | No
3 | Noe Stool | Dale Head | 900 | 2018-08-13 | 2018-12-21 | No
4 | Peaknaze | Glossop Low | 3175 | 2018-10-04 | 2018-12-21 | No
5 | Stalybridge | Chew Track | 8500 | 2018-08-13 | 2019-03-17 | No
6 | Thurlstone | Snow Road | 51 | 2018-10-15 | 2019-02-15 | No
| Total |  | 17112
Summer start date
Autumn start date
Winter start date

## Matrix (hidden)
|  | Information |  | Evaluation Criteria
Package | Site | Lift Site | No. Bags | Cost Weighting % | Quality Citeria 1 Weighting % | Quality Citeria 2 Weighting % | Quality Citeria 3 Weighting %
1 | Alport | Snake Summit | 3586 | 50 | 20 | 15 | 5
2 | Derwent and Howden | Salter's Brook | 900 | 50 | 20 | 15 | 5
3 | Noe Stool | Dale Head | 900 | 50 | 20 | 15 | 5
4 | Peaknaze | Glossop Low | 3175 | 10 | 60 | 20 | 10
5 | Stalybridge | Chew Track | 8500 | 10 | 60 | 20 | 10
6 | Turlstone | Snow Road | 51 | 30 | 30 | 30 | 10
· Quality Criteria 1: XX% weighting. Capacity of the Tenderer to deliver the works in a time critical manner and provide a detailed Program of Works demonstrating how they are going to do so.
· Quality Criteria 2: XX% weighting. Method Statement documentation detailing how the objectives of the tender will be met
· Quality Criteria 3: XX% weighting. Experience in delivering upland conservation projects/similar projects

## Package Summary
Package | 1 | 2 | 3 | 4
Site | Heptonstall and Widdop | Warley, Oxenhope, Midgley and Thornton | Rishworth North and South | Turley and Langfield
Preliminary Costs | 0 | 0 | 0 | 0
Clean Up Costs | 0 | 0 | 0 | 0
Heather Brash Total | 0 | 0 | 0 | 0
Heather Bales Total |  | 0 | 0 | 0
Stone Dams Total | 0 |  | 0 | 0
Timber Dams Total |  | 0 | 0 | 0
Peat Dams and Reprofiling Total | 0 | 0 |  | 0
Bunding Total | 0
Cutting Total |  | 0 |  | 0
Sphagnum Total | 0 | 0
Dwarf Shrub Plug Total | 0
Glyphosate Application | 0
Dwarf Shrub Seed Total | 0
Rhododendron Total | 0
Fencing Total | 0
Grand Total | 0 | 0 | 0 | 0

## Preliminary Costs
Preliminary Items - One off payment per site
Item | Total (excluding VAT)
Insurance of Works (£10,000,000 Aerial works, 5,000,000 all other)
Preparation of Pre-Tender Method Statements, Operational Risk Assessments, Safety Policy.
Preparation of Site Risk Assessments, COSHH Assessments.
Preparation of CDM Construction Phase Plan and carrying out all responsibilities as a duty holder under CDM 2015
Provision of welfare facilities for Contractor employees.
Provision of GPS record of all completed works (to the specification as outlined in Section 1 Part B)
Provision of Carbon Audit data (see Standard Conditions)
Any additional items required to meet contractual requirements
Grand Total | 0

## Clean Up
Package | Site | Total Cost for removing and disposing of all waste materials from site
1 | Heptonstall and Widdop
2 | Warley, Oxenhope, Midgley and Thornton
3 | Rishworth North and South
4 | Turley and Langfield

## Brash and LSF
Information |  |  | Supply and Deliver Heather Brash to lift site | [7 empty] | Supply and Bag Lime and Fertiliser |  |  | Airlifting Heather Brash |  |  | Spreading Heather Brash, lime, seed and fertiliser |  |  | Grand Total
Package | Site | No. Bags | Donor Site Location | Cost for Donor site documentation and permissions | Cost for Archaeological consent to cut | Positioning Fee | Unit Cost Dumpy Bag Supply | Unit cost per bag (cut and delivered) or (cut and ready for airlifting) | Total Cost | Number of Days to cut and deliver all bags | Unit Cost Supply Lime and Fertiliser (per bag) | Unit Cost Bagging and preparation of Lime, Seed and Fertiliser (per bag) | Total Cost | Unit Cost per Bag (incl. positioning fee and all crew costs and marshalling) | Total Cost | Number of days to fly all bags | Unit Cost per Bag | Total Cost | Number of days to spread all bags | Total | Total number of days
1 | Heptonstall and Widdop | 85 | Midgley Moor | [5 empty] | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 0
2 | Warley, Oxenhope, Midgley and Thornton | 745 | Midgely Moor | [5 empty] | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 0
3 | Rishworth North and South | 741 | Cupwith and Buckstones Moss | [5 empty] | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 0
4 | Turley and Langfield | 1508 | Turley | [5 empty] | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 0
[5 empty] | Additional Information – HEATHER BRASH | [7 empty] | Additional Information (for info only, not included in over all costs) |  |  | Unit Cost (exc. VAT) | Spreading
[5 empty] | Please specify method of Delivery (e.g. tractor and trailer/ Artic lorry etc.) | [7 empty] | Maximum Positioning Fee |  | Item |  | Number of Bags spread per person per day | Bags
[5 empty] | Please specify method of unloading at Delivery Site (e.g. tele-handler, tractor forks, 360 digger etc.) | [7 empty] | Maximum Re-positioning Fee |  | Item |  | Number of Spreaders available per day | Persons
[5 empty] | Number of Bags per Delivery | [7 empty] | Helicopter Hourly Rate |  | Hour
[13 empty] | Pilot |  | Day per person
[13 empty] | Ground Crew |  | Day per person
[13 empty] | Staff to recirculate strops (if needed) |  | Day per person
[13 empty] | Marshalling at the Lift Site |  | Day per person
[13 empty] | Marshalling at Drop locations |  | Day per person
[13 empty] | Marking out Drop locations ready for Airlifting |  | Day per person
[13 empty] | AOC flight for MFF staff/guests |  | 6 min. per flight
Helicopter operator
Model of Helicopter to be used for Airlifting
[13 empty] | Load Lifting Capacity of the machine |  | Kilograms (Kgs)
[13 empty] | Personnel Capacity of the machine |  | Persons
[13 empty] | Number of Hooks available per system |  | Hook
Alternative lifting mechanisms (e.g. Skips/ Cargo nets)
[13 empty] | Average number of bags per lift |  | Bags
[13 empty] | Minimum number of personnel required to run an operation |  | Persons
Airlifting method and Equipment required (e.g. Multiple secondary hook with certified lifting strops)
Number of Bags of Heather Brash per lift

## Heather Bales
Information |  |  | Supply and Deliver Heather Bales to lift site |  |  |  | Airlifting Heather Bales |  |  | Installing Heather Bales |  |  |  | Grand Total
Package | Site | No. Bales | Donor Site Location | Unit cost per bale (cut and delivered) or (cut and ready for airlifting) | Total Cost | Number of Days to cut and deliver all bales | Unit Cost per Bale (incl. positioning fee and all crew costs and marshalling) | Total Cost | Number of days to fly all bales | Provision of survey flags and marking out individual dam locations at the works site, prior to the installation | Unit Cost per Bale | Total Cost | Number of days to install all bales | Total | Total number of days
2 | Warley, Oxenhope, Midgley and Thornton | 1476 | Midgely Moor |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
3 | Rishworth North and South | 396 | Cupwith and Buckstones Moss |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
4 | Turley and Langfield | 1428 | Turley |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
|  |  | Additional Information – Heather Bales | [7 empty] | Additional Information - Heather Bales
|  |  | Please specify method of Delivery (e.g. tractor and trailer/ Artic lorry etc.) | [7 empty] | Number of bales per lift
|  |  | Please specify method of unloading at Delivery Site (e.g. tele-handler, tractor forks, 360 digger etc.) | [7 empty] | Number of workers on Site each day
|  |  | Number of Bales per Delivery | [7 empty] | Number of Bales installed per person per day
Method of airlifting bales eg. bags, cargo nets, slings etc.

## Stone Dams
Information |  |  | Supply, deliver and prepare Stone |  |  |  | Airlifting Stone and Installing Dams |  |  |  | Grand Total
Package | Site | No.Dams | Quarry Name | Unit cost per 750kg | Total Cost | Number of Days to deliver all stone | Provision of survey flags and marking out individual dam locations at the works site, prior to the installation | Unit Cost per Dam (incl. positioning fee and all crew costs and installation) | Total Cost | Number of days to fly all dams | Total | Total number of days
1 | Heptonstall and Widdop | 600 |  |  | 0 |  |  |  | 0 |  | 0 | 0
3 | Rishworth North and South | 112 |  |  | 0 |  |  |  | 0 |  | 0 | 0
4 | Turley and Langfield | 482 |  |  | 0 |  |  |  | 0 |  | 0 | 0
|  |  | Additional Information – Stone Delivery |  |  |  | Additional Information – Airlifting and Installation
|  |  | Please specify method of Delivery (e.g. tractor and trailer/ Artic lorry etc.) |  |  |  | Please specify method airlifting stone eg. skip, bags etc.
|  |  | Please specify method of unloading at Delivery Site (e.g. tele-handler, tractor forks, 360 digger etc.) |  |  |  | Number of staff required on hill
|  |  | Number of tonnes per Delivery |  |  |  | Number of staff required at lift site
Number of dam units per lift
Estimated Number of Dam Units completed each day

## Timber Dams
Information |  |  | Supply of Timber and Nails |  |  | Airlifting Timber |  |  | Installing Timber |  |  |  | Grand Total
Package | Site | No. Timber Dam | Unit cost per Dam (delivered and ready for airlifting) | Total Cost | Number of Days to cut and deliver all Timber Dam | Unit Cost per Dam (incl. positioning fee and all crew costs and marshalling) | Total Cost | Number of days to fly all Timber Dam | Provision of survey flags and marking out individual dam locations at the works site, prior to the installation | Unit Cost per Dam | Total Cost | Number of days to install all Timber Dam | Total | Total number of days
2 | Warley, Oxenhope, Midgley and Thornton | 68 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
3 | Rishworth North and South | 32 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
4 | Turley and Langfield | 48 |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
Additional Information
Please specify method of Delivery (e.g. tractor and trailer/ Artic lorry etc.)
Please specify method of unloading at Delivery Site (e.g. tele-handler, tractor forks, 360 digger etc.)
Method of airlifting timbers eg. bags, cargo nets, slings etc.
Number of dams per lift
Number of workers on Site each day
Number of dams installed per person per day

## Peat Dams and Reprofiling
Information |  |  |  | Tracking Machinery and Equipment to Work Sites |  |  | Peat Dams |  |  | Reprofiling |  |  | Grand Total
Package | Site | No. Metres Reprofiling | No. Dams | Day Rate for Tracking Machinery and Equipment on and off work site | Total Cost | No. of days required to track machinery and equipment both on and off site | Unit Cost per Dam | Total Cost | Number of days to install all Dams | Unit Cost per Metre | Total Cost | Number of days to complete | Total | Total number of days
1 | Heptonstall and Widdop | 0 | 209 |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0
2 | Warley, Oxenhope, Midgley and Thornton | 0 | 24 |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0
4 | Turley and Langfield | 290 | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0
|  |  |  | Make/model of equipment, powered machinery or fuel container | Description and details of equipment, powered machinery or fuel container
Estimate number of Dams created per day
Estimate number of metres of reprofiling per day
Number of machines on site per day

## Bunding
Information |  |  | Bunding |  |  | Grand Total
Package | Site | No. Units | Day Rate for Bund Construction | Total Cost | Number of days machine work required | Total | Total number of days
1 | Heptonstall and Widdop | 118 Hectares (80m of bunds per ha). Budget for 25 days machine work. |  | 0 | 25 | 0 | 25
|  |  | Make/model of equipment, powered machinery or fuel container |  | Description and details of equipment, powered machinery or fuel container
Estimate length of bunds created per day
Number of machines on site per day

## Cutting
Information |  |  |  | Cutting | [5 empty] | Grand Total
Package | Site | Material to cut | No. Hectares | Initial site visit with the Authority / Site Manager to discuss access and flailing areas/zones | Marking out of access route | Tracking of flailing Equipment to and from Work Site | Unit Rate cutting per Ha | Total Cost | Number of days to complete | Total | Total number of days
2 | Warley, Oxenhope, Midgley and Thornton | Heather | 10.6 |  |  |  |  | 0 | 0 | 0 | 0
2 | Warley, Oxenhope, Midgley and Thornton | Molinia | 4 |  |  |  |  | 0 | 0 | 0 | 0
4 | Turley and Langfield | Heather | 0.1 |  |  |  |  | 0 | 0 | 0 | 0
|  |  |  | Make/model of equipment, powered machinery or fuel container |  | Description and details of equipment, powered machinery or fuel container
Estimate area cut per day per day
Number of machines on site per day

## Sphagnum Planting
Information |  |  | Sphagnum Planting |  |  |  |  | Grand Total
Package | Site | No. Units - Hectares (1150 per ha) | No. Plugs planted per person per day | No. Staff on site per day | Unit Rate planting per Ha | Total Cost | Number of days to complete | Total | Total number of days
1 | Heptonstall and Widdop | 300 |  |  |  | 0 | 0 | 0 | 0
2 | Warley, Oxenhope, Midgley and Thornton | 344 |  |  |  | 0 | 0 | 0 | 0

## Dwarf Shrub Plug Planting
Information |  |  | Dwarf Shrub Plug Planting |  |  |  |  | Grand Total
Package | Site | No. Units - Hectares (2500 per ha) | No. Plugs planted per person per day | No. Staff on site per day | Unit Rate planting per Ha | Total Cost | Number of days to complete | Total | Total number of days
1 | Heptonstall and Widdop | 36 |  |  |  | 0 | 0 | 0 | 0

## Glyphosate Application
Information |  |  | Supply and Delivery of Glyphosate |  |  |  | Spraying of Glyphosate |  |  | Grand Total
Package | Site | No. Hectares | Application Rate per Ha (Litres) | Total No. Litres Required | Unit Cost per Litre | Total Cost | Unit Cost per Ha | Total Cost | Number of days to complete | Total | Total number of days
1 | Heptonstall and Widdop | 36 |  |  |  | 0 |  | 0 | 0 | 0 | 0
Name of glyphosate product to be used
Type of machinery and sprayer to be used
Number of people required for operation
Estimate number of hectares complete per day
Do you hold a certificate of Competence or PA1 and PA2 Qualification?

## Dwarf Shrub Seed Application
Information |  |  | Co-ordinate and Organise Delivery of Dwarf Shrub Seed | Application of Dwarf Shrub Seed |  |  | Grand Total
Package | Site | No. Hectares | Total Cost | Unit Rate per Ha | Total Cost | Number of days to complete | Total | Total number of days
1 | Heptonstall and Widdop | 36 |  |  | 0 | 0 | 0 | 0
Type of machinery and applicator to be used
Number of people required for operation
Estimate number of hectares complete per day

## Rhododendron Clearance
Information |  |  | Supply and Delivery of Glyphosate and adjuvant Mixture B |  |  |  | Removal of Rhododendron and Spraying of stumps |  |  | Grand Total
Package | Site | No. Hectares | Application Rate per Ha (Litres) | Total No. Litres Required | Unit Cost per Litre | Total Cost | Unit Cost per Ha | Total Cost | Number of days to complete | Total | Total number of days
1 | Heptonstall and Widdop | 22 |  |  |  | 0 |  | 0 | 0 | 0 | 0
Name of productS to be used
List of equipment and sprayer to be used
Number of people required for operation
Estimate number of hectares complete per day
Do you hold a certificate of Competence or PA1 and PA6 Qualification?

## Fencing
Information |  |  |  |  | Supply of Fencing Materials |  |  |  |  | Transportation of Materials onto site | Installing Fencing |  |  |  |  | Grand Total
Package | Site | No. Metres | No. Stiles | No. Field Gates | Unit cost per Metre Wire and Posts | Unit Cost per item for stiles | Unit Cost per Item for Field Gates | Total Cost | Number of Days to deliver all materials to site | Transportation of Materials onto site | Unit cost per Metre Wire and Posts | Unit Cost per item for stiles | Unit Cost per Item for Field Gates | Total Cost | Number of Days to deliver all materials to site | Total | Total number of days
1 | Heptonstall and Widdop | 3036 | 12 | 3 |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0