# BANKING SERVICES AGREEMENT

SCHEDULE 6.3 | Projects and Ordering

Schedule 6.3 | Projects and Ordering

## DEFINITIONS

In this Schedule, the following definitions shall apply:

| “Benchmark Review” | has the meaning given in Schedule 7.3 (Value for Money) |
| --- | --- |
| “Estimate” | has the meaning given in paragraph 11 below; |
| “Intended Project” | means a Project proposed by either Party which is under consideration by the Parties but for which a Project Work Order is yet to have been executed by the Parties; |
| “Project Initiation Process” | has the meaning set out in Paragraph 3.1 of Schedule 6.3 (Projects and Ordering); |
| “Project Request” | means a request for a Project issued in accordance with Paragraph 3.1 of Schedule 6.3 (Projects and Ordering), the format of which is set out in Annex 3 of Schedule 6.3 (Projects and Ordering) (or equivalent); |
| “Project Work Order” | means a written document setting out details of each Project in such form as may be agreed between the Authority and Supplier from time to time, the format of which is set out in Annex 1 of Schedule 6.3 (Projects and Ordering) (or equivalent); |
| “Rough Order of Magnitude” or “ROM” | has the meaning given in paragraph 4.1 below; and |
| “Supplier Proposal” | means a proposal issued by a Supplier in accordance with Paragraph 5 of Schedule 6.3 (Projects and Ordering) the format of which is set out in Annex 2 of Schedule 6.3 (Projects and Ordering) |

## INTRODUCTION

This Schedule sets out the principles and procedures applicable to the proposal, agreement and implementation of Projects.

## PROJECT REQUEST

### The Authority or the Supplier may from time to time during the Term or any Transition Assistance Period issue a Project Request to the other Party which shall initiate the process of Project consideration as described in Paragraphs 5 and 6 of this Schedule (“Project Initiation Process”).

### Each Project Request shall, unless otherwise decided or agreed by the Authority, be in accordance with the structure outlined in Annex 3 (Project Request) and shall include the following (to the extent relevant):

#### a brief context, identifying the positioning of the Intended Project in the Authority's strategy, targets and objectives;

#### a detailed and unambiguous statement of the requirements for the Intended Project (including scope);

#### the charging basis proposed for the Intended Project;

#### any known technical, time or any other constraints;

#### key assumptions and any known risks;

#### the success criteria proposed for the Intended Project (including user acceptance testing where appropriate);

#### any anticipated dependencies;

#### the desired level of progress reporting; and

#### those parts of the Authority's gated review process which the Authority or the Supplier (as applicable) anticipates will apply to the Intended Project.

### The Authority may at its discretion, at any time prior to the execution of a Project Work Order for an Intended Project terminate the Project Initiation Process for such Intended Project by providing written notice to that effect to the Supplier.

### The Party receiving the Project Request shall provide the Party which has issued the Project Request with written details of any failings of a Project Request to comply with the requirements of Paragraph 3.2 and the Parties shall seek to agree the most appropriate means of remedying such failures.

## ROUGH ORDER OF MAGNITUDE REQUEST (ROM REQUEST)

### Where requested by the Authority, the Supplier shall provide the Authority with a high-level rough order of magnitude estimate of the total charges for implementing a Project Request (“Rough Order of Magnitude” or “ROM”) within five (5) Working Days of receiving such a request or within such timescale as may otherwise be agreed in writing between the Parties.

### For each ROM, the Supplier shall provide a reasonable level of detail explaining the basis for the ROM and any assumptions that apply to the ROM.

## PROJECT REQUESTS AND SUPPLIER PROPOSALS

### Where the Authority has issued a Project Request, the Supplier shall provide to the Authority a Supplier Proposal within such time period as is reasonably requested by the Authority (taking into account the nature and complexity of the Project Request in question).

### Where the Supplier has submitted a Project Request, the Authority shall notify the Supplier whether it wishes to receive a Supplier Proposal from the Supplier and shall (acting reasonably) specify the date by which the Authority requires receipt of the Supplier Proposal (taking into account the nature and complexity of the Project Request in question).

### Each Supplier Proposal shall, unless otherwise agreed by the Authority, be in accordance with the structure as outlined in Annex 2 (Supplier Proposal). Each Supplier Proposal shall be clear and unambiguous and set out, in sufficient detail to allow a preliminary assessment by the Authority of the relevant Intended Project, the following information as a minimum:

#### outline approach, work breakdown structure (i.e. the appropriate phases, key deliverables, timescales and estimated number of each type of resource required), and Project Plan;

#### an Estimate of the expected charges to the Authority for delivering the Project which will be prepared in accordance with paragraph 11 below;

#### the identity of any Sub-contractors who will be utilised and/or who will be impacted in the delivery of the Intended Project;

#### key assumptions (including any cost assumptions) and anticipated risks and contingency;

#### Authority dependencies (if any);

#### an assessment as to whether:

##### any element of the services which would be required in respect of that Intended Project are already being provided by the Supplier under this Agreement;

##### the Supplier’s assessment is that the Intended Project would be best delivered by an alternative means and, if so, details of the Supplier’s recommendations as to the most appropriate means of delivery for the Intended Project; and

##### the options upon which the Supplier could price and charge for undertaking the Intended Project (where relevant by reference to Schedule 7.1 (Charges and Invoicing)) and the charges which would be payable by the Authority in respect of the Intended Project under each such option.

#### any proposals in respect of funding or alternative pricing or new pricing mechanisms that the Supplier wishes the Authority to consider;

#### comments upon the success criteria proposed by the Authority or the Supplier for the Intended Project;

#### any comments of the Supplier upon the gated review process proposed by the Authority or the Supplier for the Intended Project in question; and

#### outline details of the possible impact of the Intended Project upon the Transition Plan together with details of the Supplier's recommendations for addressing such possible impact.

### Each Supplier Proposal shall, where requested by the Authority, include details (including names of individuals) of the resource profile the Supplier intends to use to deliver the Intended Project to the extent that the Supplier is able to provide such information having regard to:

#### the length of time between the date of the Supplier Proposal and the proposed start date of the Intended Project; and

#### the duration of the Intended Project.

#### The names of individuals are provided for assurance purposes only and shall not be included within the relevant Project Work Order. The Supplier shall be entitled to change the resource profile unless the Parties have agreed to use specific key named individuals.

### Where any Supplier Proposal fails to set out in sufficient detail the information required by Paragraphs 5.3 and 5.4 to enable the Authority to carry out its initial assessment of an Intended Project, the Supplier shall remedy any such failing within such timescales as are reasonably requested by the Authority.

### The Authority may require the Supplier to conduct a Benchmark Review of any Supplier Proposal, such Benchmark Review to be conducted in accordance with Schedule 7.3 (Value for Money).

## PROJECT WORK ORDERS

### Following review of a Supplier Proposal, the Authority shall within a reasonable period notify the Supplier whether the request is to be dealt with under the Change Control Procedure or as an Intended Project. If the request is considered to be a Project, the Authority will confirm whether it wishes to consider the Project further, and if so shall authorise the Supplier to produce a draft Project Work Order.

### Following the notification under Paragraph 6.1 and within such reasonable time period as may be agreed by the Parties (or where the Parties cannot agree, such reasonable time period as is determined by the Authority), the Supplier shall with the reasonable assistance of a nominee or nominees appointed by the Authority, produce a draft Project Work Order for agreement by the Authority.

### Each Project Work Order shall, unless otherwise agreed by the Parties, be in accordance with the structure as outlined in Annex 1.

### The Authority may request changes to a relevant draft Project Work Order. In these circumstances the Supplier shall submit a revised draft Project Work Order as soon as practicable after the change is requested. This process shall be repeated as necessary until a draft Project Work Order is agreed by the Authority, as confirmed by the Authority Representative providing written confirmation that such draft Project Work Order is agreed.

## PROJECT COMMITMENT

### Neither Party shall become contractually committed in respect of any Project unless and until such time as a Project Work Order has been executed by both Parties.

## PROJECT KICK OFF

### Following the agreement of a Project Work Order, a Project kick off meeting shall take place between the Parties prior to any work being undertaken on that Project (unless the Parties agree otherwise).

## CHANGES TO AGREED PROJECT WORK ORDER

### Following the agreement of any Project Work Order, any changes to such Project Work Order proposed by either Party shall only become effective once they have been agreed by both Parties in writing.

## COSTS

### Save as may be otherwise provided in this Schedule, each Party shall be responsible for its own costs (including those of its related third parties) incurred in proposing, preparing, discussing, negotiating and agreeing any Project up to and including the point at which a Project Work Order is agreed for that Project.

## ESTIMATES

### Where this Schedule 6.3 (Projects and Ordering) makes reference to the Supplier providing the Authority with an estimate, the Supplier shall provide such an estimate on either or both of a fixed price and time and materials basis as requested by the Authority including, where required by the Authority, providing full and accurate detail as to:

#### the impact, if any, of the proposed changes to service provision and the Charges;

#### the rates which the Supplier proposes will apply in relation to the Project (by supplying a rate card), and any standard rate card which the Supplier holds for the same or similar services;

#### the number and seniority of Supplier Personnel required to deliver the relevant Project; and

#### the man hours or man days required to deliver the relevant Project,

#### (“Estimate”).

### If requested by the Authority, the Supplier shall provide reasonable details of the methods it has used to produce the Estimate.

### The Supplier shall promptly notify and discuss with the Authority any errors, omissions, contradictions or ambiguities in an Estimate of which it becomes aware.

## AUDIT OF A PROJECT

### Without limitation to the Authority's rights under Schedule 7.5 (Audit Rights), the Authority reserves the right to verify throughout each Project that the level of skill and experience of individuals assigned remains consistent with the Estimate for the Project. The Supplier shall provide to the Authority such information as the Authority may reasonably request to enable it to exercise its rights under this Paragraph 12.

## PRECEDENCE

### In the event and only to the extent of any inconsistency between any agreed term of any Project Work Order and any term of this Agreement then the term of this Agreement shall prevail.

### Annex 1 | Template Project Work Order

TEMPLATE PROJECT WORK ORDER (Reference Number: [Insert reference number])

- Introduction

  - This Project Work Order constitutes an addition to (and to the extent detailed in this Project Work Order a change) to the agreement between the [insert Authority name] (“Authority”) and [insert Supplier name] (“Supplier”) (“Agreement”) from the date of the execution of this Project Work Order.

  - Save as may be otherwise provided in this Project Work Order, defined terms and phrases set out in the Agreement shall apply to this Project Work Order. In the event of any contradiction between the terms of this Project Work Order and the terms of the Agreement, the terms of the Agreement shall take precedence.

  - In this Project Work Order, references to "Sections" are to sections contained within this Project Work Order.

- Description and consequences of Project Work Order

  - This Project Work Order is for the delivery of [name of project] Project.

  - This Project Work Order contains the following sections, each of which must be completed by the Supplier if requested by the Authority:

    - Project/Programme Name

    - Linked Project Work Orders

    - Project Manager

    - Service Line/Delivery Group

    - Commencement Date

    - Business Context Document

    - Authority requirements

    - Supplier Solution

    - Project Plan

    - Milestones

    - Supplier Team Structure

    - Authority Responsibilities

    - Estimation Model

    - Charging Mechanism

    - Invoicing Schedule

  - The Business Context Document is set out in Section 6.

  - The Milestones Criteria are set out in Appendix A.

  - The Authority Project Requirements are set out in Appendix B.

  - The Supplier Solution is set out in Appendix C.

  - The Estimate is set out in Appendix D.

Project Work Order

| # Project Reference Number: |  |
| --- | --- |

| The Parties hereto, each by a duly authorised representative, have executed this Project Work Order as of the date set out below and this Project Work Order is effective as of the Commencement Date set out in section 5: |  |
| --- | --- |
| Authority | Supplier |
| By: | By: |
| Signed: | Signed: |
| Title: | Title: |
| Date: | Date: |

| 1 | Project Name / Description of Project |  |
| --- | --- | --- |
|  | Project Name: | Programme Name: |
|  | Description of Project |  |

| 2 | Linked Project Work Orders |  |  |
| --- | --- | --- | --- |
|  | PWO Reference | PWO / Project Name | Date |

| 3 | Project Managers |
| --- | --- |
|  | Authority Project Manager |
|  | Supplier Project Manager |

| 4 | Lead Service Line / Delivery Group |
| --- | --- |

| 5 | Key Dates |  |
| --- | --- | --- |
|  | Project Commencement |  |
|  | Live Implementation Date |  |

| 6 | Business Context Document |
| --- | --- |
|  | The Business Overview attached hereto provides a description of the project that can be shared with the Authority. |

| 7 | Authority Project Requirements |
| --- | --- |
|  | Sets out the Authority business and technical requirements for the Project. These are set out in Appendix B. This includes the following as the case may be: Business Requirements Non Functional Requirements Technical/ Product Requirements Required Timelines Milestones (where relevant) Any other specific requirements |

| 8 | Supplier Solution |
| --- | --- |
|  | Sets out the Supplier's solution that is being contracted for, specifying its key components. |

| 9 | Project Plan |
| --- | --- |
|  | - The below plan gives an overview of the plan for the Project as agreed by the Authority and the Supplier including milestones and links to other Projects |

| 10 | Milestones Description of the deliverables should be documented in Appendix A |  |  |  |
| --- | --- | --- | --- | --- |
|  | Stage /Phase | Milestones | Date | Delay Payments (against LID) |
|  |  | [Milestone X1] |  |  |
|  |  | [Milestone X2] |  |  |
|  |  | [Milestone X3] |  |  |

| 11 | Supplier Team Structure and Key Supplier Positions |
| --- | --- |

| 12 | Authority Responsibilities |  |  |
| --- | --- | --- | --- |
|  | Responsibility | Date Required | Impact of Not Delivered |

| 13 | Estimation Model |  |
| --- | --- | --- |
|  | The Supplier has completed the Estimation Template (yes/no) |  |
|  | Reference for Estimation Template |  |
|  | Reference for Document (if applicable) setting out basis for Experience based Estimate. |  |

| 14 | Charging Mechanism |  |
| --- | --- | --- |
|  | - Man-Day Pricing (Pure T&M) |  |
|  | T&M waterfall delivery |  |
|  | Team Run Rate (T&M) |  |
|  | Fixed Price with Milestones |  |

| 15 | Invoicing Schedule for Fixed Price with Milestone Payments (as part of a fixed price) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Date | Milestone | Milestones Payment | Monthly payment | Total Charges Due |
|  | [date] of [Month] | [Milestone X1] |  |  | [Month’s charges] OR [amount] |
|  | [date] of [Month] | [Milestone X2] |  |  |  |
|  | [date] of [Month] | [Milestone X3] |  |  |  |
|  | Total Project Work Order Charges |  |  |  | [Amount] [Fixed] |

| 16 | Estimated Monthly Invoicing Schedule for T&M This box specifies the estimated payments will become due under this Project Work Order for T&M Projects. |  |
| --- | --- | --- |
|  | Date | Estimated Charges |
|  | [date] of [Month] | [Month’s charges] [amount] |
|  | [date] of [Month] |  |
|  | [date] of [Month] |  |
|  | TOTAL T&M Charges | [Amount] [Estimated] |

# APPENDIX A | Milestones Criteria

| 16 | Milestones Criteria The table below sets out the criteria and due date for each Milestone. |  |  |  |
| --- | --- | --- | --- | --- |
|  | Milestone | Deliverable Name | Date Due | Criteria |

# APPENDIX B | Authority Project Requirements

- [Insert]

# APPENDIX C | Supplier Solution

- [Insert]

APPENDIX D | Estimates

- [Insert]

ANNEX 2 | Supplier Proposal

TEMPLATE SUPPLIER PROPOSAL (Reference Number: [Insert reference number])

| 1 | Title of Intended Project | [Insert title of Intended Project.] |
| --- | --- | --- |
| 2 | Originator | [Insert name of originator.] |
| 3 | Date of Supplier Proposal | [Insert date of Supplier Proposal.] |

- Introduction

  - This Supplier Proposal has been developed pursuant to the agreement between the [insert name of Authority]  (“Authority”) and [insert name of supplier] (“Supplier”) (“Agreement”).

- Outline Approach

  - [Insert details of the outline approach and proposed work breakdown structure for the Intended Project (i.e. the appropriate phases, key deliverables, timescales and estimated number of each type of resource required)]

- Transition

  - [Insert details of the possible impact of the Intended Project upon the Transition Plan together with details of the Supplier's recommendations for addressing such possible impact]

- Price and Payment and Delay Payments

  - [Insert details of the options upon which the Supplier could price and charge for undertaking the Intended Project, the proposed delay payments and the charges which would be payable by the Authority in respect of the Intended Project under each such option]

  - [Insert any proposals in respect of funding or alternative pricing or new pricing mechanisms that the Supplier wishes the Authority to consider]

- Project Plan

  - [Insert details of the proposed timetable for the Intended Project]

- Success Criteria

  - [Insert comments upon the success criteria proposed by the Authority or the Supplier for the Intended Project]

- Project roles and responsibilities

  - [Insert details of the proposed roles and responsibilities of the Supplier and the Authority in respect of the Intended Project.]

- Resource Profile

  - [Where requested by the Authority, insert details (including names of individuals) of the resource profile the Supplier intends to use to deliver the Intended Project to the extent that the Supplier is able to provide such information]

- Risks, Assumptions and Dependencies

  - [Insert details of:

- Authority dependencies (if any);

- key assumptions (including any cost assumptions) and anticipated risks and contingency; and

- the proposed outline arrangements for risk and issue management]

- Sub-contractors

  - [Insert details of the Sub-contractors who the Supplier proposes will be utilised, and/or who will be impacted, in the delivery of the Intended Project]

- Existing services

  - [Insert details of the Supplier's assessment as to whether any element of the services which would be required in respect of the Intended Project are already being provided by the Supplier under this Agreement]

- Alternatives

  - [If the Supplier’s assessment is that the Intended Project would be best delivered by an alternative means, insert details of the Supplier’s recommendations as to the most appropriate means of delivery for the Intended Project]

- Project reporting

  - [Insert details of the desired level of progress reporting in respect of the Intended Project.]

- Project Governance

  - [Insert details of the proposed governance procedures applicable to the Intended Project and the Authority and the Supplier's obligations in respect of the same]

- Comments upon the Project Request

  - [Insert any comments upon or revisions or additions to the information set out in the Project Request for the Intended Project.]

- Business Change approach

  - [Insert details of the business change required to deliver the benefits of the Intended Project]

ANNEX 3 | PROJECT REQUEST

TEMPLATE PROJECT REQUEST (Reference Number: [Insert reference number])

| 1 | Title of Intended Project | [Insert title of Intended Project.] |
| --- | --- | --- |
| 2 | Originator | [Insert name of originator.] |
| 3 | Date of Project Request | [Insert date of Project Request.] |

- Introduction

  - This Project Request has been developed pursuant to the agreement between the [insert name of Authority]  (“Authority”) and [insert name of Supplier] (“Supplier”) (“Agreement”).

- Strategic Case

[Insert details of:

- the existing arrangements in place in relation to the Intended Project and the positioning of the Intended Project in the Authority's strategy, targets and objectives;

- the objectives and goals of the Intended Project;

- the requirements for the Intended Project (including scope);

- the main benefits of the Intended Project (e.g. cost savings and efficiencies, service delivery improvements, meeting priorities, responding to statutory requirements);

- the anticipated risks if the Intended Project is not implemented; and

- dependencies between the Intended Project and other existing Projects or programmes]

- Proposed charging mechanism

  - [Insert details of the charging basis proposed for the Intended Project by reference to Schedule 7.1 (Charges and Invoicing) (where applicable) and any guidance in respect of funding and/or pricing mechanisms and full details of agreed delay payment mechanism]

- Proposed implementation timescales

  - [Insert details of the proposed implementation timescale]

- Success Criteria

  - [Insert details of the success criteria proposed for the Intended Project (including user acceptance testing where appropriate)]

- Project roles and responsibilities

  - [Insert details of the proposed roles and responsibilities of the Supplier and the Authority in respect of the Intended Project.]

- Risks, Assumptions and Dependencies

[Insert details of:

- any anticipated dependencies;

- any known technical, time or other constraints;

- key assumptions and any known risks; and

- the proposed outline arrangements for risk and issue management]

- Project reporting

  - [Insert details of the desired level of progress reporting in respect of the Intended Project.]

- Project Governance

  - [Insert details of the proposed governance procedures applicable to the Intended Project and the Authority and the Supplier's obligations in respect of the same.]