## Appendix A Project Plan
Kettering HAZ Cultural Programme 'What’s in a Name' Project Plan
|  | Year 1 2021 | [11 empty] | Year 1 2021 | Review period | Year 2 2022 | [11 empty] | Review period | Year 3 2023 | [11 empty] | Review period | Year 4 2024 | [11 empty] | Impact report and review
|  | Launch Year | [11 empty] | Pilot year |  | Engaging Audiences | [12 empty] | Celebrating the High Street | [12 empty] | Reflection and future
| Key objectives | Develop an event delivery framework and strategy for all members. Test the programme, build the consortium membership, consolidate existing partners and forge new links to other organisations to assist the group to meet our shared objectives. | [13 empty] | Strengthen audiences, widen participation and reach, raise awareness of HAZ and mark the opening of the GLaM project | [12 empty] | A celebration of the high street, drive footfall to the town centre through a diverse cultural programme of activities for the whole community and beyond. Complete a review of funding opportunities for year 4 and beyond. | [12 empty] | Reflect and consolidate the cultural network of organisations. Review ongoing cultural strategies and funding opportunities to continue and build capacity for the consortium and implement new strategies as required
| HAZ capital works key milestones | Public realm contractor appointment and construction, Street scene procurement. Residential conversation/shopfront improvements | [13 empty] | Public realm and street scene completion. Residential conversions, shopfront improvements, Mosaic launch | [12 empty] | Public realm and street scene in use with Mosaic displayed | [12 empty] | HAZ impact report and ongoing strategy review, capital programme closes
| Quarter | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Strand | Activity
FOAGM Historic Guided Tours ; Town and Cemetry | bar: Q1 2 to Q2 4; Q3 7; Q4 10
FOAGM Interactive Heritage Trail | bar: Q3 8 to Q4 12
FOAGM Heritage Festival and History Day
Heritage | Picture the Difference: The Knibb Talks | bar: Q3 7 to Q4 10
Wicksteed Park Regatta
Wicksteed Park 'By the Sea' @Play Festival | bar: Q1 3 to Q2 5
Picture The Difference The Name We Call Ourselves | bar: Q2 6 to Q3 9
Picture the Difference Planting and Dancing Shoes | bar: Q2 5 to Q3 8
Creative | The consortium @ KETT-FEST commission TBC
Wicksteed Park Busking Trail @ Kett-fest | bar: Q2 4 to Q3 7
KCS Art in the Town with Wicksteed Park and guest curator Carole Miles | bar: Q1 3 to Q4 12
KDAS Summer Exhibition @ ArtWorks with FOAGM | bar: Q1 3 to Q3 7
Wicksteed Park Art in the Park @ Kett-Fest
KBC Bands in the Park | bar: Q2 4 to Q3 7
GLaM opening
Film | KCS The story of the Mosaic : documentary with delivery partner UK Film School | bar: Q1 3 to Q4 12
Wicksteed at War Film community film event | bar: Q2 4 to Q2 6
| KCS launch: Opening of the Mosaic, HAZ zone in partnership with the HAZ project | [14 empty] | Programme TBC with HAZ
Wicksteed Park Soap Box Derby
Consortium volunteer initiative led by FOAGM/WP + delivery partner Tresham and MDEM | bar: Q1 3 to Q3 9
KBC Play days | bar: Q2 4 to Q4 12
Consortium commission : Made with Many - Community pop up shop and exhiibition | bar: Q2 4 to Q3 8
Community | Consortium volunteer celebration weekend/recruitment drive led by WP | bar: Q2 4 to Q2 6
KBC Christmas Light Switch on | bar: Q3 8 to Q4 12
Wicksteed Park's Alternative Olympics "It's a Knock out!" | bar: Q2 4 to Q3 7
Wicksteed Park Play Festival 2022
KBC Easter Trail | bar: Q1 1 to Q2 4
Planning/Commissioning
Set up
Activity
New programme content
Enhanced existing programming
Existing programme with new collaborations between members

## Appendix B Outputs
Kettering What's In a Name Cultural programme outputs
|  |  | Number of sessions/events per year |  |  | Timescale |  | Engagement categories and numbers | [7 empty] | Partnership
Activity | Description | Output | Year |  |  | Start date | End date | Professionals per annum | Participants per annum | Audience physical per annum | Audience Digital per annum | Total audience | Success criteria | Monitoring and Evaluation | Community engagement and Marketing | Delivered by
|  |  | 1 | 2 | 3
FOAGM Interactive Heritage Trail | Interactive QR codes to be linked to mounted plaques around the town centre. Link to HAZ project who have also plans for interactive points as part of the public realm and street scene updates. The project is based on the very successful Monmouth Interactive heritage trail as the first Wikimedia town. Raising awareness of Kettering's significant heritage as a non-conformist town and link to the shoe and boot industry. Free for all users. Opportunity for local business's to invest and become one of the points of interest within the trail highlighting what shop units were previously used for and what they offer now. Which points of interest will be consulted on in the first two years with partner organisations and via the Community pop up shop's engagement strand. FOAGM also deliver a programme of town and cemetery tours which will utilise the heritage trail route. HAZ have run a pilot scheme via local schools to raise awareness of the local area for younger generations, the feedback from this pilot scheme will feed into this project in the planning stages. FOAGM existing website will support the technical infrastructure for this programme and discussions underway regarding linking to other members online platforms. Friends of the Art Gallery and Museum to coordinate and deliver this event with support from the Manor House Museum, Northampton Heritage Forum, Kettering Civic Society, Kettering Council, HAZ project and Kettering's Business Town Partnership. Kettering Station. | Up to 50 notable points of interest to be connected via this Heritage Trail from past and present. This project will be a permanent contribution to the heritage of the town for many years to come. Raises awareness of local heritage and what makes Kettering unique. Engages a wide range of audiences from schools to families to older generations who have links to these touch points and drives footfall to the town centre for both the local community and visitors from further afield. Engages FOAGM and Northamptonshire Heritage Forum volunteer pool as well as the consortium volunteer pool. |  |  |  | Research to commence in the first quarter of 2021 with the technology and first set of plaques to be delivered by Autumn 2021 and the second set due for Autumn 2022 post community consultation |  | 10 professionals, historian, printer, digital support and marketing | 20 in the planning/commission phase | 5000+ per annum | 5000+ per annum | 30,030+ across the three years and beyond | Engages the community and changes their perception of Kettering and what makes their town unique. Drives footfall to the town centre for both locals and visitors. Raises awareness of the local heritage of the town centre and HAZ/GLAM projects/widens audience reach and is accessible to any smartphone user. Creates a clear legacy for Kettering. Reduces social isolation by offering an engagement opportunity for volunteers | Website /QR codes monitoring. Ability to monitor which sites are of most interest for the programme. Community pop up shop will be used to provide feedback on the heritage trail. FOAGM to provide a yearly report of data collated from the website. Opportunity to link to the Audience agency if postcodes are collated TBC during the planning phase of the project | Branding and social media support built into the consortium budget. FOAGM have an existing website platform which received 1000+ hits per month. Plaques themselves will raise aware and community engagement strand to be delivered as part of the yearly community pop-up shop where the final points of interest are to be decided via a community consultation/panel process. Discussions with KBC and the Manor House Museum underway for when GLaM opens in 2022. KBC What's On Guide feature planned. | Friends of the Art Gallery and Museum with support from the consortium members, Northamptonshire Heritage Forum, Kettering Town Partnership, HAZ project team, Kettering station
Picture the Difference Knibb Talks | A series of yearly storytelling events to promote inspirational autobiographical 10 minute stories from a range of people in the local community. Inspiration for this event comes from TED Talks and The Moth storytelling events in the USA. The first event will be mostly known storytellers and spoken word performers, however, in the run up to the event, some members of the public will be invited to 'pitch' their story ideas and then get a chance to hone their story content and delivery skills through participating in one of six writing workshops. Run in conjunction with Youthworks who have strong links with the local BAME and LGBTQ communities. Each series will focus on different community groups The event will be to a live audience but recorded and edited for later viewing online. An audience Q&A session may follow. The event will be transmitted via community radio Revolution Radio FM in Northampton - either live or as a featured podcast - and possibly streamed live online via PTD social media platform. The audience for this event will reflect the theme of each session and whose stories we are telling. | Six writing /delivery workshop and two events for audiences. Radio broadcast and social media streaming on existing PtD platform. Volunteer opportunity. | 8 | 8 | 8 | October each year date TBC |  | 2 x PtD/Youthworks Creative Professionals plus 2 x Storytelling/Poet Professional = 4 | 20 x storytellers | 120 | 2000 | 6432 | All Picture the Difference creative events promote positive well-being and fun. Raises awareness of local stories from the local area connecting people to places. Raises awareness of local heritage and history and those communities that live within it. Widening participation by engaging members of the community and sharing stories from all people across backgrounds, religions, ethnicities, gender, sex | Consortium template for audience and workshop feedback to be collated by PtD as part of the monitoring this will include data on numbers, demographic and audiences will be asked to rate their experience in a simple, fun visual way without intruding on their evening out. Existing social media platforms monitored and feedback requested. If numbers and feedback is successful ambition to roll these events out more regularly. PTD report post event which monitors numbers, demographics, feedback and engagement levels and looks for opportunities to expand the programme | Branding and social media support built into the consortium budget. PtD have an existing website and active social media platforms. Community curation and co-creation is at the fore-front of what PtD already deliver, they will engage different communities and widen reach by delivering this event with Youthworks who will also use their social media platforms to connect with audiences and potential participant groups. KBC What's on Guide and 'This is Kettering' website. | Picture the Difference in partnership with Youthworks
Wicksteed Park Regatta | Wicksteed Park Regatta is a Centenary celebration event which was last delivered in 1921. A big celebration weekend to mark the parks centenary which includes re-enacting the regatta, water based activities including rowing competitions, swimming, water polo, rowing lessons. Traditional country fayre atmosphere, picnics, performance and heritage imagery. Community stands for WI, Grow you own, Gardens Trust, Sea Cadets. A carnival float and other town centre activities will connect the town to the park. This is a large event which is funded through the WP budgets but requires specific support being sought to allow community groups to participate without any entry fee barriers. This event will bring in families, older generations who wish to reminisce, boating enthusiasts and those connected to the community groups involved. | Full day event which celebrates the centenary year of Charles Wicksteed and Wicksteed Park. Raises awareness of the significant contribution Charles Wicksteed made to the local area as well as to children all over the world, engineering and nature. Widens participation in engaging various community groups to park activities. Builds capacity in linking various community groups including the sea cadets, rowing club. Women's institute, Grow Your own and engages WP existing volunteer pool. | 20 activity sessions |  |  | August 23rd/24th 2021 |  | 20 | 200 | 5000 | 1000 | 6220 | Drives footfall to Kettering and Wicksteed Park, raises awareness of Wicksteed Parks significant history and heritage, encourages partnership working with other local groups, upskill opportunity with WP rowing lessons offered, promotes community engagement and health and well being. Reduces social isolation for visitors and WP existing volunteer pool. | Consortium template for audience and workshop feedback to be collated by WP team as part of the monitoring requirements, this will include data on numbers and demographics, engagement and participations and audiences will be asked to rate their experience in a simple, fun visual way without intruding on their day out. WP park also generate data on general spend per head during large scale events via the car park and cafe operations. Existing social media platforms monitored and feedback requested. | Branding and social media support built into the consortium budget. WP have an existing website and active social media platforms as well as links into many local community groups who use the park for various activities. KBC What's on Guide and 'This is Kettering' website | Delivered by Wicksteed Park Community and Education department as part of a wider programme in partnership with the local Sea cadets. Women's Institute, Kettering eco group, greenpatch. Gardens trust. Pet / dog show. Animal shelter
Consortium Commission: Community Pop-Up town centre. Year one delivery partner Made with Many: Exhibition Card -Board Town | An empty shop takeover, showcasing new work co-created with local communities, work of cultural consortium members and local voluntary arts groups. The focus of this will be 'Made in Kettering' utilising local talent. Open for 3-4 days a week over a 4-week period. Year 1 will test a variety of different approaches and event styles (a mix of exhibitions, talks and workshops) dependent on what is feasible within COVID restrictions, and use that learning to build a programme for years 2 & 3. Year 1 will have a thematic focus on oral histories, (memories of the town centre etc) and include one artist commission (selected by a community panel inc the consortium from an open call) to work with local community groups and schools to create a flagship exhibition/installation around the 'card-board town' theme. Themes for further years will be developed through consultation. Exhibition could also have an online 'highlights' for those unable to attend in person. The shop in general will play a pivotal role in delivering community engagement for the consortium programme and membership. It will also be used to link to the HAZ community engagement workstream to ensure both projects are well connected and communicated to the wider community. A wall will be curated to demonstrate consortium event feedback each year in the style of the 'Peckham Peace Wall' as a visual demonstration of what has been achieved. Signposting to other key partners and health and well-being initiatives to be present. Years two and three delivery partner to be confirmed. Opportunity to integrate local business's within a community panel to inform years 2/3 pop up programme. Volunteering opportunities for the Consortium volunteer initiative. Made with Many have been selected as the delivery partner for this event due to their experience at reaching audiences in areas of lowest engagement. | Estimated to host 10 co-creation workshops, 16 exhibition days, 4 shop events per year. Acts as the central point for community engagement for years 2/3 programming and commissions. Drives footfall to the town centre and creates a clear link to the HAZ project and programme of work. Volunteer opportunity. | 30 | 30 | 30 | July/August during school holidays |  | 1 commissioned local artist, 6 artists/facilitators, 2 MWM producers= 9 total | 350 | 2000 | 1500 | 11577 | Focus on Made in Kettering and celebrating local talent, raising awareness of what makes Kettering unique and the organisations that contribute to this. Connection to the HAZ project and raising awareness of the culture led regeneration process and projects. Widening participation utilising MWM's existing connections into harder to reach communities. Engagement with the town centre business owners. Drives footfall to the town centre aiding post covid recovery and demonstrates why the high street and it's visitors are pivotal in future-proofing is a thriving local community. Volunteer opportunity for the consortium training initiative/reduces social isolation. | Post pop up consortium evaluation and feedback collation via MWM who will collate data on levels of engagement/audience numbers, demographics of audiences/participants /perception of town centre and what local communities and visitors ambition for the town centre is. MWM to collate postcodes for visitors to the shop and feedback key data on audience demographics for comparison each year for the community pop up. | This pop up will form a key part of the over-arching consortium programme, involving the community in decisions that relate to the following year's programme for instance what the theme of the pop up shop will be for years 2/3. What commission they would like to see for Kett-fest in years 2/3. What points of interest do they wish to be included in the Interactive Heritage Trail. Raising awareness of the story of the Mosaic in advance of its unveiling in Meadow Road as part of the HAZ project. Raising awareness of the regeneration works to the town centre, public realm and GLaM projects and signposting to local business, consortium members and partners. The pop up shop will form a key part of the consortium PR strategy, supported by the branding/social media resource and member/partner existing online platforms. KBC to support and showcase this event in the local 'What's on' guide and 'This is Kettering' website. | Consortium members, Made with Many, HAZ project
Wicksteed Park 'By the Sea' @Play Festival | This is another event in the wider Wicksteed centenary celebration programme to mark the official opening of the park in May 1921. The wider event focuses on the playground and lake which will involve street performances, talks and an art installation by local artist Susan Williams. National press involvement and opening of heritage play equipment based on Charles original designs. Budget for additional frames and print costs for displays in the station and town centre. | Three days of events and activities including 10 workshops and 8 activity sessions with wider ' do it yourself' participation opportunities. Volunteer opportunity. | 18 |  |  | 29th-31st May |  | 20 ( comprise artists, performers, designers, Wicksteed leisure designers input) | 1000 | 5000 | 500 | 6520 | Drives footfall to Kettering and Wicksteed Park, raises awareness of Wicksteed Parks significant history and heritage, promotes community engagement and health and well being. Reduces social isolation for visitors and WP existing volunteer pool. | Consortium template for audience and workshop feedback to be collated by WP team as part of the monitoring requirements, this will include data on numbers and demographics, engagement and participations and audiences will be asked to rate their experience in a simple, fun visual way without intruding on their day out. WP aim to ascertain whether visitors visit both WP and town or only WP when visiting. WP park also generate data on general spend per head during large scale events via the car park and cafe operations. Existing social media platforms monitored and feedback requested. | Branding and social media support built into the consortium budget. WP have an existing website and active social media platforms as well as links into many local community groups who use the park for various activities. KBC What's on Guide. | Consortium members, NHF, Consortium volunteer initiative
Picture the Difference 'The name we call ourselves' @Kett-fest | The PtD band will perform a live set from their themed project 'The Names We Call Ourselves'. The band promotes inclusivity whilst supporting performers with additional needs. This content will support creation of some original material for the band to adopt as part of their repertoire. The theme wish reflects on stories of the past but uses music to tell stories for the future with younger members of the community. The band has a wide reach including family and friends, music enthusiasts and the local creative community. All songs are based on identity, breaking free of negative labels that people give you, and reclaiming your name. Will form part of the Kett-fest line up | One annual performance, linked to Kett-fest. Volunteer opportunity. | 3 |  |  | July |  | 3 | 8 | 120 | 500 | 1893 | Drives footfall animates the town centre and aids post covid recovery. All creative events promote positive well-being and fun. Audience numbers. Builds PtD participant creatives self- esteem and sense of purpose and value in their community. Raises awareness of local talent, diversity and disability awareness. | Consortium evaluation data collection, audiences will be asked to rate their experience in a simple, fun visual way without intruding on their day out. Existing social media platforms monitored and feedback requested. If numbers and feedback is successful ambition to roll these events out more regularly. PtD report post event which monitors numbers, demographics, feedback and engagement levels and looks for opportunities to expand the programme | Branding and social media support built into the consortium budget. PtD have an existing website and active social media platforms. Kett-fest programme. KBC What's On guide distributed to town postcodes.and 'This is Kettering' website | Pitch the Difference / Kett-fest/consortium members
Pitch the Difference; ' Planting and Dancing shoes' | This event will take place in the Market Place in Kettering's town centre raising awareness of Kettering's significant connection to the shoe and boot industry. The public can come along to plant up a shoe with flowering plants and then take it away with them or leave it to decorate the square. Alongside this there will be a clog dancing demonstration and workshop for those interested - one in the morning and one in the afternoon. In addition, local shops will be asked to display their pre-prepared planted shoes or boots at the shop door and/or in the window. They will have received ideas on how to do this prior to the launch. The shoes should reflect the personality of the shop. Children and families can be encouraged to go on a shoe hunt to find all the shoes on display with a small prize on completion. The event wil appeal to gardening and dancing enthusiasts as well as children, families and those that remember the shoe and boot industry. Green-patch noted as a possible partner | A launch day event with a two week display period around the town in local business's. Could be linked to Kett-fest TBC. Volunteer opportunity. | 15 days |  |  | Summer 2021 date TBC with KBC |  | 3 | 84 | 1000 | 200 | 1287 | All creative events promote positive well-being and fun. Drives footfall to the town centre, raises awareness of the connection to the shoe and boot industry and consortium. Promotes partnership working with partners. Consortium volunteer opportunity. | Consortium evaluation data collection, audiences will be asked to rate their experience in a simple, fun visual way without intruding on their day out. Existing social media platforms monitored and feedback requested. If numbers and feedback is successful ambition to roll these events out more regularly. PtD report post event which monitors numbers, demographics, feedback and engagement levels and looks for opportunities to expand the programme | Branding and social media support built into the consortium budget. PtD have an existing website and active social media platforms. Kett-fest programme. KBC What's On guide/ This is Kettering website. | Pitch the Difference / Kett-fest/ consortium members
KETT-FEST Kettering wide festival- multiple venues, various partners | An annual celebration of all Kettering has to offer in one weekend! Local Arts, Culture and Music festival spread over the first weekend in July at various venues and location across the town. Art installations, pop up exhibitions, gigs at various pubs, opening night celebrations at Cafe Bloc with entertainment on the library steps. Saturday - Teenage market, live hosting by Shire Sounds local radio, circus trick workshops, face painting, things to do, dance, singing, spoken word, poetry, theatre performances throughout the day on the Market place. This is a community led festival with many events organised by local pubs , businesses and community groups. The consortium will commission/promote an event each year to connect members and key partners, raise awareness of the consortium programme, HAZ and GLaM projects. Year one will be developed by the consortium members, year two and three programme will be developed with the community panel comprising local businesses and community groups as part of the annual community pop-up shop. The audience reach is wide due to the variety of local shops, bars, restaurants, community groups involved and it happens within the school holidays to ensure engagement will all members of the community. This event drives significant numbers to not only the high street and public realm but all the surrounding business's who are in support and help to promote it. | Three days of rolling events across 30 + venues. Volunteer opportunity. |  | 50 | 50 | Last weekend of July each year |  | 150 Local professionals estimated per annum - including artist, performers, bands, dancers, workshop tutors. | 200 | 10000 | 2000 | 24700 | Drives footfall to the town centre and aids post covid recovery for the high street. Raises awareness of the HAZ/GLaM/Consortium projects. Increase sales for town centre businesses. Creates employment opportunities for a high number of creatives. Volunteer opportunity for the consortium volunteer initiative. Reduces social isolation. Promotes a community led cultural programme and general health and well-being for the town by bringing such a diverse range of content together over a weekend. | Consortium evaluation template to be collected from the consortium event and beyond with the help of volunteers and to inform Year's two/ three strategy. KBC footfall counter data collected. Local business evaluation forms collated. Social media engagement and feedback on members platforms. Volunteers to be utilised to collate feedback each day which will filter into a consortium report. | Branding and social media support built into consortium budget. Kett-fest facebook page utilised as well as member platforms. Years 2 and 3 consortium content/commission to be curated by the community panel within the community pop up shop. | Artists Catherine Matthews, Susan Williams, Wall by Squidge. Performers, bands, dancers, workshop tutors. Party workshops. Local Dance schools. YouthWorks, Picture the Difference, Business Network, Bright Kids, Ground Works, Green patch, Kettering Arts centre, Alfred East Art gallery, Manor House Museum, Churches, Newlands shopping centre, open spaces, gardens and parks.
Wicksteed Park Busking Trail @ Kett-fest | Part of the kett-fest programme. A new event celebrating the wider landscape of the park , showcasing local talent through performance, audiences will explore the park via a busking trail with specific performance sites located around the park. Selection process for access to these spots with a mix of performance art genres expected. Connects Kett-fest to the wider area, expanding its' capacity. | Two days of performances over the Kett-fest weekend. Volunteer opportunity. | 18 | 18 | 18 | Last weekend of July each year |  | 3 | 84 | 1000 | 500 | 4761 | Drives footfall and aids post covid recovery., cultural programme supporting creativity, economic well being of local performers and musicians. Builds confidence for those performance and provides an opportunity to showcase new work. Creates a consortium volunteer opportunity, reduces social isolation. | WP / consortium volunteers to collate visitor feedback using the evaluation template. Audiences will be asked to rate their experience in a simple, fun visual way without intruding on their day out. Existing social media platforms monitored and feedback requested. If numbers and feedback is successful ambition to roll these events out more regularly. WP report post event which monitors numbers, demographics, feedback and engagement levels and looks for opportunities to expand the programme. Car park numbers monitored. | Branding and social media support built into consortium budget. Kett-fest facebook page utilised as well as member platforms. Annual event for WP. | Wicksteed Park, Kett-Fest, local performance groups.
Wicksteed Park Art in the Park @ Kett-Fest | Art at the Park is a selected exhibition of local artists and makers work within the brand new Learning and Exhibition Space. Artists to apply for exhibition space and this will form part of the Kett Fest programme. Budget required to allow an additional 5 artists to display their work. | Two week exhibition. Volunteer opportunity. | 28 | 28 | 28 | Last two weeks of July |  | 3 | 90 | 1000 | 500 | 4779 | Drives footfall and aids post covid recovery. Cultural programme supporting creativity, economic well being of local artists. Builds confidence for those performance and provides an opportunity to showcase new work. Raises awareness of Kettering's heritage and what makes it unique. Consortium volunteer opportunity, reduces isolation. | WP / consortium volunteers to collate visitor feedback using the evaluation template. Audiences will be asked to rate their experience in a simple, fun visual way without intruding on their day out. Existing social media platforms monitored and feedback requested. If numbers and feedback is successful ambition to roll these events out more regularly. WP report post event which monitors numbers, demographics, feedback and engagement levels and looks for opportunities to expand the programme. Car park numbers monitored. | Branding and social media support built into consortium budget. Kett-fest facebook page utilised as well as member platforms. Annual event for WP. | Wicksteed Park, Kett-fest, local artists, KDAS
KCS "Art in the Town" commission with Wicksteed Park and guest curator Carole Miles | An innovative public art project to create a public work of art in the form of vitreous enamel panels to welcome and encourage Tourism to Kettering and to remind people of the life and vitality of a bustling high street. The central motif of each of the 3 panels will be Wicksteed Park in celebration the centenary of its opening as well as Kettering Train station and a location within the town centre. Alongside the installations Carole will produce 8 'how to videos' which will be available online via the WP platform for people that wish to participate in the project and she will also host a series of 8 Zoom “High Tea” online conversations where the public can join and share memories of the Park, the town and the station. The positioning of the panels will create a meaningful link between the importance of industry, travel and leisure to the history of the town. Proposed themes for the artworks include: 1. Landscape and historic structures within the park and possibly the manufacturing works. 2. High days and holidays. 3. Treasured memories, 4. Meetings and greetings, 5. Picnics in the park, 6. Having a ball, 7. Walking the dog, 8. Nature and nurture | Permanent art installations within the town, station and Wicksteed Park. Potential to move to GlaM once opened. Eight zoom workshops. Eight 'how to' videos for various methods of collating memories in various art-forms available for viewing and participation. Public participation / engagement opportunity. | 16 workshops |  |  | August-September 2021 |  | 4 | 48 | 10000 | 500 | 10552 | Drives footfall and aids post covid recovery. Cultural programme supporting creativity, economic well being of local artists. Builds confidence for those performance and provides an opportunity to showcase new work. With the wide themes reaches a diverse range of participants. | Kettering Civic Society /Wicksteed Park to collate consortium evaluation feedback using the agreed template. WP social media platform monitored and feedback requested. Participation numbers to be reported and video views to be collated. | Branding and social media support built into the consortium budget. WP have an existing website and active social media platforms as well as links into many local community groups who use the park for various activities. KBC What's on Guide. | Kettering Civic Society, Wicksteed Park, Carole Miles, KDAS, consortium members
KCS The story of the Mosaic : documentary with delivery partner UK Film School | A major piece of artwork was removed and saved by the Kettering Civic Society approximately 14 years ago. The Mosaic measuring 15 x 45ft future has recently been secured by the HAZ project team, who are currently consulting on the restoration and installation of the mosaic in Meadow Road in the centre of Kettering as part of the HAZ zone capital programme of works. This significant process and moment in history will be captured by delivery partners the UK Film School and made into a documentary film which focuses on telling stories of the mosaics past and those connected to it as well as launching it's future. KCS will also act as advisors regarding historical facts. The film will be available on members online platforms and will be made available within local care homes, schools and community groups. Most of the Kettering community has been touched by this mosaic at some point in their lives and this event will support it's re-launch back into the community for many years to come. Will form part of the yearly exhibition/film showing in the community pop-up shop. | Permanent art installation in the town centre with accompanying documentary for onwards roll out via various platforms. Mosaic artists commission. |  |  |  | Mosaic launch and film launch TBC Summer 2022 |  | 30 mosaic artistic team, UK film School. Local historians | 45 | 20000 | 5000 | 25075 | Drives footfall to the town centre. Engages older generations in local care homes who have memories of the mosaic and school. Raises awareness of Dementia UK.Creates civic pride in the town centre. Commissions a artistic specialism. Raises awareness of local heritage. Opportunity for consortium volunteers, builds confidence and reduces social isolation. | Kettering Civic Society to collate consortium evaluation feedback using the agreed template from Mosaic launch in partnership with HAZ team and from film viewings. KCS social media platform monitored and feedback requested. Town centre footfall to be monitored for launch event and after. | Branding and social media support built into the consortium budget. KBC What's on guide. Link to HAZ communication strategy and community engagement plan. | KCS, HAZ, Consortium members
Wicksteed at War Film community film event | Next year (2021) marks the return after two years of this high profile event which brings large numbers to the park, and is led by the Military Vehicle trust in partnership with WP. The community and Heritage team will be delivering a programme of learning experiences on the Friday for schools and home educators alongside a community engagement project over the weekend with participation in dance, music, film installations. This is full site event - and includes re-enactment, military transport exhibition and stalls. Budget is to support a community viewing of the existing 'Wicksteed at War film'. | 2 x community film viewing. Volunteer opportunity. | 2 |  |  | 2021-06-01 |  | 4 WP professionals | N/A | 400 | N/A | 404 (film viewing only/wider activities reach 10000) | Drives footfall to WP, creates a volunteer opportunity, opportunity to play in local care homes and connection to Dementia UK as a delivery partner. | WP / consortium volunteers to collate visitor feedback using the evaluation template. Audiences will be asked to rate their experience in a simple, fun visual way without intruding on their day out. Existing social media platforms monitored and feedback requested. If numbers and feedback is successful ambition to roll these events out more regularly. WP report post event which monitors numbers, demographics, feedback and engagement levels and looks for opportunities to expand the programme. Car park numbers monitored. | Branding and social media support built into the consortium budget. WP have an existing website and active social media platforms as well as links into many local community groups who use the park for various activities. KBC What's on Guide. | Wicksteed Park, Military Vehicles Trust
Wicksteed Park Soap Box Derby | This is an existing event but additional funding will support the introduction of a new event on the Friday for schools and colleges. It encourages competitors to use their ingenuity and imagination to create karts capable of tackling a challenging course, with the thrills and spills attracting competitors and spectators from across the region. This is a fun event which focuses on design and innovation and STEMM development. STEMM is an approach to learning and development that integrates the areas of science, technology, engineering and mathematics. Through STEM, participants develop key skills including: problem solving, creativity and critical analysis. The event raises awareness of engineering as a career prospect in a fun way. A number of workshops will be provided for Schools to learn about the design of Karts that will then be built by the schools and raced by the young people in teams. The open event for families with both adult and junior teams will take place on Saturday where people create their own gravity powdered kart and there is a race on the track with digital timers. Prizes for team and design. | Budget to fund one additional days workshop with schools /community groups | 4 |  |  | 2021-06-01 |  | 4 WP professionals | 50 | 500 | 500 | 1054 for the Friday (audience for the rest of the weekend 10,000+) | Drives footfall to WP, aids post covid recovery, creates a volunteer opportunity, raises awareness of Charles Wicksteed and the heritage of the park. STEMM development opportunity for local schools/community group. | WP / consortium volunteers to collate visitor feedback using the evaluation template. Audiences/participants will be asked to rate their experience in a simple, fun visual way without intruding on their day out. Existing social media platforms monitored and feedback requested. If numbers and feedback is successful ambition to roll these events out more regularly. WP report post event which monitors numbers, demographics, feedback and engagement levels and looks for opportunities to expand the programme. Car park numbers monitored. | Branding and social media support built into the consortium budget. WP have an existing website and active social media platforms as well as links into many local community groups who use the park for various activities. KBC What's on Guide. | Wicksteed Park/Consortium volunteer initiative
Consortium volunteer initiative led by FOAGM/WP + delivery partner Tresham College and MDEM | Consortium volunteer initiative led by Friends of the Art Gallery and Museum (FOAGM) and Wicksteed Park, with delivery partners Tresham College and MDEM. The consortium members have an existing pool of volunteers between Picture the Difference, Wicksteed Park and Friends of the Art Gallery and Museum which totals 150. The programme presents an opportunity to strengthen this volunteer pool, develop their skills and build capacity across this cultural network. The budget for this initiative will fund an online training series delivered by Tresham College and Museum Development East Midlands which will cover local history, customer service, confidence workshops and diversity training. Option to roll out in person training for those not digitally connected at WP. The consortium alongside the volunteers will also have an opportunity to identify other training requirements they may wish to develop in Years 2 and 3. The programme aims to recruit new volunteers and offer training and work experience opportunities for students who have left further education and due to the current economic situation, do not have the opportunity to gain paid employment. There will be a particular focus on recruiting from the arts and culture, heritage and tourism sectors using existing links with local institutions including Tresham, Bedford Colleges and Northampton University. | A series of at least six themed training opportunities for the consortium to role out annually over this programme and beyond. A series of training opportunities linked to each of the events detailed within this programme. Led by / coordinated by FOAGM and WP on behalf of the consortium. Recruitment new volunteers for the consortium network. | 20 (training and event opps) | 20 (training and event opps) | 20 (training and event opps) | March 2021-March 2024 |  | 8 | 150 | 150 | 50 | 1074 | Recruitment of at least 10 additional volunteers. Recruitment of young volunteers from the tourism/arts and culture sectors/ Numbers of events which volunteers support across the programme/ Development of skills and training of each volunteer/ Confidence building and impact on volunteers health and well-being/ Building capacity across the consortium's volunteer pool/ Reduces social isolation for volunteers who are not in work/retired | FOAGM/WP to provide quarterly reports on the volunteer initiative. And monitor recruitment and retainment levels. Feedback to be taken from volunteers port training and post event experience to develop the programme year on year. General feedback from volunteers on how the programme has impacted their lives. Consortium to monitor and report against how the volunteer pool has impacted the event delivery strand of the programme. | Branding and social media support built into the budget to assist with advertising the initiative. Members to advertise the training and recruitment of volunteers on each of their respective platforms. Word of mouth between networks to assist in spreading the word to volunteer who are not connected digitally. The Community Pop up will have a yearly signposting to opportunities for training and work experience at events. KBC's What's on Guide and Kettering Town Partnership to support | FOAGM/WP, Kettering Volunteer forum, Consortium members, MDEM, Tresham College
Consortium volunteer celebration weekend/recruitment drive led by WP | This event aims to form part of the volunteer training and recruitment programme. WP will offer space within the park to host a volunteer picnic which is part of a national volunteer week. This will also combine an information point for recruitment of new volunteers. Budget is marketing materials to support the day. This is a celebratory, social event to celebrate volunteers important contributions to respective member organisations and the cultural programme. | An annual event volunteer | 1 | 1 | 1 | Summer TBC |  | 12 | 100 | 100 | 100 | 312 | Reduces social isolation/ recruitment of new volunteers/ assists with retainment of existing volunteers/ confidence building and positive impact on volunteers health and well being | FOAGM/WP to report on attendance numbers and general feedback that will be collated as part of the more detailed report linked to the over-arching Volunteer training programme | Branding and social media support built into the budget to assist with advertising the initiative. Members to advertise the training and recruitment of volunteers on each of their respective platforms. Word of mouth between networks to assist in spreading the word to volunteer who are not connected digitally. Emailed invite to all volunteers members for the event. KBC's What's on Guide and Kettering Town Partnership to support | FOAGM/WP, Kettering Volunteer forum, Consortium members, MDEM, Tresham College
Wicksteed Park's Alternative Olympics "It's a Knock out!" | WP hosted the well known TV extravaganza ' It's a knockout' in the 1980s. This event will provide 'fun, messy, sporty' outdoor activities for the local community to coincide with the Tokyo Olympics in 2021. Budget is required to provide 10 places for local community teams that cannot meet the entry fees. | One day event, 10 team places available | 10 |  |  | Summer 2021 TBC |  | 5 | 65 | 1000 | 500 | 1570 | Drives footfall and aids post covid recovery, creates community activity opportunity for those that could not enter otherwise. Creates a consortium volunteer opportunity, reduces social isolation. | WP / consortium volunteers to collate visitor feedback using the evaluation template. Audiences and participants will be asked to rate their experience in a simple, fun visual way without intruding on their day out. Existing social media platforms monitored and feedback requested. If numbers and feedback is successful ambition to roll these events out more regularly. WP report post event which monitors numbers, demographics, feedback and engagement levels and looks for opportunities to expand the programme. Car park numbers monitored. | Branding and social media support built into the consortium budget. WP have an existing website and active social media platforms as well as links into many local community groups who use the park for various activities. KBC What's on Guide. | Northamptonshire local leisure and sport team. Local accessible sports club
Wicksteed Park Play Festival 2022 | Wicksteed wish to programme a series of community events from May-September 2022 with an @Play conference for this key sector which underpins early years play and learning. This will rasie awareness of Charles Wicksteed's contribution to early years development through play. Budget required to develop two community events focused on children's early development. Possible forest school workshops. | Two community events |  | 4 sessions |  | May- September 2022 |  | 5 | 92 | 100 | 500 | 697 | Drives footfall to the park/ focus on early years development and it's impact on general health and well-being in adulthood/ supports the play business sector/ creates a volunteer opportunity /reduces social isolation./ Raises awareness of the heritage of WP and it's contribution to engineering and early years development/STEMM. Other key success criteria to be identified as this programme develops | WP / consortium volunteers to collate visitor feedback using the evaluation template. Audiences and participants will be asked to rate their experience in a simple, fun visual way without intruding on their day out. Existing social media platforms monitored and feedback requested. If numbers and feedback is successful ambition to roll these events out more regularly. WP report post event which monitors numbers, demographics, feedback and engagement levels and looks for opportunities to expand the programme. Car park numbers monitored. | Branding and social media support built into the consortium budget. WP have an existing website and active social media platforms as well as links into many local community groups who use the park for various activities. KBC What's on Guide. | Heritage Forum, University of Northampton, Play and education specialists, Wicksteed Leisure
Total audience/participation = 151,407
Please note there complimentary programming content that will be delivered by consortium members as part of the overarching programme but already has budget secured. It remains visible on the project plan as this strengthens the overall offering of consortium programme.

## Appendix E Task list
Task no. | Task details | Staff | No. days | Completion date
Establish a cultural consortium/Governance / Programme development/ submission of bid
1 | Call out to cultural organisations ad partners to join the consortium | KBC | 4 | ongoing
2 | Establish consortium meetings | KBC | 1 | complete
3 | Develop Memorandum of Understanding | KBC | 1 | complete
4 | Agree core objectives and outputs for the programme | KBC | 1 | complete
5 | Confirm membership | KBC/Members | 1 | complete
6 | Schedule consortium meetings | KBC | 1 | complete
7 | Member community engagement with their audiences | ALL | 4 | complete
8 | Develop programme themes | ALL | 2 | complete
9 | Develop programme content | ALL | 40 | ongoing
10 | Identify and recruit key partners | ALL | ongoing | ongoing
11 | Write application | KBC/ACP | 10 | complete
12 | Submit application | KBC/ACP | 1 | complete
13 | Confirm funding opportunity | HE | n/a | 2021-01-01
14 | Review and confirm final programme | ALL | 5 | 2021-01-01
15 | Complete a RACI of roles and responsibilities | ALL | 2 | February-March 2021 / reviewed every six months
Develop event delivery framework
16 | Design consortium brand | ALL | 5 | April-May 2021
17 | Develop event milestones | ALL | 5 | March - May 2021
18 | Develop event evaluation feedback template | ALL | 2 | March - May 2021
19 | Develop event delivery checklist | ALL | 2 | March -May 2021
20 | Develop RAMs framework for all members to standardise H&S compliance and COVID considerations | ALL | 2 | March - May 2021
Commissions, training and content development
21 | Confirm the brief for commissions | ALL | 2 | March-May 2021
22 | Develop volunteer training material with delivery partners | FOAGM/WP | 4 | March-July 2021
23 | Develop heritage trail points of interest with local historians and HF | FOAGM | 4 | ongoing - community engagement summer 2021 @ pop up shop
Branding, Communications, Marketing and Community Engagement
24 | Recruit branding and social media resource | ALL | 4 | March-May 2021
25 | Develop consortium identity | New resource | 4 | March - May 2021
26 | Develop communications timeline using consortum brand and confirmed porgramme | KBC | 4 | May-August 2021
27 | Develop the community engagement programme in conjunction with the HAZ project team | KBC/HAZ/ALL | 6 | April-August 2021
28 | Monthly attendance at HAZ Board sessions | KCS/KBC | 2 | Monthly attendance - ongoing
Event delivery + Year two / three planning
29 | Event delivery | ALL | TBC once programme known | ongoing
30 | Year two programme planning | ALL | 6 | ongoing
Monitoring and Evaluation
31 | Monitoring and evaluation reporting against projected objectives and outcomes | ALL | TBC once programme known | First report July 2021
32 | Monthly budget and risk register updates | ALL | 1 per month | ongoing
33 | Annual HE report | KBC | 4 | Due March 2022
Volunteer training programme
34 | In line with task 23 develop training material/complete a gap analysis | FOAGM/WP | 2 | March-July 2021
35 | Commission delivery partners | Delivery partners | 2 | March-May 2021
36 | Develop communications strategy for combined pool of volunteers | FOAGM/WP | 4 | March-July 2021
37 | Develop and confirm training programme and participants | FOAGM/WP | 4 | Mrch-July | A
38 | Target new recruits via further education | FOAGM/WP + stakeholders (Tresham etc) | 4 | ongoing
39 | Deliver first phase of training | Delivery partners | 4 | Summer 2021
40 | Monitor and evaluate participant feedback, filter into future phases | FOAGM/WP | 6 | Autumn 2021