Trialling and Sampling Framework Agreement – STA 0090

Call-Off Contract No:STA 0090/29

Title: 2018 Key Stage 2 National Curriculum Science Sampling Test

Pursuant to the terms of the Trialling and Sampling Framework Agreement (STA 0090):

| Service Commencement Date: | 9 October 2017 |
| --- | --- |
| Call Off Value: | £1,999,723 |
| Trial Type: | Key stage 2 Sampling Test |
| Awarded to: | NFER |
| Relationship Manager for Department for Education: | Debbie Hughes |
| Relationship Manager for the Supplier: | Maria Charles |

- Background

Delivery of the biennial Science Sampling Test (SST) is required at the end of Key Stage 2 in 2018. The contract includes printing, collation, distribution, administration and coding. The SST will provide data on the performance of all items included in the test papers.

- Functional Requirements

| Subjects: | Science |
| --- | --- |
| Key Stage or Other Measure: | Key stage 2 |

- Required Service Elements

The table below sets out which Service Elements the Supplier shall provide under this Call-Off Contract.

| KEY: | Included in trial |  | Not included in trial | X |
| --- | --- | --- | --- | --- |

| Service Element | Included / not included | Service Element Requirements |
| --- | --- | --- |
| Project Management |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Recruiting schools | X | N/A |
| Informing schools |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Recruit and train administrators |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Printing |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Collation and distribution |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Administration of assessments |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Helpline |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Script Management during coding |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Data Capture |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Handling pupil background data |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Trial / Sample Administration Report |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Recruitment, management and payment of coders |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Coding (on-screen) |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Systems management |  | As per requirements set out in Invitation to Quote (Annexe A) and subsequent clarifications (Annexe B) |
| Optional Services |  |  |
| Disseminating an incentive payment to participating schools | X | N/A |
| Drawing the sample | X | N/A |

Annexe A – Invitation to Quote, including specification of requirements

Annexe B – Clarifications since issue of Invitation to Quote

- Performance Requirements

| No. |  | Service Requirement | Performance Measure |
| --- | --- | --- | --- |
|  | Project management | Full attendance at project start-up meeting, process walk-through, project management meetings and lessons learnt meeting (face to face and teleconference as agreed). Progress reports, product descriptions, strategies, exit and transition plans, and risk and issue reports are submitted. Management information (MI) is provided as agreed in product descriptions. Change requests are written for any deviations from the agreed contract. Security incident reports are written for all breaches and potential breaches of security and confidentiality. STA are notified of critical issues and incidents immediately upon discovery on the working day that the event occurs and receive an incident report within 2 hours of the event and twice daily updates thereafter until the issue / incident is resolved. For non-critical issues and incidents, STA are notified via an incident report within 24 hours of the event and receive daily updates thereafter until the issue / incident is resolved. After resolution of all issues and incidents, STA receives a final report that describes the incident, timelines and steps taken to resolve it and to prevent it happening in future. | 100% Meeting documents to be provided at least 24 hours prior to organised project checkpoint meetings. MI to be submitted as agreed in signed off product descriptions. All project documentation submitted according to the timescales in this document. All incident reports submitted and updated according to the timelines in this document. |
|  | Equalities | The Supplier provides reports at intervals as agreed, fulfilling their obligations under the Equality Act 2010. | 100% |
|  | Exit and transition | The Supplier provides and maintains detailed, fully resourced and costed routine and emergency exit and transition plans. | 100% |
|  | Informing schools | The Supplier provides confirmation of the complete testing timetable by the date specified in section 1.b. | 100% |
|  | Pupil selection | Schools acknowledge selected pupils and provide necessary administration details in advance of test administration, allowing the appropriate arrangements to be made. | 100% |
|  | Updating of trialling documentation | Supplier updates the administrator guidance, attendance register, administrator questionnaire and administrator training materials to quality criteria agreed with STA. | 100% |
|  | Helpline availability | Helpline SLAs are achieved, according to signed off product description. | 100% |
|  | Recruitment of administrators | Sufficient administrators are recruited to administer the tests. | 100% |
|  | Training of administrators | All administrators have received specific training for this testing. | 100% |
|  | Collation and distribution of test booklets to administrators | Correct test materials are collated and distributed to correct test administrators. All test papers, scripts and other test materials are returned from administrators. Notification and acknowledgement of delivery of all materials is confirmed. | 100% – all materials to be accounted for at all stages of the administration process. |
|  | Test administration | Tests are administered securely and completed on time in all schools selected. Test combinations are administered to the correct pupils, in the correct order and attendance status is accurately captured. | 100% |
|  | Validation of returned scripts and reporting of nil responses | Supplier confirms that all scripts and supporting documents, including unused papers, have been returned from administrators following administration. | 100% |
|  | Scanning and matching | Supplier confirms that all scripts have been scanned within the agreed exception rate and that the electronic matching of expected pupils to scripts is completed with all exceptions being resolved by the required date. | 100% |
|  | Recruitment of coders | Supplier confirms that coder recruitment has been completed and that the agreed capacity requirement has been met. | 100% |
|  | Coder training | All coders are trained as documented in the coder training plan. | 100% |
|  | Data capture of attendance registers | Accurate capture of all attendance codes as documented on attendance registers and reconciliation with results data. | 100% |
|  | Initial sample of scripts (SST) | Initial sample of scripts is made available for selection of standardisation scripts and items for ongoing quality assurance by the date specified in this ITQ. | 100% |
|  | Completion of coding (SST) | Coding of scripts is completed within the designated coding window (as per On-screen coding and coding quality assurance measures product description). | 100% |
|  | Coder quality assurance | Supplier provides evidence that the coder quality assurance processes are being carried out as documented in the product description. | 100% |
|  | Coder coding and quality assurance data | Supplier captures and provides to STA all standardisation, ongoing coder quality assurance and re-coding data including all required management information. | 100% |
|  | Coder register | Supplier captures and provides to STA a valid record in the coder register for all data fields required by STA. | 100% |
|  | Data capture of questionnaires | Accurate data capture of all responses from administrator questionnaires is provided to STA in an electronic file format as agreed with STA. Outcomes from the analysis of the questionnaires is provided in a spreadsheet formatted in line with STA instructions. | 100% |
|  | Data feed of item level data (100% of codes) | Supplier provides data feeds to STA on agreed dates with evidence that all checks have been completed as documented in the relevant product descriptions. | 100% |
|  | Final Administration report | Administration report, comprising: Part A – administration report Part B – analysis of questionnaire responses. Part C – reporting on the test papers Report content to be reviewed and agreed by STA prior to handover. | Parts A, B and C completed and submitted to STA by required date to agreed quality standard. |
|  | Handover of electronic archive | Electronic archive (questionnaires and scripts) is handed over to STA on the required date. All scanned script files must follow the naming convention specified in this ITQ. | 100% accurate |
|  | Handover of coder training materials and coding frames | All training materials and finalised coding frames are handed over on the required date and in the format agreed with STA. | 100% |
| 29. | End-to-end testing | End-to-end testing demonstrates Supplier’s capability to produce test materials of appropriate quality, in terms of readability, scanning and data transposition. | STA acceptance of Supplier’s End-to-End testing outcome report. |
| 30. | Printing | - A print proof of each test version is signed off by STA before printing commences. - The correct quantity and type of materials are produced by the required date. - No defective materials are presented for use by pupils, coders or administrators. - Test materials are compatible with the scanning solution. | - All proofs approved by STA Test Development Deputy Director - Manufacturing MI demonstrates actual quantity of each item produced is equal to 100% of the quantity requested by the required date. - Manufacturing QA MI demonstrates application of QA regime. No incidents of irreplaceable defective materials reported by pupils, coders, or administrators - Scanning MI demonstrates scanning exception rates do not exceed 2% - 100% tests meet print quality standards, on time and are signed off by STA. |
| 31. | Apprentices | The Supplier is required to support the DfE apprenticeship policy and shall employ apprentices and report the numbers of apprentices employed during the delivery of this contract to the STA. | 100% |

- Payment Milestones

Payment will follow the completion of the milestones listed below:

| Payment No | Activity (see deliverables and outputs table section 1.b of ITQ for further detail) | Payment due date | Amount |
| --- | --- | --- | --- |
| 1 | 1, 2, 3, 4, 5, 6, 7, 9, 10, 13, 14, 20, 21, 22, 23, 25 | 30/03/2018 | £499,930.75 (25%) |
| 2 | 2, 8, 11, 12, 15, 16, 17, 18, 19, 27, 29 | 06/07/2018 | £599,916.90 (30%) |
| 3 | 1, 2, 31, 33, 35, 37, 38, 39, 40, 41, 44, 45, 46, 47, 48 | 01/11/2018 | £899,875.35 (45%) |

In witness whereof this Call-Off Contract has been duly executed.

Signed for and on behalf of the Department for Education:

Name: Una Bennett

Date:

Signed for and on behalf of the Supplier:

Name:

Date: