| KPI Number | KPI Title | KPI Description | SoR Reference | Incident Measure | Threshold MOE | Remediation Process |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Delivery Plan | The Contractor shall produce a comprehensive, costed delivery plan within one month of contract award. | Annex B | Delivery of a comprehensive, costed delivery plan within one month of contract award. Report to be delivered during a F2F mtg with the Project Officer. | A costed (+/-5%) and time specific (+/- 4 weeks) delivery plan | Failure to deliver a comprehensive, costed delivery plan within 1 calendar month of contract award will result in a F2F Contract Review mtg between the Contractor and the Project Officer. The contractor will then need to provide a comprehensive, costed delivery plan enabling timely delivery of both prototype devices for testing within one further month. Failure to do this will result in a formal review of the contract. |
| 2 | Prototype Mission Training System (MTS) Factory Acceptance Test (FAT) | The Contractor shall complete initial hardware and software procurement, system build and demonstrate an initial capability for both use cases within six months of contract award. | Annex B | Demonstration of an initial representative device for both use cases at a customer agreed-industry site within 6 months of contract award. Demonstration to be given to the Project Officer and selected Gladiator and ISTAR Force personnel. | 80% of hardware and software at customer-agreed site no later than the specified deadline | If unable to demonstrate delivery of an initial capability against both use cases within 6 months, the contractor will have 2 weeks to present a revised delivery plan demonstrating their ability to deliver the rest of the contract to Performance, Time and Cost specifications. The revised plan is to be delivered during a F2F mtg with the Project Officer. |
| 3 | Prototype MTS Site Acceptance Test (SAT) | The Contractor shall complete build, Gladiator system integration and demonstrate the capability in both use cases within eight months of contract award. | Annex B | Demonstration of a representative capability for both use cases at RAF Waddington within 8 months of contract award. Demonstration to be given to the Project Officer and selected Gladiator and ISTAR Force personnel. | 80% of hardware and software delivered to RAF Waddington no later than the specified deadline | If unable to demonstrate delivery of a capability against both use cases within 8 months, the contractor will have 2 weeks to present a revised delivery plan demonstrating their ability to deliver the rest of the contract to Performance, Time and Cost specifications. The revised plan is to be delivered during a F2F mtg with the Project Officer. |
| 4 | Prototype MTS Mission Training Trial (MTT) | The Contractor shall facilitate and conduct MTT for both prototype MTS within eleven months of contract award. | B.1, B.2, B.3 | Delivery of MTT on prototype capability for each use case using operational mission scenarios agreed with ISTAR Force reps within 11 months of contract award. Delivery is to be to the Project Officer, and selected Gladiator and ISTAR Force personnel at RAF Waddington. | Both prototype synthetic devices integrated into the Gladiator system with operational scenarios built and demonstrated at RAF Waddington no later than the specified deadline | Failure to deliver both prototype MTT within 11 months of contract award will result in a F2F Contract Review Mtg with the Project Officer. The Contractor will need to demonstrate a viable plan to complete all CCD activity within 13 months of contract award. Failure to achieve this will result in a formal review of the contract. |
| 5 | Social value progress reports on Tackling Economic Inequality and Fighting Climate Change | The contractor shall demonstrate progress against selected Social Value requirements (Tackling Economic Inequality, Fighting Climate Change) by submitting electronic reports every 4 months (3 reports in total) to the Project Team. | N/A – Included in tender evaluation criteria | Receipt of 1 progress report including both Social Value Themes (Tackling Economic Inequality, Fighting Climate Change) every 4 months from the start date of the contract until the end date. The report is to be sent electronically to the Project Officer. | Minimum 1 x A4 progress report per Social Value theme to be sent electronically to [Project Team] outlining the contractor’s commitment to each Social Value theme, how it has been implemented in relation to this contract and what progress has been made since the previous report. | Failure to deliver regular progress reports will result in a F2F mtg between the Contractor and Project Officer to discuss progress against Social Value criteria. Failure to deliver multiple progress reports will result in a formal review of the contract. |