Land Warfare Centre (LWC)

Business Centre

Driver Training Project (DTP)

Civilian Driving Licence Acquisition Contract

STATEMENT OF REQUIREMENT

(SoR)

# Document Approval

| Author: | LWC-BusCen-PD-SO1C |
| --- | --- |
| Owner: | LWC-BusCen-PD2 AH |
| Document Ref: | DTP/Requirements/ |
| Version No: | 3.2 |
| Originator: | LWC-BusCen-PD-SO1C |

# Amendment History

| Name | Signature | Appointment | Comments | Date |
| --- | --- | --- | --- | --- |
| Brig Lee Daley | Lee Daley | Senior User/ Commander DCSp |  | 17 Oct 24 |

| Revision date | Revision No | Author | Summary of changes |
| --- | --- | --- | --- |
| 08/08/24 | 2.1 | SO1J PD PM | Updated to reflect revised KPIs. |
| 27/08/24 | 2.2 | SO1J PD PM | - Updated following review by Commercial. - Para 33 inserted reference supply and maintenance of vehicles and equipment for civilian driving licence acquisition. - KURs removed and provided at Ref B. • Policy and Standards reviewed and updated. |
| 13/09/24 | 2.3 | SO1J PD PM | • Annex A updated to include 5 year estimate. |
| 03/10/24 | 3.0 | SO1J PD PM | • Endorsed by OF5s for ITT release. |
| 22/10/24 | 3.1 | SO1J PD PM | • Updated to reflect revised numbers. |
| 22/10/24 | 3.2 | SO1J PD | • Updated to reflect revised numbers to include Reserves. |

Endorsed for the purpose of Invitation to Tender (ITT). This document requires the following endorsement to confirm the requirements are captured in their entirety in the SoR:

| Name | Signature | Appointment | Date |
| --- | --- | --- | --- |
| Col Laura Craig-Braddock | Laura Craig-Braddock | Comdt DST | 2 Oct 24 |
| Col Andy Redding | Andy Redding | AH Trg Plans | 1 Oct 24 |
| Col Ed Launders | Ed Launders | ACOS Plans, RC | 1 Oct 24 |

Approval for the purpose of Invitation to Tender (ITT). This document requires the following approvals:

INDEX

| SECTION 1 | SoR Introduction |
| --- | --- |
| SECTION 2 | Document Structure |
| SECTION 3 | Scope of Supply |
| SECTION 4 | Mandatory Requirements |
| SECTION 5 | Service Requirements |

Sub-sections:

SR1  	DTP SoR 1 TRAINING DELIVERY MANAGEMENT

SR2  	DTP SoR 2 TRAINING PLANNING

SR3  	DTP SoR 3 TRAINING DELIVERY

SR4            DTP SoR 4 TRAINING SUPPORT

SR5   	DTP SoR 5 EQUIPMENT SUPPORT

Annex A ESTIMATED TRAINING THROUGHPUT

References:

A. 	Draft Civilian Driving Licence Acquisition Demand and Pipeline Management Process. B. 	Key User Requirements

# STATEMENT OF REQUIREMENT (SoR) GUIDE

SECTION ONE – SoR INTRODUCTION

1. 	This SoR sets out the requirements and services (Training Services) to be delivered by the Service Provider (SP) to the Authority under the Driver Training Project. In delivering the requirements and services set out in this SoR, the SP shall comply with, and act in accordance with, the obligations set out in this Delivery solution and relevant Legislation, regulations and Authority policies and procedures.

## Training Services

- The Authority is responsible for contributing to the development and delivery of Operational Capability by ensuring that Service Personnel (SPers) are trained to the necessary standards and levels of performance, and have sufficient knowledge, skills, attitudes and capabilities to be able to acquire essential driving licences and perform their designated driving roles in operational environments, and when supporting operations.

- The Training Services to be delivered by the SP shall be the provision of services for the civilian driving licence acquisition training of SPers as detailed in Annex A to enable the Authority in fulfilling their responsibilities and delivering Operational Capability, as set out above.

- Training will be in line with Civilian Driving Licence Acquisition Demand and Pipeline Management Process at Ref A.

- The aims of the Training Service are to:

  - provide relevant, effective, innovative and modern training, underpinned by collaborative working and a joint management approach, which enables delivery of the human component of Force Elements at Readiness to enable operational success;

  - contribute to an attractive and rewarding employment ‘offer’ for individual SPers, by inspiring and enabling them to realise their full potential; and

  - continuously improve and modernise Training Services delivery, so that the Training Services continue to meet the needs of the Authority throughout the delivery period.

- As one of the Defence Lines of Development (DLODs), training is an essential factor in contributing to operational success. By instilling and reinforcing an appropriate mix of Knowledge, Skills and Attitudes, individual training inducts recruits into Defence, prepares them for their future employment, and develops them throughout their careers.

## Outcomes from Training Services

- The outcomes the Training Services are intended to support are:

  - the provision of training to the requisite performance standard and within agreed timelines.

  - the management and support of equipment and vehicles to enable training;

  - the ability to adapt the training to remain effective and relevant as training, technologies and methodologies change;

  - the ability to work collaboratively between the Authority and the SP to realise the intended outcomes of this Training Service.

- In achieving the outcomes set out above, the Training Services are expected to operate in accordance with a number of constraints. These constraints describe how the Training Services must:

  - comply with legislation and policy;

  - ensure training is safe and complies with safety standards and practices;

  - protect the environment and personnel’s health and comply with environmental and health standards and practices;

  - ensure information is properly managed, exploited and protected;

- The Service Requirements the SP shall deliver are derived from the outcomes and constraints described above and are set out below.

# SECTION TWO - DOCUMENT STRUCTURE

- For ease of reference, the DTP SoR has been divided into five sections. Each of the sections have been structured so that they may be read largely in isolation. However, Section 5, detailing the Service Requirements and Service Options, has been further divided into 7 sub-sections.

| Section |  | Requirement |
| --- | --- | --- |
| 1 |  | Introduction |
| 2 |  | Document Structure |
| 3 |  | Scope of Supply |
| 4 |  | Mandatory Requirements |
| 5 |  | Service Requirements |
|  | SR1 | DTP SoR 1 TRAINING DELIVERY MANAGEMENT |
|  | SR2 | DTP SoR 2 TRAINING PLANNING |
|  | SR3 | DTP SoR 3 TRAINING DELIVERY |
|  | SR4 | DTP SoR 4 TRAINING SUPPORT |
|  | SR5 | DTP SoR 5 EQUIPMENT SUPPORT |

Table 1 – SoR contents

- Each of the Section 5 sub-section defines the output required, rather than the processes involved, unless there is a process which the SP shall be required to comply with. Each output requirement, where applicable, is accompanied by:

  - An estimated volume of work (at Annex A) which the SP could be expected to provide to deliver the requirement. These volumes have been provided by LWC Training Plans as a baseline.

  - The minimum acceptable performance standard required.

  - Additional information, where appropriate.

# SECTION THREE - SCOPE OF SUPPLY

- DST is the result of incremental changes from the former Army School of Mechanical Transport, starting with the large-scale civilianisation of driving instructor roles. Subsequent changes included reducing and restructuring of the Civil Service and military workforce and delivery solution for much of the driving licence acquisition output.

- The DTP seeks to find the optimal Whole Force mix of military, Civil Service and commercial delivery solutioned workforce to provide a flexible, resilient and cost-effective driver training capability for the future. While founded in delivery of current demand, outputs must be flexible to adjust to an uncertain future where the driver training requirements of Defence will change in volume, mix and nature as new vehicle platforms and force structures are introduced. Modern training methods and learning technologies will be key to success, enabling training which is efficient in time and cost and helping to position Defence to exploit future technologies.

- The following high-level goals for DTP have been identified:

  - Deliver Defence Wheeled driver training outputs from 1 April 2026.

  - Manage the in-year driver training demand profile and delivery within resources (instructional staff, vehicles, delivery solution funding allocation).

  - Enable efficient delivery alongside other DST outputs.

  - Implement modernised learning methods to realise financial and environmental savings, to deliver improvements in training quality and to meet the expectations of the 21st century trainee.

  - Provide an adaptable solution that can use a Continuous Improvement approach to remain relevant and cost-effective and can adapt to the evolving needs of Defence.

- The DTP will provide wheeled driver training, to maximise the benefits of a balanced workforce whilst modernising training delivery to meet the needs of the FLCs and the aspirations of the trainees. The solution will support Defence direction to reduce residential training where the FLCs are supportive of increased training in the workplace. This work needs to start now to ensure a seamless transition from the current Future Licence Acquistion Training System (FLATS) without risk to ongoing training output. DTP will meet the full set of URs as agreed and traded between stakeholders during the project concept phase. These UR+s shall underpin the future operating model and will remain constant.

# SECTION FOUR - MANDATORY REQUIREMENTS

16. 	This section describes the mandatory requirements and general principles which the SP shall adhere to, and act in accordance with, in the delivery of the Training Services under this delivery solution.

## Relevant Law and Authority Standards and Policies

- The SP shall proactively identify and comply with the most up-to-date rules, guidance, instructions and policies applicable to the services in the scope of this delivery solution.

- Where rules, guidance, instructions and policies are referenced in this document, the latest version of these rules, guidance, instructions and policies shall apply for the duration of the tender process and delivery solution.

- Any listed rules, guidance, instructions and policies that are referenced in this document does not absolve the SP from conforming with any other relevant publications or legislation.

## Personnel Standards

20. 	In delivering the Training Service defined in this SoR the SP shall ensure that their Personnel comply with:

- Enhanced Disclosure and Barring Service (Enhanced DBS) checks (or Disclosure Scotland or AccessNI as appropriate) and JSP 893, as appropriate to their task;

- All personnel must hold a Counter Terrorist Clearance (CTC) unless individuals are exempted by the Authority.

- the personnel qualifications, competencies and experience set out in the SoR;

## Continuous Improvement

21. 	The SP shall continually monitor the services delivered under this delivery solution for the purpose of identifying and implementing continuous improvement throughout the delivery solution period, to support the ongoing improvement in the quality and cost-effectiveness of service provision and help improve overall Value for Money for the Authority.

## Authority Personnel

22. 	The SP shall note that, in relation to the requirements of this Delivery solution, there are

Authority posts which may support elements of the Training Services (including, but not limited to, Trainers). The number, roles and responsibilities of these Authority posts are reviewed and established annually by the Authority.

## Supervisory Care

- The SP shall note that the Commanding Officer (CO) of any Defence establishment utilised retains the ultimate responsibility for the Supervisory Care of Trainees and SPers within their command.

- SP personnel shall follow the principles of good conduct and behaviour for Trainers (as described in JSP 822  Defence direction and guidance for training and education (February 2024) and Defence Training Support Manuals (DTSM) 4 Delivery of Individual Training. and shall act as ‘first response’ to Trainee Administrative Care issues whilst Trainees are under the SP’s instructions, until such time as the issue can be handed over to an appropriate Authority member of staff.

- When Trainees are under the supervision of SP Trainers, either during Training Delivery or when delivering mentoring or remedial training outside of periods of training, the SP shall:

  - ensure that SP Trainers apply Unit Standing Orders and single Service regulations to uphold the expected standards of discipline for Trainees, and that, in the event of discipline issues, the nominated chain of Command point of contact for the relevant Trainee(s) is notified by the SP as soon as possible;

  - provide initial support to Trainees in a positive, sensitive and humane manner, and shall hand this duty over as soon as reasonably possible to a suitable Authority member of staff, ensuring continuity of care and support until the Authority’s staff have taken control;

  - ensure that any complaints made to SP Personnel, as defined in JSP 831 - Redress of individual grievances: service complaints (April 2024) and JSP 763 Defence direction and guidance for training and education (June 2021) are dealt with immediately by whichever member of SP personnel is approached, and that the relevant details and information concerning the complaints are passed to an appropriate Authority representative as soon as reasonably possible, ensuring continuity and preservation of any material evidence until the Authority’s staff have taken control of the complaint;

  - adhere to the Authority’s complaints procedures for complaints made against a member of SP personnel, and shall work with the Authority to resolve and manage the response to the complaints and/or Representations, to achieve a satisfactory conclusion;

  - work with the Authority to help the Authority to manage any complaints made by the SP’s personnel against the Authority’s staff and/or Trainees;

  - ensure that Specific Learning Differences and Neuro-Diversity requirements for coaching, mentoring and remedial training are recognised and responded to in an appropriate manner, in accordance with the Authority’s requirements.

- To support the Commanding Officers in exercising their supervisory care responsibilities, the SP shall also ensure that the  planning and management of training considers and appropriately responds to all factors which may affect the wellbeing of SP personnel, Trainees, SPers and visitors, including, but not limited to, health and safety regulations, the physical state of personnel under training, suitable facilities for the activity being undertaken, religious issues, risk assessments, class timings and sizes, breaks and personal admin requirements.

# SECTION FIVE – SERVICE REQUIREMENTS AND SERVICE OPTIONS

27. 	This section provides the description of the Service Requirements (i.e. these are requirements that must be met as part of the scope of the supply). Service Options may not (in some

circumstances) be mandatory but can be responded to as part of the bid. This section details some of the constraints bounding the requirement and should be read in conjunction with the five sub-sections as detailed in SR1 to SR5.

## Training Courses

- In providing the training courses within the scope of this Delivery solution, the SP shall take account of, and comply with, the constraints identified in the relevant SoTT and Training Authorisation Documents (TrADs), including in relation to course numbers, durations and sizes, and shall ensure that training courses are provided in accordance with the Authority’s training pipelines and sequencing requirements.

- In planning and programming the training in scope of this Delivery solution, the SP shall prioritise and deconflict demands to make best use of available training resources to meet the Authority’s requirements and associated KPI. This may include making short-notice changes to training schedules.

- In providing the Training Services in the scope of this Delivery solution, the SP shall, as far as practical, ensure that the Training Services are tailored to the circumstances and learning needs of individual Trainees’, to ensure that Trainees’ are not disadvantaged due to their personal circumstances and/or specific learning needs.

- The Authority reserves the right to place any appropriately qualified Trainee it sees fit on the training courses within the scope of this Delivery solution. This includes, but is not limited to, staff from RN, Army, RAF, MOD civilian staff and staff from other Government Departments, MOD sponsored Defence Industry Trainees, foreign Trainees via UK Government-to-Government agreements and international Government-to-Government (G2G) Trainees.

## Suitably Qualified and Experienced Personnel (SQEP) Staff

32. 	The delivery of the Training Services will be delivered by SQEP staff in accordance with the relevant sections of the SoR. Documentary evidence of SQEP qualification should be provided by the SP for staff in post at Service Commencement Date. The requirement to comply with JSP 822, Vol 4: Care and Welfare in Training (February 2024) remains.

## Civilian Driving Licence Acquisition Vehicles and Equipment

33. 	Vehicles and equipment required for the delivery of civilian driving licence acquisition will be supplied and maintained by the SP.

## Governance

- The SP shall participate in and support the governance structures and forums to manage this Delivery solution in accordance with the requirements of Governance and Delivery solution

Management. As a minimum, the SP is to attend Monthly Working Groups (Monthly Governance and Performance Review Meeting (MGPRM)) with the Authority to present reports and updates agreed with the Authority at delivery solution outset and as agreed for the duration of the delivery solution.

- The SP shall provide training Subject Matter Expert (SME) support to Authority meetings, seminars, committees and other similar events, when required by the Authority, to disseminate and raise awareness of current training practices and processes and industry good practice in training provision.

## Interfaces with Other Training and Entities

- The SP shall note that the Training Services interface with other aspects of training delivered to SPers, and other elements of the wider Authority and Government departmental portfolio which have a potential impact on the training of SPers.

- The SP shall liaise and work with 3rd Party Providers, Authority teams and organisations and wider Government departments and entities to support the provision of effective and coherent training.

## Integration of New Capabilities

38. 	The SP shall note that during the delivery solution period, the Authority will procure and bring into service new Authority capabilities (New Capabilities). These New Capabilities may give rise to increased volume of training through a Request for Change.

## Change

39. 	The identification, planning and assessment of the implications of change on the Training Service shall be part of the SP’s management responsibility, and included as part of the Training Services.

## Hours of Operation

- As a minimum, the Training Services set out in this SoR shall be provided during core hours of 0800 -1700 hrs on week days (1600 hrs on Friday).

Unusual Working Hours.

- Some work will routinely be required to be undertaken outside of normal working hours due to additional training requirements or where conduct of some work would otherwise interfere with training delivery, or smooth running of the establishment.

- When required by the Authority the SP shall deliver training on weekends, public and Bank

Holidays (except for Christmas Day and New Year’s Day), on early mornings (before 0800 hours), and evenings (after 1700 hours).

## Training Phases UK Armed Forces

- United Kingdom Armed Forces training is delivered in 3 distinct Phases:

  - Basic Training (BT) - Undertaken by all new entrants to the Armed Forces and delivers basic military skills and training to introduce individuals to life in the Armed Forces. The delivery of Basic Training is not included in this Delivery solution.

  - Initial Trade Training (ITT) - Delivers initial individual specialisation, sub-specialisation and technical training following Basic Training and takes place immediately prior to joining the Trained Strength, it includes driver training and likely trade related modules on other sites that may need to be sequenced.

  - Subsequent Trade Training (STT) - A period of individual training undertaken at any stage in a Service person’s career after Basic and Initial Trade Training.

- This Delivery solution is principally for the provision of Training Services to the Delivery solutioning Authority for elements of Initial and Subsequent Trade training Armed Forces personnel.

## Distance Learning and Distributed Training

45. 	During this Delivery solution the Authority may wish, or be required, to make changes to the method, content and media of training and include training delivery off site either through Distance Learning or Distributed Training.

## Flexibility and Responsiveness

46. 	The output requirements, as expressed in the Training Plan are dynamic in terms of variations in volume, length, type and level of training; changes are encapsulated in formal revisions to these documents. Some training changes may stem from Urgent Capability Requirements (UCRs) and may therefore require a quicker in-year response. The SP shall adjust planning, scheduling and programming of all courses accordingly.

## Personal Protective Equipment (PPE)

47. 	PPE for SP staff and trainees will be provided by the SP.  The SP will remain responsible in all circumstances, as the Employer, for ensuring that PPE used by its staff is fit for purpose, that they are trained to use it and that they understand the risks mitigated by the PPE.

Annexes:

A. 	Estimated Training Throughput

## DTP SoR 1 - TRAINING DELIVERY MANAGEMENT

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 1 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | The SP shall operate an effective management organisation able to interface with the Authority in the management, administration and control of all areas of work specified in the Statement of Requirement. | 1.1.1 | The SPs management organisation shall be structured so that it can respond effectively to the requirements of the Authority (at the appropriate level). | All SP staff to comply with the Authority’s Standing Orders and Procedures, and other Delivery solution terms (including 3rd Party). | As articulated in KPI 1. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
|  |  | 1.1.2 | The SP shall provide a Single Point of Contact (SPOC) to interface effectively with the Authority and their Representatives at Leconfield and other agreed locations |  | SPOC or nominated deputy to be available (and contactable by phone) at all times within agreed core hours in accordance with the SP's Contract management plan and Out of Hours Call out Plan. SPOC details to be provided to the Authority. | The SPOC shall be a suitably empowered manager to be normally located at the Leconfield and agreed training locations and available during agreed working hours as specified. The SPOC shall have the executive authority to ensure that advice, assistance and resources are made available to meet the delivery solution requirements. |
| 1.2 | The SP shall manage and operate a process to undertake the administration of Enhanced DBS checks for SP employees who are identified as having unsupervised contact with SPers under the age | 1.2.1 | The SP shall provide a managerial interface with the Authority's Enhanced DBS focal point manager, to determine and agree the requirement for Enhanced DBS checks. | JSP 834 Safeguarding (June 2023) Rehabilitation of Offenders Act 1974 DBS Disclosure Scotland | 100% Enhanced DBS checks on respective personnel. Status reported and validated (excepting where Authority agreement for noncompliance) at the | The process shall include a review of the Enhanced DBS status if the work associated with a post or the incumbent changes. All SP employees shall hold, a current, valid |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 1 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  | of 18 years and other vulnerable adults. |  |  | AccessNI Civilian Driving Licence Acquisition Demand and Pipeline Management Process | Monthly Governance and Performance Reporting Meeting (MGPRM). | Enhanced DBS certificate that is no more than 3 years old. This is to include anyone who has unsupervised access to trainees, related information or content. |
|  |  | 1.2.2 | The SP shall take the administrative steps necessary to undertake employee Enhanced DBS checks and will maintain an accurate register of SP Staff employed to deliver the delivery solution and record the agreed level of DBS check (if any) on each member of staff. It will also provide confirmation to the Authority DBS focal point of the DBS status of SP employees as required. - Post Title - Staff/Pay Number - Rank/Title - Surname - DBS Check Status This is to be in line with local commanders Supervisory Care Directive. | Rehabilitation of Offenders Act 1974 UK Gov DBS Guidance Civilian Driving Licence Acquisition Demand and Pipeline Management Process | 100% Enhanced DBS checks on respective personnel. Status reported and validated (excepting where Authority agreement for noncompliance) at the Monthly Governance and Performance Reporting Meeting (MGPRM). | The Authority should also be aware of the following document from the Disclosure and Barring Service as it articulates the actual requirement for. All SP employees shall hold, a current, valid Enhanced DBS certificate that is no more than 3 years old. The process shall include a review of the DBS status if the work associated with a post or the incumbent changes. IAW the rehabilitation of offenders act all positions that require Enhanced DBS need to scrutinise fully to ensure a blanket approach is not applied. SP to share |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 1 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | information of Enhanced DBS qualified personnel with responsible military owner. |
| 1.3 | All SP personnel to be trained and competent in line with current standards including mandatory training requirements (e.g. COTS, health and safety trg). |  |  | Conform to the Driving & Vehicle Standards Agency (DVSA) Driver Training Code of Practice. Relevant driving licences and DVSA requirements. ADI Registration. JSP 822, Vol 7: Defence Individual Training (February 2024) Become an LGV driving instructor - GOV.UK (www.gov.uk) Are you ready to become PCV trainer? (safedrivingforlife.info) Civilian Driving Licence Acquisition Demand and Pipeline Management Process | 100% Status reported and validated (excepting where Authority agreement for non-compliance) at the Monthly Governance and Performance Reporting Meeting (MGPRM). | The Authority maintains the right refuse the use of SP Personnel as applicable. SPs shall ensure that they have conducted their own assessment on potential driving instructors, to include: - Theory Test. - Driving assessment. - Instructional ability. The SP shall retain record of the assessment and present to the Authority within 24 hours of the request. If required by the Authority, a Trainer shall be assessed by an Authority Driving Instructor Trainer against the DVSA national standard. |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 1 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | If the Authority notifies the SP that an Instructor has not demonstrated the required capability and competence the Trainer shall not be permitted to continue to deliver training until they have undertaken additional training provided by the SP and have been reassessed by the Authority as competent to deliver training. |
| 1.4 | Provide and implement an agreed plan for the transition of services in the form of a Transition Plan. | 1.4.1 | Provide and implement an agreed plan for the transition of services in the form of the Transition Plan. To include but not limited to: - Civilian Driving Licence Acquisition Training Vehicle delivery plan - Staff recruitment plan including managers, Trainers etc - SPOC - TUPE Plan - Business Continuity Plan (BCP). | N/A | The Transition Plan shall be subject to agreement by the Authority prior to entering into the Contract and must articulate the route to successful delivery to Vesting Day. | To be reviewed at agreed transition milestones throughout Transition period. Evidence required: Milestone 1: - Outline vehicle delivery schedule. - Outline recruitment plan. - Updated TUPE plan - Draft BCP. Milestone 2: - Refined vehicle delivery schedule |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 1 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | including contractual details. - Refined recruitment plan including names of staff / offers of employment. - Refined TUPE plan including staff details. - Refined BCP following Authority feedback. Milestone 3: - Confirmed delivery plan including vehicle registration details. - Confirmed recruitment including staff names, dates, qualifications, mandatory training requirements and clearances. - Confirmed SPOC contact details. - Confirmed TUPE Transition Plan - Final BCP following Authority. |
| 1.5 | Provide effective management of the Exit Period. The SP shall propose a Exit Plan to | 1.5.1 | Provide effective management of the Exit Period. The SP shall propose an Exit Plan to affect a transition to any subsequent SP. | N/A | The Exit Plan will be subject to agreement by the Authority. The detailed Exit Plan shall include plans, | To be formally agreed prior to Vesting Day and reviewed and updated annually. |
| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 1 | Notes |
|  | affect a transition to any subsequent SP. |  | To include but not limited to: - TUPE information - Course details - Course training materials. In accordance with DEFCON 703 all artefacts, training data analysis, records and documents created under the contract will be retained by the Authority at the end of the contract. |  | programmes and explanatory documents for all services and activities covered by the Contract. This is to be agreed with the Authority when an end date for the Contract is agreed. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |

## DTP SoR 2 – TRAINING PLANNING

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicators (PI) Linked to KPI 2 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1 | The SP shall plan, programme, schedule and manage the resourcing of training to meet the Authority’s training and assurance requirements. | 2.1.1 | The SP shall: - Take account of, and comply with, the constraints identified in the SoTRs in the scope of this Delivery solution and relevant TRA. - Forecast resource requirements to deliver the SoTT, taking account of the capacity and availability of Trainers and supporting personnel. - Take account of the capacity and availability of facilities, Training Equipment and other resources necessary to deliver training. - Prioritise and deconflict individual and team training to make best use of available resources to meet the Authority’s requirements. - Assimilate and respond to Authority comments and feedback within agreed time lines on the SoTT, including the production of new iterations if required. | JSP 822 Defence direction and guidance for training and education ( February 2024). Defence Training Support Manual (DTSM) 4: Delivery of Individual Training ACSO Governance of Army Training 3248 Civilian Driving Licence Acquisition Demand and Pipeline Management Process | Training resourcing to be met as articulated in KPI 2. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | HQ LWC shall produce a realistic and deliverable SoTR which meets the Authority’s training requirements defined in the SoTR in an efficient and costeffective manner and shall submit the SoTT to the Authority for endorsement. In producing the SoTT, HQ LWC shall liaise with Authority Providers. Timings for the production of the SoTR and SoTT will be provided by the Authority. |
|  |  | 2.1.2 | The SP shall create, coordinate, programme and maintain accurate and up-to-date training schedules which fulfil the overall SoTT. In | Defence Training Support Manual (DTSM) 4: Delivery of Individual Training | Training resourcing to be met as articulated in KPI 2. | This must lead to creation and publishing of Training Task Programs listing all |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicators (PI) Linked to KPI 2 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | delivering this service, the SP shall: - Ensure that the resource and equipment necessary to deliver the training are programmed, scheduled, coordinated and booked. - Ensure that capacity constraints are identified and managed effectively, to best achieve the overall SoTT. - Prioritise and deconflict training to make best use of available resources to meet the Authority’s requirements. - Ensure that accurate and up-to-date schedules are accessible to Trainers and Trainees via the Authority TMIS. - Ensure that dependencies and interfaces with Establishments are identified and managed effectively to achieve the overall SoTT. - Ensure that relevant feedback and recommendations from Assurance of Training is incorporated into training planning, programming and scheduling. | Civilian Driving Licence Acquisition Demand and Pipeline Management Process | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | start/end dates for all SoTT requirements and promulgated to all stake holders in the training sphere. Including the overall year schedule. Short-notice changes to training schedules may include continuation and certification for operational training, e.g. training to enable units to commence operations. The Authority will for all other/new systems introduced provide user training for the SP as per RFC process in Delivery solution. |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicators (PI) Linked to KPI 2 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | - Ensure that other Authority endorsed requirements and demands on Training Establishment capacity and resources are taken into account and reflected in the planning and scheduling of training, and potential conflicts are managed to minimise the impact on training provision. - Maintain, update (weekly) and make available a training resource database to include Trainers, facilities, equipment and vehicles. - Update training schedules to incorporate short-notice changes to training, to ensure that the Authority’s requirements are met in an efficient and cost-effective manner. - Work with Authority to absorb and accommodate shortnotice changes to training schedules in an agile and flexible manner within the current resource and escalate accordingly where this cannot be met. - Make use of the Authority provided functional electronic TMIS and Management Information Systems and other systems that pre-exist or that are introduced |  |  |  |
| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicators (PI) Linked to KPI 2 | Notes |
|  |  |  | during the lifetime of the delivery solution. • Support the scheduling of 1st and 2nd Party assurance. |  |  |  |
|  |  | 2.1.3 | The SP shall provide information, analysis and support to assist in the production of monthly and annual creation of long-term, medium-term and short-term plans and resource assumptions by the Authority. | Civilian Driving Licence Acquisition Demand and Pipeline Management Process | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |

## DTP SoR 3 - TRAINING DELIVERY

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1 | The SP shall provide and maintain a service for the management, delivery and supervision of driver licence acquisition. | 3.1.1 | The Service shall be delivered to Officers and Other Ranks from the RN, Army, RAF. To MOD Civil Servants, IDT & IG trainees civilian commercial training and MOD, as directed by the HQ LWC, sS IDT requirements. | JSP 822: Vol 2: Defence Individual Training (February 2024). Civilian Driving Licence Acquisition Demand and Pipeline Management Process | Pass rate per classification to be met as articulated in KPI 3. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | Trainees must obtain a Cat B licence for Manual vehicles not Automatic. The training requirement (type and volume) is contained in the LWC HQ endorsed TPg. The TPg is produced annually and the relevant indicators are included within this section of the SoR at Annex A. The Authority may allocate student places on courses or modules either to Overseas Military trainees, or third parties to utilise spare capacity and generate income. Trainee management may include input all course competencies Authority systems/ TMIS). |
| 3.2 | The SP shall ensure the provision of SQEP Trainers. | 3.2.1 | The SP shall provide sufficient Trainers with the requisite skills, competencies and experience to deliver civilian licence acquisition training in a safe and secure | JSP 822, Vol 2: Defence Individual Training (February 2024) | As per SR 1.3 Ensuring maintenance of requisite Trainee/ Trainer ratios. | Current Trainee - Trainer ratios: Cat B - 2:1 |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | manner to the Performance Metrics (PM) required by the Authority. | Civilian Driving Licence Acquisition Demand and Pipeline Management Process JSP 375 Health and Safety (August 2024) Conform to the Driving & Vehicle Standards Agency (DVSA) Driver Training Code of Practice. Relevant driving licences. ADI Registration. Become an LGV driving instructor - GOV.UK (www.gov.uk) Are you ready to become PCV trainer? (safedrivingforlife.info) The Road Traffic Act 1988 (as amended) The Motor Cars (Driving Instruction) Regulations 2005 (as amended) Driving Instruction (Suspension and Exemption Powers) Act 2009 | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | Cat CE- 2:1 Cat D / D1- 3:1 - It may be necessary on occasion for the Authority to present Trainees individually. - Permission must be requested through the Authority before ratios are exceeded. - Trainees to have same instructor and vehicle throughout the course. - In exceptional circumstances, if the SP cannot provide the same Instructor and / or training vehicle, the SP shall notify the Authority of this and shall provide an alternate Instructor and / or training vehicle so that there is no pause in training. |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | The Driving Instruction (Compensation Scheme) Regulations 2012 The Motor Vehicles (Driving Licences) Regulations 1999 |  |  |
|  |  | 3.2.2 | The SP shall provide CPD for all Trainers, to ensure they remain competent, with up-to-date skills and knowledge for their relevant subject specialisation. CPD shall include: • The development of knowledge, skills and competencies as a Trainer. | JSP 822, Vol 1: Introduction (February 2024) JSP 822, Vol 2: Defence Individual Training (February 2024) JSP 822, Vol 4: Care and Welfare in Training (February 2024) | As per SR 1.3 Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
|  |  | 3.2.3 | The SP shall provide Teaching, Coaching and Mentoring to Trainers, to assist them in developing their skills and realising their full potential as Trainers. | JSP 822, Vol 2: Defence Individual Training (February 2024) | As per SR 1.3 Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
|  |  | 3.2.4 | The SP shall provide access for the Authority to monitor their Trainers. | JSP 822, Vol 5: Assurance of Training in Defence (February 2024). Civilian Driving Licence Acquisition Demand and Pipeline Management Process | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 3.3 | Shall deliver training to trainees in accordance with the TPg and | 3.3.1 | The SP shall review, assess and update Training Delivery to incorporate relevant | JSP 822, Vol 5: Assurance of Training in Defence (February 2024). | 100% Status reported and validated (excepting where | . |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  | incorporate recommendations and feedback |  | recommendations and feedback from InVal, ExVal and assurance (including 3rd Party audits). | Civilian Driving Licence Acquisition Demand and Pipeline Management Process | Authority agreement for non-compliance) at the MGPRM. |  |
| 3.4 | The SP shall monitor Trainee performance and provide feedback and/or mentoring to trainees and the Authority on their performance. | 3.4.1 | The SP shall provide remedial training, including outside Core Training Periods where necessary and approved by the Authority, for trainees who fail assessments and/or do not meet the required standards of performance within the prescribed conditions to assist such trainees in meeting the required standards. Record, track and be able to demonstrate to the Authority the remedial training provided to trainees. | JSP 822, Vol 2: Defence Individual Training (February 2024) | Effect to be achieved is a tailored remedial trg pathway specific to the trainee. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | The SP should consider how to tailor training to the individual trainee’s circumstances. |
|  |  | 3.4.2 | The SP Trainer shall provide input to Trainee Review Boards (TRB) as required. |  | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
|  |  | 3.4.3 | The SP shall provide extra instruction to trainees required to re-sit their driving tests outside standard formal instruction period. | JSP 822, Vol 2: Defence Individual Training (February 2024) Civilian Driving Licence Acquisition Demand and Pipeline Management Process | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | The SP shall consider how to tailor training to the individual trainee’s circumstances. The SP shall record, track and be able to demonstrate to the Authority the remedial training provided to trainees. |
| 3.5 | The SP will liaise with Defence Licencing and | 3.5.1 | The SP will liaise with Defence Licencing and Testing Authority | Civilian Driving Licence Acquisition Demand and | As per SR 1.3 | • It may take the Authority up to 3 |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  | Testing Authority (DeLTAs) regarding arranging Driving Tests. |  | (DeLTAs) regarding arranging Driving Tests. | Pipeline Management Process | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | working days to arrange a practical test. • Trainees will not be permitted to re-take a practical test for a period of 24 hours after a fail. The SP shall provide additional Tuition to the Trainee prior to their next practical test being taken as per the Civilian Driving Licence Acquisition Demand and Pipeline Management Process. The SP shall note that this requirement also includes assessments of Trainer competence and capability, where required by the Authority and/or regulatory requirements. This will be in line with the Civilian Driving Licence Demand and Pipeline Management Process |
| 3.6 | The SP shall provide a SpLD support service for trainees and SP staff, this shall include: | 3.6.1 | The SP shall provide a SpLD support service for trainees and staff, this shall include: | JSP 822 Defence direction and guidance for training and education - Volume 7: | As per SR 1.3 Status reported and validated (excepting |  |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  | - ensure that there are suitably trained, qualified, and placed SpLD Advisors throughout the SCs. Including making provision for ongoing SpLD Advisor training and Continuous Professional Development (CPD). - ensure that the Chain of Command, including trainers are, suitably educated as to the nature of SpLD and emphasise the necessity to take appropriate action early but sensitively when a SP displays signs of a learning difficulty / difference. - treat all records with care, obtaining a MOD Consent to Share SpLD Information and Data form when required, marking up any documentation as OFFICIAL SENSITIVE – PERSONAL - fund appropriate and feasible support for |  | - ensure that there are suitably trained, qualified, and placed SpLD Advisors throughout the SCs. Including making provision for ongoing SpLD Advisor training and Continuous Professional Development (CPD). - ensure that the Chain of Command, including trainers are, suitably educated as to the nature of SpLD and emphasise the necessity to take appropriate action early but sensitively when a SP displays signs of a learning difficulty / difference. - treat all records with care, obtaining a MOD Consent to Share SpLD Information and Data form when required, marking up any documentation as OFFICIAL SENSITIVE – PERSONAL - fund appropriate and feasible support for the SP, as well as making changes to the working or training environment, which may also need external support, such as assessments by a Specialist Teacher or Psychologist. Advise the SP on what funding support they may expect. | Specific Learning Differences (February 2024) Civilian Driving Licence Acquisition Demand and Pipeline Management Process The SP shall ensure that SpLD support is provided by suitably qualified and experienced personnel, in accordance with the qualification, competency and experience requirements. The SP shall ensure that personnel providing SpLD support remain competent, with up-to-date skills and knowledge appropriate to their roles. | where Authority agreement for noncompliance) at the MGPRM. |  |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  | the SP as agreed with the Authority, as well as making changes to the working or training environment, which may also need external support, such as assessments by a Specialist Teacher or Psychologist. Advise the SP on what funding support they may expect. |  |  |  |  |  |
| 3.7 | The SP shall adhere to the relevant TQM as laid out in DVSA driver training standards. | 3.7.1 | The SP shall adhere to the relevant TQM as laid out in DVSA driver training standards to ensure that the Training Services are provided to the quality and standards required by the Authority and are compliant with endorsed policies. | ISO 9001:2015 Quality Management System. DVSA Driver Training Standards In accordance with applicable Authority Standing Orders and instructions. | In accordance with applicable Authority Standing Orders and instructions. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 3.8 | The SP shall facilitate Training Evaluations. Shall ensure that relevant actions and recommendations from Training Evaluations are implemented to improve the quality and costeffectiveness of the Training Services. | 3.8.1 | The SP shall undertake Evaluation of Training in accordance with the Training Evaluation Strategies agreed with the Authority, and shall implement relevant actions and recommendations to improve the quality and cost-effectiveness of training | JSP 822: Defence Training Support Manuals (DTSM) 5: Evaluation of Individual Training | As per SR 1.3 Recommendations to be implemented within 10 working days of Authority approval. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 3.8.2 | The SP shall participate and support InVal of training to assess and assure that training is effective, efficient and achieves the the relevant training standards, and shall implement relevant actions and recommendations from InVal to improve the quality and cost-effectiveness of training. | JSP 822, Vol 5: Assurance of Training in Defence (February 2024). | As per SR 1.3 Recommendations to be implemented within 10 working days of Authority approval. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
|  |  | 3.8.3 | The SP shall provide administrative support, information and analysis to help coordinate and facilitate ExVal by the Authority (or their designated representatives) so, that the Authority can assess, in an effective and efficient manner, how well training has prepared trainees for their role and the contribution of training towards the achievement of operational goals. | JSP 822, Vol 5: Assurance of Training in Defence (February 2024). | Recommendations to be implemented within 10 working days of Authority approval. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | This supporting the delivery of ExVal by the Authority not conducting. |
| 3.9 | The SP shall manage and deliver 1st Party Audits of the Training Service. The SP shall also facilitate and support 2nd Party and 3rd Party Audits and inspections of the Training. | 3.9.1 | The SP will coordinate, manage and deliver 1st Party Audits of the Training Services, in accordance with their assurance plan and 1st Party Audit Terms of Reference and reporting results to the Authority. | JSP 822, Vol 5: Assurance of Training in Defence (February 2024). | To be delivered in accordance with 1st Party Audit plan which is endorsed by Authority annually. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | The scope of this 1st Party, 2nd and 3rd Party Audit service is included within the JSP 822. |

### 10

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 3.9.2 | The SP shall ensure that relevant actions and recommendations from 1st Party Audits are implemented in a timely manner to improve the quality and cost-effectiveness of training. | JSP 822, Vol 5: Assurance of Training in Defence (February 2024). | Recommendations to be implemented within 10 working days of Authority approval. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | The SP shall not unreasonably withhold access to relevant data, personnel, facilities and resources required to complete inspections. |
|  |  | 3.9.3 | The SP shall provide information, analysis and administrative to help coordinate and facilitate 2nd Party and 3rd Party Audits. Shall implement relevant actions and recommendations from such audits to improve the quality and cost-effectiveness of training and duty of care of the trainees whilst they are under their supervision. | JSP 822, Vol 5: Assurance of Training in Defence (February 2024). . | Recommendations to be implemented within 10 working days of Authority approval. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
|  |  | 3.9.4 | The SP shall provide information, analysis and administrative to help coordinate and facilitate inspections of training. Shall implement relevant actions and recommendations from such inspections to ensure adherence to required regulations and standards and to improve the quality and cost-effectiveness of training. | JSP 822, Vol 5: Assurance of Training in Defence (February 2024). | Recommendations to be implemented within 10 working days of Authority approval. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |

9

DTP SoR 4 - TRAINING SUPPORT (COMPRISING BUSINESS AND GENERAL TRAINING SUPPORT)

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 4.1 | The SP is to support visits, inspections and audits. |  | The SP is to support authorised visits, inspections and audits. They must co-operate with the authorised auditing crown servants personnel by allowing access to data managed and maintained by the SP on behalf of the Authority. |  | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.2 | The SP shall be responsible for all GFA issued to them. |  | The SP shall be responsible for all GFA issued to them to deliver the outputs under this Delivery solution in line with the relevant standards and policies. |  | As articulated in KPI 4. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | Details of GFA can be found in Schedule 13. The Authority will provide office space for SP On-Site Management, but the SP will be responsible for providing the office furniture, phone, IT equipment, and internet access |
| 4.3 | The SP shall comply with and maximise the Authority’s Energy Management Policies. |  | The SP shall maximise, promote and maintain an agreed positive energy and conservation policy to avoid waste, conserve energy and reduce emissions. | JSP 418 Management of environmental protection in Defence (December 2014) | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.4 | The SP shall produce a Risk Management Plan (RMP) for the delivery of the Delivery solution. |  | The SP shall provide and maintain a RMP plan which shall be reviewed and tested annually. |  | To be reviewed annually. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 4.5 | The SP shall operate within the Site Safety Management Plans. |  | The SP shall operate within the following: - Legionella Management Plan. - Gas safety Plan - Asbestos Plan - Electrical Safety | JSP 375 Health and Safety (August 2024) | To be reviewed annually. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | Hard FM Supplier to provide Safety Management Plans. |
| 4.6 | The SP shall produce, maintain and annually update a Business Continuity Plan including Risk Register, for the resilience and the prioritised recovery of essential equipment and services. |  | The SP shall provide and maintain a business continuity and Disaster Recovery plan which shall be reviewed and tested annually. |  | To be reviewed and tested annually. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.7 | The SP shall establish, implement and deliver a programme of measures which are designed to secure continuous improvement and innovation throughout the life of the delivery solution. |  | The SP is to provide an annual Continuous Improvement Plan (CIP). The SP shall maintain a Continuous Improvement Register, shared with the Authority, recording all CI initiatives, whether approved or not, when implemented and completed, the benefits anticipated and realised. Programme those continuous improvement initiatives which it has been agreed with the Authority should be implemented. |  | To be reviewed annually. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | The SP shall submit substantive and deliverable proposals and recommendations in accordance with Delivery solution. The SP shall provide SMEs to engage with the Authority in gaining endorsement for change and in managing its implementation. |  |  |  |
| 4.8 | The SP will deliver a Performance Management Plan. |  | The SP shall provide and maintain a Performance Management Plan which shall be reviewed and tested annually. |  | To be reviewed and tested annually. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.9 | The SP shall provide a Quality Management Plan specifying how all Delivery solution related quality requirements shall be fulfilled. |  | The SP shall provide and maintain a Quality Management Plan which shall be reviewed and tested annually. |  | To be reviewed and tested annually. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.10 | The SP is to provide, implement and maintain a QA System. |  | The SP shall provide and maintain a QA System which shall be reviewed and tested annually. | ISO 9001:2015 Quality Management System. or equivalent Industry Standard ISO 45001 Occupational Health & Safety | To be reviewed and tested annually. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 4.11 | The SP shall provide accurate and accessible information, analysis and reporting to the Authority relating to the delivery of the Service Requirements in the scope of this Delivery solution, to enable the SP and the Authority to monitor and assure service delivery. |  | The SP shall provide accurate input to and use the Authority provided TMIS in line with standards and policies. | Civilian Driving Licence Acquisition Demand and Pipeline Management Process JSP 940 MOD policy for Quality (May 2020 & June 2021) | Input within a maximum of 5 working days and to be reviewed and agreed monthly . Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.12 | The SP shall provide accurate and accessible forecast, in-year and outturn financial information and analysis to the Authority in relation to the delivery of the Training Service, against categories to be agreed with the Authority. |  |  |  | Financial status reported and validated (excepting where Authority agreement for non-compliance) at the MGPRM. | The Authority reserves the right to access any additional SP data and records related to any aspect of the Training Service as it deems necessary, in accordance with the terms and conditions of the Delivery solution. Categories for the itemisation of financial information will be agreed with the Authority prior to the relevant Service Commencement Date for the Training Service. The Authority reserves the right to require changes in the categorisation of financial information |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | during the life of the Delivery solution. |
| 4.13 | The SP shall provide accurate and accessible information, analysis and reports to the Authority, to enable the Authority to manage and assure the SP’s performance and exercise effective management of the Delivery solution. | 4.13.1 | The SP shall provide data collection and reporting to the Authority in accordance with the KPI and Performance Management Strategy. | JSP 441 Defence-recordsmanagement-policy-andprocedures (July 2019) Civilian Driving Licence Acquisition Demand and Pipeline Management Process | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.14 | The SP shall provide Delivery solution information, analysis and reports to the Authority, to enable the operation of effective delivery solution management Information and analysis shall include, qualitative supplementary and contextual information and analysis to enable the Authority to interpret performance management information accurately, and information and analysis required to inform governance and decision making. |  |  | JSP 441 Defence-recordsmanagement-policy-andprocedures (July 2019) Civilian Driving Licence Acquisition Demand and Pipeline Management Process | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.15 | The SP shall provide information, analysis and reports to the Authority to enable the Authority to | 4.15.1 | Information and analysis shall in line with the CIP and relevant standards and policies. | JSP 441 Defence-recordsmanagement-policy-andprocedures (July 2019) | Status reported and validated (excepting where Authority agreement for non- | The Continuous Improvement Plan shall be provided to the Authority in accordance |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  | assure Continuous Improvement opportunities and the SP’s performance against the CIP. |  |  | Civilian Driving Licence Acquisition Demand and Pipeline Management Process | compliance) at the MGPRM. | with the terms and conditions of the delivery solution. |
| 4.16 | The SP shall notify the Authority immediately in the event of instances or events related to the Training Services which are likely to attract media interest. | 4.16.1 | The SP shall notify the Authority immediately of any media approaches/ queries to the SP which relate to the Training Services and/or the services provided by the SP under this Delivery solution, prior to the SP responding to such approaches / queries. Information shall normally be provided to the Authority within five (5) working days of the Authority’s request. The Authority may, by exception, request a shorter response time, which the SP shall make best endeavours to achieve. | JSP 441 Defence-recordsmanagement-policy-andprocedures (July 2019) Civilian Driving Licence Acquisition Demand and Pipeline Management Process | To notify the Authority within 1 working day of media approach. To respond to the Authority requests for information within 5 working days or less as directed. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM | The SP shall not respond to media approaches/queries relating to the Training Service and/or the services provided by the SP under this Delivery solution without the prior approval of the Authority. |
| 4.17 | The SP shall provide administrative support necessary to enable delivery of the training required to meet the Authority's training requirements in a timely, efficient and effective manner. | 4.17.1 | The SP shall provide general administrative support to establishments to ensure their effective operation in line with relevant standards and policies.. | Civilian Driving Licence Acquisition Demand and Pipeline Management Process Data Protection Act 2018 | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.18 | Where the SP occupies Authority provided premises, the SP shall provide a Building Custodian Service. | 4.18.1 | The SP shall provide a Building Custodian Service. In addition to the terms of reference for Building Custodians (BCs) this service shall include: | The Management of Health and Safety at Work Regulations 1999 Health and Safety at Work Act 1974 | Need to ensure timelines are met. There are zero missed training days due to lack of appropriate inspections and any | This requirement is not applicable if only office space is provided within an Authority owned and controlled building. |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | - Appointing BCs in order to manage building areas used to deliver work specified in the Statement of Requirement. - Checking to confirm the provision and proper use of any personal protective equipment required for the SP to minimise the risk of injury to as low as reasonably practicable. - Checking all non GFA electrical equipment is PAT tested and in the correct state of repair. - Ensure that the Authority’s Delivery solutioned SP is made aware of any shortcomings in provision of general furniture, fixtures and fittings. - Liaise with the Authority’s Delivery solutioned SP to ensure the correct management and disposal of hazardous waste from the building. - Building Security and access control. - Health and Safety and Fire Warden. - Risk assessments as appropriate for the building and its usage. (Not the Risk assessments | The Workplace (Health, Safety and Welfare) Regulations 1992 The Personal Protective Equipment at Work Regulations 1992 The Control of Substances Hazardous to Health Regulations 1999 The Control of Substances Hazardous to Health (Amendment) Regulations 2004 The Provision and Use of Work Equipment Regulations 1998 ACSO 1200 British Army safety and environmental management system JSP 375 Health and Safety (August 2024) | subsequent repair/maintain requirements. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | PAT Testing for GFA undertaken by Authority 3rd Party. A nominated custodian provided by the SP on behalf of the Authority. The BCs will have to respond effectively to the Authority and Regional Prime SPs at the appropriately level. In regards to the provision and proper use of any personal protective equipment, this includes any general equipment required in offices, classrooms and building. The Authority will provide equipment associated with specific training serials All equipment to be tested prior to initial use and annually thereafter under Authority arrangements. |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | for the training activity, Functional groups are the owner and custodians of these.) - Nominated and in date and qualified First Aider. - Co-ordinate building facilities bookings. - Opening and closing buildings. |  |  | Liaise with the Authority to ensure that buildings are available as required by the Authority. Health and Safety Warden will conduct briefings to all staff and joining briefs when required, maintain records, H&S Logs and notice boards. A qualified First Aider is to be nominated for each building. The Authority will conduct and record annual inspections rounds of all buildings. All buildings are to be open for core hours unless otherwise specified. The responsibility for opening and closing buildings shall be a shared responsibility between Authority and SP staff. Access to the register to be allowed during normal working hours |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | by the Authority, the Authority’s Delivery solutioned SP, and authorised 3rd parties |
|  |  | 4.18.2 | The SP shall provide a service that will conduct routine inspections of building facilities report all material defects to Authority Establishment Office and ensure that all rectifications are carried out correctly, safely and in the appropriate timescales. | The Provision and Use of Work Equipment Regulations 1998 | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
|  |  | 4.18.3 | For buildings occupied by the SP, the SP shall provide H&S briefs for all new staff members, trainees and other personnel as required. | The Management of Health and Safety at Work Regulations 1999 | 100% for all new personnel and trainees. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.19 | The SP shall produce, maintain and annually update a Health, Safety and Environmental Protection Plan. |  | The SP shall produce, maintain and annually update a Health, Safety and Environmental Protection Plan. | JSP 375 Health and Safety (August 2024) | To be reviewed and updated annually. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.20 | The SP and their delivery and supply chains are, at all times, to comply with the requirements of the | 4.20.1 | The SP shall provide a qualified Health & Safety Advisor responsible for ensuring that the SP's employees and the DO are | JSP 375 Health and Safety (August 2024) | 100% compliance. Status reported and validated (excepting | Utilise Authority MIS |
| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
|  | Health and Safety at Work Act 1974 and all relevant legislation. They must also conform to all requirements as specified in the LWC Health, Safety and Environmental Protection (HS&EP) policy, practices and safe working procedures of the Authority covering their activities. The SP shall keep records to demonstrate that this is being carried out. |  | kept fully informed on H&S matters related to the Contract. The SP shall adhere to the LWC and RC HS&EP policy and integrate into the Garrison HS&EP organisation as required by the DO and shall participate fully in such meetings, discussions and committees as required by the Authority. No instances of non-compliance or unwarranted/unmanaged hazards. Accidents including near misses are to be reported to the SHEF Cell within 48 hours on Army Form 510 in accordance with HS&EP Policy. The SP shall inform the SHEF Cell of any pending inspections by the HSE or other legislative bodies. Subsequent reports and any proposed remedial action plans from such inspections are also to be copied to the SHEF Cell. |  | where Authority agreement for noncompliance) at the MGPRM. |  |
|  |  | 4.20.2 | The SP shall provide and manage personnel who are trained, qualified and in date in First Aid at Work (FAWR), appropriate for the conditions and equipment they will be working with, ensuring cover is available when training is being undertaken | JSP 375 Health and Safety (August 2024) FAWR. | As per SR1.3. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 4 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 4.21 | Provide environmental control and management in line with the SPs Environmental Control and Management plan. The SP shall control, monitor and report any environmental issues that impact on Service delivery and take prompt action to minimise any adverse environmental impact. |  | Provide environmental control and management in line with the SPs Environmental Control and Management plan. The SP shall control, monitor and report any environmental issues that impact on Service delivery and take prompt action to minimise any adverse environmental impact. | JSP 375 Health and Safety (August 2024) | 100% compliance. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 4.22 | The SP is to provide, implement and maintain Environmental Management System (EMS). |  | The SP shall provide and maintain a Environmental Management System (EMS) which shall be reviewed and tested annually. | ISO 14001:2015 Environmental Management System ISO 45001 Occupational Health and Safety | To be reviewed and tested annually. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |

## DTP SoR 5 - EQUIPMENT SUPPORT

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1 | The SP shall work with the Authority or its Designated Delivery solution or to ensure vehicle and equipment maintenance is carried out by appropriately qualified personnel. | 5.1.1 | The SP shall provide a service to operate and provide maintenance for vehicles and equipment supplied by the SP. | Vehicles and equipment availability to be such to meet the TP and weekly TP. | As articulated in KPI 3. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | SP will need maintenance facilities off site. The Authority shall retain the right to evidence of insurance and road worthiness of vehicles. - Insurance shall cover Defence Driving Examiners (DDE’s) and Driving Licence Acquisition Instructors (DLAI) whilst they are: - driving and/or in control of the SPs vehicles. - conducting assessments as part of the Assessment Point Withdrawal process. |
|  |  | 5.1.2 | The SP will carry out a before use inspection of all vehicles, training aids equipment and infrastructure they are going to use prior to use by trainees. Any safety issues are to be highlighted immediately to the Authority and unless immediate rectification can take place is to be placed out of bounds unless the Authority accepts the risk. |  | 100% of inspections to be carried before equipment use. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | The use of MoD facilities is not guaranteed, therefore the SP shall be required to identify alternative parking and manoeuvring areas which could be used in the event of non-availability within 1 hour travelling time of the OTT pick up point to ensure no break in training. |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | These will be agreed between the SP and Authority on a case by case basis as required. |
| 5.2 | The SP shall ensure the vehicles for licence acquisition training complies with DVSA vehicle requirements and Authority age requirements. |  | The SP shall ensure all SP supplied vehicles for delivery of licence acquisition training comply with DVSA vehicle requirements and Authority age requirements: - Cat B/BE vehicles shall be no more than 5 years old. - Cat C/CE/D1 and D1E vehicles shall be no more than 10 years old. - Cat D vehicles have no prescribed age limit; however, vehicles shall be serviceable clean and presentable. | Driving test: cars: Using your own car for your test - GOV.UK (www.gov.uk) Rules for lorries used for driving tests - GOV.UK (www.gov.uk) Rules for buses and coaches used for driving tests - GOV.UK (www.gov.uk) | 100% compliance. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | - The Authority shall retain the right to inspect all vehicles and trailers for roadworthiness at any time during the Contract period and to reject the use of any training vehicle that it deems to be unsuitable for training. - There is no requirement to fit Vocational vehicles with dual controls; however, Trainees may be limited in experience and only passed their Category B Practical test the previous week, therefore it is recommended. |
| 5.3 | The SP shall provide vehicle and equipment management, support, and maintenance service for SP supplied vehicles and equipment. | 5.3.1 | The SP shall support and maintain vehicles and equipment to ensure such equipment is available and ready for use to enable Training Delivery as scheduled in the Training Plan. | The Road Vehicles (Construction and Use) Regulations 1986 (legislation.gov.uk) Rules for lorries used for driving tests - GOV.UK (www.gov.uk) | 100% availability to meet training demand. An unserviceable vehicle or vehicle that is regarded as unsuitable by the Authority shall be repaired or replaced by no later than the start of the next training day. |  |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | In the event of a break down the SP is to return the trainees to the pick up point. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
|  |  | 5.3.2 | The SP shall undertake all the activities necessary to support and maintain SP vehicles and equipment to ensure that such equipment is safe, compliant with relevant regulations and ready and available to enable Training Delivery in accordance with the Training Plan. |  | 100% SP supplied vehicles meet DVSA Minimum Test Standards for vehicle category and presented for training at MOT standard. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 5.4 | When agreed between the Authority and the SP, the SP shall provide dispose of SP Assets/ Equipment to support training and move training vehicles to locations as required. | 5.4.1 | When agreed between the Authority and the SP, the SP shall dispose of Assets/ Equipment to support training in a safe and secure manner and in accordance with Legislation. | The Road Vehicles (Construction and Use) Regulations 1986 (legislation.gov.uk) | 100% within 1 month unless agreed with the Authority in line with SP disposal plan. Status reported and validated (excepting where Authority | The Authority reserves the right to request sight of disposal documentation. |

| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | agreement for noncompliance) at the MGPRM. |  |
|  |  | 5.4.2 | The SP shall provide a service to load, off-load and manoeuvre equipment on site. |  | 100% completed within timeframe agreed within MGPRM or equivalent trg delivery coordination mtg. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
|  |  | 5.4.3 | Provide a service to move vehicles being used as training aids, on site, to the location of training and if necessary moved to a storage location on completion of training. |  | 100% completed within timeframe agreed within MGPRM or equivalent trg delivery coordination mtg. Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 5.5 | The SP must dispose of all waste including hazardous waste using the site-specific delivery solutions in place. The SP must work with the |  |  | JSP 375 Health and Safety (August 2024) | 100% within 1 week of identification unless agreed with the Authority in line with SP disposal plan. |  |
| SR# | Level 2 Service Requirement | SR# | Level 3 Service Requirement | Standards and Policies (current and superseded) | Performance Indicator (PI) Linked to KPI 3 | Notes |
|  | Authority site management team (who are not within this delivery solution scope) to ensure waste is disposed of in a legal and environmentally responsible manner. |  |  |  | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. |  |
| 5.6 | The SP may be required to operate Authority vehicles. | 5.6.1 | The SP may be required to operate Authority vehicles. This will include but not be limited to: - Cars for the purpose of the coordination of driving tests. - Other Authority vehicles when requested. Contractor personnel operating Authority vehicles must do so in strict compliance with JSP 800. Other Authority vehicles as and when requested. | JSP 800: Vol 5 Road Transport Policy (Leaflet 16: Use of MOD Vehicles by Contractors (August 2024) | Status reported and validated (excepting where Authority agreement for noncompliance) at the MGPRM. | The use of Authority vehicles will be limited to DST Leconfield; if the Authority has specific requirement, and sufficient assets permit, the Authority may request this service in other locations. |

OFFICIAL-SENSITIVE COMMERCIAL

Annex A to

DTP CDLA SoR

## Dated 22 Oct 24 ESTIMATED TRAINING THROUGHPUT

Note:

- For all serials in Annex A, where a Theory element / test is required in order to start / complete the respective qualification / competency this is delivered by the Authority prior to training by the SP.

- Current training locations for Civilian Driving Licence Acquisition can be found at Ref A

- Min, Most Likely and Max figures are subject to change.

- Courses are subject to change.

Training Year 26/ 27 Estimate

| Joint Service Course Code (Subject to change) | Joint Service Course Name | Training Vehicles | Min TY 26/27 | Most Likely TY 26/27 | Max TY 26/27 |
| --- | --- | --- | --- | --- | --- |
| (a) | (b) | (c) | (d) | (e) | (f) |
| 11C/CS11 11C/CA11 | Licence Acquisition Category B (ITT and STT) | DVSA test standard compliant manual car | 3350 | 5385 | 6950 |
| 11C/A11E | Licence Acquisition Category E for B (STT) | DVSA test standard compliant manual car | 0 | 5 | 10 |
| 11C/SC11 11C/AC11 | Licence Acquisition Category C (ITT & STT) | DVSA test standard compliant | 570 | 765 | 860 |
| 11C/CS16 11C/CA16 | Licence Acquisition Category E for C (ITT & STT) 3 4 | DVSA test standard compliant | 45 | 80 | 180 |
| 11C/CS15 11C/CA15 | Licence Acquisition Category C+E for C (ITT & STT) | DVSA test standard compliant | 1740 | 3300 | 4125 |
| 11C/A021 | Licence Acquisition Category D1 | DVSA test standard compliant | 35 | 50 | 60 |
| 11C/A21E | Licence Acquisition Category E for D1 (Adv Trg only) | DVSA test standard compliant | 0 | 5 | 15 |
| 11C/0021 | Licence Acquisition Category D | DVSA test standard compliant | 10 | 40 | 65 |

Table 2: Training Year 26/ 27

- For those who already have Cat C Licence.

- Includes Service Leavers Licence Acquisition Course

OFFICIAL-SENSITIVE COMMERCIAL

A1 of 2

OFFICIAL-SENSITIVE COMMERCIAL

Annex A to

DTP CDLA SoR

Dated 22 Oct 24

- Year Most Likely Estimate

| Joint Service Course Code (Subject to change) | Joint Service Course Name | Most Likely TY 26/27 | Most Likely TY 27/28 | Most Likely TY 28/29 | Most Likely TY 29/30 | Most Likely TY 30/31 |
| --- | --- | --- | --- | --- | --- | --- |
| (a) | (b) | (c) | (d) | (e) | (f) | (g) |
| 11C/CS11 11C/CA11 | Licence Acquisition Category B (ITT and STT) | 5385 | 5385 | 5385 | 5385 | 5385 |
| 11C/A11E | Licence Acquisition Category E for B (STT) | 5 | 5 | 5 | 5 | 5 |
| 11C/SC11 11C/AC11 | Licence Acquisition Category C (ITT & STT) | 765 | 765 | 765 | 765 | 765 |
| 11C/CS16 11C/CA16 | Licence Acquisition Category E for C (ITT & STT) 5 6 | 80 | 80 | 80 | 80 | 80 |
| 11C/CS15 11C/CA15 | Licence Acquisition Category C+E for C (ITT & STT) | 3315 | 3315 | 3315 | 3315 | 3315 |
| 11C/A021 | Licence Acquisition Category D1 | 50 | 50 | 50 | 50 | 50 |
| 11C/A21E | Licence Acquisition Category E for D1 (Adv Trg only) | 5 | 5 | 5 | 5 | 5 |
| 11C/0021 | Licence Acquisition Category D | 40 | 40 | 40 | 40 | 40 |

Table 3: 5 Year Most Likely (ML) Estimate

- For those who already have Cat C Licence  requirement is under review.

- Includes Service Leavers Licence Acquisition Course

OFFICIAL-SENSITIVE COMMERCIAL

A2 of 2

Security Clearnce (SC) may be required at some locations – the Authority will confirm.

Training volumes can increase and decrease due to a number of factors including, but not limited to, recruitment and operational requirements.