## Sheet1
Cemetery Chapel, Tabley Road, Knutsford
SCHEDULE OF WORKS
ITEM | DESCRIPTION | QTY | UNIT | RATE (£)
1 | GENERAL ITEMS
1.0.1 | Internal repair and refurbishment of an existing chapel.
1.1 | DRAWINGS/PLANS/SPECIFICATIONS
1.1.1 | The drawings provided (if provided) are to be used as a basis for estimating, work scope and for any other purposes the Principal Contractor may wish.
1.1.2 | Responsibility for ascertaining quantities or areas other than those identified and the actual detailed construction will remain with the Contractor, and claims for failure to correctly identify or ascertain the same will not be entertained.
1.1.3 | The Principal Contractor is to retain on site for use by sub-contractors, Contract Administrator, Employer and others all plans, specifications and other reference documents.
1.1.4 | The Contractor shall allow for ascertaining and complying with all notices required under the Acts of Parliament, Police requirements, regulations and bylaws and pay all fees legally due.
1.2 | PLANT, SCAFFOLDING TOWERS, CRADLES, HOISTS AND TOOLS
1.2.1 | The Principal Contractor shall provide all necessary plant, scaffolding, propping, cradles, hoists and tools that might be required for the execution of the works and for all materials, carriage, cartage, labour, tarpaulins and whatever else may be required in connection therewith for the proper execution of the works.
ITEM | DESCRIPTION | QTY | UNIT | RATE (£)
1.2.2 | The Principal Contractor shall include to erect and maintain all necessary plant, shoring, cranes, hoists, cradles and similar that might be required for the proper execution of the works, and shall adapt, adjust or alter as necessary until no longer required or completion of the works, whichever is later. Inspect and test equipment regularly and daily before use in accordance with Health and Safety Regulations.
1.2.3 | The Principal Contractor must accept full responsibility for the stability and structural integrity of all works during the contract and maintain and replace as necessary.
1.2.4 | The Principal Contractor will bear sole responsibility for provision, maintenance and insurance for loss and expense of all plant, scaffolding, hoists, cranes, cradles, tools and vehicles used on site.
1.2.5 | The Principal Contractor shall be responsible for any damage to fabric or property or any adjoining properties as a result of any plant, scaffolding, cranes, hoists, tools, cradles and vehicles and must make good at his own expense.
1.2.6 | The site and adjoining highways, paths, etc, must be kept free from obstruction, rubbish and surplus materials and at all times the fire escape routes from the building should remain free from obstruction.
1.2.7 | The Contractor shall include for clearing away from the site all debris, waste and redundant materials which may accumulate as a result of the work and leave the whole of the premises clean and tidy on completion.
1.2.8 | The JCT Agreement for Minor Works will be employed. With the employers to insure the building and the contractor to insure the works. Payment will be made within 28 days of receipt of certificate. Contractors banking account details should be sent to the Project Surveyor prior to commencement.
1.3 | SUB-CONTRACTORS
1.3.1 | Make the CA aware of all sub-contractors for approval prior to appointment.
ITEM | DESCRIPTION | QTY | UNIT | RATE (£)
1.4 | PROGRAMME
1.4.1 | No works to be started without prior arrangement with the Contract Administrator (CA) and agreement of the Programme of Works. No claims for loss of time and other changes will be entertained should the above procedure not be complied with.
1.5 | INSTRUCTIONS ON PRICING SCHEDULE OF WORK
1.5.1 | Each item must be priced individually and totals provided for each section on the Collection pages.
1.5.2 | To save time please ask your sub-contractors to provide a breakdown of their costs at the outset and include this with the priced specification if asked to do so after the tender results.
1.5.3 | The works are to generally comply with the reference specification (Available upon request) for standards and workmanship, inform the CA of any conflict between the reference specification and the schedule of works.
1.5.4 | Should it be apparent that where there is a conflict between any specified materials or products with the actual construction or that of another specified product the contractor will inform the CA for further instruction.
1.5.5 | Before placing orders for materials and products ensure that a compatibility check is carried out and sub-contractors communicate to avoid compatibility issues on site.
1.6 | LISTED BUILDING
1.6.1 | Note that the building is Grade II listed.
2 | WORK ITEMS
2.1 | SITE SET UP
2.1.1 | Allow for providing Heras type fencing to areas of the site where applicable. Maintain fencing through contract period as per BS5837:2550.
ITEM | DESCRIPTION | QTY | UNIT | RATE (£)
2.1.2 | The contractor to provide a WC and rest area. All materials are to be stored within the site.
2.1.3 | All debris must be removed from site throughout and at completion of project.
2.1.4 | Note working hours are limited to between 7am – 7pm Monday to Friday. Extension to these hours by agreement with the client only.
2.2 | HEALTH AND SAFETY
2.2.1 | The project is not notified to the HSE, allow for compliance with all parts of the CDM 2015 Regulations.
2.2.2 | The principal contractor is to submit prior to commencement of the works, for approval by the Principal Designer a Health and Safety Plan, incorporating the pre-tender Health and Safety plan, project specific method statements, procedures, emergencies, communications, training and COSHH data and the like as the project demands. The contractor is to maintain and keep the Health and Safety plan on-site for inspection and throughout the project.
2.2.3 | Contractor to carry out a pre demolition asbestos survey. Asbestos survey to be carried out and a copy given to the contract administrator prior to commencement of works on site.
3 | WORK SCHEDULE
3.0.1 | Carry out a test patch of all specified systems for approval prior to the work commencing.
3.0.2 | Allow for safe access to all elevations for high level works to the roof and external walls.
3.0.3 | Allow for an Electrical test to be carried out to the existing installations.
3.1 | Demolition / Stripping Out
3.1.1 | Ensure that all services are disconnected or isolated in areas where the contractors are to work, prior to any stripping out or work being undertaken. Allow for a temporary supply of water and electricity for use by contractor.
ITEM | DESCRIPTION | QTY | UNIT | RATE (£)
3.1.2 | Hack off existing damaged plaster to internal walls in preparation to receive new work.
3.1.3 | Remove all existing rain water goods, cart arising to tip.
3.1.4 | Remove all existing pews from the chapel for storage by the client. Make good flooring to match the existing.
3.2 | Building Work
3.2.1 | To the defective and perished sections of the plasterwork most notable to the ante room, price here to hack off the defective plaster and renew with good quality lime plaster to match the existing. Include for carting all arising to tip.
3.2.2 | Remove the existing cast iron rainwater goods and renew with new cast iron rainwater goods. Size and section of the goods to match the existing. N.B. Include for decorating rainwater goods with colour to match the existing.
3.2.3 | To the corroded steel supports within the basement price here to strip back the corrosion to good sound metal and painted with a zinc primer and suitable painted finish.
3.2.4 | Several sections of the steel reinforcement to the floor are in a poor condition. Price here to remove the steel beams and renew to match the existing. Include for galvanic protection to the steel beams and for all propping of the floor and reinstatement of any affected sections of the concrete floor.
3.2.5 | Price here to internally form an opening within the chimney breast and install a vent. Externally the chimney pots are to be capped off with a mushroom type cap to allow for continual passive ventilation.
3.2.6 | Price here to provide ventilation to the cellar in the form of 2 no air bricks.
ITEM | DESCRIPTION | QTY | UNIT | RATE (£)
3.2.7 | There are localised areas of frost damaged, missing and inappropriately replaced clay tiles throughout the roof. Price here to renew the affected tiles throughout the roof slope with clay tiles to match the existing, for pricing purposes assume 50 tiles to be renewed in localised areas.
3.2.8 | Rake out the pointing to all elevations including the chimney stack to a minimum depth of 20mm. Pointing is to be renewed with a lime mortar mix to match the existing, finish to match the existing.
3.2.9 | Clean approximately 50m2 stonework utilising the DOFF superheated water system and remove all algae and moss and the like.
3.2.10 | Remove the ridge tiles to the dual pitched roofs and re-bed on lime mortar. Include for carting away all arising and making good where required.
3.2.11 | Price here to form new opening to the toilet from the chapel, include for 100x225mm p.c.c. lintels to support the masonry over. N.B. opening to accommodate a disabled width door.
3.2.12 | Price here to widen the existing door to the new kitchen, include for 100x225mm p.c.c. lintels to support the masonry over. N.B. opening to accommodate a disabled width door.
3.3 | Joinery
3.3.1 | Price here to remove the decayed timber door to the cellar and install a new timber door. Door to be renewed on a like for like basis including the renewal of all ironmongery on a like for like basis.
3.3.2 | Price here to cut out the decayed timber to the base of the door and frame to the anti rooms. Include for splicing in new timber to both the door and frame to match the existing.
3.3.3 | Remove and renew the cast iron opening lights to the stained glass windows. The cast iron opening sections are to be renewed on a like for like basis to fit within the existing window, include for re-using the stained glass from the original casement.
ITEM | DESCRIPTION | QTY | UNIT | RATE (£)
3.3.4 | Price here to remove and renew all cracked or damaged window panes. Window panes to be renewed on a like for like basis to match the existing.
3.3.5 | Price here to supply and install 2 no hardwood doors and frames including architraves to the kitchen and W.C. respectively. Door design to match the existing internal doors.
3.3.6 | Price here to supply and install new kitchenette to the left hand side anteroom. Fittings to include a range of high and low units including stainless steel sink, tap waste etc. For pricing purposes only kitchen to be based on a howdens shaker kitchen.
3.3.7 | Price here to provide a new glass external entrance door located within the arched opening. Allow for glazed panels over and adjacent to the door. Include N.B. all glass to be toughened and comply with the requirements of the Equality act and part M of the building regulations.
3.4 | Plumber
3.4.1 | Price here to create a disabled accessible toilet within the front right-hand side anteroom. Facilities to include new toilet, sink and baby changing facilities. Include for installation of all pipework as required and for connection with the existing incoming water supply. All for the supply and installation of an electric water heater to provide hot water to the sink only.
3.4.2 | Price here to connect all new kitchen incoming supplies and drainage. Include for the supply and installation of an electric water heater and connection with the kitchen sink.
3.4.3 | Price here to supply and install all new foul drainage, include for all excavation for new pipework and connection with the kitchen and toilet. Include for the supply and installation of new cast iron soil and vent pipe and connection with all above and below ground foul drainage. N.B. assume connection with the septic tank behing the lodge / making good of all surfacing on a like for like basis.
ITEM | DESCRIPTION | QTY | UNIT | RATE (£)
3.5 | Decoration
3.5.1 | Price here to renew the internal decoration throughout including all repaired and existing surfaces, prepare as required, and apply 2-coats good, quality emulsion paint finish to all painted walls and ceilings. N.B. Colours to match existing and be conservation approved paint suitable for lime plaster.
3.5.2 | Price here to renew the external decoration throughout including all repaired and existing surfaces, prepare as required, and apply 2-coats good, quality external quality paint finish to all painted timbers, and metals. N.B. Colours to match existing and be conservation approved paint.
3.5.3 | Price here to sand back the varnish finish to the woodblock flooring, include for renewing the varnished finish to match the existing.
3.6 | Electrics
3.6.1 | All existing lighting to be removed and replaced with LED bulbs. Contractor to design lighting system.
3.6.2 | Price here to supply and install an electric convector heating system throughout the chapel. System to be designed by the contractor.
3.6.3 | Price here to supply and install a new hardwired interlinked fire detection system throughout the chapel. System to be designed by specialist contractors.
3.6.4 | Price here to supply and install new hardwired mains operated intruder alarm with back up battery. Alarm to be designed by a specialist contractor and include for PIR sensors.
3.6.5 | Price here to supply and install a sound / PA system to the chapel only. System to be designed supplied and installed by specialist contractor.
3.6.6 | Price here to renew the electrical system including all switches, sockets and distribution board. For pricing purposes assume a like for like renewal of the existing.
ITEM | DESCRIPTION | QTY | UNIT | RATE (£)
4.1 | DAYWORKS AND CONTINGENCY
4.1.1 | The contractor is reminded that where overtime is worked at his own option, the wage rate payable will be the basic rates calculated, no allowance for additional cost of overtime working.
4.1.2 | Allow for a contingency of £7,000.00 only to be expended on the written authority of the CA. The contingency as a whole or part can be omitted from the contract sum. |  |  | 7000
5.1 | HANDOVER
5.1.1 | Contractor is to allow for providing all user manuals, commissioning certificates and the like at handover and for a repeat visit to provide user training.
| Total |  |  | 7000