## COVER PAGE
SCHEDULES OF WORK
-in respect of-
EXTERNAL REPAIR AND REDECORATION WORKS
-at-
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
-for-
THE HORNIMAN PUBLIC MUSEUM &
PUBLIC PARK TRUST
Chartered Quantity Surveyors
Unit 83, Capital Business Centre
22 Carlton Road
South Croydon
August 2021 |  | Surrey, CR2 0BS

## CONTENTS
Schedules of Work
-in respect of-
External repair and redecoration works
-at-
100 London Road, Forest Hill, London, SE23 3PQ
-for-
The Horniman Public Museum &
Public Park Trust
- comprising -
Section No. 1 | - | Conditions of Contract / Preliminaries
Section No. 2 | - | Work to the external elevations of the North / South Halls and Tower
Section No. 3 | - | Work to the external elevations of the Emslie Horniman building
Section No. 4 | - | Provisional redecoration works
Summary
Appendix A | - | Detailed terms of the Conditions of Contract
Appendix B | - | Detailed terms of the Preliminaries
Appendix C | - | Information relating to the Section No. 4 works

## SECTION No. 1
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
EXTERNAL REPAIR AND REDECORATION WORKS
SECTION No. 1
CONDITIONS OF CONTRACT / PRELIMINARIES
£ p
Following review of Appendix "A" and Appendix "B" the Contractor is to insert below his proposed costs in respect of the "Conditions of Contract" and "Preliminaries". In the event that no specific allowance is stated below the Contractor will be deemed to have covered elsewhere within the body of the pricing for the cost of fully complying with the terms detailed in Appendix "A" and "B".
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
1.14
1.15
SECTION No. 1 - CONDITIONS OF CONTRACT / PRELIMINARIES
|  |  | To Summary £ | 0

## SECTION No. 2
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
EXTERNAL REPAIR AND REDECORATION WORKS
= Contractor to insert pricing
SECTION No. 2
WORK TO THE EXTERNAL ELEVATIONS OF THE NORTH / SOUTH HALLS AND TOWER
£ p
2.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
2.1 - Temporary access / protection
2.2 - External survey / report
2.3 - Repair work (All approximate)
2.4 - New carpentry works
2.5 - Redecoration works
2.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 2.1 - TEMPORARY WORKS |  |  |  | 0
0
2.1.1 | Contractor Designed Portion: Provide alarmed scaffold (or access plant) in gaining access to the North, South and East Elevations of the North/South Halls and the South, East and West elevations of the Tower. Include for all necessary costs in respect of licences, hoists, safety netting, fans etc. Allow for altering and adapting the scaffold as required and remove on completion. | 1 | Item |  | 0
0
2.1.2 | in pricing the item above, given the scope of works so described in this document, the Contractor is requested to state how many weeks hire has been duly allowed for. |  | weeks |  | 0
0
2.1.3 | in the event that the CA instructs additional works (over and above that described below) thereby requiring the extended hire of the scaffold then the Contractor is requested to quote here his additional cost per week for such an eventuality. Should the Contractor elect to claim prolongation costs on this basis then he is reminded that the Contract provisions are to be followed and as such due 'cause and affect' will need to be demonstrated before the inclusion of costs will be considered. |  | / week |  | 0
0
0
2.1.4 | Note: The Contractor is to allow the Horniman Museum access to the scaffolding for the repositioning of site security cameras as required. | 0 | 0 | 0 | 0
0
2.1.5 | Note: The Museum will require any temporary access towers to be dismantled at the end of each day and stored securely overnight. | 0 | 0 | 0 | 0
0
0
0
| 2.2 - EXTERNAL SURVEY / REPORT |  |  |  | 0
0
2.2.1 | Allow for undertaking a condition survey, by a suitably qualified professional, to all elements of the existing external fabric of the building located on the elevations described in this section of the document (i.e. external brick walls, windows, doors, roof, chimneys etc.) in identifying where repair works are necessary to allow the building to be made fully weatherproof. In pricing this item, the Contractor is to allow for all necessary liaison in gaining access into the building as required. Upon completion of the survey allow for producing a detailed written report for subsequent handing to the CA / Employer. | 1 | Item |  | 0
0
0
0
| 2.3 - REPAIR WORK (ALL APPROXIMATE) |  |  |  | 0
0
2.3.1 | The works measured under this heading will be subject to remeasurement. As detailed at item 2.2.1 the Contractor is required to keep a detailed schedule of the repair works required / undertaken and this will serve as the basis of remeasurement of the below. | 0 | 0 | 0 | 0
0
0
| Replacement of broken glazing to existing windows |  |  |  | 0
0
| Standard clear float glass; 4mm thick; including careful removal of existing broken pane, preparation works to opening, installation of new pane and all necessary putty / making good works; as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
2.3.2 | panes (1No), area not exceeding 0.07m2 | 5 | No |  | 0
0
2.3.3 | panes (1No), area not exceeding 0.14m2 | 5 | No |  | 0
0
2.3.4 | panes (1No), area not exceeding 0.21m2 | 5 | No |  | 0
0
0
| Work to defective window glazing putty |  |  |  | 0
0
| Allow for raking out all loose putty material and for replacing with new, where glazing panes are unbroken but the glazing putty is defective; as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
2.3.5 | to single pane of glass; total length not exceeding 250mm | 50 | No |  | 0
0
2.3.6 | to single pane of glass; total length not exceeding 500mm | 25 | No |  | 0
0
2.3.7 | to single pane of glass; total length not exceeding 1000mm | 25 | No |  | 0
0
0
| Repair work to existing window frames / cills |  |  |  | 0
0
| Carefully remove defective timber to window frame / cill and undertake a 2 Pack epoxy resin window care repair; as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
2.3.8 | to area of decayed timber less than 50mm in diameter | 150 | No |  | 0
0
0
| Replacement of defective window cills |  |  |  | 0
0
| Carefully cut out defective timber window cill and replace with a hardwood cill to match the existing profile; as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
2.3.9 | not exceeding 600mm in length | 5 | No |  | 0
0
2.3.10 | not exceeding 1300mm in length | 5 | No |  | 0
0
2.3.11 | not exceeding 2500mm in length | 15 | No |  | 0
0
0
| Mastic |  |  |  | 0
0
2.3.12 | Allow for raking out defective mastic sealant and for providing new; as Landolt + Brown "Redecoration and Repair Specification" | 250 | m |  | 0
0
0
| Work to existing masonry walls |  |  |  | 0
0
| Allow for replacing missing or damaged facing brick; colour / standard of material all to match existing; as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
2.3.13 | brick repair comprising 1No new brick | 5 | No |  | 0
0
2.3.14 | brick repair comprising less than 3No new bricks | 3 | No |  | 0
0
2.3.15 | brick repair comprising less than 5No new bricks | 1 | No |  | 0
0
0
2.3.16 | Rake out defective mortar joints to facing brickwork and renew pointing in a colour / standard of material to match existing; as Landolt + Brown "Redecoration and Repair Specification" | 20 | m2 |  | 0
0
2.3.17 | Allow for cleaning face of masonry wall where staining evident; as Landolt + Brown "Redecoration and Repair Specification" | 20 | m2 |  | 0
0
0
| Work to existing rainwater goods |  |  |  | 0
0
2.3.18 | Allow for cleaning out and sealing any open/failing joints between the rainwater gutters and the fibreglass lining | 1 | Item |  | 0
0
0
| Work to existing flat roofs |  |  |  | 0
0
2.3.19 | Contractor Design Portion: Allow for removing the existing roof coverings to the single storey structure that is located at the bottom of the external steps on the East elevation; allow for providing new felt coverings together with all necessary flashings to the perimeter walls in ensuring that a weather tight installation is achieved to the flat roof upon completion | 1 | Item |  | 0
0
2.3.20 | extra for replacing the existing roof deck structure if it is found to be beyond serviceable use | 1 | Item |  | 0
0
2.3.21 | extra for reforming the timber fascia / soffit structures if they are found to be beyond serviceable use; including the temporary removal and subsequent reinstatement of the rainwater goods | 1 | Item |  | 0
0
0
| Provisional sums |  |  |  | 0
0
2.3.22 | Provide the Provisional Sum of £1,000.00 for additional repair works to the existing cupolas located above the North Hall | 1 | Item | 1000 | 1000
0
0
0
| 2.4 - NEW CARPENTRY WORKS |  |  |  | 0
0
| Work to existing cupolas |  |  |  | 0
0
| Allow for supplying and installing new louvre vents to the following cupolas; specification of the works to be all as described at section 7.0 of the Landolt + Brown "Redecoration and Repair Specification" (NB access can be obtained using the existing safety line system) |  |  |  | 0
0
2.4.1 | as described to East side of the 3No existing cupolas located above the North Hall; ref R.01, R.02 & R.03 | 1 | Item |  | 0
0
2.4.2 | Note: No work is required to the 4No cupolas to the South Hall as these were repaired and redecorated in 2017 | 0 | 0 | 0 | 0
0
0
| New insect mesh screens |  |  |  | 0
0
| Allow for supplying and installing new aluminium framed insect mesh screen to the internal face of the external windows; specification of the works to be all as described at section 7.0 of the Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
2.4.3 | as described to window sized 400 x 1275mm; location refs 2.13 | 1 | No |  | 0
0
2.4.4 | as described to window sized 2450 x 1200mm; location refs 2.07, 2.08, 2.09, 2.10 & 2.11 | 5 | No |  | 0
0
0
| New external door |  |  |  | 0
0
2.4.5 | Allow for supplying and installing a new single external door (type 'X') at roof level between flat roof (located above the South Hall) and the natural history lab; location ref 2.12; the style and construction of the door are all to match the existing installation | 1 | Item |  | 0
0
0
0
| 2.5 - REDECORATION WORKS |  |  |  | 0
0
| Work to the North elevation of the North Hall |  |  |  | 0
0
| Prepare and repaint all existing painted surfaces to the following external timber elements; specification to be as Landolt + Brown "Redecoration and Repair Specification"; the scope of works is to include the filling of any small cracks within the surface of the timber with any larger repairs being measured separately as a repair |  |  |  | 0
0
2.5.1 | window type ‘K’; approximate size 600 x 1050mm overall; at SF level refs 2.01 & 2.02 | 2 | No |  | 0
| ______________________________________________ |  |  |  | 0
0
2.5.2 | Note: No redecoration works are required to the external door at GF level. The door is now enclosed by a timber structure which is also outside the scope of these works. | 0 | 0 | 0 | 0
0
0
| Work to the East elevation of the North/South Halls |  |  |  | 0
0
| Prepare and repaint all existing painted surfaces to the following external timber elements; specification to be as Landolt + Brown "Redecoration and Repair Specification"; the scope of works is to include the filling of any small cracks within the surface of the timber with any larger repairs being measured separately as a repair |  |  |  | 0
0
2.5.3 | window type ‘A’; approximate size 1250 x 1450mm overall; at FF level; refs: 1.23 & 1.24 | 2 | No |  | 0
0
2.5.4 | window type ‘B’; approximate size 1250 x 2050mm overall; at GF level; refs: G.07, G.09, G.10 & G.11 | 4 | No |  | 0
0
2.5.5 | window type ‘C’; approximate size 1250 x 1800mm overall; at FF level; refs: 1.16, 1.17, 1.18, 1.19 & 1.20 | 5 | No |  | 0
0
2.5.6 | window type ‘D’; approximate size 2450 x 1200mm overall: |  |  |  | 0
0
2.5.7 | at GF level; refs G.01.NA, G.02, G.03, G.04, G.05 & G.06 | 6 | No |  | 0
0
2.5.8 | at FF level; refs 1.01.NA, 1.02.NA, 1.03.NA, 1.04.NA, 1.05.NA, 1.06.NA, 1.07.NA, 1.08.NA, 1.11.NA, 1.12.NA, 1.13.NA & 1.15 | 12 | No |  | 0
0
2.5.9 | at SF level; refs 2.03, 2.04, 2.05, 2.07, 2.08, 2.09, 2.10 & 2.11 | 8 | No |  | 0
0
| window type ‘E’; approximate size 2450 x 1850mm overall: |  |  |  | 0
0
2.5.10 | at FF level; ref 1.14 | 1 | No |  | 0
0
2.5.11 | at SF level; ref 2.06 | 1 | No |  | 0
0
2.5.12 | window type ‘G’; approximate size 900 x 1200mm overall; at FF level; refs 1.09 & 1.10 | 2 | No |  | 0
0
2.5.13 | window type ‘H’; approximate size 1200 x 1450mm overall; at FF level; ref 1.21 / 1.22 | 1 | No |  | 0
| ______________________________________________ |  |  |  | 0
0
2.5.14 | external double doors and infill panel over; doors located at GF level below windows G.12 & G.13 | 1 | Item |  | 0
0
0
| Prepare and repaint all existing painted surfaces to the following existing external metalwork; specification to be as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
2.5.15 | all existing rainwater gutters | 1 | Item |  | 0
0
2.5.16 | all existing rainwater downpipes, hoppers and anti-climb casings to the downpipes | 1 | Item |  | 0
0
2.5.17 | existing metal security grille (and timber panel behind) to redundant window opening; ref B.01 | 1 | Item |  | 0
0
2.5.18 | all sundry metalwork previously painted including: gas pipe, vent grilles, soil and vent pipes, security bars etc. | 1 | Item |  | 0
0
2.5.19 | 2No metal access ladders and handrails located on the North / South Halls barrell vaulted roofs | 1 | Item |  | 0
0
0
| Prepare and restain all existing stained surfaces to the following existing external timber elements; specification to be as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
2.5.20 | Pipe casing located next corner of East / North elevations | 1 | Item |  | 0
0
2.5.21 | external wall located at the bottom of the existing external steps to the East elevation | 1 | Item |  | 0
0
0
| Work to the clock tower elevations |  |  |  | 0
0
| Prepare and repaint all existing painted surfaces to the following external timber elements; specification to be as Landolt + Brown "Redecoration and Repair Specification"; the scope of works is to include the filling of any small cracks within the surface of the timber with any larger repairs being measured separately as a repair |  |  |  | 0
0
2.5.22 | window type ‘F’; approximate size 500 x 1400mm overall; at FF level; refs: 1.25, 1.26 & 1.27 | 3 | No |  | 0
0
2.5.23 | window type ‘N’; approximate size 1000 x 2000mm overall; at GF level; refs G.12 & G.13 | 2 | No |  | 0
0
2.5.24 | window type ‘J’; approximate size 900mm diameter overall; at FF level ref 1.28 | 1 | No |  | 0
| ______________________________________________ |  |  |  | 0
0
2.5.25 | external screen / double doors; doors located at GF level between windows G.01.NA & G.02 | 1 | Item |  | 0
0
0
| Prepare and repaint all existing painted surfaces to the following existing external metalwork; specification to be as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
2.5.26 | 3No existing metal grilles located on the South elevation of the Tower (below and left of windows G.12 & G.13) | 1 | Item |  | 0
0
0
| Prepare and restain all existing stained surfaces to the following existing external timber elements; specification to be as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
2.5.27 | external reception entrance doors / screen at base of the Tower; type 'T'; ref G.14 & G.15 | 1 | Item |  | 0
0
2.5.28 | external display board; at GF level next reception entrance at base of the Tower; type 'U'; ref G.16 | 1 | Item |  | 0
0
0
| Work at roof line level |  |  |  | 0
0
| Prepare and repaint all existing painted surfaces to the following external timber elements; specification to be as Landolt + Brown "Redecoration and Repair Specification"; the scope of works is to include the filling of any small cracks within the surface of the timber with any larger repairs being measured separately as a repair |  |  |  | 0
0
2.5.29 | window at roof level between flat roof (located above the South Hall) and the natural history lab; approximate size 400 x 1275mm overall; type 'Z'; ref 2.13 | 1 | Item |  | 0
0
2.5.30 | external single door at roof level between flat roof (located above the South Hall) and the natural history lab; type 'X'; ref 2.12 | 1 | Item |  | 0
0
2.5.31 | timber cupola located at ridge line level of the roof over the North Hall (NB access can be obtained using the existing safety line system); ref R.01, R.02 & R.03 | 3 | No |  | 0
| ______________________________________________ |  |  |  | 0
0
2.5.32 | Note: No work is required to the 4No cupolas above the South Hall as these were repaired and redecorated in 2017 | 0 | 0 | 0 | 0
0
2.5.33 | Note: No work is required to the existing metal access ladders (3No) and handrails | 0 | 0 | 0 | 0
0
0
0
0
SECTION No. 2 - WORK TO NORTH / SOUTH HALLS AND TOWER
|  |  |  | To Summary £ | 1000

## SECTION No. 3
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
EXTERNAL REPAIR AND REDECORATION WORKS
= Contractor to insert pricing
SECTION No. 3
WORK TO THE EXTERNAL ELEVATIONS OF THE EMSLIE HORNIMAN BUILDING
£ p
3.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
3.1 - Temporary access / protection
3.2 - External survey / report
3.3 - Repair works (All approximate)
3.4 - Redecoration works
3.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
3.0.3 | The scope of works measured in this section of the document relates to the confirmed redecoration works to the Emslie Horniman building (i.e. West elevation windows and South elevation GF doors). All other items of repair / redecoration is provisional and is covered separately within Section 4. | 0 | 0 | 0 | 0
0
| 3.1 - TEMPORARY WORKS |  |  |  | 0
0
3.1.1 | Contractor Designed Portion: Provide all necessary temporary access equipment in gaining access to the windows on the West elevation of the Emslie Horniman Building (Education terrace side) | 1 | Item |  | 0
0
3.1.2 | Note: The Contractor is to allow the Museum access to the scaffolding for the repositioning of site security cameras as required. | 0 | 0 | 0 | 0
0
3.1.3 | Note: The Museum will require any temporary access towers to be dismantled at the end of each day and stored securely overnight. | 0 | 0 | 0 | 0
0
0
0
| 3.2 - EXTERNAL SURVEY / REPORT |  |  |  | 0
0
3.2.1 | Allow for undertaking a condition survey, by a suitably qualified professional, to all elements of the existing external fabric to the East elevation of the Emslie Horniman building (i.e. external brick walls, windows, doors, roof, chimneys etc.) in identifying where repair works are necessary to allow the building to be made fully weatherproof. In pricing this item, the Contractor is to allow for all necessary liaison in gaining access into the building as required. Upon completion of the survey allow for producing a detailed written report for subsequent handing to the CA / Employer. | 1 | Item |  | 0
0
0
0
| 3.3 - REPAIR WORKS (ALL APPROXIMATE) |  |  |  | 0
0
| Repair work to existing window frames / cills |  |  |  | 0
0
| Carefully remove defective timber to window frame / cill and undertake a 2 Pack epoxy resin window care repair; as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
3.3.1 | to area of decayed timber less than 50mm in diameter | 10 | No |  | 0
0
0
| Replacement of defective window cills |  |  |  | 0
0
| Carefully cut out defective timber window cill and replace with a hardwood cill to match the existing profile; as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
3.3.2 | not exceeding 2500mm in length | 4 | No |  | 0
0
0
| Mastic |  |  |  | 0
0
3.3.3 | Allow for raking out defective mastic sealant and for providing new; as Landolt + Brown "Redecoration and Repair Specification" | 20 | m |  | 0
0
0
0
| 3.4 - REDECORATION WORKS |  |  |  | 0
0
3.4.1 | Note: The confirmed redecoration work to the Emslie Horniman | 0 | 0 | 0 | 0
0
0
| Work to the South elevation |  |  |  | 0
0
| Prepare and restain all existing stained surfaces to the following existing external timber elements; specification to be as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
3.4.2 | external double doors; at GF level; type 'W' location ref G.17 & G.18 | 2 | No |  | 0
0
0
| Work to the West elevation (off the Education Terrace) |  |  |  | 0
0
| Prepare and repaint all existing painted surfaces to the following external timber elements; specification to be as Landolt + Brown "Redecoration and Repair Specification"; the scope of works is to include the filling of any small cracks within the surface of the timber with any larger repairs being measured separately as a repair |  |  |  | 0
0
3.4.3 | window type ‘S’; approximate size 2300 x 1400mm overall (location refs 1.33, 1.34, 1.35, 1.36 & 1.37) | 5 | No |  | 0
0
0
0
0
SECTION No. 3 - WORK TO EMSLIE HORNIMAN BUILDING
|  |  |  | To Summary £ | 0

## SECTION No. 4
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
EXTERNAL REPAIR AND REDECORATION WORKS
= Contractor to insert pricing
SECTION No. 4
PROVISIONAL REDECORATION WORKS
£ p
4.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
4.1 - Provisional work - Emslie Horniman Building
4.2 - Provisional work - External areas
4.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
4.0.3 | The works measured in this Section of the document relate to possible additional works which may be instructed by the Museum. Prior to the works commencing the Contract Administrator will confirm the scope to be undertaken in a formal Contract Administrator's Instruction. | 0 | 0 | 0 | 0
0
0
| 4.1 - PROVISIONAL WORK - EMSLIE HORNIMAN BUILDING |  |  |  | 0
0
4.1.1 | NOTE: All information depicting the scope / specification of the works described in this section of the works is as detailed in Appendix C | 0 | 0 | 0 | 0
0
0
| Temporary works |  |  |  | 0
0
4.1.2 | Contractor Designed Portion: Provide alarmed scaffold (or access plant) in gaining access to the South and West Elevations of the Emslie Horniman Building. Include for all necessary costs in respect of licences, hoists, safety netting, fans etc. Allow for altering and adapting the scaffold as required and remove on completion. | 1 | Item |  | 0
0
4.1.3 | in pricing the item above, given the scope of works so described in this document, the Contractor is requested to state how many weeks hire has been duly allowed for. |  | weeks |  | 0
0
4.1.4 | in the event that the CA instructs additional works (over and above that described below) thereby requiring the extended hire of the scaffold then the Contractor is requested to quote here his additional cost per week for such an eventuality. Should the Contractor elect to claim prolongation costs on this basis then he is reminded that the Contract provisions are to be followed and as such due 'cause and affect' will need to be demonstrated before the inclusion of costs will be considered. |  | / week |  | 0
0
0
| External survey / report |  |  |  | 0
0
4.1.5 | Allow for undertaking a condition survey, by a suitably qualified professional, on all elements of the existing external fabric to the South and West elevations of the Emslie Horniman building (i.e. external brick walls, windows, doors, roof, chimneys etc.) in identifying where repair works are necessary to allow the building to be made fully weatherproof. In pricing this item, the Contractor is to allow for all necessary liaison in gaining access into the building as required. Upon completion of the survey allow for producing a detailed written report for subsequent handing to the CA / Employer. | 1 | Item |  | 0
0
0
| Redecoration works |  |  |  | 0
0
| Prepare and repaint all existing painted surfaces to the following external glazed metal windows; specification to be as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
4.1.6 | South elevation (including the side and rear elevation of the 2No turrets): |  |  |  | 0
0
4.1.7 | window type ‘T’; circular; approximate size 800mm diameter overall; window refs W12, W13, W14, W15, W16 & W17 | 6 | No |  | 0
0
4.1.8 | window type ‘U’; approximate size 2000 x 1100mm overall; window refs W23, W24 & W25 | 3 | No |  | 0
0
4.1.9 | window type ‘V’; approximate size 300 x 1000mm overall; window refs W26 & W27 | 2 | No |  | 0
0
4.1.10 | window type ‘W’; approximate size 300 x 1000mm overall; window refs W28 & W29 | 2 | No |  | 0
0
4.1.11 | window type ‘X’; approximate size 400 x 700mm overall; window refs W30, W31, W32, W33 & W34 | 5 | No |  | 0
0
0
| Prepare and repaint all existing painted surfaces to the following external timber elements; specification to be as Landolt + Brown "Redecoration and Repair Specification"; the scope of works is to include the filling of any small cracks within the surface of the timber with any larger repairs being measured separately as a repair |  |  |  | 0
0
| South elevation (including the side and rear elevation of the 2No turrets): |  |  |  | 0
0
4.1.12 | soffit / overhanging eaves to the south elevation (above windows W30 – W34) | 1 | Item |  | 0
0
0
| West elevation (plant courtyard): |  |  |  | 0
0
4.1.13 | window type ‘Q’; approximate size 1400 x 2900mm overall (window refs W1, W2, W3, W4 & W5) | 5 | No |  | 0
0
4.1.14 | window type ‘R’; approximate size 1400 x 2300mm overall (window ref W6) | 1 | No |  | 0
0
4.1.15 | window type ‘S’; approximate size 1400 x 2900mm overall (window refs W7, W8, W9, W10 & W11) | 5 | No |  | 0
0
4.1.16 | external single door and infill panel over (door ref D1) | 1 | Item |  | 0
0
0
| Prepare and repaint all existing painted surfaces to the following existing external metalwork; specification to be as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
4.1.17 | all rainwater gutters serving the Emslie Horniman Building; including cleaning out and sealing any open/failing joints between the gutter and fibreglass lining | 1 | Item |  | 0
0
4.1.18 | all rainwater goods serving the Emslie Horniman Building | 1 | Item |  | 0
0
4.1.19 | all metalwork to the 2No external lamps located above external doors D3 & D4 | 1 | Item |  | 0
0
4.1.20 | 5No metal vent grilles, sized approximately 200 x 200mm; located above windows W1 – W5 | 1 | Item |  | 0
0
0
| Provisional sums |  |  |  | 0
0
4.1.21 | Provide the Provisional Sum of £1,500.00 for pre-decoration repairs | 1 | Item | 1500 | 1500
0
0
0
| 4.2 - PROVISIONAL WORK - EXTERNAL AREAS |  |  |  | 0
0
| Redecoration works |  |  |  | 0
0
| Prepare and repaint all existing painted surfaces to the following existing external metalwork; specification to be as Landolt + Brown "Redecoration and Repair Specification" |  |  |  | 0
0
| Work at the front of the Museum: |  |  |  | 0
0
4.2.1 | 3No pedestal lantern lights; located on the stair flights leading up to the security entrance (refer to images IMG_8823 to IMG_8826) | 1 | Item |  | 0
0
4.2.2 | 3No lengths of handrail; located on the stair flights leading up to the security entrance (refer to images IMG_8827 to IMG_8833) | 1 | Item |  | 0
0
4.2.3 | metal railings located in front of external door G.17 to the Emslie Horniman building | 1 | Item |  | 0
0
0
| Work at the rear of the Museum: |  |  |  | 0
0
4.2.4 | existing metal gate / railings located at the corner of the building where the West/North elevations meet (next conservatory structure) | 1 | Item |  | 0
0
4.2.5 | existing metal gate / railings located at the corner of the building where the East/North elevations meet (next site boundary) | 1 | Item |  | 0
0
0
| Prepare and repaint all existing painted surfaces to the following external timber elements; specification to be as Landolt + Brown "Redecoration and Repair Specification"; the scope of works is to include the filling of any small cracks within the surface of the timber with any larger repairs being measured separately as a repair |  |  |  | 0
0
4.2.6 | existing external hoarding located next to the bin store area | 1 | Item |  | 0
0
0
| Provisional sums |  |  |  | 0
0
4.2.7 | Provide the Provisional Sum of £1,000.00 for pre-decoration repairs | 1 | Item | 1000 | 1000
0
0
0
0
SECTION No. 4 - PROVISIONAL REDECORATION WORKS
|  |  |  | To Summary £ | 2500

## SUMMARY
.
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
EXTERNAL REPAIR AND REDECORATION WORKS
SUMMARY
£ p
| Section No. 1 | - | Conditions of Contract / Preliminaries |  | 0
| Section No. 2 | - | Work to the external elevations of the North / South Halls and Tower |  | 1000
| Section No. 3 | - | Work to the external elevations of the Emslie Horniman building |  | 0
| Section No. 4 | - | Provisional redecoration works |  | 2500
|  |  |  | Sub-total £ | 3500
| - |  | Provide the Provisional sum of £5,000.00 for contingencies |  | 5000
|  |  |  | OPTION A - TOTAL £ | 8500 | #
Name of Contractor:
Address:
Date: