## Index
NEC 3
ENGINEERING AND CONSTRUCTION CONTRACT
OPTION A
SINGLE STAGE
TENDER PACKAGE - CONTRACT DATA PART 2 (TP- CD2)
(Including Price Submission Spreadsheets)
TENDER FOR
BATSUB LCR Phases 1 and 2A
|  |  | Project No: | DIOCB1/203
|  |  | Economic Operator: | [Insert Name] |  |  | ECONOMIC OPERATORS TO INSERT THEIR NAME
Published Document Revision History
First Issued
|  | Revision | Date |  | Changes
Contents
Spreadsheet Label |  |  |  |  | Description | Page No
1 | CD-PT2 |  | Contract Data Part 2 |  |  | 2
2 | CD-PT2 Add Info |  | Contract Data Part 2 - Additional Information |  |  | 5
3 | Guidance |  | Guidance for Completion of Price Submission |  |  | 6
4 | Guidance 2 |  | Preamble to Activity Schedule |  |  | 8
5 | Act Sch |  | Activity Schedule |  |  | 11
5A | MPS |  | Milestone Payment Schedule |  |  | 14
5B | Guidance 3 |  | Guidance on Completion of Acct Sch & MPS |  |  | 15
8 | MCE |  | Model Compensation Event |  |  | 16
| Summary |  | Summary Sheet |  |  | 17

## 1. CD-PT2
Main Works Contract
| Project: | BATSUB LCR Phases 1 and 2A
| Project No: | DIOCB1/203
| Tenderer: | [Insert Name]
Contract Data Part two - Data provided by the Contractor
Completion of the data in full is essential to create a complete contract.
Statement given in all contracts
THIS CONTRACT DATA IS FOR OPTION A - SINGLE STAGE PRICED CONTRACT WITH ACTIVITY SCHEDULE
• | The Contractor is
| Name: | [Insert Name]
| Address: | [Line 1]
[Line 2]
[Line 3]
[Line 4]
[Line 5]
• | The direct fee percentage is |  |  |  | 0%
• | The subcontracted fee percentage is |  |  |  | 0%
Note: The Fee %'s above to be carried forward to the relevant s'sheets as appropiate
• | The working areas are the Site and |  |  | [Enter details ] limited to 150 characters
• | The key people are
| (1) Name | [Enter name] limited to 75 characters
| Job | Contracts Director
| Responsibilities | [Enter responsibilities] limited to 100 characters
| Qualifications | [Enter Qualifications] limited to 100 characters
| Experience | [Enter experience] limited to 100 characters
| (2) Name | [Enter name] limited to 75 characters
| Job | Contracts Manager
| Responsibilities | [Enter responsibilities] limited to 100 characters
| Qualifications | [Enter Qualification] limited to 100 characters
| Experience | [Enter Experience] limited to 100 characters
| (3) Name | [Enter name] limited to 75 characters
| Job | Contractor Design Coordinator
| Responsibilities | [Enter responsibilities] limited to 100 characters
| Qualifications | [Enter Qualification] limited to 100 characters
| Experience | [Enter Experience] limited to 100 characters
| (4) Name | [Enter name] limited to 75 characters
| Job | Planner / Programme Manager
| Responsibilities | [Enter responsibilities] limited to 100 characters
| Qualifications | [Enter Qualifications] limited to 100 characters
| Experience | [Enter experience] limited to 100 characters
| (5) Name | [Enter name] limited to 75 characters
| Job | Other Personnel
| Responsibilities | [Enter responsibilities] limited to 100 characters
| Qualifications | [Enter Qualifications] limited to 100 characters
| Experience | [Enter experience] limited to 100 characters
• | The following matters will be included in the Risk Register
[Enter risk] limited to 75 characters
[Enter risk] limited to 75 characters
[Enter risk] limited to 75 characters
[Enter risk] limited to 75 characters
[Enter risk] limited to 75 characters
• | The Works Information for the Contractor’s design is in |  |  |  | [Enter document title]
• | The project bank is |  |  |  | Not used
• | The activity schedule |  | is in Tender Package - Contract Data Part 2 (TP-CD2) Spreadsheets 5
• | The tendered total of the Main Works Prices is |  |  |  | 0
as brought forward from cell G19 (Summary Sheet)
Data for Shorter Schedule of Cost Components
• | The percentage for people overheads is |  |  |  | 0%
• | The published list of Equipment is the last edition of the list published by
Civil Engineering Contractors Association (CECA) Dayworks Schedule
The percentage for adjustment for Equipment in the published list is
| 0% | (State plus or minus)
• | The rates for other Equipment are
| Equipment |  |  | size/capacity |  | rate
| [Enter Equipment] |  |  | [Enter size/capacity] |  | 0
| [Enter Equipment] |  |  | [Enter size/capacity] |  | 0
| [Enter Equipment] |  |  | [Enter size/capacity] |  | 0
| [Enter Equipment] |  |  | [Enter size/capacity] |  | 0
• | The hourly rates for Defined Cost of design outside the Working Areas are
• | The percentage for design overheads is |  |  |  |  | Not Used
• | The categories of design employees whose travelling expenses to and from the Working Areas
are included in the Defined Cost are
[Enter category of design employee]
[ Enter category of design employee]
Instructions for Tenderers
PLEASE ENTER INFORMATION
AS REQUIRED
PLEASE DELETE THIS BOX ONCE COMPLETE.

## 2. CD-PT2 Add. Info.
Tender Package Contract Data Part 2( TP - CD2 )
| Project: | BATSUB LCR Phases 1 and 2A
| Project No: | DIOCB1/203
| Economic Operator: | [Insert Name]
Contract Data Part two - Data provided by the Contractor(Cont.)
• | The key people are(Cont.)
| (6) Name | [Enter name] limited to 75 characters
| Job | [Enter Job title] limited to 75 characters
| Responsibilities | [Enter responsibilities] limited to 100 characters
| Qualifications | [Enter Qualifications] limited to 100 characters
| Experience | [Enter experience] limited to 100 characters
| (7) Name | [Enter name] limited to 75 characters
| Job | [Enter Job title] limited to 75 characters
| Responsibilities | [Enter responsibilities] limited to 100 characters
| Qualifications | [Enter Qualification] limited to 100 characters
| Experience | [Enter Experience] limited to 100 characters
Instructions for Tenderers
PLEASE ENTER ADDITIONAL INFORMATION
AS REQUIRED SUPPLEMENTARY TO THAT ENTERED IN SPREADSHEET ENTITLED
1. CD.- PT2.
PLEASE DELETE THIS BOX ONCE COMPLETE.

## 3. Guidance
Tender Package Contract Data Part 2( TP - CD2 )
3 | GUIDANCE FOR COMPLETION OF PRICE SUBMISSION
3.1 | GENERAL REQUIREMENTS
This document should be read in conjunction with all other parts of the Tender Documents. All defined terms within this document are explained within the Tender Documentation.
This guidance explains the background and sets out the price information required by the Employer as part of the Competition, the actual price data is to be entered and submitted in the attached spreadsheets.
The contract shall be NEC3 Engineering and Construction Contract (ECC) – Option A (Amended by MOD) with associated payment mechanisms.
The Tenderer must enter/carry forward where applicable, a value for:
r direct fee percentage (Negative rates must not be used)
r subcontracted fee percentage (Negative rates must not be used)
r percentage of works to be subcontracted;
r all hourly rates where applicable
in the appropriate cell (highlighted in blue) and contained in the data entry sheets listed below:
r Activity Schedule Spreadsheet
r Model Compensation Event Spreadsheet
r Summary Spreadheet
People rates priced within the Model Compensation including sub-contracted labour/operative rates are to be used as the basis to value Compensation Events, and will be included in the calculation of, or added to the calculated value of any net costs assessed for the expenditure of any Compensation Events using the Shorter Schedule of Cost Components
The Summary Spreadheet collates the prices from each individual sheet and calculates the Tender Assessment Total Price for the Tenderer’s tender submission.
The ‘Tender Assessment Total Price’ (excluding VAT), as calculated in the Summary Spreadheet, is used only for tender assessment purposes. However, the hourly rates (for site employees) inserted in the Model Compensation Event shall be used, where appropriate, in any actual compensation event during the contract.
The Tendered Total of the Prices (excluding VAT) as calculated on the Summary Spreadsheet shall be entered in the Form of Tender contained within the Declarations document.
Failure by a Tenderer to complete all data entries in accordance with all requirements therein and to return Tender Package – Contract Data Part 2 together with the Price Submission Spreadsheets no later than the specified submission date and time will result in tender submission being rejected.
Contract Data Part 2 including the Price Submission Spreadsheets shall be submitted as representative of the Tenderer and his Team as a whole.
All fees shall be entered as a number; the spreadsheet will recognize the entry as a percentage i.e. to enter a fee of ‘6.66%’ enter only the numerical ‘0.0666’.
Economic Operators must not use negative rates or prices,or omit rates,or use zero rates.
No additional supporting information, beyond that typed into the document/spreadsheet, will be assessed. No general marketing or promotional material from the Tenderer or any Subcontractor either in answer to any of the questions or for any other reason, should be included.
Tender Package – Contract Data Part 2 (TP-CD2) has been electronically locked in order to maintain formatting. The Tenderer must enter its response within the cells with the blue font. No attempt must be made to unlock the document/spreadsheet or tamper with the calculation process.
Tenders will be corrected to take into account misplaced decimal points, etc, or patent errors in arithmetic. Tenderers will be notified and asked within 2 working days to either confirm the corrected tender or withdraw from the competition.
3.2 | SPECIFIC REQUIREMENTS
Where an Employer has requested design work to be undertaken the intellectual property rights for that design work shall remain with the Employer at all times, even if the Contract is terminated.
FEE PERCENTAGES
The Tenderer shall enter the specified fee percentages in the appropiate Spreadsheet
COST OF PEOPLE
The Tenderer shall enter the specified cost in Spreadsheet 1. CD-PT2

## 4. Guidance 2
Tender Package Contract Data Part 2( TP - CD2 )
PREAMBLE to ACTIVITY SCHEDULE
NOTE: Tenderers to check dimensions on site before price submission
Tenderers are to submit a priced activity schedule with their tenders showing proposed activities with lump sum payments. This document will comprise a list of activities with an amount entered against each activity. Each amount is the sum due to the Contractor on full completion of each activity. The sum of the Prices of the activities shall be the lump sum total Price for the works.
Activity descriptions must be clear and complete so that the work included in each can be identified after the completion of the activity. The Tenderers may provide Prices for any activity included in the works, provided they are also identified as an activity on the programme of the works submitted with the tender. Identified activities which should be included in the tendered Activity Schedule and Project Programme are listed in the Indicative Activity Schedule herein.
Prices shall be entered in pounds and whole pence (i.e. values to two decimal places).
Tenderers must not include more than 100 (one hundred) activities on the activity schedule. If more than one hundred individual activities are included on the tendered activity schedule then the Employer reserves the right to combine individual activities so that the number of activities does not exceed one hundred.
The terms “nil”, “n/a” “included” and/or “– “ are NOT to be used but should be indicated as £0.00. Figures MUST be inserted against each activity in the activity schedule. If a figure is not inserted against any activity the Employer will assume that the Contractor is prepared to complete this activity for a price of £0.00.
'Credit' values in favour of the Employer shall NOT be inserted against any activity in the activity schedule.
TENDERERS SHOULD PARTICULARLY NOTE that the principles governing public procurement require that, as far as is reasonably possible, payments for Goods, Works or Services are made AFTER provision. Therefore, any indication of a pricing strategy within a tender which provides for substantial payments at the outset of a Contract will be examined carefully to decide whether or not a tender in such form can be accepted. If in the opinion of the Employer such substantial early payments appear excessive in relation to the requirements of the Contract the Employer reserves the right to require the Economic Operator to spread such proportion of the costs as are considered excessive over the duration of the Contract. The Employer reserves the right to reject the lowest or any tender where in the opinion of the Employer early payments appear excessive.

## 5. Act Sch
Tender Package Contract Data Part 2( TP - CD2 )
Project: | These headings are a guide and may be broken down into smaller 5:26
Project No: | DIOCB1/203
Economic Operator: | [Insert Name]
ACTIVITY SCHEDULE
CONTRACTOR TO POPULATE THIS SCHEDULE LISTING THE ACTIVITIES THE CONTRACTOR EXPECTS TO CARRY OUT IN PROVIDING THE WORKS ALONG WITH THE LUMP SUM FOR THAT ACTIVITY.
NOTE: ADDITIONAL ROWS CAN BE ADDED TO THIS SPREADSHEET BY RIGHT CLICKING ON THE ROW NUMBER DOWN THE LEFT HAND SIDE. SELECT INSERT FROM THE MOUSE MENU. A NEW ROW WILL BE ADDED ABOVE THE ROW SELECTED.
Item | Stage/Activity | Description of Activity | Sum
Preliminaries
1 | [ENTER TEXT HERE] | Text Boxes have been limited to Max Number of characters as indicated. Max number includes spaces.Text Boxes have been limited to Max Number of characters as indicated. Max Number is 180
Contractors Fees, Risk, Overheads and Profit
The Lump Sum total for each Activity includes all direct fees, subcontractor fees, risk, overheads and profit.
Preliminaries Total |  |  | 0
M&E Works
1 | [ENTER TEXT HERE] | Text Boxes have been limited to Max Number of characters as indicated. Max number includes spaces.Text Boxes have been limited to Max Number of characters as indicated. Max Number is 180
Contractors Fees, Risk, Overheads and Profit
The Lump Sum total for each Activity includes all direct fees, subcontractor fees, risk, overheads and profit.
M&E Works Total |  |  | 0
BUILDERS WORK
1 | [ENTER TEXT HERE] | Text Boxes have been limited to Max Number of characters as indicated. Max number includes spaces.Text Boxes have been limited to Max Number of characters as indicated. Max Number is 180
Contractors Fees, Risk, Overheads and Profit
The Lump Sum total for each Activity includes all direct fees, subcontractor fees, risk, overheads and profit.
Builder's Work Total |  |  | 0
| TOTAL FOR ACTIVITY SCHEDULE (CARRIED FORWARD TO SUMMARY SHEET) |  | 0

## 5A. MPS
Ser | Milestone Description | Date Expecting to reach milestone | Price (£) (excluding 5% retention) | Price (£) (Including 5% Retention)
(a) | (b) | (c) | (d) | (d)
1 | [ENTER TEXT HERE] | [ENTER TEXT HERE] | 0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Total | 0 | 0

## 5B. Guidance 3
Guidance on Completion of Acct Sch & MPS
The following are suggested headings for completion of the Acct Sch and MPS:
1. Contract start up meeting
2. Project Governance meetings and document production
3. Procurement schedule and long lead in order placement
4. Site establishment
5. Phase 1 works
a. Pipeline/ductwork installation
b. Equipment installation
c. Handover including testing and commissioning
6. Phase 2 works
a. Storage Building
i. Substructures
ii. Frame
iii. Walls
iv. Cladding
v. Service installation
vi. Internal fit out
vii. Handover including testing and commissioning
b. Welfare Building
i. Alterations
ii. Minor Building works
iii. Service installation
iv. Handover including testing and commissioning
These headings are a guide and may be broken down further if necessary.

## 6. MCE
Tender Package Works Contract - Contract Data Part 2
| Project: | BATSUB LCR Phases 1 and 2A
| Project No: | DIOCB1/203
| Tenderer: | [Insert Name]
Main Works Model Compensation Event
NOTES
1. Rates are to be inserted in £'s Sterling to two decimals.
3. The Model Compensation Event must be completed fully, rates for Equipment (Owned / Leased), Manufacturing staff, Design staff and all percentages are carried forward from the spreadsheet entitled 'CD-PT2'.
VARIABLE COSTS
Rates are to be inserted in £'s Sterling to two decimal places
1 | PEOPLE
| Item |  |  | Cost |  | Total
| Add % for people overheads |  | 0% | 500000 |  | 0
| TOTAL FOR PEOPLE (Forward to Summary) |  |  |  |  | 0
2 | EQUIPMENT
The published list of Equipment is the last edition of the list published by:
Civil Engineering Contractors Association (CECA) Dayworks Schedule
| Item |  |  | Cost |  | Total
| Plant Adjustment % | 0% |  | 500000 |  | 0
| Equipment |  |  | Hours
| [Enter Equipment] |  | 0 | 400 |  | 0
| [Enter Equipment] |  | 0 | 400 |  | 0
| [Enter Equipment] |  | 0 | 400 |  | 0
| [Enter Equipment] |  | 0 | 400 |  | 0
| TOTAL FOR EQUIPMENT (Forward to Summary) |  |  |  |  | 0
3 | DIRECT WORKS
| Item |  |  | Cost | % | Total
| Direct Fee % |  |  | 500000 | 0% | 0
| TOTAL FOR DIRECT WORKS (Forward to Summary) |  |  |  |  | 0
4 | SUB-CONTRACTED WORKS
| Item |  |  | Cost | % | Total
| Sub-contracted Fee % |  |  | 500000 | 0% | 0
| TOTAL FOR SUB-CONTRACTED WORKS (Forward to Summary) |  |  |  |  | 0
5 | DESIGN WORKS
| Item |  |  | Cost |  | Total
| Add % for design overheads |  |  |  |  | Not Used
TOTAL FOR DESIGN (Forward to Summary)
SUMMARY
1 | PEOPLE |  |  |  |  | 0
2 | EQUIPMENT |  |  |  |  | 0
3 | DIRECT WORKS |  |  |  |  | 0
4 | SUB-CONTRACT WORKS |  |  |  |  | 0
5 | DESIGN WORKS
| Model Compensation Event Total (Carried Forward to Grand Summary Sheet cell G23) |  |  |  |  | 0

## Summary
Tender Package Contract Data Part 2( TP - CD2 )
Project: | BATSUB LCR Phases 1 and 2A
Project No: | DIOCB1/203 |  |  |  |  | NOTICE TO Economic OperatorS
Economic Operator: | [Insert Name] |  |  |  |  | ALL INFORMATION IS ENTERED ON
OTHER SHEETS AND CARRIED FORWARD
|  | SUMMARY SHEET |  |  |  | TO THIS SHEET
Total
|  |  | ACTIVITY SCHEDULE |  | 0
|  |  |  | Tendered Total of the Prices | 0
|  |  | TOTAL COST OF COMPENSATION EVENT |  | 0
|  |  | Tender Assessment Total Price |  | 0
Total of Model Compensation event
(brought forward from spreadsheet entitled MCE)