## Showcases
Isles of Scilly Museum Tender Process Q&A - Showcases
Date of Query | Item Number | Item Name | Question | Answer | Response file
23.10.2024 | Various | All steel plinths & drawers | For the steel structure components, could you please specify the required material thickness (gauge)? A fixed specification would allow for better quality and price comparison. | Please cost for 3mm thick steel. Drawers - include allowance for a suitable structural solution that means they are suitable for containing handling objects and interactives that children will use. | Rev A
23.10.2024 | 1.4 | Reception & Welcome Landing – Vitrine display | In item #1.4, could you confirm where the Baumann fabric will be applied? Will it be wrapped around both the rear and the base, similar to other pieces? | Yes. Please cost for fabric wrapping the rear and base dress panels. | Rev A
23.10.2024 | 1.5 | Reception & Welcome Landing – HW display case | In item #1.5 (and similar items), there is some ambiguity regarding the number of drawers requested. The front elevation drawing shows 1 drawer, while the text indicates 2 drawers. Could you clarify the correct number? Additionally, would you prefer access to the prosorb cassette and LED drivers through a push-open system or with a lock? Please confirm if our understanding as noted below is correct? | Please cost for 1no drawer and a lockable access solution for drivers and Prosorb cassettes. Your understanding as shown in the annotated elevation is correct. | Rev A
23.10.2024 | Various |  | Could you please specify the material or finish of the piece where the labeling will be attached (the 30-degree component)? And could you please provide details for white acrylic number cubes? | ZFMDF sealed with Mositop and wrapped in Baumann fabric. Please do not cost for the acrylic number blocks - they are part of the fabrication and fit out contract, not the showcase work package. | Rev A
23.10.2024 | Various |  | Can you confirm that the contractor will be responsible for providing pattressing where units require wall or ceiling fixing? | The base build Principal Contractor will be responsible for wall and ceiling patresses. | Rev A
23.10.2024 | 6.4 | Gallery 1 - Shipwreck display showcase & drawers plinth | The Captain's Chair Plinth (mechanically rotating unit) has been assigned a duplicate number (#6.4), which is " Shipwreck display showcase & drawers plinth" Could you assign a new number for the rotating unit to avoid confusion? | This is not a duplicate number; the Captain's Chair is a display element within ref 6.4 and will be costed as part of the fabrication and fit out contract, not the showcase work package. | Rev A
23.10.2024 | Various |  | Would it be acceptable to propose a substitute brand for the 3mm Dibond? We are prepared to provide a sample for your consideration. | The in-case graphics will be costed as part of the fabrication and fit out contract, not the showcase work package. | Rev A
25.10.2024 | 7.7 and 7.8 | Ancient life wall graphic and Model buildings & 3D puzzle plinth | Could you please check references 7.7 I believe to be 6 small cases on the wall, and 7.8 to be 1 case on a plinth. They are missing of the costing sheet. | 7.7 and 7.8 cases will not part of the showcase display contract and will be part of the Fabrication & Fit-Out contract. | Rev C
30.10.2024 | 1.4 and 10.8 | Reception & Welcome Landing – Vitrine display and Gallery 5 - Vitrines display | Our understanding is that the oak/timber finish/cladding to these types of cases will be supplied and fitted by the Fit Out/Joinery contractor on site with coordination by the showcase supplier -can you confirm this is accurate ? | No. the whole vitrine will be a part of the showcase contract. Only the production & installation of graphics will be a part of the Fabrication & Fit-Out contract. | Rev D
30.10.2024 | 6.5 | Gallery 1 – Nornour display showcase & drawers plinth | We understand the showcase contractor can offer alternative/better solutions for case design/engineering. Case 6.5 is a complex structure and as such we can offer alternatives whilst keeping the original design aesthetics; please confirm alternate solutions are acceptable. | Yes, alternate solutions can be accepted, if the design reflects the original design aesthtics and keeps the original function. | Rev D
30.10.2024 | 9.5 | Gallery 4 – Central display table | We suggest the sanding down and re touching/lacquering of the existing wooden showcase is carried out by the Fit Out/Joinery contractor with the showcase contractor providing new internal dress panels as described – please confirm this is acceptable | We envisage the refurbish of the Victorian case will be a part of the showcase contract. This could be discussed post tender as a variation, but for now please supply cost allowance. | Rev D
30.10.2024 | 9.6 | Gallery 4 – Cased bird display | We understand this structure in its entirety is supplied and installed by the Fit Out / Joinery contractor – please confirm | Yes, 9.6 is not a part of the showcase contract. Cased birds will be supplied by museum, It's entirety will be installed by Fabrication & Fit-Out contractor. | Rev D
30.10.2024 | 9.7 | Gallery 4 – Local birds showcase | Please confirm our assumption that the Victorian timber construction header detail will be supplied by the Fit Out/Joinery contractor | Yes, the Victorian timber construction header is part of the Fabrication & Fit-Out contract. | Rev D
30.10.2024 | 10.3 | Gallery 5 – Long plinth with book shelves | Please confirm the plinth below and to the side along with the bookshelf structure will be supplied and installed by the Fit Out/Joinery contractor with coordination by the showcase contractor for the connecting showcase | Yes, the plinth below and bookshelf structure is part of the Fabrication & Fit-Out contract. | Rev D
30.10.2024 | 1.5 & 5.1 | Reception & Welcome Landing – HW display case & Atrium - Wall mounted boat collection | The combined weight of these 2 showcases will be substantial; can you provide information with regards floor loadings and wall structure/loading with regards case position and fixing points. | Understood. Pattressing and floor loading has been discussed with the architect, building contractors and their structural engineer, allowances have been/will be made. | Rev D
30.10.2024 | Various | Drawers Units | Our proposal would include soft close drawers without "automatic closure" , would this be an acceptable proposal ? | Yes. | Rev D
2024-11-01 | Various | Site | Please can you provide a full Building GA of both ground a first floor. Is there Site access restriction that we should be aware of? Small Door ways, routes, stair cases etc | Please refer to plans in Detailed Design Plan. Internal lift size: 1100mmW x 1400mmD x 2130mmH; Internal stairs leading to all galleries: 1200mm wide; Smallest door access is 846mm wide; | Rev E
2024-11-01 | Various | Site | What delivery restriction are in place for the Museum - we would be looking to delivering in three phases - potentially 3no 20ft containers - there a holding yard that we can make use of? | Please refer to on island contact provided under the useful contact section in ITT - Page 4. Only 1no container at a time. | Rev E
2024-11-01 | Various | Site | Is there Site access restriction that we should be aware of? Small Door ways, routes, stair cases etc | Internal lift size: 1100mmW x 1400mmD x 2130mmH; Internal stairs leading to all galleries: 1200mm wide; Smallest door access is 846mm wide; | Rev E
2024-11-01 | Various | Site | Will base build works still be underway during our installation dates? | Not within the galleries. | Rev E
2024-11-01 | Various | Site | Power supplies - it is assumed that power will be placed above or below cases not behind for annual servicing. | Final positioning to be agreed after appointment. | Rev E
2024-11-01 | Various | Site | What is the show control system in place for the lighting - Is it a last man our switch or similar? | It is the intention that to have one switch per gallery. | Rev E
2024-11-01 | Various | Label holders | Please confirm that all base sloped units where noted are just sloped label holders and not sloped raise plinths? | They're sloped raise plinths where labels are attached to the front. | Rev E
2024-11-01 | Various | Drawers | We are concerned about the longevity and accessibility restraints of the monkey fist knot handles - Can you confirm that this has been considered - these will not be included in our Guaranty | Yes, that's fine for the monkey fist knot handles. Client request. | Rev E
2024-11-01 | Various | Case Conditioning | Is it correct to assume that access to some conditioning reservoirs are through the case void not remote? | Please refer to Row 6. | Rev E
2024-11-01 | 5.1 | Reception & Welcome Landing – HW display case & Atrium - Wall mounted boat collection | Access equipment - for the Atrium - will this be provided? - how does the client intend on servicing DC 5.1b? | A MEWP would be available in the atrium. | Rev E
2024-11-01 | 6.5a,b,c | Nornour display showcase & drawers plinth | Please confirm what access the designer/client would prefer? | Please refer to Detailed Design Plan - item 6.5, where it says 2no glass suction lifters to be provided so client can access contents. | Rev E
2024-11-01 | 6.5a,b,c | Nornour display showcase & drawers plinth | On the schedule Sent 31/010/24 each line of 6.5 b&c state Drawers "as above". Please confirm total Drawers required for unit 6.5 is 3no @ 450x300x100 | Yes, there're 3no drawers for 6.5, all @450mmW x 100mmH x 300mmD. | Rev E