# Annex A

| Title of Project | Environmental data management and data flows in British Virgin Islands |
| --- | --- |
| Date and Time for Return of Bids | Wednesday 12 October 2022 @ 16:00 hours |
| Contract Reference Number | C22-0482-1696 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO ELEONORA MANCA OR SHARON JOYCE VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below; (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Joint Nature Conservation Committee Please email: Eleonora Manca Email: Eleonora.Manca@jncc.gov.uk Nicola Abram Email: Nicola.Abram@jncc.gov.uk International Implementation Team Joint Nature Conservation Committee Monkstone House City Road Peterborough, PE1 1JY |
| Contact for Queries Regarding the Procurement Procedure | Sharon Joyce Finance Team Joint Nature Conservation Committee Email: Sharon.Joyce@jnccgov.uk or contractqueries@jncc.gov.uk Telephone: 01733 866826 |
| Proposed Start Date | 17/10/2022 |
| Proposed End Date | 28/02/2023 |

- Environmental data management and data flows in British Virgin Islands

Contents

1.	Project Aims	3

2.	Project Summary	3

3.	Project Objectives	4

4.	Outputs	5

5.	Timescale	5

6.	Health and safety	6

7.	Available Budget	6

8.	Additional Contractor requirements	6

9.	Evaluation Criteria	7

## Project Aims

The goal of this project is to build on previous projects and experience gained elsewhere in the Caribbean and South Atlantic Territories, to provide BVI with a self-sufficient, secure data management system and geospatial data hub for environmental spatial data. The work will be delivered in phases and the focus of this first phase contract is on data management fundamentals, standards and data flows and to provide an expanded datasets inventory and metadata catalogue that will support the creation of a centralised data hub and the general vision outlined in previous work.

## Project Summary

JNCC is providing technical assistance to the Overseas Territory (OT) of British Virgin Islands (BVI) to develop data management capacity (discovery, access, manage, analyse & use).

Data handling and management requires careful consideration and can be a significant demand on resources, both human and physical. The ability to generate large qualities of new data through space, ship and airborne sources is growing rapidly and as such a wealth of environmental research data on BVI has been generated.

This project is part of a wider data management project which aims to build on previous projects and experience gained elsewhere in the Caribbean and South Atlantic Territories, to provide BVI with a self-sufficient, secure data management system.  This project will focus on establishing a solid data management practice and a dataset inventory with the view to build a data hub for BVI that will:

- Be the authoritative single source of the latest environmental data which can be accessed by all departments and authorised third parties;

- Support BVI’s national reporting to regional and international agreements (e.g. environmental indicators defined under the 25 Year Environment Plan);

- Enable effective management and rapid access to the latest baseline of data to allow reporting following a natural hazard event when an Environment Damage and Loss Assessment (EDLA) is required;

- Increase accessibility and consistency of data;

- Enable the collection of data once for use many times;

- Store and retrieve data effectively;

- Protect BVI data from future extreme events;

- Meet sustainable management goals by integrating data;

- Help stakeholders understand the value of BVI’s natural environment; and

- Support reconstruction of built infrastructure and agricultural capacity ‘post event’.

In 2021 JNCC commissioned a work aimed at describing how to create an Environment Damage and Loss Assessment (EDLA) system to assess and quantify environmental damage to support disaster resilience in the BVI.  The work has produced a vision for managing environmental data and a general proposed system architecture centred around a centralised data hub (Figure below). The key recommendations were to work with the Department of Town and Country Planning (DTCP) and Ministry of Natural Resources and Labour (MNRL) to develop both the Hub and Apps and pre-populate the Hub with the existing and most recent environmental baseline.

The DTCP provides a central hub for spatial datasets from across the BVI and holds a number of the required environmental datasets already. The work also included a draft list of available datasets.

Figure 1 Draft proposed system architecture to support the EDLA in BVI.

The work to realise this vision will be delivered in phases. The focus of this contract is on data management fundamentals, standards and protocols and to provide an expanded datasets inventory, metadata catalogue that will support the creation of a centralised data hub and the general vision outlined above

Details of previous work and contacts in BVI will be provided by JNCC..

This work is funded through Conflict, Stability & Security Fund (CSSF) and the contract must be completed by February 2023.

## Project Objectives

The contractor will be working with JNCC, DTCP,  MNRL, and other BVI government departments, building on previous work to deliver the following project objectives:

- Meet stakeholders to:

  - agree and select 6 to 10 environmental indicators to prioritise

  - gather detailed user’s requirements for a data hub to support the EDLA and reporting of selected environmental indicators;

- Describe existing GIS infrastructure, provide diagrams of data flows (from monitoring programmes to selected indicators, for example for priority habitats, for 6 to 10 environmental indicators) and current data management practice;

- Review the draft table of data types and data owners and expand inventory of datasets to be included in the hub;

- Agree and setup improved data management systems (e.g. metadata management protocols and templates, agreements on standard controlled vocabularies);

- Design and develop, test and deploy a fully functional public facing metadata catalogue;

- Engage with data owners and populate the metadata catalogue;

- Train key Government of BVI personnel in the new data management protocols and systems;

- Recommend next steps, describe improved data flows and provide costed solutions for the creation of the data hub.

Example of data flow diagrams are available at https://data.jncc.gov.uk/data/43e4c894-8b35-4aed-b0e0-af3846caed99/jncc-report-712b.pdf. The level of detail of the data flow will be scoped out in the initial workshop in BVI.

## Outputs

- A workshop and a story board to summarise users stories and needs for a data hub, and a decision on selected indicators.

- A short report describing existing GIS infrastructure, data flow diagram and current data management practices.

- An inventory of datasets to be included in the hub.

- Data and metadata management protocols, data sharing agreement forms, guidelines and templates.

- A fully functional populated metadata catalogue, with available geospatial datasets required for the reporting 6 to 10 environmental indicators.

- Training workshop and material for key Government of BVI personnel in the new data management protocols and systems.

- A short report with recommendations for next steps and costed solutions for the creation of the data hub. It must include a section describing how the outcomes are scalable to other OTs.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor, BVI partners and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Kick off meeting with JNCC and regular fortnightly updates | From 17th October 2022 |
| Workshop in BVI and user story board (Output 1) | During October 2022 (Depending on availability) |
| Delivery of report with data flow diagrams (Output 2) and dataset inventory (Output 3) | End November 2022 |
| Delivery of agreed data and metadata protocols (Output 4) | Mid December 2022 |
| Delivery of metadata catalogue (Outputs 5) and training in BVI (Output 6, training in person in BVI or online) | End January 2023 |
| Delivery of Output 7 | 28th February 2023 |

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor)

Any incidents occurring within the contract should be immediately reported to JNCC.

## Available Budget

The total value of this project is £53,500.00 (This includes VAT charges if applicable)

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

The contractor is expected to organise and carry out the scoping workshop on island (and preparatory meetings).

The overall quote for the contract needs to include:

  - Daily rates for all members of the Project Team;

  - Quote for both-in person and remote training workshop on island;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

## Evaluation Criteria

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (80% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 15 |  |
|  | Understanding of, and relevance to, the requirements. . In particular, adequate details of the proposed process for achieving the required outputs in BVI. | 20 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of milestones | 5 |  |
|  | Identification and proposed solutions to potential problems/risks | 5 |  |
|  | Probability of success | 15 |  |
|  | Sub Totals | 55 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team, including demonstrable experience of working with small islands in general and BVI in particular. | 10 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Sub Totals | 20 |  |
| 3. Cost (20% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 5 |  |
|  | Clarity of each team member’s contribution and value added | 5 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

25 Year Environment Plan

https://www.gov.uk/government/publications/25-year-environment-plan