## Guidance
Supplementary Information Document (SID) Guidance
This document is made up of three sections: The Supplementary Building Information Tool (SBIT), a project breakdown and a risk register. All three sections need to be completed in their entirety and if any elements are incomplete then the project will not pass initial quality check and move to assessment.
1. Supplementary Building Information Tool
This Supplementary Building Information Tool aims to provide a place to capture information that will form the basis of your heat decarbonisation plan and/or detailed designs. Any questions regarding the Supplementary Building Information Tool please contact: Phase4lcsfgrants@salixfinance.co.uk The tool should be filled out on a building by building basis, with 1 building and associated UPRN per line. The columns D to R are to be submitted at the point of application by all applicants. The remaining columns S to AE are to be submitted for all applications over £100,000. Salix will not assess applications where incomplete data on these columns is submitted or there is a failure to submit at the point of application. The information, in columns S to AE, will need to be completed and submitted to Salix, by the remaining applicants under £100,000, alongside your heat decarbonisation plan and/or detailed designs when completed by 28th March 2024.
Green Columns are mandatory at the point of application
Blue columns are optional at the point of application, except where bids are received for over £100,000. For bids over £100,000, this information is to enable proportionality of assessment.
Purple columns are requested at post contract award stage to provide a cost breakdown of work per building, this will be used to help benchmark costs in future schemes
COMPLETING THE FORM - COLUMNS D TO R
Organisation name* | The name of the public sector body applying for funding.
Total Number of Buildings | The formula will automatically calculate the total number of buildings listed in column E. This will also be used to answer the question 'The number of buildings covered in your HDP' in the application.
Total Gross Internal Area | The formula will automatically calculate the value from column K. This value is to be used in the application question 'Total Gross Internal Area'.
Site Name* | The actual name of the site: for instance ABC University; XYZ School, Town Hall, Hospital.
Building Name* | The name of the specific building: for instance; Science Block; ABC wing (of a hospital), Sports Hall, etc. An individual row must be completed for each building that funding has been applied for to prepare/include in the Heat Decarbonisation Plan. The total number of buildings entered in your support tool will be automatically calculated in row 5 and will need to match what is entered in the application portal.
Building Type* | Select from the drop down list.
Specific Building Use | If 'other' has been selected in building type, please specify.
Unique Property Reference Number (UPRN)* | See specific guidance in the UPRN tab.
School / Academy URN (if applicable) | The DfE Unique Reference Number (URN) for schools and academies.
Postcode* | Provide the building postcode.
Gross Internal Area (m^2)* | Provide the actual internal area of the building. The total gross internal area from all the buildings listed in this column will be automatically calculated in row 7 and will need to match what is entered in the application portal.
Site Life (years)* | Enter the number of years the building is expected or projected to be in use for or under the public sector ownership.
Age of Building (Year building finished)* | Select the timeframe in which the building finished construction from the drop down
Condition of building* | Does the building fabric require immediate improvement work (e.g. leaking roof, severe draught, etc)? Indicate here if there are specific factors affecting the building, e.g. Grade 1, Grade II, Heritage site, Conservation area, PFI agreement, any other factor. Rate the condition of the building as Poor (immediate attention <5 years), Fair (5-10 years), or Good (little to no action required in next 10 years).
Existing Heating System* | Specify the heating system that is used in building- Gas boiler, oil/coal boiler, heat pump, electric heating, biomass, etc.
Existing Heating Fuel* | Select from the drop down list
Age of Existing Heating System (years)* | How old is the heating system - in number of years.
Display Energy Certificate (DEC) Rating* | Display Energy Certificates (DECs) are designed to show the energy performance of public buildings. Select from the drop down list.
COMPLETING THE FORM - COLUMNS S TO AE
State the type and condition in upgrading these technologies. Poor - Short-term action needed in the next 5 years. Fair - Medium term action over 5 to 10 years. Good - Recently upgraded, little to no action required in the next 10 years.
Existing Annual Fossil Fuel Use (kWh/year) | Provide the annual heating kWh data in the building - for the previous year or as an average over 3 or 5 years if last years usage of the building doesn't reflect expected fuel usage going forward, due to covid for example.
Existing Annual Electricity Use (kWh/year) | Provide the annual electricity kWh data in the building - for the previous year or as an average over 3 or 5 years if last years usage of the building doesn't reflect expected fuel usage going forward, due to covid for example.
Heating controls/BEMS | What heating controls and/or BEMS (building energy management system) are in place in this building? Specify condition- Poor/ Fair/ Good (see guidance above).
Wall insulation type | What wall insulation types are in place in this building: Cavity wall insulation, external wall insulation, internal wall insulation, etc? Specify condition- Poor/ Fair/ Good (see guidance above).
Roof insulation type | What type of roof insulation is in this building: Spray foam roof insulation, rigid insulation boards, blanket insulation (also called matting insulation), glass rock and mineral wool insulation, loose fill insulation, structural insulated panels and others. Specify condition- Poor/ Fair/ Good (see guidance above).
Window type | Windows types are: Single, double or triple glazing and metal, plastic or wooden frames. Specify condition- Poor/ Fair/ Good (see guidance above).
Lighting type | Lighting types are: Incandescent bulbs, fluorescent lamps, halogen lamps, LED. Specify condition- Poor/ Fair/ Good (see guidance above).
Other key electrical loads | What facilities or large equipment's add to electrical load in the building? E.g. large clinical or industrial equipment, laundry, etc.
COMPLETING THE FORM - COLUMNS AF TO AN
State the cost per output in each building
1. Preparation of a strategic plan to decarbonise building(s)/estate | State the cost for the preparation of a strategic plan to decarbonise building(s)/estate for each building. If this output will not be completed for this building leave blank
2. Building Audit | State the cost for the completion of a building audit for each building. If this output will not be completed for this building leave blank.
3. Feasibility Study | State the cost for the completion of a feasibility study for each building. If this output will not be completed for this building leave blank.
4. Specialist technical site surveys | State the cost for the completion of specialist technical site surveys for each building. If this output will not be completed for this building leave blank.
5. Detailed Design | State the cost for the completion of a detailed design for each building. If this output will not be completed for this building leave blank.
6. Investment Grade Audit | State the cost for the completion of specialist technical site surveys for each building. If this output will not be completed for this building leave blank.
7. Desktop Assessment | State the cost for the completion of a desktop assessment for each building. If this output will not be completed for this building leave blank.
Total Cost (£) | Will autofill the total cost from all outputs
Comments | Provide any relevant commentary on the cost breakdown
2. Project Breakdown
1. Project Cost Breakdown Please provide a breakdown of project costs for the application as a whole, including VAT if unclaimable. Internal management costs cannot be included within the grant funding requested, however an external consultants costs can be included within project delivery costs. 2. Commentary on Project Costs Please describe how the project costs for the project were deduced, including: • Cost breakdown per activity detailed above - please include the specific works within each activity (Salix appreciates that costs may not be finalised at this stage). • How the cost breakdown split has been estimated. • How the approach taken is cost effective. • Do costs reflect recent changes in demand and price inflations for similar works? Has contingency been built in to account for this? 3. Project Programme All key milestone dates must be entered in this section - please bear in mind that the final completion date for all LCSF projects is 28th March 2024.
3. Risk Register
Please provide all of the key risks that are associated with the project.

## UPRN Guidance
Guidance on finding the correct UPRN for your building(s)
Most public sector organisations have difficulty with the identification of the Unique Property Reference Number (UPRN). Therefore, we have prepared this guidance.
The most common website, that has been suggested previously, to find your UPRN is:
Find My Address (findmyaddress.co.uk)
Please note: There is a limit to the number of postcode searches that can be carried out in a single day, which is 30.
Frequently Asked Questions (FAQs) can be found here.
For organisations who need to understand the importance of the UPRN, the following link is useful.
Unique Property Reference Number ¦ Power of UPRN ¦ GeoPlace LLP
Within 5 minutes, readers will learn what a UPRN is, how a building is allocated a UPRN, and why it is important.
Please note: it is the Local Authority responsibility to assign UPRN’s to buildings, and each Local Authority will have a custodian of the data.
Public Sector bodies have the right of use of the UPRN database, which is held by the Ordnance Survey. To learn more about how to access the free database of UPRN’s click here:
AddressBase Premium ¦ OS Products (ordnancesurvey.co.uk)

## 1. SBIT
Phase 4 Public Sector Low Carbon Skills Fund - Supplementary Building Information Tool (SBIT)
Please use the table below to provide building details for all measures included within this application.
Green Columns are mandatory at the point of application
Blue columns are optional at the point of application, except where bids are received for over £100,000. For bids over £100,000, this information is to enable proportionality of assessment.
Purple columns are requested at post contract award stage to provide a cost breakdown of work per building, this will be used to help benchmark costs in future schemes.
Information is required for all buildings which will be covered by the project. *An asterisk denotes fields that are mandatory for all applicants at the time of application, additional information may be required during the assessment process or upon award of funding. Specific Building Use will be mandatory if you enter Other in the Building Type dropdown. School / Academy URN is mandatory if the building is owned by a School or Academy.
[30 empty] | Total Cost | 0
| Submission ID | Organisation Name:* | Central Swindon North Parish Council |  |  | Total Number of Buildings | 14 |  | Do the number of rows entered match across mandatory columns? | Yes | [8 empty] | State the type and condition in upgrading these technologies. Poor - Short-term action needed in the next 5 years. Fair - Medium term action over 5 to 10 years. Good - Recently upgraded, little to no action required in the next 10 years. | [10 empty] | State the building specific activity cost. If the activity was not undertaken please leave the column blank. If the building is part of a larger building for e.g. a classroom within a school or a building within a campus and you do not have the cost for that specific building but you do for the wider building (e.g. school or campus building) please estimate how much of the total cost of that activity is associated with that building. *Definitions are available for each activity if you select the cell.
Submission ID:
[6 empty] | Total Gross Internal Area (m^2) | 4023 |  | Total Cost | 0
[19 empty] | Heating Controls/BEMS |  | Wall Insulation |  | Roof Insulation |  | Windows |  | Lighting |  |  | Activity Cost (£)
| Submission ID? | Site Name* | Building Name* | Building Type* | Specific Building Use | Unique Property Reference Number (UPRN)* | School / Academy URN (if applicable) | Postcode* | Gross Internal Area (m^2)* | Site Life (years)* | Age of Building (Year building finished)* | Condition of building* | Existing Heating System* | Existing Heating Fuel* | Age of Existing Heating System (years)* | Display Energy Certificate (DEC) Rating * | Existing Annual Fossil Fuel Use (kWh/year) | Existing Annual Electricity Use (kWh/year) | Controls Type | Condition (of controls) | Wall Insulation Type | Condition (of wall insulation) | Roof Insulation Type | Condition (of roof insulation) | Window Type | Condition (of windows) | Lighting Type | Condition (of lighting) | Other Key Electrical Loads | 1. Preparation of a strategic plan to decarbonise building(s)/estate | 2. Building Audit | 3. Feasibility Study | 4. Specialist technical site surveys | 5. Detailed Design | 6. Investment Grade Audit | 7. Desktop Assessment | Total Cost (£) | Comments
|  | Pinetrees Community Centre | Parish Offices | Community Centre | Multifunction | 10091989871 |  | SN2 1QR | 1029 | 99 | 2011 Onwards | Fair | Gas boiler | Gas | 1 | E
|  | John Moulton Hall | John Moulton Hall | Community Centre | Multifunction | 10009419819 |  | SN2 5DU | 455 | 95 | 1951-1960 | Fair . | Gas boiler | Gas | 5 | E
|  | Western Community Centre | Western Community Centre | Community Centre | Multifunction | 100121343597 |  | SN2 1NF | 394 | 95 | 1981-1990 | Fair, some roof repairs needed. | Gas boiler | Gas | 10 | D
|  | Gorse Hill | Gorse Hill Community Centre | Community Centre | Multifunction | 100121344685 |  | SN2 8DA | 604 | 95 | 1981-1990 | Fair, some roof repairs needed. | Gas boiler | Gas | 10 | B
|  | Moredon | Moredon Community Centre | Community Centre | Multifunction | 100121344376 |  | SN25 3ER | 449 | 95 | 1971-1980 | Good | Gas boiler | Gas | 1 | E
|  | Even Swindon | Even Swindon Community Centre | Community Centre | Multifunction | 100121344256 |  | SN2 2BG | 547 | 95 | 1981-1990 | Fair. | Gas boiler | Gas | 10 | D
|  | Chippenham Close | Chippenham Close Community Centre | Community Centre | Multifunction | 10022791959 |  | SN2 5DB | 70 | 95 | 1981-1990 | Fair . | Electric heating | Electricity | 1 | N/A
|  | Moredon & Rodbourne Cheney Library | Moredon & Rodbourne Cheney Library | Library | Library | 100121344272 |  | SN25 3DJ | 61 | 95 | 1981-1990 | Fair . | Gas boiler | Gas | 10 | N/A
|  | Chapel Street Toilet | Chapel Street Toilet | Other | Public Convenience | 10009420737 |  | SN2 8AG | 75 | 95 | 1991-2000 | Fair | Electric heating | Electricity | 2 | D
|  | 32 the Circle (The Reading Rooms) | The Reading Rooms | Council Office | Council Chambers | 10009420520 |  | SN2 1RB | 55 | 95 | 1971-1980 | Fair, some roof repairs needed | Gas boiler | Gas | 10 | D
|  | Southbrook Recreation | Southbrook Pavilion | Outdoor Sport Facilities | Changing Rooms | 10090041538 |  | SN2 1QP | 80 | 95 | 1991-2000 | Fair | Electric heating | Electricity | 10 | N/A
|  | Mannington Recreation | Mannington Pavilion | Outdoor Sport Facilities | Changing Rooms | 10022792294 |  | SN5 7YW | 87 | 95 | 1981-1990 | Fair. | Electric heating | Electricity | 2 | N/A
|  | Penhill Recreation | Penhill Pavilion | Outdoor Sport Facilities | Changing Rooms | 10009420513 |  | SN25 3AQ | 57 | 95 | 1901-1950 | Fair . | Electric heating | Electricity | 10 | N/A
|  | St Marks Recreation | St Marks Tennis Pavilion | Outdoor Sport Facilities | Multifunction | 10009420928 |  | SN2 1DB | 60 | 95 | 2011 Onwards | Good. | Gas boiler | Gas | 7 | N/A
All numbers in this row should be the same as they count how many rows of data you have entered in the above column |  | 14 | 14 | 14 |  | 14 |  | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
Note on AF16: The preparation and production of your HDP.
Note on AG16: A report that evaluates energy performance of a building. This could include information related to: - the building features such as energy performance of building fabric, heating and cooling system. - Energy consumption baseline, type of energy sources and energy benchmarks - Energy measure that can be implemented to reduce and energy consumption and to switch fossil fuel system to low carbon solution.
Note on AH16: A report that evaluates the practicality and deliverability of a proposed project. A feasibility study aims to: holistically appraise the strengths and weaknesses of an existing system; deduce opportunities and risks present in different solutions; consider the resources required to complete the project; and conclude the best course of action or likelihood of success.
Note on AI16: Site surveys for the building included in the HDP where specific low carbon technologies are evaluated to be installed and specialist site survey would support the suitability of the low carbon solution identified. An example could be borehole sample/inspection for installing a Ground Source Heat Pump.
Note on AJ16: Project design as defined in RIBA stages in RIBA plan of work. Detailed design is defined as stage 4.
Note on AK16: The investment grade proposal (IGP) is produced by the ESCO and should detail key information including the Energy Conservation Measures (ECMs) to be installed, guaranteed energy savings, tonnes of CO2 to be saved each year, capital costs, maximum payback period and a measurement and verification (M&V) plan.
Note on AL16: Desktop assessments are high level assessments (energy and decarbonisation) often executed considering only information of the building without any site visit of the building.

## 2. Project Breakdown
Phase 4 LCSF Project Breakdown
1. Project Cost Breakdown
If pre-tender please provide cost estimates, and final costs to be provided when available. Please only specify the total VAT if non-reclaimable in appropriate box.
1. Preparation of a strategic plan |  | 0
2. Building Audit |  | 0
3. Feasibility Study |  | 0
4. Specialist technical site surveys
5. Detailed Design
6. Investment Grade Audit
7. Desktop Assessment |  | 0
Can the organisation reclaim VAT?
VAT (£)
Only include here if non reclaimable
Total Project Costs (£) |  | 0
2. Commentary on Project Costs
Have you estimated the costs for the project? |  |  | No
Please describe how the project costs for the project were deduced, including:
• Cost breakdown per activity detailed above - please include the specific works within each activity (Salix appreciates that costs may not be finalised at this stage).
• How the cost breakdown split has been estimated.
• How the approach taken is cost effective.
• Do costs reflect recent changes in demand and price inflations for similar works? Has contingency been built in to account for this?
3. Project Programme
Please input dates of key milestones in the table below. Note that these milestones will be estimated and oversimplified.
Milestone | Completion Date |  | Days of contingency included in step
Project Approval | Late June
Procurement Start Date | Early July 2023
Work Prior to Site Visit | Early July 2023
Work Undertaken on Site | Early September 2023
HDP Report Write-Up | Early January 2024
HDP Approval Date | Early February 2024
HDP Submitted to Salix | Late February 2024
Submission of Final Invoices | Late February 2024
Please provide commentary on the project delivery timescales
• Include commentary to demonstrate readiness to deliver project
• Comment also on what contingency is built into the programme
© Salix 2023
Note on D8: The preparation and production of your HDP.
Note on D10: A report that evaluates energy performance of a building. This could include information related to: - the building features such as energy performance of building fabric, heating and cooling system. - Energy consumption baseline, type of energy sources and energy benchmarks - Energy measure that can be implemented to reduce and energy consumption and to switch fossil fuel system to low carbon solution.
Note on D12: A report that evaluates the practicality and deliverability of a proposed project. A feasibility study aims to: holistically appraise the strengths and weaknesses of an existing system; deduce opportunities and risks present in different solutions; consider the resources required to complete the project; and conclude the best course of action or likelihood of success.
Note on D14: Site surveys for the building included in the HDP where specific low carbon technologies are evaluated to be installed and specialist site survey would support the suitability of the low carbon solution identified. An example could be borehole sample/inspection for installing a Ground Source Heat Pump.
Note on D16: Project design as defined in RIBA stages in RIBA plan of work. Detailed design is defined as stage 4.
Note on D18: The investment grade proposal (IGP) is produced by the ESCO and should detail key information including the Energy Conservation Measures (ECMs) to be installed, guaranteed energy savings, tonnes of CO2 to be saved each year, capital costs, maximum payback period and a measurement and verification (M&V) plan.
Note on D20: Desktop assessments are high level assessments (energy and decarbonisation) often executed considering only information of the building without any site visit of the building.

## 2.2 - Project costs Breakdown
Building | Floor Area (m2) | Preparation | Site Surveying | Produce Report | Total Support
|  | Hours | Hours | Hours | Hours | Days
Pinetrees Community Centre | 1029
John Moulton Hall | 455
Western Community Centre | 394
Gorse Hill | 604
Moredon | 449
Even Swindon | 547
Chippenham Close | 70
Moredon & Rodbourne Cheney Library | 61
Chapel Street Toilet | 75
32 the Circle | 55
Southbrook Recreation | 80
Mannington Recreation | 87
Penhill Recreation | 57
St Marks Recreation | 60
TOTALS | 4023

## 3. Risk Register
Phase 4 LCSF Risk Register
Project Risks and Mitigation
Please detail what you think the key risks or issues surrounding the deliverability of this bid. • In the description highlight whether this is a potential risk or issue. • Include potential risks of internal resourcing for management of project within timescales. • Please describe the mitigation measures in place to manage each issue.
Description of Risk | Level of Risk | Type of Risk | How will the Risk be Managed and Mitigated?
Internal Governance Set Up | Low | Project Delivery
Project team resourcing | Low | Resource
Engineering Support | Low | Resource
Planning to minimise disruption to services during Site Survey Process | Moderate | Project Delivery
Data provision | Moderate | Other
Unknown DNO and in house network costs | High | Cost
Delays to DNO Assessment and upgrades | High | Project Delivery
Allowing for Planning issues | Moderate | Feasibility
Safety risks and preparation for site surveys | Moderate | Other
© Salix 2023

## Energy consumption
| Building | Floor Area from DEC m2 | Annual energy use (kWh/m2/year) |  | Annual energy use kWH
|  |  | Electricity | Other fuels | Electricity | Other fuels
1 | Pinetrees Community Centre | 1028.66 | 85.06 | 121.88 | 87497.8196 | 125373.0808
2 | John Moulton Hall | 454.85 | 29.99 | 207.24 | 13640.9515 | 94263.114
3 | Western Community Centre | 394.19 | 31.91 | 139.13 | 12578.6029 | 54843.6547
4 | Gorse Hill | 604.11 | 21.9 | 44.23 | 13230.009 | 26719.7853
5 | Moredon | 449.02 | 66.2 | 76 | 29725.124 | 34125.52
6 | Even Swindon | 546.67 | 41.46 | 123.53 | 22664.9382 | 67530.1451
7 | Chippenham Close | 70 | no data
8 | Moredon & Rodbourne Cheney Library | 61 | no data
9 | Chapel Street Toilet | 75 |  |  | 7701
10 | 32 the Circle (The Reading Rooms) | 55 | no data
11 | Southbrook Recreation | 80 |  |  | 10364 | 0
12 | Mannington Recreation | 87 |  |  | 21475 | 0
13 | Penhill Recreation | 57 | no data
14 | St Marks Recreation | 60 | no data
| Totals | 4022.5 |  |  | 218877.4452 | 402855.2999

## Backing Sheet (hidden)
Building Type | Existing Heating Fuel | Condition | Heating controls/BEMS | Wall insulation | Roof insulation | Windows | Lighting | Building Finished | DEC rating | Site Life (years)*
Ambulance station | Gas | Poor (Short-term) | No heating controls | Dry wall lining | Spray foam roof insulation | Single glazed | Incandescent bulbs | Prior to 1800 | A | 5
Campus Building | Gas Oil | Fair (Medium-term) | Manual controls | Cavity wall insulation | Rigid insulation boards | Double glazed | Fluorescent lamps | 1800-1900 | B | 10
Canteen/Cafeteria | Fuel Oil | Good (Recently upgraded) | BEMS - not remotely managed | Internal wall insulation | Blanket insulation/ Matting insulation | Triple glazed | Halogen lamps | 1901-1950 | C | 15
Car park | Electricity |  | BEMS - remotely managed | External wall insulation | Glass rock and mineral wool insulation | Other | LED | 1951-1960 | D | 20
Classroom | Coal |  | Heating - discrete controls | No thermal insulation | Loose fill insulation | Don't know | Other | 1961-1970 | E | 25+
Clinical space | Burning Oil |  | Heating - zone control valves | Other | Structural insulated panels |  | Don't know | 1971-1980 | F
Community Centre | LPG |  | Other | Don't know | No loft insulation |  |  | 1981-1990 | G
Corridors | Wood Pellets |  | Don't know |  | Other |  |  | 1991-2000 | N/A
Council Office | Wood Chips |  |  |  | Don't know |  |  | 2001-2010
Data Centre/IT Facilities | Bespoke | [6 empty] | 2011 Onwards
Fire Rescue Station
Gallery/Museum |  | Existing Heating System
Halls of Residence
Laboratory |  | Gas boiler
Lecture Room |  | Oil boiler
Leisure Centre |  | Coal boiler
Library |  | Biomass
Non-clinical space |  | Electric heating
Offices |  | Heat pump
Outdoor Sport Facilities |  | Fossil fuel powered district heating
Parish/ Town Council |  | CHP
Plant room |  | Other
Police Station |  | Don't know
Renewables Site
Residential Care Home
Sports Hall
Streetlighting
Students Union
Warehouse
Other