# Our Heritage

Organisation	Heritage Lottery Fund

Department	Strategy & Business Development

Title of procurement	Our Heritage Review

Brief description of supply	Evaluation services

Estimated value of tender	Up to £15,000 including VAT and expenses

Estimated duration	3 Months

Name of HLF Contact		        Kion Ahadi

Head of Evaluation

Heritage Lottery Fund

7 Holbein Place

London SW1W 8NR

Phone: 020 7591 6073

Email: Kion.Ahadi@hlf.org.uk

Website: www.hlf.org.uk

Timetable	Response deadline: 18 September 2017

Clarification & Negotiation meetings: 26 September 2017

Confirmation of contract: 28 September 2017

Completion of research: 15 December 2017

# 1.	Overview

  - The Heritage Lottery Fund (HLF) was set up in 1994 under the National Lottery Act and distributes money raised by the National Lottery to support projects involving the national, regional and local heritage of the United Kingdom. We operate under the auspices of the National Heritage Memorial Fund (NHMF). Since April 2013 we have been operating under our current Strategic Framework: ‘A lasting difference for heritage and people’. See the HLF website for more details.

  - HLF invests in the full breadth of the UK’s heritage and, through our funding, we aim to make a lasting difference for heritage and people. This is reflected in the outcomes for heritage, people and communities which underpin our grant-making.

  - Our Heritage is an open grants programme that funds projects involving all kinds of heritage with grants of between £10,000 and £100,000. The programme opened in April 2013 with an annual budget of £22m, for five years. We anticipated this budget would fund between 300 and 400 projects per year over the five year period. The programme funds applications from not-for-profit organisations, private owners of heritage (including individuals and for-profit organisations) and partnerships.

  - Our Heritage is one of three open programmes operating under the current strategic framework and supports HLF’s key objective to ‘sustain and transform a wide range of heritage and generate a lasting impact on people and places’. Funded projects range from museums, parks and historic places to archaeology, the natural environment and cultural traditions.

  - In 2013 we commissioned an evaluation to draw upon evidence from a random sample of funded projects in order to provide an insight into the extent to which the desired outcomes for heritage, people and communities were being achieved.  We now want to look further at a subset of these projects.  The size of the sample is to be agreed, but we would like to include projects that were included in the original evaluation and have come to the end of their grant.  The original evaluation was contracted to look at 360 projects.

  - Building on this study we would like to further investigate a sample of completed projects that were part of the original study.

  - The first audience for the evaluation is HLF, where it will inform our policy and decision making. However, the results will be made publicly available and may be of interest to other policy makers, funders and practitioners in the heritage sector.

# Method

  - The aim of the evaluation is to

a) identify the quality of self-evaluations from a sample of completed Our Heritage projects; and
b) map the activities and outcomes achieved by projects against our Outcome framework.

  - Self-evaluation review

This task will primarily involve reviewing material held by HLF. Consultants should use the methodology already developed to assess the quality of the project self-evaluations (see: https://www.hlf.org.uk/about-us/research-evaluation/programme-evaluation/review-grantee-evaluations).

Outcomes review

In the second part of the research, consultants should use the assessment, monitoring and evaluation information held by HLF to review and summarise the type, range and quality of activities and outcomes achieved by completed projects, and to map these onto HLF’s 14 outcomes for heritage, people and communities.

As well as helping to quantify and evaluate the achievements of completed Heritage Grants projects, this task will support the design of future evaluation of HLF’s programmes.

  - HLF will make available the data it holds on the Our Heritage Grants programme and the 177 projects completed between January 2015 and April 2016.  As well as programme-level funding data and completed self-evaluations, this includes application forms (where applicants are asked a specific question about how they intend to evaluate their project), project budget information, and project completion reports.

# Outputs

  - The following outputs will be required:

- a draft final report in word;

- a final report in word;

- any other reports as set out here or agreed between HLF and the contractor; and

- a set of research data, to be stored in a readily accessible electronic format such as Excel

A project plan with specific deliverables* and timetable will be agreed with the successful consultant/ies. However, HLF expects the following deliverables in accordance with the following timetable as a minimum:

| Deliverable/Key Milestones* | Due date |
| --- | --- |
| Inception meeting to agree plans and frequency of reporting. | TBC |
| A draft report of maximum 30 pages which details the review. This should include a one page executive summary with narrative and a one page infographic presenting the main findings. The report should include a description of the evaluation framework, key findings and recommendations for improvement. | 15 December 2017 |
| A finalised report of maximum 30 pages which details the review. This should include a one page executive summary with narrative and a one page infographic presenting the main findings. The report should include a description of the evaluation framework, key findings and recommendations for improvement. | 5 January 2018 |

  - All reports must adhere to HLF’s accessibility and formatting guidance (appended).

  - The initial findings will be confidential to HLF. HLF may prepare or commission summary reports and other materials for subsequent wider distribution, based on the results.

  - All reports to include appendices as agreed between HLF and the contractor. The contents and structure of the report to be agreed in advance of writing. All reports to be supplied in electronic format and hard copy if requested.

  - All bidders are required to adhere to all appropriate regulations and guidelines on the collection, storage, transmission and destruction of personal data (MRS/SRA, Data Protection Act 1998: Guidelines for Social Research, April 2013).

# Contract management

  - We expect the research/evaluation to begin 3 October 2017 and be completed by 15 December 2017. The final report shall be submitted to HLF by 5 January 2018

  - The anticipated budget is up to £15,000 to include all expenses and VAT. The contract will be let by the National Heritage Memorial Fund.

  - The payment schedule will be 20% at start up after contract exchange; other payments will be agreed with the contractor based on completion of agreed milestones, with 10% to be paid after approval of the final report..

  - The contract will be based on the HLF standard terms and conditions.

  - The research will be managed on a day to day basis for HLF by Kion Ahadi.

# Award Criteria

  - The proposal for undertaking the work should be a maximum of 15 pages and include:

- a detailed method for undertaking the study;

- details of staff allocated to the project, together with experience of the contractor and staff members in carrying out similar projects. The project manager / lead contact should be identified;

- the allocation of days between members of the team;

- the daily charging rate of individual staff involved;

- a timescale for carrying out the project;

- an overall cost for the work.

  - Your Bid will be scored out of 100%. 

50% of the marks will be awarded to Quality

Each question will be scored using the methodology in the table below.

Tender responses submitted will be assessed by HLF against the following Quality Questions:-

| - Demonstrated a clear understanding of the aims, objectives and main concerns of the evaluation. | Weighing 25% |
| --- | --- |
| - Demonstrated the proposed design and methods are well developed, appropriate and meet the aims and objectives of the evaluation | Weighting 25% |
| - Demonstrated the bidder has the capacity and resources to carry out the evaluation within the timescale, or if working in partnership, each organisation has the capacity to fulfil its role and roles of each partner is clear. | Weighting 25% |
| - Demonstrated a clear and realistic project plan, showing phases of the evaluation, tasks for each phase and roles and responsibilities for each member of the team. | Weighting 25% |

Scores will be given for each criteria in a range of 1 (low) to 5 (high), as per the descriptions in the quality questions scoring methodology table below.

## Quality Questions scoring methodology

| Score | Word descriptor | Description |
| --- | --- | --- |
| 0 | Poor | No response or partial response and poor evidence provided in support of it. Does not give the HLF confidence in the ability of the Bidder to deliver the Contract. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Satisfactory | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives the HLF confidence in the ability of the Bidder to deliver the contract. Meets the HLF’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the HLF a high level of confidence in the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the HLF a very high level of confidence the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in most respects. |

50% of marks will be awarded for Price
The evaluation of price will be carried out on the Schedule of charges you provide in response to Table A

## Price Criterion at 50%

- The scores for quality and price will be added together to obtain the overall score for each Bidder.
50 marks will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your fixed and total costs figure in your schedule of charges table will be used to score this question.

- For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced bidder gets 50% (full marks) for price and the second placed bidder gets 46% and so on. (8/100 x 50 =4 marks; 50-4 =46 marks)

- The scores for quality and price will be added together to obtain the overall score for each Bidder.

## Table A - Schedule of Charges

Please show in your tender submission, the number of staff and the amount of time that will be scheduled to work on the contract with the daily charging rate.

Please complete the table below providing a detailed breakdown of costs against each capitalised description, detailing a total and full ‘Firm Fixed Cost’ for each element of the service provision for the total contract period. Bidders may extend the tables to detail additional elements/costs if required.

VAT is chargeable on the services to be provided and this will be taken into account in the overall cost of this contract.

As part of our wider approach to corporate social responsibility the National Heritage Memorial Fund/Heritage Lottery Fund prefers our business partners to have similar values to our own. We pay all of our staff the living wage (in London and the rest of the UK) and we would like our suppliers and contractors to do likewise. Please highlight in you proposal/tender/bid whether you do pay your staff the living wage.

Bidders shall complete the schedule below, estimating the number of days, travel and subsistence costs associated with their tender submission.

TABLE A: (firm and fixed costs)

| Cost | Post 1 @cost per day (No of days) e.g. Project Manager/ Director @ £2 | Post 2 @cost per day (No of days) e.g. Senior Consultant/manager/researcher @£1.5 | Post 3 @cost per day (No of days) Junior Consultant/equivalent e.g. £1 | Total days | Total fees |
| --- | --- | --- | --- | --- | --- |
| Inception meeting to agree plans and finalise requirements with the Fund | Example 0.5 | 1 | 1.5 | 3 | £4 |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |

| Cost Type | Value (£) |
| --- | --- |
| Sub - Total |  |
| VAT |  |
| Total* |  |

* (This must include all expenses as well as work costs; this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements set out in the ITT)

Notes: 	HLF reserves the right to clarify quality and prices and to reject tenders that demonstrate an abnormally low quality response. HLF also reserves the right to amend the timetable of work where required.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

# Procurement Process

  - HLF reserves the right to reject abnormally low scoring tenders. HLF reserves the right not to appoint and to achieve the outcomes of the research/evaluation through other methods.

  - The procurement timetable will be:

Tender return deadline: completed proposal to be returned to HLF by 10.00 am on 18 September 2017.

Clarification/ Negotiation meetings* may be held with shortlisted consultants and would take place on 26 September 2018.

HLF will notify bidders of our procurement decision by 28 September 2017.

* We reserve the right to carry out clarifications if necessary; these may be carried out via email or by inviting bidders to attend a clarification meeting.  In order to ensure that both HLF’s and Bidder’s resources are used appropriately, we will only invite up to three (the ultimate number will depend on the closeness of the scores) highest scoring bidders to attend a clarification meeting.  Scores will be moderated based on any clarifications provided during this meeting.  You are responsible for all your expenses when attending such meetings.

  - Your tender proposals must be sent electronically via e-mail before the tender return deadline of 10.00 am  on 18 September 2017 to the following contact:

Emily Griffiths

Heritage Lottery Fund

Holbein Place

London

SW1W 8NR

Emily.griffiths@hlf.org.uk

  - Please visit the HLF website for further information about the organisation.

# Appendix: Accessibility and formatting guidance

HLF is committed to providing a website that is accessible to the widest possible audience. Our website is annually tested by accessibility auditors and we must meet the WCAG 2.0 AA compliance level. Our accessibility testing covers all of our content, including downloadable documents, as well as the design and functionality of the site.

Reports and other documents created for HLF (including the tender submissions) need to be clear, straightforward to use, and ready to circulate internally, externally and online, as well as suitable for use by screen reading software. Tips for creating accessible documents can be found below. However, we strongly recommend referring to the RNIB, Gov.uk and WebAIM for more detailed information.

## Readability

In the final report, and all other documents that may be published online including the tender application consultants should ensure that:

- The size of the font is at least 11pt;

- There is a strong contrast between the background colour and the colour of the text. Black text on a white background provides the best contrast. This also applies to any shading used in tables and/or diagrams;

- Italics are only used when quoting book titles for citations and items on the reference list should be arranged alphabetically by author

- Colour formatting and use of photos should be of a resolution size that is easily printable and does not compromise the printability of the document.

For further guidance on ensuring readability of printed materials, please refer to the RNIB Clear Print guidelines. These can be found on the RNIB website.

## Accessibility

Reports should adhere to the following guidelines:

### Formatting

Headings and content in your document should be clearly identified and consistently formatted, to allow easy navigation for users. Heading Styles should be used to convey both the structure of the document and the relationship between sections and sub-sections of the content.

### Spacing

Screen readers audibly represent spaces, tabs and paragraph breaks within copy, so it is best practice to avoid the repetitive use of manually inserted spaces. Instead, indenting and formatting should be used to create whitespace (e.g., use a page break to start a new page, as opposed to multiple paragraph breaks).

### Alternative text

Alt text is additional information for images and tables. This extra information is essential for both document accessibility (screen reading software reads the Alt text aloud) and for the web. Alt text should be concise and descriptive, and should not begin with ‘Image of’ or ‘Picture of’.

### Images

These should be formatted in-line with text, to support screen readers. Crediting pictures may be necessary, usually in response to a direct request from a third party.

### Tables

These should be for used for presenting data and not for layout or design. They should also be simple, and include a descriptive title.

### Additional documents

Any additional information, separate to the report, for example proformas and transcripts which may be used as standalone documents must be fully referenced to the piece of work being submitting and therefore dated, formatted and numbered appropriately.

### Acknowledgement

All reports should acknowledge HLF. Our logo can be found on the HLF website.

### Further resources

Please refer to the links below for further information:

- 'Microsoft Word: creating accessible documents' - webaim.org

- 'How to create an accessible PDF' - GOV.UK

We also recommend using an accessibility consultant to help you produce your reports. Agencies that HLF have worked with include Shaw Trust and The Accessible Digital Documents Company.

HLF retains the right to amend documents in order to create accessible versions for publishing.