# Annex A

| Title of Project | 0922S Survey Benthic Infaunal and PS Sample Analysis |
| --- | --- |
| Date and Time for Return of Bids | 31 October 2022 @ 16:00 hours |
| Contract Reference Number | C22-600-1672 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO TOM TANGYE, DAVID REYNOLDS, OR JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below; (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Joint Nature Conservation Committee Name: Tom Tangye Email: tom.tangye@jncc.gov.uk Telephone:01733 866944 OR Joint Nature Conservation Committee Name: David Reynolds Email: david.reynolds@jncc.gov.uk Telephone: +44 (0)1733 943167 |
| Contact for Queries Regarding the Procurement Procedure | Finance and Planning Team Joint Nature Conservation Committee Email: @jncc.gov.uk or contractqueries@jncc.gov.uk Telephone: 01733 866894 |
| Proposed Start Date | TBC |
| Proposed End Date | March 20th 2022 |

0922S Survey Benthic Infaunal and PS Sample Analysis

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	5

5.	Outputs	7

6.	Product Specification	8

7.	Dissemination	9

8.	Timescale	9

9.	Health and Safety	9

10.	Project Management	10

11.	Instructions for Bid Submission	10

12.	Evaluation Criteria	11

13.	Payment	13

14.	Additional Requirements	13

15.	References	13

16.	Appendix B: Sample Reference Collection Requirements	13

17.	Appendix 3: Example Table of Contents for Report	14

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to  protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

JNCC wishes to commission a contract to undertake the Particle Size and infaunal taxonomic analysis of samples collected on the 0922S cruise. There were 128 samples collected on the survey to the West Shetland Shelf MPA.

Bidders are invited to provide a description of how the requirements set out below will be met and a per sample quote.

A taxonomic sample reference collection is required, which the successful contractor will provide to the National Museum of Scotland (see Appendix B).

The sample residues will be stored by the contractor until completion of the contract (i.e. after any remedial action identified through quality checks has been actioned).

## Project Background

JNCC and Marine Scotland Science (MSS) will undertake an offshore seabed survey to the West Shetland Shelf MPA (WSS hereafter) onboard the Marine Research Vessel (MRV) Scotia (survey code 0922S).

The 0922S survey will depart from Aberdeen on 21st July 2022 and returned to Aberdeen on 3rd August 2022.

WSS lies in offshore waters to the north of Scotland. For more information regarding WSS please see http://jncc.defra.gov.uk/page-6491.

Sampling at WSS will be focussed on the designated Offshore Subtidal Sands and Gravels feature. Samples will be collected from stations within nested boxes in and outside of the WSS site boundary, from water depths of 70 to 150 m (Figure 1).

Sampling will be conducted using a 0.1 m2 Hamon Grab.

128 ml Particle Size (PS) sediment sub-samples will be extracted from each sample and frozen with the remaining sample sieved using a 1 mm mesh diameter sieve.

All material retained after sieving will be transferred to an appropriately sized plastic sample container and preserved in 5% formaldehyde solution buffered with borax.

For more information regarding the survey design and methodology, please contact JNCC.

Please note the following documents will be supplied to the successful contractor:

Survey programme

Associated metadata

Draft Cruise Report (after the survey has been completed)

MEDIN compliant MS Excel proforma spreadsheets (after the survey has been completed)

A

F

H

G

Figure 1. 0922S survey location showing boundary of West Shetland Shelf MPA and planned nested survey sampling boxes. Suvery boxes A, F, C, G and H was where the infaunal samples were collected, which is from predominatly from circalittoral sand areas. The green dots are where the succesful samples were collected.

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are to conduct a Particle Size analysis and Infaunal taxonomic analysis of the 128 samples have been collected on this survey, (see Table 1 for sample inventory and container sizes). Seventy of the 128 samples would have suited smaller container sizes but had to be put in larger containers due a lack of appropriately sized containers onboard the vessel.  All 128 samples have corresponding PSA samples.

Table 1. summarising infaunal samples collect at WSS during the 0922S survey in 2022.

| Number of Samples | Size of Container (e.g., 1 x 0.5L, 2 x 3L) | Comments |
| --- | --- | --- |
| 18 | 0.5 | Correct sizing |
| 43 | 1 | 33 would fit in 0.5 litre containers |
| 50 | 2.5 | 32 would fit in 1 litre containers 2 would fit in 1.5 litre containers |
| 11 | 5 | 2 would fit in 2.5 litre containers |
| 6 | 10 | 1 would fit in a 5 litre container |
| Total: 128 |  |  |

Particle Size analysis

Particle Size analysis must comply with NMBAQC guidelines for completing analysis for biological reasons1. This analysis is inclusive of the ‘greater than 1 mm’ fraction, which will be enumerated by dry sieving.

The ‘smaller than 2mm’ fraction will be analysed using laser diffraction. Each sample will be run for 1 minute, and all laser settings should be provided alongside the final dataset, such as what dispersants are used (if any), which type of correction (if any) are used and the replicate number per run.

Infaunal taxonomic analysis

Processing of samples is to be undertaken to extract and identify all biota retained following sieving on 1 mm mesh diameter sieves, as per the NMBAQC guidelines detailing extraction and identification protocols. Sub-sampling is permissible following consultation and agreement with the contract manager. However, it is not envisaged that this will be required.

Enumeration, identification and biomass should be carried out following the NMBAQC Processing Requirement Protocol and Taxonomic Discrimination Protocol2.

Biomass per recorded taxon (wet weight in grams to at least 4 decimal points) is required for all countable taxa.

The abundance and biomass data matrices should be sent via email to the project manager following completion. Please include an additional column to include the Aphia ID for each species in the taxon list, where appropriate, and order the species list by major taxonomic group.  Where data matrices span multiple tabs in Excel, identical species lists should be used in each tab to facilitate merging later.

All species names must be run through the WoRMS ‘Match Taxa’ tool3 so that all naming is current.

Quality Assurance

JNCC requires that the successful contractor complies with our EQA Policy. The policy can be found here: http://jncc.defra.gov.uk/default.aspx?page=6675.

Work under this contract will be subject to the provisions within the EQA policy.

Tenderers are required to provide details of internal Quality Assurance and Quality Check procedures, including details of present and past participation in relevant NMBAQC Scheme Components.

External Quality Assurance

Following award of the contract, and dependent on the evaluation scores they achieved, unsuccessful bidders may be invited to undertake the Particle Size and/or infaunal taxonomic independent external QA aspects of this project. Please indicate in your tender if you do not wish to be considered for this work.

Award of the external QA aspects of this work will be made following completion of the 0922S survey.

5% of Particle Size and 5% of infaunal samples processed are to be subject to an independent external QA process.

Comparison between external QA and original analysis will be undertaken as described below.

Prospective contractors should note the following:

- Adherence with the NMBAQC guidelines is not an end in and of itself, but contractors Standard Operating Procedure must be sufficiently rigorous in practise to achieve the required QA standards.

- The Remedial Action process may be iterative until the QA standards are achieved.

- Samples may be withdrawn, and refunds requested if samples fail to achieve satisfactory QA within a set number of rounds or within a specified time schedule.

- Contractors should alert the project manager if any samples they receive are deemed to be atypical, such that they require, or would benefit from, some method variation of their Standard Operating Procedure.

External Quality Assurance process for Particle Size Analysis

External QA Particle Size analysis will comply with NMBAQC guidelines for completing analysis for biological reasons.

The Particle Size analysis QA will consist of a 5% reanalysis of the processed samples, in line with the NMBAQC Own Sample scheme.

Where remedial actions are required, these are to be completed following discussions between the appointed contractor and JNCC at no additional cost.

External Quality Assurance process for infaunal taxonomic analysis

External QA infaunal taxonomic analysis will be carried out following the Own Sample NMBAQC Processing Requirement Protocol and Taxonomic Discrimination Protocol.

The following steps will be adhered to:

- Cluster analysis of the dataset is done by the original processing laboratory and sample selection is undertaken by JNCC;

- The original processing laboratory is to send the selected samples to the auditing laboratory within a day of receiving confirmation from JNCC of which samples are to be sent for QA;

- The auditing laboratory receives the sample sediment for selected samples to assess for missed fauna. Counts of individuals found are sent to the JNCC;

- The auditing laboratory receives the sample fauna and project level identifications (i.e. identifications from all samples processed by the original processing laboratory. Abundance data and biomass weights are not provided to the auditing laboratory;

- The auditing laboratory checks the identifications, incorporating any fauna found in the sediment residue, and counts and weighs the fauna;

- The auditing laboratory may request additional specimens for review though JNCC;

- The results are sent to JNCC and original processing laboratory;

- JNCC then sends the original results and images of the taxonomic reference collection to the auditing laboratory; and,

- The Bray-Curtis score can then be calculated by the auditing laboratory to determine the audit score (pass/fail) with complete transparency, which is issued to JNCC within the Own Sample Scheme spreadsheet standards.

It is the responsibility of the successful contractor to ensure this process is completed before the final delivery of each dataset.  Any remedial action required following the QA process must be completed within an agreed timeframe at no extra cost to the project.

All remedial action taken, and associated rationale, are to be recorded and provided as outputs of this contract. The contract shall not be deemed complete until this external Quality Assurance step has been completed successfully.

## Outputs

Any products or outputs submitted to JNCC [for publication] should adhere to JNCC’s house-style and should be produced in an accessible format (see product specification for more information).

| Output/Deliverable | Format |
| --- | --- |
| Particle Size Analysis of Particle Size samples as per NMBAQC Standards (http://www.nmbaqcs.org/media/1255/psa-guidance_update18012016.pdf) | MS Excel spreadsheet (proforma spreadsheet will be provided by JNCC) |
| Biological analysis of infaunal samples; full taxon and biomass as per NMBAQC Standards (http://www.nmbaqcs.org/media/1175/nmbaqc-inv-prp-v10-june2010.pdf) in species matrix | MS Excel spreadsheet (proforma spreadsheet will be provided by JNCC) |
| Infaunal sample taxonomic reference collection and associated metadata as per Appendix B | Reference collection (Reference Collection holder to be confirmed), MS Excel spreadsheet |
| ArcGIS point shapefiles for area surveyed including PSA summary per station (Folk classification and corresponding EUNIS broadscale habitat) Shapefile should be imbedded with INSPIRE compliant metadata (INSPIRE metadata template available in ArcGIS) and fully georeferenced in a defined coordinate system | ArcGIS point shapefiles |
| Final report | MS Word DOC |

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style (to be provided) and be produced using a JNCC template (to be provided), unless otherwise stated.  All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

(Note for author if research project/contract: see EQA Policy (Communicating Evidence Quality). Ensure that data management and storage requirements are stipulated taking into account relevant policy for data access. See https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

## Dissemination

The products/outputs produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC, the UK country nature conservation bodies (Marine Scotland, Nature Scot).

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting | TBC |
| Collection of samples from Marine Scotland Science, Aberdeen | TBC |
| Completion of analysis and reporting, provision of draft deliverables to JNCC and external QA samples to external QA laboratory | 27/03/2022 |
| Completion external QA and remedial action (if necessary) | 20/03/2022 |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2022/23 is subject to availability of funds.

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Tom Tangye

Email: tom.tangye@jncc.gov.uk

Telephone: +44 (0)1733 866944

Name: David Reynolds

Email:  david.reynolds@jncc.gov.uk

Telephone: +44 (0)1733 943167

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (note for author if research project/contract: see EQA Policy Appendix 1 (Bias, Conflicting Evidence and Uncertainty) and EQU Policy Appendix 3 (Quality Assurance of Expert Knowledge and Opinion):

Details of the bidder’s own internal Quality Management System;

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project;

Availability of the Project Team for a start-up virtual meeting

Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached, and should be used. These rates are analogous to the civil service rates).

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 14.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation will be undertaken by a panel consisting of JNCC staff only

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  | Understanding of, and relevance to, the requirements in particular the adequacy of outputs | 10 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors if any | 6 |  |
|  | Sub Total | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation what does presentation mean here in relation to cost? | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Total | 30 |  |
| Total Score |  | 100 |  |

## Payment

Unless a payment schedule is stated in your submission and agreed by JNCC project manager. Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## References

Mason. C. (2016) NMBAQC’s Best Practice Guidance Particle Size Analysis (PSA) for Supporting Biological Analysis. Available online at: http://www.nmbaqcs.org/media/1255/psa-guidance_update18012016.pdf

2 http://www.nmbaqcs.org/media/1175/nmbaqc-inv-prp-v10-june2010.pdf

3 http://www.marinespecies.org/aphia.php?p=match

## Appendix B: Sample Reference Collection Requirements

JNCC makes biological samples collected on survey available to museums and other researchers once they’ve been analysed. Survey data are expensive to collect, and it is important to ensure these data are used to their full potential. JNCC and MSS currently collaborate with the National Museums of Scotland (NMS) to allow ongoing use, and to secure long-term management, of seabed sample data.

To facilitate the incorporation of invertebrate specimens collected on behalf of JNCC into museum collections, specimens should be:

- Separated by species and by station/sample

- Preserved in 70 – 75% Industrial Methylated Spirit or similar (not formaldehyde)

- Placed in glass sample vials with polyethylene closures. The external diameter of the vials should be less than or equal to 15 mm and the height should be less than or equal to 55 mm. ‘Oversized’ specimens may be placed in any suitable container and will be transferred to glassware by the NMS.

- Glass vials must be 21.25ml 66 x 25.5mm and ideally supplied from here: https://uk.vwr.com/store/product/579261/sample-vials-trident-vials-squat-or-tall

- Each specimen vial should contain a visible internal label which includes (in pencil or alcohol-proof ink):

  - Species/Taxon name (in full)

  - Station/Sample Code

  - Number of specimens contained

- When specimens are delivered to NMS they must be in the same order as the metadata. This is to speed up initial checks and sign off the data.

A Sample Reference Collection Metadata spreadsheet should be provided detailing:

- Project/survey title and relevant project codes

- Client details (including nominated officer)

- Contractor details (including a nominated contact)

- Survey Vessel and Cruise number

- Generalised Description of Survey Area/Site

- Sampling Date (dd/mm/yyyy)

- Sampling Gear

- Position (Lat/Long including Datum e.g. WGS84)

- Depth (m)

- Species name and authority

- Station/sample code and replicate number– the original project coding is preferred so that the specimen data can be linked to physical and chemical data which may come from other sources/contractors (e.g. latitude/longitude, sediment characteristics)

- Sample substrate (should be entered as Folk)

- Biotope Classification (should be entered as MNCR 04.05)

- Biotope name (exact copy of MNCR 04.05 descriptor)

- Biotope code (exact copy of MNCR 04.05 code)

- Number of specimens per vial

- Details of preservative used

- Initials of identifier/taxonomist

A Species Matrix should also be included.

## Appendix 3: Example Table of Contents for Report

1	Introduction										1

2	Aims and objectives									2

2.1	Aim										2

2.2	Objectives									2

3	Methods										3

3.1	Survey										3

3.2	Particle Size Analysis – Laboratory methods					6

3.2.1 Particle size analysis (PSA) samples					6

3.2.2 Quality assurance (internal)						6

3.3	Macrobenthic Analysis – Laboratory methods				6

3.3.1 Macrobenthos samples							6

3.3.2 Quality assurance (internal)						7

3.4	Quality control (external)							8

3.5	Biotope assignment and GIS							8

4	Results										9

4.1	Sediment composition							9

4.2	Macrobenthos									12

4.2.1 Biotope composition							13

4.2.2 Taxonomic notes and notable species					14

4.2.3 Discrepancies with WoRMS						16

4.3	External Quality Control							19

4.3.1 Particle size analysis							19

4.3.2 Macrobenthic analysis							19

5	Discussion										20

6	References										21

Appendix 1: Internal macrobenthic sample quality assurance log				26

Appendix 2: Particle Size data for survey							29

Appendix 3: Macrobiota data for survey							30

Appendix 4: Particle size analysis external AQC Report 					31

Appendix 5: Macrobiota analysis external AQC Report 					48

Appendix 7: Details of changes made to macrobenthic dataset following external AQC	66