Schedule 17 to 714085455

KEY PERFORMANCE INDICATORS (KPIs)

SUPPORT OF GAS CYLINDER CHARGING TROLLEYS AND ASSOCIATED EQUIPMENT

Introduction

- The Contractor’s performance shall be monitored against the Key Performance Indicators (KPIs) contained in this Schedule 17. The Contractor’s achieved level of performance against the KPI shall determine the level of payment to be made for the Programme Management at Line Item 1 of the Schedule of Requirement.

KPI Reporting & Performance Review

- In accordance with the Statement of Requirement at Schedule 10 to the Contract and the KPI in this Schedule, the Contractor is required to submit Quarterly Progress Review Reports, which shall report on the level of performance against the KPI, which are measured against the adherence to the lead times at Appendix 6 to Schedule 10.

- As part of the KPI report, the Contractor shall provide proof of collection information for the demands that have been dispatched to allow for the KPI to be tracked. The information supplied by the Contractor shall be used to support the Authority’s decision as to the performance level that the Contractor has achieved for the Contract quarter.

- Once agreed, the Authority shall issue a price acceptance letter to the Contractor finalising the value the Contractor can claim for the Contract quarter. The Incentivisation or Remedy shall be applicable to the total payments in arrears due for Line Item 1 in the respective calendar quarter. The Contractor shall then submit a claim for payment in accordance with Clause G to the Contract Terms & Conditions.

- Any claim for relief against KPI performance, and any associated available information, must be submitted to the Authority within the quarter for which it relates. The Contractor shall not be permitted to retrospectively submit information for KPI alleviations after the Contract quarter. The Authority shall then consider the alleviation request and either,

  - authorise alleviation against KPI performance or

  - include the incident in the KPI calculation or

  - where there is insufficient information to reach a conclusion, discount the incident from KPI calculations until there is sufficient information to sentence the incident.

Assessment of KPIs

- Based on the Contractor’s performance against the KPI, the Contractor can achieve either a GREEN, AMBER or RED in descending order, as defined in the Performance Table for the KPI.

- If the Contractor fails to provide a complete KPI report within the timescale required, the KPI shall be scored AMBER for that Reporting Period. If the Contractor fails to provide a complete KPI report for two (2) or more consecutive quarters, the KPI shall be scored RED for the second quarter and any subsequent quarters until a complete report is received.

- If the KPI is scored AMBER or RED, the Contractor shall provide in the KPI Report a summary of the reasons for this score and the actions being taken to resolve this.

- If a KPI is scored RED in any three (3) Reporting Periods within six (6) rolling Reporting Periods, the Contractor shall issue to the Authority a Recovery Plan. Until the Contractor has implemented to the Authority’s satisfaction, all aspects of the Recovery Plan, the KPI shall be scored RED.

- Both parties reserve the right to review and propose adjustments to the Incentive/Remedies within the Performance Table to ensure that the KPI generates the desired outcome.

Spare Lead Time Adherence

- In the event that the Contractor achieves a GREEN Performance Indicator for the KPI in a Contract quarter, then the Authority shall classify the Contractor as performing against the KPI and authorise payment in accordance with the sliding sale for the KPI. If the Contractor achieves a score of 100% for the KPI, then a 2% incentive award will be paid in addition to 100% of the quarterly payment due under Line Item 1 of the Schedule of Requirement. In addition to this, the Contractor shall receive a GREEN indicator against the KPI for the Contract quarter.

- In the event that the Contractor achieves either a RED or AMBER Performance Indicator for the KPI in a Contract quarter, then the Authority shall classify the Contractor as ‘underperforming’ against the KPI for that Contract quarter and shall deduct a level of the Programme Management Fee as identified in the Performance Table for the KPI. In addition to this, the Contractor shall receive an AMBER/RED indicator for the Contract quarter.

- As stated in Clause 12 above, in the event that the Contractor achieves an AMBER or RED status for the KPI, then the payment for that quarter shall be deducted as per the Performance Table for the KPI. In the event that the score is AMBER, and the preceding quarters score is GREEN, the Authority will only temporarily withhold payment giving the Contractor an opportunity to claim back the retainment in the following quarter following achievement of an acceptable performance; a GREEN indicator for that quarter. If the Contractor however achieves a status of RED, the retainment % will be permanently withheld.

| Key Performance Indicator (KPI) | KPI 1a – Adherence to Spares Lead Times iaw Appendix 6 to Schedule 10 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| KPI Performance Weighting % (Incentive) | GREEN - 100% of Programme Management (Line Item 1) paid + a 2% incentive payment. 90 – 99% - 100% of Programme Management (Line Item 1) paid | Phase(s) of applicability: |  | Commencement from Contract Award for the Programme Management SOR Line Item 1 |  |
| Specific Measure | The percentage of spares that are dispatched within the lead times within Appendix 6 to Schedule 10. | KPI Performance Weighting % (Deduction) |  | Deduction of Programme Management Quarterly Price: AMBER: 94% - 90% adherence to spares lead times RED: <89% adherence to spares lead times |  |
| Information Period | Quarterly from Contract Award |  |  |  |  |
| Data Source(s) | Starting Point: Date order received on Exostar Closing Point: Date order is booked to be collected |  |  | Measurement Point | 5 working days following end of each Contract Quarter |
| KPI Description | The Contractor’s performance shall be measured against schedule adherence in accordance with the lead times listed at Appendix 6 to Schedule 10. An agreed delivery for spares is a delivery where the product lead times (PLTs) are adhered to and a conforming item is received by the Authority. If an item is dispatched by the Contractor within the PLTs and a conforming item is received the item would be considered as a Pass against the KPI. If an item is dispatched after the PLTs, the item would be considered as a Fail against the KPI. If a non-conforming item is received this will be automatically considered as a Fail against the KPI. Where a spares delivery date is forecast for delivery in a Contract Month and is not delivered on time and/or consequently the delivery falls into the next Contract Month, the assessment of the Schedule Adherence shall be in the next Contract Month when the Spare is delivered. The level of lead time adherence shall be measured using the following formula: Number of agreed delivery promises achieved within the Contract Quarter Divided by the Number of agreed deliveries within the delivery profile in the Contract Quarter Multiplied by 100= X% |  |  |  |  |
| Example | Example: Number of agreed delivery promises achieved within the Contract Quarter: 20 Divided by the Number of agreed deliveries within the delivery profile in the Contract Quarter: 20 Multiplied by 100 = 100% Performance Indicator: GREEN Number of agreed delivery promises achieved within the Contract Quarter: 26 Divided by the Number of agreed deliveries within the delivery profile in the Contract Quarter: 35 Multiplied by 100 = 74% Performance Indicator: RED |  |  |  |  |
| Retention Attribution | In accordance with the Performance Table below. |  |  |  |  |
| Performance Table |  |  |  |  |  |
| Band | Lead Time Adherence Achieved in Contract Quarter - % |  | % of payment due |  |  |
| Green | 100 |  | 100 plus 2% incentive payment |  |  |
| Green | 95 to 99 |  | 100 plus 1% incentive payment |  |  |
| Green | 90 to 94 |  | 100 |  |  |
| Amber | 89 |  | 97.5 |  |  |
| Amber | 87 |  | 95 |  |  |
| Amber | 86 |  | 92.5 |  |  |
| Amber | 85 |  | 90 |  |  |
| Red | 80 to 84 |  | 85 |  |  |
| Red | Under 80 |  | 75 |  |  |