Matthewsgreen Primary (NEW) School and Community Facility

Anticipated Key dates:

PIN out as a Call for Competition – 23rd March 2018

Deadline for EOI’s – 29th April 2018 23:59

Scheduled date for start of award procedures = PQQ out/ITT – 8th May 2018

PQQ return – 8th June 2018

PQQ assessment/tender list – 2 weeks

ITT out for pricing – 25th June 2018

Mid –tender information session – w/c 16th July (to be confirmed)

Tender return – 16th August (7½ weeks)

Tender interviews – 29th August

Tender award subject to Alcatel – 7th Sep, Alcatel period expires – 17th Sep

Contract Award – 18th Sep

Possession of site by the appointed Contractor: 1st October 2018

Facility Completed and ready for occupation: 1st July 2020

NOTE: This is the anticipated schedule that WBC wishes to follow; however, WBC reserves the right to alter these dates, subject to the constraints of the PCR2015, at its absolute discretion.