Integrated Community Services

Engagement document

January 2020

Version 4

Table of Contents

Section one – Background

  - Introduction

  - The Borough of Merton

1.2.1 Our population

1.2.2 Joint Strategic Needs Assessment: The Merton Story 2018

1.2.3 Strategic direction

Section two – Vision and outcomes

  - Vision

  - Outcomes

  - Service design

    - Design principles

    - Primary care networks in Merton

    - Scope including financial envelope

    - Interdependencies

Section three – Implementation approach

3.1 Procurement approach

3.2 Financial envelope

3.3 Transformation

3.4 Indicative Timeline

Appendices

    - Phasing and scope proposal

    - Capability framework

Section one – Background

- Introduction

Community health services provide support across a range of needs and age groups but are most often used by children, older people, those living with frailty or chronic conditions and people who are near the end of their life. Community health services cover an extensive and diverse range of activities and are delivered in a wide range of settings – including in people’s own homes as well as in community clinics, community centres and schools.

Our ambition is to deliver better outcomes by integrating health, social care and community services, by moving to a model that is personalised; starts with the needs of the individual and ensures care and support is delivered, as much as is possible, in the community.

We wish to commission differently to secure community services which are person centred, support prevention and are fully integrated across physical health, mental health and social care. We envisage that at the core of this will be a partnership between providers that combines health, social care and voluntary sector providers who, through collaboration, address long standing inequalities and tackle the wider determinants of health and wellbeing.

This presents an opportunity to engage the wider community; creating the conditions for voluntary sector and other partners to play key roles in health and social care delivery fully utilising Merton’s community assets.

This document is intended to be a platform to engage potential providers, (primarily health, social care and voluntary sector providers but not limited to) on a new vision and set of outcomes for community services and stimulate an innovative and collaborative culture.

This document does not prescribe a service model for delivery, it is intended that commissioners together with providers and the wider community in Merton will develop the model collaboratively. We believe the best model will result from drawing on the evidence of what works, the energy and ideas of staff providing care and the lived experience of people and communities needing care.

We believe this represents a unique opportunity to bring about significant benefits for our population through delivery of a truly seamless service offer from the resident’s perspective, including rapid access to the right services and a strong ethos of prevention, well-being and self-care.

For the purposes of this document:

- ‘community based care’ refers to all care delivered in the community including primary, physical and mental healthcare as well as social care

- ‘Resident’ refers to all adults, children and young people either residing in the London Borough of Merton, registered with a GP practice in Merton or attend a school in Merton.

- ‘Commissioners’ refers to the London Borough of Merton and Merton Clinical Commissioning Group

- Based on the experiences of service users, and research evidence, the term ‘integrated’ care is defined as:

- Be organised around the needs of individuals (person centred)

- Focus always on the goal of benefiting service users

- Be evaluated by its outcomes, especially those which service users themselves report

- Include community and voluntary sector contributions

- Respond to carers as well as the people they are caring for

  - The Borough of Merton

1.2.1 Our population

Merton has a diverse and growing population. In 2018, Merton has an estimated resident population of 209,400, which is projected to increase by about 3.9% to 217,500 by 2025. The GP registered population is 223, 580 people. The age profile is predicted to shift over this time, with notable growth in the proportions of older people (65 years and older) and a decline in the 0-4-year-old population. Additionally:

- The number of births in Merton in 2017 was 3,172. There is a general downward trend. By 2025 it is projected that there will be an estimated 2856 births.

- By 2025 there will be a 17% increase those aged 11-15 years. East Merton currently has a higher proportion of younger people compared to west Merton.

- There are 141,000 people of working age in Merton, increasing by 3.1% by 2025

- The over 65 population in Merton is projected to grow by 10.3% by 2025.  The Over 75 population will double

- 37% of Merton’s population are from a Black, Asian, or Minority Ethnic (BAME) group; remaining unchanged by 2025.  English, Polish and Tamil are the most commonly spoken languages in Merton. Children and young people from BAME backgrounds make up 67.9% of those attending a Merton school

These trends have important, well-reported, impacts on health and care demand as well as public space and housing. Working-age disability, with more disabled people surviving longer and the costs of their support increasing, means social care for people of working age now costs local authorities as much as that of older people.

    - Joint Strategic Needs Assessment: The Merton Story 2018

The Joint Strategic Needs Assessment (JSNA) is a statutory assessment of population health and wellbeing needs for the Health and Wellbeing Board. It focuses on a description of the risk and resilience factors that influence health and wellbeing in a defined locality, and the distribution of diseases, looking at both the current pattern and the trend. Its purpose is to provide common evidence for relevant partners and decision makers to help inform policy, strategy, commissioning and service delivery.

Merton’s JSNA consists of several user-friendly products, including Ward Health Profiles for each of Merton’s electoral wards, and a range of more in depth Topic Health Profiles and Health Needs Assessments on priority topic areas. The Merton Story is part of the JSNA, forming a snapshot of what Merton is like as a place to live, the key risk factors for health and wellbeing through the life course, and important health outcomes and health inequalities that exist between different population groups, as identified through the ongoing JSNA process. All JSNA products can be viewed at the following address: https://www.merton.gov.uk/healthy-living/publichealth/jsna

Some key facts on children and young people:

- ‘School readiness’ is a key measure of a child’s development.  In 2016/17, 73.94% of children living in Merton achieved this standard, like London, but we want to do better

- Parental mental health problems, parental misuse of alcohol and drugs and domestic violence are the most significant risk factors that impact on a child’s health and wellbeing.  Merton has a higher rate of these issues than London and England

- There has been a greater increase in children with an Education Health and Care Plan (EHCP) or Statement of special education needs (SEN) than London and England, driven by increases in diagnosis of autism, but also through an increase in social, emotional and mental health needs.

- Childhood immunisations are below the national target of 95%.

- 4,500 primary school children are estimated to be overweight or obese. One in 5 children entering reception are overweight or obese and this increases to 1 in 3 children leaving primary school in Year 6 who are overweight or obese.

- There is a higher rate of A&E attendances for children than the England average

- Around 8% of people in Merton reported low levels of happiness, broadly in line with London and England.

Some key facts on mental health and wellbeing:

- A greater number of people in Merton reported high levels of anxiety compared to London and England.

- There are an estimated 24,000 adults in Merton with common mental health disorders such as depression and anxiety, around 16% of the adult population, which is lower than London but higher than England

- Only 7% of these adults are known about by Merton GPs.  This suggests that many adults in Merton experiencing common mental health conditions remain undetected, and potentially unsupported

- Common mental health problems are proven to make managing diabetes, and other long-term conditions, much more challenging, with poorer overall health outcomes as a result.

Some key facts on integrated health and social care:

- The population is ageing and increasing numbers are living into older age with multiple long-term conditions such as heart disease, diabetes, and dementia

- Merton currently supports around 4,000 adults aged 18 and over with social care needs.  Merton performs well for providing social care support to people in the community, higher than comparable local authorities and England

- Merton has comparably low rates of delayed transfers of care from hospital to home but the proportion of older people who were still at home 91 days after discharge from hospital following reablement is lower than London and England

- 10.8% of people in Merton were diagnosed with a long-term illness, disability or medical condition

- Merton has around 17,000 carers.  We know that caring can have a negative impact on the carer’s physical and mental health, and that caring can adversely affect education and employment.

- Feeling isolated and lonely has a profound negative effect on physical and mental health and wellbeing. This is particularly important given we have an estimated 5,900 people aged over 75 living alone

    - Strategic direction

Strengthening community services with enhanced prevention and bringing care closer to home has been a long-standing policy ambition across health and social care. Closer working between local government and the NHS has always made sense; health and wellbeing are closely intertwined, and local government has significant influence on many of the wider determinants of health and wellbeing, such as housing, transport, education, leisure and the built environment.

The Care Act 2014 created a new legal framework for adult social care services. A duty was placed on local authorities to collaborate and integrate with other public services, such as the NHS and housing. The long-term funding of children’s and adult social care is not yet decided. It is expected, however, that any funding arrangement will have further progress on integration as a condition.

The Children and Families Act 2014 aims to ensure children, young people and parents understand a joined-up system, designed around their needs. The reforms aim to join up help across education, health and care, from birth to age 25.  Help will be offered at the earliest possible point, with children and young people with SEND and their parents fully involved in decisions about their support and what they want to achieve.  This will help lead to better outcomes and more efficient ways of working.

The NHS Long Term Plan reinforced the need for NHS services to change to meet the future needs of the population, arguing for a greater emphasis on prevention, integration and putting patients and communities in control of their health. It particularly calls for the traditional divide between primary care and community services to be dissolved enabling placed based personalised care to become the norm. Tackling inequalities is one of the overarching purposes of integration laid out in the plan.

Personal budgets shift the control of resources for health and care services to people or their carers and families, allowing them to choose from a wider range of care and support options tailored to their individual needs and preferences. There is evidence that this can improve quality of life and psychological wellbeing, and that they can be cost effective, particularly for those with complex needs and for individuals with mental health problems. Social care personal budgets have been linked to improvements in quality of life for both budget holders and their carers. Expanding the offer of personal health budgets is a key priority within the NHS Long Term Plan with challenging targets to be set to ensure delivery at scale is achieved by 2024.

Multiple commissioners of community services give rise to duplication and overlap and can be a barrier for teams delivering care to achieve holistic personalised care. To combat unnecessary complexity and fragmentation commissioners of health and social care in Merton have come together to jointly commission and strategically plan. The forthcoming ‘Merton Health and Care Plan’ outlines the shared agenda and identifies transforming and the integration of community health and social care services as a key priority.

Commissioners together with key providers and partners within health and social care in Merton have been working together as part of the ‘Merton Health and Care Together’ Programme under the auspices of the Health and Wellbeing Board to tackle challenges and strategically plan transformation collaboratively. The development of integrated community services is a key priority identified by the Merton Health and Care Programme.

It has been agreed that the iThrive conceptual model will be adopted and implemented in Merton. The model completely fits with our ambitions outlined on page one of this paper as it encourages an integrated, person-centred and needs led approach to the emotional wellbeing and mental health of children, young people and their families. This was launched in September 2019 in Merton with a developing plan to fully implement over the next 18 months. There are four key principles that underpin the THRIVE Framework:

- Shared decision making at the heart of choice

- Acknowledgement of limitations to treatment

- Distinction between treatment and support

- Greater emphasis on how to help children and young people and communities build on their strengths

Section two – Outcomes and scope

  - Vision for change

Our Vision:

Working together, to provide truly joined up, high quality, sustainable, modern and accessible health and care services, for all people and partners of Merton, enabling them to start well, live well and age well.

What this means for community services in Merton is that, by working together, we can enable the people of Merton to:

- Have the same opportunities and life chances – regardless of where they are born or live

- Receive safe, effective and compassionate care,

- Live healthy, independent, fulfilling lives

- Be part of dynamic, thriving and supportive communities

- Have equitable access to health and social care services

For this vision to be a reality, person and community centred ways of working need to be widely understood and valued as core to the whole health and care system, woven into the infrastructure and culture of delivery.

We believe this represents a unique opportunity to bring about significant benefits for our population through delivery of truly seamless service offer from the resident’s perspective, including rapid access to the right services and a strong ethos of prevention, well-being and self-care.

Commissioners wish to work with organisations who share its vision and who demonstrate innovation and willingness to work in partnership to deliver a community services model that can turn this vision into a reality.

  - Outcomes

Our joint ambition is that through strengthening the role of community health and care services we improve health outcomes for people in Merton. It is expected that the provider will deliver the following outcomes, split into six domains, for Merton residents.

We recognise that it is better for residents themselves to be active partners in their care therefore we need a health and social care community service offer that listens to what is important to residents and works with them to build the best care that supports their needs. This rationale underpins the first domain which is focused on outcomes identified by Merton residents reflecting what is important to them. There are three domains of outcomes across the broad life course of Start Well, Live Well and Age Well, followed by a domain identifying outcomes that benefit the whole system of health and social care in Merton and last, but not least, a domain on prevention outcomes.

Table 1. Outcomes framework for Community Services Contract 2021

| Domain 1. Person focused outcomes Ensuring that community health and social care services work in a way which offers a good experience to the residents of Merton. - I can access services when I need them - I receive care and treatment in a seamless and timely way - I have an active role, when I want to, in making decisions about my care, treatment and support - My family or carer was also involved in these decisions as much as I wanted them to be |  |  |
| --- | --- | --- |
| Domain 2. Start Well The focus of this domain is to ensure that all children and young people have the best start in life, achieving good health, well-being and resilience and a positive childhood experience in Merton. - Embedded ‘Think Family’ culture and ethos. ‘Think Family’ practice makes sure that we recognise that an issue which affects one member of a family will have a knock-on effect on the family. As a result, the support provided by children’s, adults’ and family services takes into consideration the impact on other family members, on adults’ ability to parent well. - All children in Merton achieve a good level of development by school Reception. - Halt and begin to reduce the increase in children that are overweight or obese when leaving primary school in Year 6 and reduce the gap between east and west by levelling up. - Those children and young people with mental health difficulties are able to receive the right support in the right place and in a timely way. - All children and their families are supported to flourish and achieve their potential with appropriate support and care. | Domain 3. Live Well The focus of this domain is to ensure that all adults in Merton can contribute to and benefit from sustained health and wellbeing. 3.1 People will lead healthy lifestyles and have improved quality of life - All Merton residents can look after and improve their own health and wellbeing and live in good health for longer - Health and social care services contribute towards reducing the gap in healthy life expectancy between those suffering from mental health and those that do not | Domain 4. Age Well The focus of this domain is to ensure that all residents in Merton continue to live full and meaningful lives into older age. - People who use health and social care services have positive experiences of services and have their dignity respected - People, including those with disabilities or long term conditions, or who are frail, can live, independently as possible and at home in the community, as long as that is possible. - Reduction in the impact of social isolation and loneliness through greater community involvement in health and wellbeing issues |
| Domain 5. System focused outcomes Ensuring that community health and social care services in Merton are sustainable for the long term. - There will be reduced variation in outcomes and access - We will have a financially sustainable health and social care system; resources are used efficiently and effectively - We have a sustainable flexible workforce with shared principles and values comfortable working across boundaries with professionals and non-professional experts in both statutory and voluntary sectors. - People who work in health and social care services feel engaged with the work they do, work in healthy workplaces and are supported to continuously improve the information, support, care and treatment they provide - That there is sufficient, good quality, diverse and stable provision of health and care ensuring that residents and their carers have choice over how their needs are met and that they can achieve the things that are important to them. |  |  |
| Domain 6. Prevention outcomes - Pro-active prevention focused service provision with healthy lifestyles embedded in health and care pathways 6.2 Community services harnesses the power of the wider community to support people in their own homes, combat social isolation, and create healthier communities |  |  |

2.3 Service design principles

We want provision that is based on an integrated approach, with community services playing a leading role in enabling effective working between different professionals and organisations, ensuring that people in Merton experience care that is seamless and well-co-ordinated. The Provider(s) will need to deliver its services taking account of the following design principles that are embedded in a strong sense of ‘Place’ is ‘personalised’ and are delivered through an improvement culture.

Place based:

- Seek to make the most of Merton’s community assets, including the voluntary sector, the Wilson Health and Wellbeing Campus in East Merton which will offer a range of healthy lifestyle and preventative services along with clinical services

- Social prescribing supports people to take control and explore behaviour change as well as building social networks and enhancing community cohesion. The new model must ensure these principles are adopted at scale and encouraged to flourish and expand reaching more Merton residents, including opportunities for developing a social prescribing model for children and young people.

- It is important that teams can tailor their services to the needs of their communities and innovation is promoted and enabled at the front line. Have a strong sense of local ‘place’ which the community recognises and values. Services should be provided at the most local level possible.

- To be evidenced based; with resources and delivery models informed by localised data and need. Demonstrable link between how knowledge is being used to re-design and shape services.

Person centred care:

- Recognise health and wellbeing is about whole people (social, physical and mental) who are part of whole communities and families. Provision must unite physical, mental and social care together.

- Services must prioritise continuity of care for the most vulnerable, moving away from ‘episodic’ or ‘transactional’ community services. This could include the allocation of a key worker, person centred planning and common care planning. This should reduce gaps, unnecessary complexity and confusion in access to the community services.

- Wrap multidisciplinary teams around groups of practices aligned to the Primary Care Networks to offer holistic proactive approach to residents with complex needs (including the identification of high risk individuals with the ability to review and support the entirety of a resident’s health and social care needs.)

- Improved responses to crises and exacerbation of conditions in the community, including rapidly available alternatives to hospital admission, supported hospital discharge, rehabilitation intermediate care and reablement.

Improved culture:

- Designed to facilitate resident empowerment and support greater self-care

- Innovative in its design and delivery with a drive to continuously learn and adapt to improve

- Community services should be developed through co-production meaning that services should work with community groups and residents as equal partners to plan and run services.

- Strengthen positive workforce values; ensuring space to enable skill mix to diversify and adequate support is provided to unpaid carers and volunteers.

- Resources, focus and attention is distributed evenly and proportionately, avoiding dominance of one area or service user group to the detriment of others.

- Has prevention at its core.

  - Primary Care Networks (PCN) in Merton

It is envisaged that successful delivery of the vision will not possible without developing integration with GP Practices within the PCN configuration. The role of the Practice is therefore fundamental and this is reflected in the design principles.

Merton commissions services from 22 GP practices, meeting the needs of 223,580 registered patients (residing in Merton and neighbouring boroughs). Practices are arranged into six PCNs (North Merton, East Merton, South West, Morden, North West Merton and West Merton). The practice locations and sizes are shown below in table 2.

A Primary Care Network consists of a group of practices working together with a range of local providers, including social care and the voluntary sector to offer more personalised, coordinated health and social care to a local population.

It is anticipated that a Primary Care Network will typically service a population of between 30,000 and 50,000 people.  The configuration of PCN in Merton is outlined in the table below:

Table 2. Primary Care Networks configuration in Merton together with registered patient number

| Primary Care Network | Practice | List size | Collective list size |
| --- | --- | --- | --- |
| North Merton | Mitcham Family Practice | 3,625 | 37,411 |
|  | Riverhouse Medical Practice | 5,822 |  |
|  | Merton Medical Practice | 8,163 |  |
|  | Mitcham Medical Centre | 8,988 |  |
|  | Colliers Wood Surgery | 10,813 |  |
| East Merton | Rowans Surgery | 7,330 | 45,728 |
|  | Figges Marsh Surgery | 8,083 |  |
|  | Tamworth House Medical Centre | 9,241 |  |
|  | Wide Way Medical Centre | 9,486 |  |
|  | Cricket Green Medical Practice | 11,588 |  |
| South West | Grand Drive Surgery | 8,870 | 39,441 |
|  | Nelson Medical Practice | 29,571 |  |
| Morden | Stonecot Surgery | 8,586 | 37,735 |
|  | Central Medical Centre | 8,909 |  |
|  | Morden Hall Medical Centre | 14,725 |  |
|  | Ravensbury Park Medical Centre | 5,515 |  |
| North West Merton | Vineyard Hill Surgery | 4,333 | 31,748 |
|  | Alexandra Road Surgery | 5,646 |  |
|  | Wimbledon Medical Practice | 9,358 |  |
|  | Wimbledon Village Practice | 12,411 |  |
| West Merton | Francis Grove Surgery | 13,720 | 31,517 |
|  | Lambton Road Medical Practice | 17,797 |  |

2.5 Scope

Rather than introducing a ‘new service’ most of the change required to deliver the outcomes and vision will come from realigning existing community services into an integrated model. Additional areas of transformation are to be included within the scope which are to be achieved through growing capacity and skills within the existing teams rather than adding discrete services.

The financial contract envelope represents £50,919,925 of funding per annum (after phasing has completed, year 4 onwards).

Freedom will be passed to the provider to innovate and flex resources accordingly within the financial envelope to meet the outcomes identified. The following table outlines the proposed scope aligned to outcomes and transformation priorities. Although organised into the three broad life stages, sufficient focus on key transition points is to be maintained to ensure seamless experience for residents.

Table 3. Proposed scope of community services contract Merton

|  | Outcomes | Thematic service areas | Transformation priorities | Financial envelope |
| --- | --- | --- | --- | --- |
| Start Well | - Embedded ‘Think Family’ culture and ethos. Think Family practice makes sure that the support provided by children’s, adults’ and family services is co-ordinated and focused on issues affecting the whole family. - School readiness-all children in Merton achieve a good level of development by school Reception. - Halt and begin to reduce the increase in children that are overweight or obese when leaving primary school in Year 6 and reduce the gap between east and west by levelling up. - Those children and young people with mental health difficulties are able to receive the right support in the right place and in a timely way. - All children and their families are supported to flourish and achieve their potential with appropriate support and care they need. | - CAMHS - 0-25 services e.g. universal healthy child services - Community therapies and nursing services - Community Paediatric services | - Improved Personalisation - Embedded ‘Think Family’ approach - iThrive approach to CAMHS delivery - Improve the experience of children, young people and their parents pre/during and post ASD diagnosis - Seamless transition into adulthood. - Continue and develop the Whole School approach to emotional wellbeing and mental health. Children with SEND are supported to reach their potential through timely identification of additional needs and delivery of Education Health and Care Plans (EHCP). Health, Education and Care Services will work together to transform elements of the SEND model in line with our Written Statement of Action (WSOA). | £10,024,619 |
| Live Well | - People will lead healthy lifestyles and improved quality of life - All Merton residents can look after and improve their own health and wellbeing and live in good health for longer - Health and social care services contribute towards reducing the gap in healthy life expectancy between those suffering from mental health and those that do not | - Community mental health services - Drug and substance misuse - Intermediate care; including rapid response to support people to stay at home or - Community-based outpatient and diagnostic services | - Telecare and Telehealth - Use of the Wilson Health and Wellbeing Campus and the East Merton Model of Care delivery. - Rapid response in the community to support timely secondary care discharge and avoid unnecessary admission. - Increase in ‘step up’ proactive provision | £23,865,668 |
| Age Well | - People who use health and social care services have positive experiences of services and have their dignity respected - People, including those with disabilities or long term conditions, or who are frail, can live, independently as possible and at home in the community, as far as that is possible. - Reduction in the impact of social isolation and loneliness through greater community involvement in health and wellbeing issues | - Community nursing and therapies - Specialist community nursing teams -Dementia services - End of life care including specialist support and hospice care - Carers services -Falls prevention - Integrated stroke pathway incorporating early supported discharge and six-month post stroke reviews | - Integrated End of life care for all - Enhanced health in care homes agenda - Proactive risk management through multi-disciplinary team meetings. - Personalisation and increased offer of Personal Health Budgets -Reducing unnecessary admissions to secondary care or premature entry to institutional care - Timely diagnosis of dementia | £10,723,077 |
| Prevention | - Pro-active prevention focused service provision - Community services harnesses the power of the wider community to support people in their own homes, combat social isolation, and create healthier communities | - Prevention and management of disease e.g. diabetes service - Community navigation - Community equipment - community transport - Social prescribing - Expert patient programme - Health improvement e.g. stop smoking and NHS health checks. - Primary care local incentive schemes** | - Self-care and self-management - Training and support to the wider community on health and wellbeing - Healthy lifestyles including nutrition support - Equality of access for all residents | £6,306,561 |
|  |  |  |  | £50,919,925 |

** The CCG commissioned ‘Local Incentive Schemes’ are included in the scope pending the outcome of the scheduled review and further engagement with primary care to determine whether these services would benefit from an integrated contractual approach.  The introduction of new national contracts planned to go directly to Primary Care Networks could mean that it is not viable to be included within the scope of CCG commissioned activity. It could be that these services are heavily aligned and still deliver a seamless service from a resident’s perspective although may take a different contractual route. The areas known to be affected by this include; Enhanced Health in Care Homes (End of Life and complex patients LIS), and Access Hubs.

  - Interdependencies

Merton Clinical Commissioning Group (MCCG) together with the London Borough of Merton and other health and social care partners are working together through the Merton Health and Care Together Programme. Transformation is underpinned by early integration with physical and mental health, social care, primary and secondary care, public health, community services and community based voluntary sector services as a ‘whole system’ to support people to start well, live well and age well.

It is important that new community health and social care services connect well with services outside the scope of the community service contract. It may be that some services will be heavily aligned, perhaps adopting the same place based footprint so that from a resident’s perspective they offer a seamless joined up service offer whilst retaining separate contractual approach. Key areas that are not currently included within the scope but will be aligned and remain key delivery partners include:

- Directly provided services by London Borough of Merton e.g. Reablement Service, social workers and case managers

- Acute hospitals

- Children’s Centres

- Urgent Treatment Centres and outpatient

- Mental Health Placements

- Brokerage services including placements in nursing and residential care and Continuing Health Care

Section three – next steps for implementation

3.1. Procurement approach

Commissioners plan to undertake a formal NHS procurement process with the intention of entering a long-term contract of up to seven years with services in place from April 2021.

Whilst it for participating providers to decide how to arrange themselves in organisational, legal and operational forms to deliver the future model, it is the intention of commissioners to replace the current array of individual contracts for services in scope with a single contractual arrangement. Commissioners do not believe the vision can be delivered by a single agency without a significant commitment to partnership and integrated working. Merton Primary Care Network and the London Borough of Merton are vital delivery partners for any solution. Commissioners require that the facilities of the Wilson are included in any delivery plans.

Following wider engagement and discussion with the community in Merton, service users and patients, their carers, families and networks and providers of health and social care, we hope to collaboratively finalise the specification for community services. High level specifications will outline the parameters for delivery with commissioners committed to working in partnership with providers to determine the model of delivery and subsequent transformation and implementation programmes.

Diagram 1. Commissioners approach to developing the model for community services

The commissioners will use a capability assessment to test the ability of interested providers to work collaboratively together and with commissioners both strategically and operationally to develop the future operating model to meet the outcomes and deliver the vision. The framework setting out the scope and focus of the capability assessment is attached as appendix 2 of this document.

Commissioners wish to work with potential providers who share our vision for community services and consider that they have the right capacities and capabilities to respond to the challenge ahead.  The capability assessment will seek evidence and demonstration of the providers’ appetite and potential to work collaboratively with commissioners and the residents of Merton to deliver community services. The focus of the assessment will be broad, but fundamentally seek to drive and test a new collaborative way of working between providers so that their organisation, governance, decision making and commitment is in place to enable the required service transformation at a pace.

Where a competitive process becomes necessary to select which group of providers is most capable, the capability assessment will be used as the basis of a competitive evaluation tool. Each group of interested providers will be invited to respond as bidders, through a transparent, structured and equitable process, providing all necessary evidences to enable commissioners to conclude a ranking of bidders in terms of confidence to be had in their capability.

It is key that the provider have ownership of, and commitment to the vision. A cultural shift to new ways of working as well as practical support in making teams work effectively is needed as part of organisational development strategies and transformation programmes.

Merton CCG will be amalgamating with neighbouring CCGs to form South West London CCG from April 2020. Therefore, any award of contract for community services for April 2021 will be issued from South West London CCG. This new larger geography will enable NHS commissioning to fulfil a more strategic role, reduce duplication and pool resources and expertise to improve delivery. The CCG will remain committed to working locally with partners at a borough level and strengthening integration with NHS organisations, the local authority and voluntary sector partners in Merton. Further detail on how the new commissioning arrangements will operate will be shared as soon as they are approved.

3.2 Financial envelope:

The financial contract envelope represents £50,919,925 of annual funding building up iteratively over the first four years of the contract life. The following table highlights the indicative funding. The figures are indicative as commissioners reserve the right to alter the values.

Table 4. Proposed figures for the community services integration contract phasing

| Year | Annual contract value (indicative) |
| --- | --- |
| Year 1 2021-22 | £30,540,600 |
| Year 2 2022-23 | £44,235,458 (+£13,694,853) |
| Year 3 2023-24 | £48,499,925 (+£4,264,467) |
| Year 4 2024-25 | £50,919,925 (+£2,420,000) |

It is expected that the new service model will deliver financial efficiencies to the health and social care system. Any savings that identified through integration will be reinvested into new service development and ensuring long term sustainability of community services. It is expected that these savings should be modelled to cover the life course of the contract.

It is anticipated that the 2021 values will include a reduction of £400k, due to a pressure on local authority children’s services budgets, however, the new contract approach should provide flexibility to maximise resources and efficiencies across the whole contract so that the impact of this reduction is mitigated,

Adults and Children’s social care budgets are subject to the upcoming spending review; financial envelopes are indicative until then. The figures in this document are 2019/20 figures, they are for guidance only, the final values for 2021 are yet to be finalised.

3.3. Transformation

Delivering the vision will mean considerable work to build new relationships and a significant level of commitment to new ways of working. Therefore, it is recognised that the agreed new delivery model is unlikely to be delivered in its full form on day one (April 2021) of the new service. A phased approach is promoted to ensure the delivery remains achievable within the timeframes without compromising quality or business continuity. Appendix 1 of this document outlines proposals for phasing across the first four years of the contract.

Key to delivering the phased implementation will be the design and execution of a transformation programme. Commissioners would expect the following elements to be included in a transformation plan to develop integrated community health and social care in Merton:

- Commitment to culture change; Identifying and demonstrating the core values and behaviours that underpin approaches to integration. Ensuring change to services on the ground as priority over structure and organisational change.

- Commitment to developing strong leadership; Professional leaders will play a crucial role in the success of developing and implementing integrated care. The effective leadership required can be characterised by sustained long-term commitment, enthusiasm to deliver to standard and involvement to work together to deliver integrated care locally.

- Commitment to workforce development; NHS England’s Integrated Care Pioneers have demonstrated the importance of development to achieving the goals of integrated care. Transformation programmes should include tasks that build on these lessons. This presents an opportunity to address some of the known national and local challenges to recruiting and retaining health and social care staff in Merton.

- Harnessing digital technology; using technology as an enabler to deliver integrated care.

3.4 Timeline

Indicative timeline is as follows:

| Action | Date |
| --- | --- |
| Provider engagement phase | January 2020 – March 2020 |
| Process to select preferred provider | April 2020 – June 2020 |
| Co-produce specification with preferred provider | July 2020 – December 2020 |
| Mobilisation period | January 2021 – March 2021 |
| New contract goes live | April 2021 |

Appendix 1. Scope of community services to be included in the new community contract April 2021Year 1 April 2021-22

|  | Service title (as currently commissioned 2019-20) | Current provider | Annual value (2018-19) |
| --- | --- | --- | --- |
| Start Well | CAMHS Tier 1-3 | SWLSG | 1,960,217 |
|  | Child sexual abuse support | NSPCC | 15,339 |
|  | Counselling for young people with anxiety or depression | Off the record | 120,000 |
|  | Self-harm interventions | TBC | 40,000 |
|  | Community eating disorder service | SWLSG | 216,000 |
|  | Community paediatric service | Epsom St Helier Hospital NHS Trust | 570,000 |
|  | Perinatal mental health in the community | SWLSG | 52,000 |
|  | Specialist nursing special schools | CLCH | 364,732 |
|  | Educational health care plan team embedded in to the Specialist Educational Needs and Disabilities Integrated Service | CLCH | 256,645 |
|  | Children’s therapies; dietetics service | CLCH | 121,512 |
|  | Children’s therapies; OT | CLCH | 413,796 |
|  | Children’s therapies; Physio | CLCH | 288,134 |
|  | Children’s therapies; SLT | CLCH | 802,716 |
|  | 0-19 universal Healthy Child Services; including health visiting, school nursing, safeguarding | CLCH | 3,813,528 |
|  | Educational OT | CLCH | 195,000 |
|  | Enuresis Service | TBC | TBC |
| Live Well | Integrated HARI service | CLCH | 1,261,850 |
|  | Intermediate Care inpatient services including integrated home first service | CLCH | 3,527,328 |
|  | Integrated domiciliary packages of care | TBC | 2,000,000 |
|  | MERIT (Rapid response) | CLCH | 310,090 |
|  | In reach services | CLCH | 692,313 |
| Age Well | Dementia specialist nurses | CLCH | 152,000 |
|  | Voluntary Sector Aging Well programme: Carers support services, Dementia Hub and Ageing Well programme initiatives | Carers support Merton, Alzheimer’s Society | 217,000 |
|  | Hospice Care | St Raphael’s Hospice Trinity Hospice London | 665,399 |
|  | Bereavement services | Wimbledon Guild | 25,000 |
|  | Community nursing; Care navigators and case managers | CLCH | 507,635 |
|  | Community Nursing | CLCH | 4,619,253 |
|  | Domiciliary therapies | CLCH | 280,004 |
|  | Falls | CLCH | 223,509 |
|  | Community continence service | CLCH | 556,233 |
|  | End of life service | CLCH | 301,597 |
|  | Cardiology service | CLCH | 285,973 |
|  | Tissue viability service | CLCH | 259,742 |
|  | Night nursing and end of life care | Marie Curie** | 131,000 |
|  | Neuro therapies | CLCH | 120,544 |
|  | Podiatric surgery | CLCH | 83,889 |
|  | Podiatry service | CLCH | 487,985 |
|  | Dietetics / nutrition | CLCH | 324,808 |
|  | Speech and language therapy | CLCH | 134,808 |
|  | Specialist nursing HIV service | CLCH | 75,399 |
|  | Respiratory specialist nursing service | CLCH | 596,299 |
|  | Memory assessment service | SWLSG | 123,000 |
| Prevention | Social prescribing | MVSC | 139,000 |
|  | Community musculoskeletal service | Connect | 971,801 |
|  | Diabetes service | CLCH | 537,404 |
|  | Community Equipment* | Croydon Council | 948,706 |
|  | Community based outpatient and diagnostic services | TBC | TBC |
|  | Integrated Locality team coordination | Merton Health Limited | 180,824 |
|  | Improving quality, support and education | Merton Health Limited | 80,678 |
|  | One You Merton – healthy lifestyles | Hounslow and Richmond Community Healthcare NHS Trust | 199,410 |
|  | NHS Health checks | Merton Federation | 150,500 |
|  | Befriending | Age UK Merton | 40,000 |
|  | Personal Health budgets | TBC | 100,000 |
| TOTAL |  |  | 30,540,600 |

*Community Equipment likely to be a subcontracted arrangement, so inclusion represents potential provider commissioning budget.

** currently providers are sub contracted by CLCH

Year 2 April 2022-23

|  | Service title (as currently commissioned 2019-20) | Current provider | Annual value (2018-19) £ |
| --- | --- | --- | --- |
| Start Well | Services for vulnerable children and young people (Advocacy, Young Carers, Short Breaks etc.) | Catch 22, Carers Support Merton, Merton Mencap, Jigsaw4U | 375,000 |
| Live Well | Recovery support teams | SWLSG | 8,790,156 |
|  | Early intervention and psychosis service | SWLSG |  |
|  | Home Treatment team | SWLSG |  |
|  | Complex needs service (personality disorder) | SWLSG |  |
|  | Merton Assessment team | SWLSG |  |
|  | Autism and ADHD service | SWLSG |  |
|  | Specialist Community Adult (sun project, perinatal community teams and traumatic stress) | SWSLG |  |
|  | LBM contribution to the integrated mental health service | n/a | 1,566,000 |
|  | Community mental health older adults service | SWLSG | 1,453,464 |
| Age Well | Adult Social Care Occupational therapy team | London Borough of Merton | 552,000 |
| Prevention | ***Primary Care Local Incentive Scheme: Anticoagulation | Merton GP Practices | 221,187 |
|  | Primary Care Local incentive scheme: near patient testing | Merton GP Practices | 11,079 |
|  | Primary care local incentive scheme: Menorrhagia Management | Merton GP Practices | 94,948 |
|  | Primary care local incentive scheme: Phlebotomy | Merton GP Practices | 68,697 |
|  | Primary care local incentive scheme: Insulin initiation | Merton GP Practices | TBC |
|  | Primary care local incentive scheme: End of life and complex patients | Merton GP Practices | 527,327 |
|  | Primary care local incentive scheme: minor surgery | Merton GP Practices | TBC |
|  | Primary care local incentive scheme: Ambulatory blood pressure monitoring | Merton GP Practices | 35,000 |
| TOTAL |  |  | 13,694,858 |

*** The CCG commissioned ‘Local Incentive Schemes’ are included in the scope pending the outcome of the scheduled review and further engagement with primary care to determine whether these services would benefit from an integrated contractual approach.  The introduction of new national contracts planned to go directly to Primary Care Networks could mean that it is not viable to be included within the scope of CCG commissioned activity. It could be that these services are heavily aligned and still deliver a seamless service from a resident’s perspective although may take a different contractual route.

Year 3 April 2023-24

|  | Service title (as currently commissioned 2019-20) | Current provider | Annual value (2018-19) £ |
| --- | --- | --- | --- |
| Live Well | Sexual Health Services**** |  |  |
|  | Inpatient detox services | London Borough of Merton | 100,780 |
|  | Needle exchange and supervised consumption | Community Pharmacies | 23,000 |
|  | Alcohol and drug service | Westminster Drug Project | 1,270,687 |
|  | Primary Mental health services (Merton Uplift) | SWLSG | 2,870,000 |
| TOTAL |  |  | 4,264,467 |

**** Pending the result of the review of service provision, one option could be inclusion in this contract. Reserve the right to make an informed decision considering recommendations from the review.

Year 4 April 2024-25

|  | Service title (as currently commissioned 2019-20) | Current provider | Annual value (2018-19) £ |
| --- | --- | --- | --- |
| Start Well | Risk and resilience services | Catch 22 | 420,000 |
| Prevention | Community Transport Services | London Borough of Merton | 2,000,000 |
| TOTAL |  |  | 2,420,000 |

Glossary:

SWLSG = South West London St Georges Mental Health NHS Trust

NSPCC =

CLCH = Central London Community Healthcare NHS Trust

MVSC = Merton Voluntary Sector Council

LBM = London Borough of Merton

n/a = not applicable

Appendix 2 Capability assessment

| Capability area: | Developing (confidently in place May 2020) | Maturing (during 2021/22) | Thriving (post 2022) |
| --- | --- | --- | --- |
| - Governance and leadership Potential questions could be: - Can you describe the leadership and governance model you have adopted to drive sustainable system improvement in health and social care in Merton? - What will be done to ensure the bidder and any sub-contractors support workforce development? - How does establishing a provider collaborative and delivering against the outcomes identified align with partner’s organisations strategies? - How would you develop a culture of learning and sharing with system leaders solving problems together and drawing in the experiences of others? | - A clear description of the nature of the provider collaboration form and an organogram of the partnership, providing clarity around accountability and decision making routes -Formal organisational commitment from each partner organisation in the provider collaborative e.g. board discussion and agreement, signed governance documentation - Evidence of effective engagement with Primary Care Networks and the London borough of Merton as key stakeholders of a community services provider collaboration. -Governance structures agreed with all partners are simple, transparent, and provide clarity about how accountability will work and what the responsibilities of the constituent organisations will be. - Shared vision and objectives building a shared common purpose and a collectively owned narrative for the provider collaborative - Dedicated clinical and managerial capacity and infrastructure to develop plans - Details of the provider collaborations approach towards risk/gain share agreements - A description of the key leadership roles, both clinical and managerial, their responsibilities, reporting relationships and accountabilities. -Agreed dispute resolution policy between all partners in the collaboration. | -Governance and clear accountability structures are agreed and are maturing supporting leaders to make decisions -Robust governance and clear accountability structures are in place. -Embedded infrastructure with LBM and Primary Care Networks with clear communication channels, levels of influence and scrutiny -Corporate identity established -Corporate governance arrangements to deliver the contract and to meet all statutory and regulatory obligations are in place. - Confirmation of the sufficiency and capability of the senior leadership and change management team to enable transition and subsequent transformation. Details of additional resources and enhancement of skills capability. - Alignment of component organisations strategies and corporate objectives with integrated community services outcomes and vision. | -Leading as one single voice -Robust policies and procedures embedded into practice - Ability to carry out decisions made, with the capability to execute on priorities |
| - Transformation change Potential questions could be: - Outline your plan for working collaboratively with commissioners and Merton residents to design and agree service models to deliver the outcomes. What systems and processes will you put in place? - What barriers and challenges do you think you will face and how as a provider collaborative will you mitigate against them? - How do you see the relationship with commissioners working effectively? - How will you provide opportunities for all, including the most vulnerable, to make a valuable contribution and promote social integration? - What skills and capabilities do you have to enable transformation that leads to improvement? | - Robust plan of how the bidder will work together with commissioners, service users including children and young people and the public to co-produce the service model and final specification for delivery against the vision and outcomes. To include: - Details of the management methodology to transformation e.g. Programme Management approach - Organigram of the suggested structure, outlining how different working groups could be established, how decisions will be made and; - Evidence of commitment of resources - Description of approach taken to harness the expertise and experience of front line staff in the transformation process - Commitment and approach to co-production to ensure that service users including children and young people and residents are involved in the process of development and embedded into continuous improvement. - undertaken an infrastructure and asset mapping assessment to understand the opportunities there are at a local level to build capacity and enable system transformation -Clear plans to organize delivery around local neighbourhoods and the needs of the population | -Terms of reference for key boards and sub-committees/working groups identified -Comprehensive transition/mobilisation plan outlining the implementation schedule to sustainably and safely to put the new contract arrangements into place. - Mobilisation plan includes consideration of: - New collective governance arrangements (clinical and organisational) - Digital and IT requirements - Premises, estates, infrastructure - Workforce - Equipment (clinical and non-clinical) - Clinical services - Monitoring and reporting of contractual arrangements -Communications and engagement strategy and plan to support effective transition to new working - Dedicated capacity and supporting infrastructure in place to enable change -Details of how the bidder draws on the skills and leadership of frontline staff, service users including children and young people and Merton residents. - Consider equality and diversity in the provision and operation of services, including a workforce that is representative of Merton, where relevant and proportionate. | - coproduction is embedded as a core function that drives decision making. - Culture of continuous improvement is embedded into delivery of front line community services. |
| - Commitment to culture change/continuous improvement Potential questions could be: - Explain to us your commitment and passion to Merton as a place and how the development of integrated community services can positively contribute -How would you approach community engagement and empowerment – working with and for the people and communities we serve; explicitly using and developing assets and strengths; -How will you ensure equal if not more focus is given to enable positive agency and collective change amongst the workforce rather than on structural change? - How would you ensure prevention is prioritised? | - The bidder has an agreed set of values demonstrating a culture that values the experiences of others, committed to equalities and recognises the enormous benefits diversity within the workforce adds to quality of care -The bidder has in place necessary skills and behaviour required of healthcare professionals to use and promote personalised care approaches in daily practice -System partners will start to establish the infrastructure and develop their analytical capability required to understand the population health needs from partners differing perspectives - Promote initiatives which retain, protect, enhance and/or promote the character of Merton’s natural environment for the benefit of local people and wildlife. - Prevention is a core activity - Demonstrable evidence that the provider is committed to the level of ambition – striving to national policy standards and innovation laid out in the vision and outcome frameworks | A culture is developed that supports diversity, learning, capacity building, innovation and improvement in which the Merton system solves problems collaboratively Person and community centred ways of working are widely understood and valued as core to the whole health and care system, woven into the infrastructure and culture of delivery. Priority workforce issues, for the initial service transition are identified and confirmation that the service will be appropriately staffed and managed with a sufficiently skilled workforce in place. There is an agreed approach to ensure all staff groups, across all services are competent and supported to professionally develop. | The partners have agreed how to ensure an integrated approach toward workforce planning, recruitment and development. Personalised care approaches are a part of everyday practice. |
| - Managing resources Potential questions could be: - How will you ensure efficient use of resources by minimising waste, reduce energy and fuel consumption and achieve improved environmental performance? - What are the main environmental impacts associated with delivering community services in Merton and how will the impacts be reduced, managed and verified? -what support will be provided to the local supply chain through this contract, including activities, information, resources and organisations? For example, promoting supply chain opportunities to local voluntary and community sector organisations and social enterprises? -Public services face ongoing challenge to improve quality of provision and improve value for money. What will be your approach to identifying financial efficiencies and delivering sustainable services? | - Emerging understanding of workforce, estates and digital infrastructure across community services -Bidder will establish the infrastructure to develop their analytical capability required to understand the population health needs. -Sustainable- confirmation that the Preferred Provider offers value for money and can deliver safely within the financial envelope. -A strong culture and robust plans for continuous improvement with financial efficiencies reinvested into areas of need and growth. - Commercial and contractual model to deliver integrated community services has been identified, is viable and sustainable to deliver community services from April 2021. | Clarity that resources are targeted towards the areas of evidenced need. Pooled budgets and alliancing arrangements are used across health and social care, where appropriate, to deliver more integrated service - Reduced energy and fuel consumption in the provision of service -Plans and commitment to consolidating and ensuring transparency of data across community services and a road map towards developing capitated budgets is being developed. - Mechanisms identified to measure performance of integrated care -Information Governance policies and processes to support the new partnership solution are in place. -Information Sharing Agreements to enable new shared working and governance. -Strong financial management with a collective commitment from commissioners and providers to system planning and shared financial risk management | -Efficient use of resources by minimizing waste; reduced amount of waste sent to landfill, improved recycling rates and reduced carbon footprint of community services |

The definition of eligible populations will be worked through as part of service re-design given the difference approaches between being ordinarily resident and GP registration. Also some Start Well services have eligibility based on attendance at a school in-borough.

https://www.nationalvoices.org.uk/publications/our-publications/principles-integrated-care