Specification for Addressing future overheating risks within existing buildings

Tender Reference Number: RM/1221

Specification of Requirements

Invitation to Tender for Addressing future overheating risks within existing buildings

Tender Reference Number: RM/1221

Deadline for Tender Responses: 1pm on 4th January 2022

Contents

1.	Background

2.	Aims and Objectives

3.	Detailed Methodology

4.	Outputs Required

5.	Ownership and Publication

6.	Quality Assurance

7.	Timetable

8.	Challenges

9.	Skills and experience

11.	Consortium Bids

12.	Budget

13.	Evaluation of Tenders

- Background

The Climate Change Committee

The Climate Change Committee (CCC) was set up as part of the Climate Change Act. The CCC is an independent body that advises both on reducing emissions in the UK and adapting to the climate changes in the UK.

The Committee has recently provided its advice to the UK Government on the risks and opportunities facing the UK from current and future climate change as required under the Climate Change Act as part of the third Climate Change Risk Assessment – this was summarised in its Independent Assessment of UK Climate Risk which was published in summer 2021.

The CCC’s full range of past reports are available here: http://www.theccc.org.uk/reports/.

Overheating as a key risk to the UK

The CCC’s Independent Assessment of UK Climate Risk identifies a large number of risks to the UK for which there is a good case for doing more to address these risks over the coming five years as part of the UK Government’s next National Adaptation Programme. One of the most significant risks identified was ‘Risks to human health, wellbeing and

productivity from increased exposure to heat in homes and other buildings’. This risk was highlighted as one of the eight highest priority risks with opportunities to make progress in address them over the coming two years.

Without additional adaptation efforts, heat related deaths and impacts on productivity are expected to grow significantly over the coming decades. Whilst the majority of these impacts are going to be experienced in the South-East of the UK – impacts will be felt right across the country.

Addressing these risks will require ensuring new built houses and offices are fit for purpose, well-designed and effective heat-wave emergency response plans are in place and that the state of existing homes are upgraded where needed to reduce risks of overheating.

In England it is currently estimated that around 20% of houses are at risk of overheating. There are multiple adaptation options identified in the evidence base to help address overheating in existing UK homes, but there is little in terms of coordinated efforts to help address overheating risks in existing buildings. Options include the installation of passive cooling measures (e.g external shading including natural shading, additional internal blinds and curtains, cool and green roofs, installing reflective surfaces and improved ventilation) and mechanical cooling (e.g. air conditioning).

- Aims and objectives

This aim of this project is to map out a quantitative picture of how exposed different parts of the UK’s existing housing stock is to overheating risks under expected future climate conditions, and how much deployment of credible options to retrofit existing homes can limit these overheating risks.

The key tasks in this project will be:

- Assessing the extent of overheating risk in the future across the UK’s current housing stock

  - This task should design a decomposition of the existing UK housing stock into sub-category pools (depending on both housing attributes and geographies) useful for assessing the levels of overheating that might be experienced today and in the future.

  - This categorisation of the housing stock should be used to quantitatively estimate the overall extent of heat-related impacts in the future under possible future climate change scenarios without additional retrofit measures.

- Assessing the options to reduce current and future overheating risks in existing properties

  - This task should assess the evidence base regarding the options for retrofitting existing home to reduce overheating risks regarding their effectiveness, the overall costs and benefits of retrofitting, and how widely could they be applied across the existing housing stock.

- Assessing to what extent deployment of measures to address overheating in existing buildings could help limit future heat-related impacts

  - This task should estimate to what extent plausible large-scale deployment of packages of retrofitting options (from task 2) could reduce the levels of possible future heat-related impacts in existing homes identified in task 1.

This project will feed into the CCC’s wider adaptation work programme and in particular ongoing work around what might be a credible scale of adaptation action to address the risks presented by climate change in the UK. This work package will integrate into efforts to improve the quantitative nature of the CCC’s progress monitoring framework on adaptation.

3. Detailed methodology

This project is aimed specifically at the aspects of dealing with overheating risks that are concerned with existing homes. New built homes and heatwave emergency response measures are not within scope of this project.

Task 1: Assessing the extent of overheating risk in the future across the UK’s current housing stock

We are looking to understand (quantitatively) the extent to which different parts of the current UK housing stock (across of range of geographical locations) would reach levels of internal temperature hazardous to human health under possible future heatwave conditions without further retrofitting measures.

- We expect this task to be satisfied using some elements of modelling and drawing on available existing datasets regarding the state of current UK housing stock.

- A clear and evidence-based categorisation of the current UK housing stock should be undertaken to break-down the UK’s current housing stock into a small number of groups that would be expected to have similar thermal properties and future overheating risks for the purpose of analytical assessment.

- Future overheating risks should be assessed using a range of future climate scenarios consistent with 2C and 4C global warming levels (as in UKCP18 and CCRA3).

- Ideally modelling should include: the use of CIBSE TM52 criteria to define risk, clear assumptions regarding occupant behaviour and occupancy vulnerability across different sections of the current housing stock.

- Spatial disaggregation of risks is very important to this project. A sufficiently granular regional aggregation should be chosen to allow important differences in overheating risk (e.g. between Northern England and South-East England) to emerge. At very minimum disaggregation to the level of the UK’s devolved administrations would be required, with fine spatial disaggregation highly desirable.

- For this task no additional adaptation actions should be considered to further modify the existing housing stock to help reduce overheating risks.

Task 2: Assessing the options to reduce current and future overheating risks in existing properties

This task requires a dedicated assessment of what options are available to retrofit existing homes to reduce overheating risks below the levels identified in Task 1. This task should provide a clear (and quantitative) assessment of the evidence regarding each of the questions below:

- What are the options available to retrofit existing homes to address current and future overheating risks?

- What categories of the housing stock could each option be appropriately installed in (using a consistent categorisation of the housing stock as used in Task 1)?

- How much would each option cost to install in differing categories of housing?

- How effective might each option/housing category combination be in reducing overheating risks?

- What other co-benefits (outside of reduced temperature) or trade-offs would installation of these options create?

It is expected that this task is satisfied by literature review and/or modelling. This task should seek to utilise and build on recent work conducted for MHCLG and BEIS where appropriate and should aim to not duplicate (but hopefully utilise) the assessment in previous work commissioned by the CCC as part of its 2020 Housing Report. A key point of difference in this work should be about building a more nationwide view of the efficacy, cost and benefits of different retrofit options together with incorporating a more robust definitions of overheating (e.g. CIBSE criteria). Assessment of the costs and benefits should be conducted using the spatial disaggregation used in Task 1 – which should be sufficient granular to pick up important sensitivities in the cost-benefit assessment across the UK (e.g. differences between Northern England and South-East England).

Retrofit options considered in this task should include multiple passive cooling measures (e.g. installation of external shading of both natural and engineered varieties) and mechanical cooling options (e.g. air conditioning). Where possible the assessment of the costs in this task should try to include the impact of possible cost reduction in the overheating retrofit supply chains if uptake of measures increases and possible cost sharing with heating retrofit conducted at the same time as energy efficiency retrofits.

The main output from this task should be tables/spreadsheets containing for each retrofit option and housing stock category that it could be applied to a quantitative assessment for each category in the bullet point list above. Uncertainties should be appropriately assessed where possible.

Task 3: Assessing to what extent deployment of measures to address overheating in existing buildings could reduce future heat-related impacts

This task should bring together the outputs of tasks 1 and 2 to provide an overall quantified estimate of how much a credible scale deployment of measures to address overheating could reduce future heat-related risks in existing homes.

- Coherent ‘packages’ of options from task 2 should be formed for different levels of adaptation action beyond current levels to address overheating risks within existing properties.

- For each of these packages credible deployment levels should be estimated based on the fraction of properties within each housing categorisation (from task 1) that are expected to have benefit-cost-ratios greater than one for the retrofit options entailed, together with additional constraints regarding deployment rates.

- The overall effect of these packages for additional retrofit ambition on reducing the risks identified in task 1 should be calculated (using the same metrics as in task 1).

- This data should be summarised using the same spatial disaggregation used in task 1 and 2.

Overall, this task should provide a quantified picture of how much heat-related impacts could be avoided through credible scales of retrofit ambition where appropriate across the country.

# Outputs Required

The outputs of the work should include:

- Spreadsheets, containing quantitative data on the output from Task 1, 2 and 3 – including the projections for potential heat-related impacts under possible climate futures and the possible deployment of retrofitting measures to reduce these risks. This should be in a clear and easily accessible format.

- A detailed assumptions log

- A report, setting out the scope of work, assumptions, methodology and findings.

Where excel workbooks are used these should be shared, fully unlocked and linked to rest of the excel workbook deliverable above, allowing future capability to update assumptions.

We envisage that bidders may need to make use of pre-existing knowledge to enable delivery and welcome this. However, this should not limit the transparency of approaches used in this project and all outputs should be provided in a publishable format. In the event of any limitations on sharing (e.g. in wider sharing beyond the CCC), these should be specified as part of the tender.

In addition to the above, we also expect interim deliverables to be required, including slide packs for the purposes of milestone and/or steering group meetings.

# Ownership and Publication

The key deliverables will be handed over to the CCC, who may choose to publish these as supporting evidence on their website. Spreadsheets should be open access and unrestricted, to enable full QA of results and assumptions.

# Quality Assurance

This project must comply with the ‘CCC – Quality Assurance of Evidence and Analysis’ guidance and bidders must set out their approach to quality assurance in their response to this ITT.

All research tasks and modelling must be quality assured and documented. Contractors should:

- Include a quality assurance (QA) plan that they will apply to all of the research tasks and modelling,

- Specify who will take lead responsibility for ensuring quality assurance and ensure that this responsibility rests with an individual not directly involved in the research, analysis or model development,

- Provide QA log to demonstrate the QA undertaken, including who undertook the QA and the scope, type and level of QA that has been undertaken (e.g. a log entry only stating ‘the data was checked’ will not be sufficient),

- Allow for a meeting with CCC staff to run through QA performed.

Sign-off for the quality assurance must be done by someone of sufficient seniority within the contractor organisation to be able take responsibility for the work done.  Acceptance of the work by the CCC will take this into consideration. The CCC reserves the right to refuse to sign off outputs which do not meet the required standard specified in this invitation to tender.

The successful bidder will be responsible for any work supplied by sub-contractors and should therefore provide assurance that all work in the contract is undertaken in accordance with the quality assurance expectation agreed at the beginning of the project.

# Timetable

The proposed timetable for the project is set out in the following table. Ability to start work early in January is highly desirable for this project.

| Date | Action |
| --- | --- |
| w/c 17th January | Kick-off meeting |
| w/c 28th March | First interim presentation/report on progress across all three tasks |
| w/c 16th May | Second interim presentation/report on progress across all three tasks |
| w/c 27th June | Latest date for delivery of final report, analytical outputs and assumptions log |

In addition to the formal reporting points, the CCC would expect to have regular scheduled discussions (weekly meetings or calls) to ensure the work is progressing as expected. It is expected a more detailed timeline would be proposed in bids documents and agreed with the CCC at the kick-off meeting.

# Challenges

The specific challenges that the CCC envisage with this project include:

- Establishing an analytical methodology and approach which enables high quality insights to be delivered in short timeframes

- Ensure the scenarios and wider project findings are robust given the wider state of scientific literature

- Ensuring that the project findings can be integrated effectively and coherently with the previous work in this area

Bids should set out how these risks will be managed alongside any other risks and challenges to successfully undertaking this work.

The successful contractor will be expected to identify one named point of contract through whom all enquiries can be filtered. A CCC project manager will be assigned to the project and will be the central point of contact.

# Skills and experience

CCC would like you to demonstrate that you have the experience and capabilities to undertake the project. Your tender response should include a summary of each proposed team members experience and capabilities.

Contractors should propose named members of the project team, and include the tasks and responsibilities of each team member. This should be clearly linked to the work programme, indicating the grade/ seniority of staff and number of days allocated to specific tasks.

Contractors should identify the individual(s) who will be responsible for managing the project.

# Consortium Bids

In the case of a consortium tender, only one submission covering all of the partners is required but consortia are advised to make clear the proposed role that each partner will play in performing the contract as per the requirements of the technical specification.  We expect the bidder to indicate who in the consortium will be the lead contact for this project, and the organisation and governance associated with the consortia.

Contractors must provide details as to how they will manage any sub-contractors and what percentage of the tendered activity (in terms of monetary value) will be sub-contracted.

If a consortium is not proposing to form a corporate entity, full details of alternative proposed arrangements should be provided. However, please note CCC reserves the right to require a successful consortium to form a single legal entity in accordance with Regulation 28 of the Public Contracts Regulations 2006.

CCC recognises that arrangements in relation to consortia may (within limits) be subject to future change. Potential Providers should therefore respond in the light of the arrangements as currently envisaged. Potential Providers are reminded that any future proposed change in relation to consortia must be notified to CCC so that it can make a further assessment by applying the selection criteria to the new information provided.

# Budget

The budget for this project is £160,000 excluding VAT.

Contractors should provide a full and detailed breakdown of costs (including options where appropriate). This should include staff (and day rate) allocated to specific tasks.

Cost will be a criterion against which bids which will be assessed.

Payments will be linked to delivery of key milestones. The indicative milestones and phasing of payments can be adjusted and agreed with the contractor and Project Manager. Please advise in your tender response how this breakdown reflects your usual payment processes:

In submitting full tenders, contractors confirm in writing that the price offered will be held for a minimum of 60 calendar days from the date of submission. Any payment conditions applicable to the prime contractor must also be replicated with sub-contractors.

The Committee on Climate Change aims to pay all correctly submitted invoices as soon as possible with a target of 10 days from the date of receipt and within 30 days at the latest in line with standard terms and conditions of contract.

# Evaluation of Tenders

Contractors are invited to submit full tenders of no more than 30 pages, excluding declarations and CV’s. Tenders will be evaluated by at least three CCC staff.

CCC will select the bidder that scores highest against the criteria and weighting listed below, see the ITT for further information.

EVALUATION CRITERIA AND SCORING METHODOLOGY

| #### Criterion | #### Description | #### Weighting |
| --- | --- | --- |
| 1 | RELEVANT EXPERIENCE / DEMONSTRATION OF CAPABILITY | 15% |
| 2 | MANAGING YOUR RELATIONSHIP WITH THE CCC | 5% |
| 3 | QUALITY ASSURING THE SERVICES YOU PROVIDE | 10% |
| 4 | MANAGEMENT STRUCTURE | 5% |
| 5 | PROJECT TEAM – SKILLS AND KNOWLEDGE | 20% |
| 6 | METHOD, ABILITY AND TECHNICAL CAPACITY | 30% |
| 7 | UNDERSTANDING OF REQUIREMENTS | 5% |
| 8 | RISK AND CHALLENGES | 10% |
|  |  | 100% |

Scoring Method

Tenders will be scored against each of the criteria above, according to the extent to which they meet the requirements of the tender. The meaning of each score is outlined in the table below.

The total score will be calculated by applying the weighting set against each criterion, outlined above; the maximum number of marks possible will be 100.  Should any contractor score 1 in any of the criteria, they will be excluded from the tender competition.

| Score | Description |
| --- | --- |
| 1 | Not Satisfactory: Proposal contains significant shortcomings and does not meet the required standard |
| 2 | Partially Satisfactory: Proposal partially meets the required standard, with one or more moderate weaknesses or gaps |
| 3 | Satisfactory: Proposal mostly meets the required standard, with one or more minor weaknesses or gaps. |
| 4 | Good: Proposal meets the required standard, with moderate levels of assurance |
| 5 | Excellent: Proposal fully meets the required standard with high levels of assurance |

Scoring for Pricing Evaluation

Price will be marked using proportionate pricing.  Please see the example below.

Marking proportionate to the lowest price.

Price will be scored as set out below.

There will be a maximum of e.g. 20 marks

The lowest priced bid will receive the full 20 marks, all other bids will then be marked as set out below.

Proportionate Pricing scoring example

If 20% = 20 marks

| Supplier | Price | Marks |
| --- | --- | --- |
| 1 (lowest bid) | £140,000 | 20 |
| 2 | £150,000 | 140/150 * 20 = 18.7 |
| 3 | £160,000 | 140/160 * 20 = 17.5 |

Structure of Tenders

Contractors are strongly advised to structure their tender submissions to cover each of the criteria above and supply a price schedule specifying the daily rates (ex-VAT) you will charge for each level of your staff.

Evaluation for Interviews, if held

CCC reserves the right to award the contract based on applicants’ written evaluation only if one candidate emerges from the evaluation stage as significantly stronger than the others.

Should interviews go ahead, CCC will shortlist the top three suppliers with the highest marks from the written proposals. Interviews are provisionally expected to be held on or around 10th January. If this date changes, CCC will notify applicants.

The areas to be covered in the interview, and markings allocated to each topic area will be sent to the shortlisted supplier prior to interview.

Further details of interviews will be sent to successful applicants on selection.

Feedback

Feedback will be given in the unsuccessful letters or emails.

https://www.theccc.org.uk/wp-content/uploads/2013/02/Quality-Assurance-interim-guidance.pdf