## Clarificaiton Log
Clarification Log
ENV0001002 Cotswolds Groundwater Model Update and Refinement
Log No. | Question | Date received | Response | Date Response Posted
1 | We have received two queries about the possibility of extending the current submission deadline of 20th September 2019. | 2019-09-05 | Our project team have reviewed the project plan and have agreed to extend the two week proposal to three weeks, resulting in a new submission deadline of the 27th September 2019 at 17:00. This also changes subsequent deadlines for the following: - Evaluation of Request for Quote submissions due 04th October 2019 - Period for Clarifications due 11th October 2019 - Award of contract due 18th October 2019 - Contract start date – 21st October 2019 | 2019-09-09
2 | From RFQ: "Invoices shall be issued after specific project tasks and milestones have been completed". Please could you clarify the tasks/milestones that will need completion prior to each invoice. | 2019-09-17 | Invoices should be issued after the completion of each of the six tasks outlined in Section 5.6 of the Request for Quotation document. | 18-Sep-2019 [via Email]
3 | From RFQ: "Some recent project work in the Frome catchment has identified better characterisation of how groundwater abstractions are constructed, which will be provided, which will aid improvement as to how some abstractions are characterised in the model." Please could you clarify which source(s) this relates to. | 2019-09-17 | This relates to a single source, Chalford Springs. Chalford Springs are large public water supply (c.13Mld/) spring catchment system which has a series of springs discharging out of the limestones/ clay interface on the Cotswold escarpment up gradient. These springs have all been captured in Victorian times by trenches and pipework to a central collection point at the base of the escarpment which is channelled in the Frome valley into what is called the ‘Black Gutter’ which is in essence a tunnel will has been constructed underneath a railway line where all the spring flows have been brought together into this tunnel. The water is then conveyed from the tunnel into large holding chamber (called Fibrocrete chamber) which is then culverted to the water treatment works before supply. | 18-Sep-2019 [via Email]
4 | From RFQ: "Groundwater level data for existing calibration sites and a collection of new boreholes that are currently not captured as calibration targets will be provided ". Please could you clarify approximately how many new boreholes there are with groundwater levels data that will need to be added to the model post-processing spreadsheets? | 2019-09-17 | There are four new boreholes that have been drilled since 2009 which could be used as new calibration site, one of which replaces a current calibration site. There may also be a couple of existing monitoring boreholes that aren’t calibration sites that might be candidates to be included as new sites. | 18-Sep-2019 [via Email]
5 | From RFQ: "Rainfall data in to the recharge model is based on continuous estimation of rainfall (CERF) also referred to as 1-GRID data. Currently EA only has access to CERF data to the end of 2013. Therefore this dataset will be extended with the EA’s Daily Rainfall Tool to produce data in the same gridded format as the 1-GRID data". Please could you clarify whether the EA will be using the Daily Rainfall Tool and providing the consultant with the grids, or if this needs to be done by the consultant. | 2019-09-17 | We can confirm that the EA will be using the Daily Rainfall Tool and providing the consultant with the grids. | 18-Sep-2019 [via Email]
6 | From RFQ: "Other data that will be provided includes the surveying of a number of observation boreholes in the Cotswolds areas, where the datum’s for some sites have changed" Please could you clarify approximately how many OBH datasets are affected by datum errors and whether any of these errors are large enough to affect the assessment of model calibration. | 2019-09-17 | From the surveys undertaken, around 13 are for monitoring boreholes in the Cotswolds groundwater model. The half of these sites the measured datum that is within 0.25 m of the existing recorded datum and unlikely to strongly affect current calibration. The remaining are within 1.0 m of the existing recorded datum while two have differences greater than 1.0 m. These last two sites may have a larger bearing on current model calibration. | 18-Sep-2019 [via Email]
7 | From RFQ: "A selection of reports relevant to the River Frome, River Churn and Ampney Brook that have been produced since the original model was delivered and explore how the groundwater model performs in this catchments can be made available at the start of the project. Pumping test reports and data for testing of current and new abstraction sites since the original model was delivered can also be made available." Please could you clarify approximately how many reports and pumping tests will need to be reviewed. | 2019-09-17 | We anticipate that there will be approximately five reports that can be provided for review. As well as these reports, there are five sites where pumping test data has been collected since the original model was delivered. Two of these sites are for existing public water supplies in the area. The data collected during these tests and pumping test summaries or reports will be provided. | 18-Sep-2019 [via Email]