# Cornwall Development Company

# Invitation to Tender (ITT)

# Innovation Fund for Cornwall & Isles of Scilly Skills Hub – Apprenticeship Campaign 2019

# TEN 442

# December 2018

# Overview

Cornwall Development Company (CDC) operates as Cornwall Council’s economic development arm and is a member of the Corserv group of companies.  CDC has been successful in its bid to the European Growth Programme 2014 – 2020 to establish and operate the Cornwall & Isles of Scilly (CIoS) Skills Hub service.  This project is funded by the European Social Fund (ESF), with match funding from Cornwall Council and Cornwall & Isles of Scilly Local Enterprise Partnership (LEP).

The Skills Hub encourages and supports businesses to grow, innovate and invest in training and skills development through a one-stop service for information and guidance on and access to skills development provision. They do this through a content-rich online portal and social media activity backed by a telephone and face-to-face service delivered by office-based Business Navigators and a team of experienced Business Connectors covering Cornwall & Isles of Scilly.

CIoS Skills Hub, working alongside CIoS Local Enterprise Partnership, has set up the Innovation Fund to deliver a refreshed Apprenticeship Campaign for Cornwall & Isles of Scilly during 2019.  The Campaign will promote and encourage employers, particularly micro and small and medium sizes enterprises (SMEs), to recruit Apprentices (of all ages).  This might be for the first time, or where employers have previously had Apprentices to encourage re-engagement with Apprenticeships; either within new areas of their business or to take on more Apprentices.  Or it might be to utilise Apprenticeship training and funding to upskill existing staff.  The Campaign and its component parts will generate ‘warm’ leads to the CIoS Skills Hub to convert into Apprenticeship starts.  This Fund and Campaign supports the CIoS Employment and Skills Strategy strategic objective SO2: “Drive employer and individual engagement and investment in skills” and will assist that strand to:

- Create an effective apprenticeship service for CIoS employers

- Enable the demand and supply of skills (at all levels) to meets the needs of high employment sectors

- Support small, micro, social and community businesses as well as those who are self-employed to engage in training

The national 2017 UK Employer Skills Survey (ESS), one of the largest business surveys in the world with the data from over 87,000 employers, shows that investment in training and development has flatlined over the past 4 years with 66% establishments training their staff and 48% providing off-the-job training.

Locally, the Chamber of Commerce Business Plan for Cornwall 2017 2018 shows just 20% of businesses see CIoS as a good place to recruit people with the right skills and over half think it is not a good place for developing employee skills.

The employment and skills element of Cornwall’s Devolution Deal focusses on increasing the number of people with higher level skills, combating underemployment and supporting those who are furthest from the labour market to get the skills and experience needed to find work. Improving apprenticeships brokerage activities targeted at SME’s is a key action of the deal.

CIoS has a high proportion of small and micro businesses, and the highest proportion of self-employed business owners of all the LEP areas. These businesses tend to be the ones that most need help yet are often the least able to engage as time away from the business has cost implications.

The wider Innovation Fund and Apprenticeship Campaign will aim to address some of the issues above and help remove barriers to accessing skills and encourage employers, sector groups and training providers to carry out research, collaboration projects and try new approaches to accessing and developing skills within sectors with growth potential.

They will be aligned to the CIoS Employment & Skills Strategy and the refreshed vision for Employment and Skills 2030:

“For Cornwall and the Isles of Scilly to have a healthy, skilled and productive workforce with access to rewarding jobs, clear progression pathways and opportunities for all.”

CIoS LEP Employment and Skills Strategy 2016-2030: https://www.cioslep.com/employment-and-skills/employment-and-skills-strategy-2016-2030

UK Employer Skills Survey (ESS) 2017

https://www.gov.uk/government/publications/employer-skills-survey-2017-uk-report

Cornwall Chamber Business Plan for Cornwall 2017/2018

https://chambermaster.blob.core.windows.net/userfiles/UserFiles/chambers/2836/File/8W14186-Layout-V9_lowres.pdf

Please note that this fund is under ESF priority 2 and is therefore under the skills for growth, employer-led strand.

# Background

Apprenticeships certainly make good business sense.  Skills shortages are still one of the biggest threats to businesses.  Apprenticeships can help businesses across all our sectors in CIoS by offering a route to harness fresh talent or to upskill existing staff.  By training people with the right skills for the job they can do a wider range of tasks and take on new responsibilities which can help reduce skills shortages, minimise staff turnover and increase productivity.  The Chartered Institute of Personnel and Development’s (CIPD) research finds that firms report average increases in productivity of £214 a week from Apprentices, with 75 per cent of bosses saying their Apprenticeship programme also reduces recruitment costs.

According to the Federation of Small Businesses (FSB), perceptions about bureaucracy and the time and investment needed as well as lack of awareness of funding are all things that reportedly put smaller firms off.  However, FSB research also encouragingly stated, one in four small businesses said they’d already had at least one Apprentice, and 24 per cent of those that didn’t have an Apprentice wanted to take one on in the future.  The top reason small businesses want to support apprentices is overwhelmingly that they feel it’s their duty.

CIoS has previously invested in a successful Apprenticeship campaign.  In 2013 the Cornwall Apprenticeship Campaign was launched to raise awareness of Apprenticeships not only with businesses but also young people, parents and schools and is now dormant.  This previous county-wide campaign included:

- A dedicated campaign coordinator.

- A website with information on local vacancies, success stories, news and advice & guidance.

- Events throughout the County, attended by thousands of young people and influencers.

- Social media activity and regular e-marketing.

- Content marketing via news articles and case studies on the website.

Since this previous campaign there has been a steady decline nationally and locally in Apprenticeship starts, particularly for the 16-18 year old age group.  This decline is thought to be due to recent and significant changes to Apprenticeship policy, delivery and funding. Apprenticeship starts for CIoS for the academic year 2016/17 totalled 5,280; a decrease on the previous year of 180.

The Employer Perspectives Survey run by the UK Commission for Employment and Skills found that in 2014 12% of employers in Cornwall and the Isles of Scilly offered formal apprenticeships.  So, with over 23,000 registered enterprises in CIoS there remains plenty of scope to expand Apprenticeships beyond current levels.

# Commission

On behalf of the CIoS Skills Hub and CIoS Local Enterprise Partnership, CDC wishes to procure a year-long Apprenticeship Campaign which delivers localised and compelling messages to CIoS employers to engage with Apprenticeships.  The Campaign should positively address any perceptions which act as barriers to engagement for employers and highlight local (case study) employers who have engaged and the benefits Apprenticeships have given their businesses.  It should also address the recent Government policy changes and importantly, the Campaign will need to embed a clear call to action for employers to contact the CIoS Skills Hub who will provide the ‘effective Apprenticeship service for employers’.

The Campaign must be aligned to the CIoS Employment and Skills Strategy and support achievement of some key Apprenticeship starts within the Strategy, including increasing the awareness and demand for higher/degree level Apprenticeships.

The elements and outcomes the CIoS Skills Hub and CIoS Local Enterprise Partnership would like to see through this Innovation Fund Apprenticeship Campaign includes (but not necessarily limited to, as other ideas are welcomed):

|  | Campaign Elements | Activity | Outcomes |
| --- | --- | --- | --- |
| 1 | Apprenticeship Hub/Website | - Refresh the branding and update the content within the current Cornwall Apprenticeships website, checking relevant links and adding any new ones (access to be provided). - Place greater emphasis on key employer messaging and information within the website. - Retain but update the information and website pages for young people, individuals and parents. - Make clear links with the CIoS Growth Hub website and update the call to action for employers; describing the support available to employers from the Skills Hub. - Refresh/renew website case studies; these may include video/audio. - Continue to allow for the CIoS LEP officer to make any minor amendments to the website. | - Main updates and website refresh to be completed by April 2019, ongoing update work may be required thereafter. - Collection of a variety of local case studies (at least 12) reflecting key and priority sectors within CIoS. Template for this purpose to be developed for training providers/Colleges and employers to use. - Increase website hits from current levels by 300%. |
| 2 | Social Media | - Design and deliver a social media year-long campaign/plan. - The plan should address key employer messages and dispel myths/misconceptions in a positive way but also show that not all Apprenticeship journeys are perfect, so as to bring some realism. Localise the messaging and case studies and use the ‘voice’ of real employers. - Refresh but retain the current Cornwall Apprenticeship Facebook and Twitter pages/accounts. - Possible linkages with a social media partner - Production of apprenticeship social media toolkit for use by partners and stakeholders for use during and after the campaign. - Continue to allow for the CIoS LEP officer to add any content/make changes to the above social media pages. | - 12-month social media plan designed and agreed within 6 weeks of contract agreement with regular reviews built in. - Increase and drive ‘hits’ to the refreshed Cornwall Apprenticeship website. - Overall 7,000 businesses to be reached during the Campaign to include all elements, not just Social Media. |
| 3 | Telemarketing (this element may be delivered by a sub-contracting organisation) | - Telemarketing campaign to CIoS employers – a list of up to 5,000 individual employer contacts will be provided for this purpose. - Telemarketing ‘script’ to be developed with CIoS Skills Hub and agreed ahead of calls commencing. - Employer ‘warm’ leads to be identified and passed to the CIoS Skills Hub within 24 hours of being identified. | - 5,000 businesses telephoned. - Generating 1500 ‘warm’ employer leads. - Telemarketing activity to be complete by end of August 2019. |
| 4 | Events/Webinars | - Deliver a ‘soft’ Campaign launch. - Working with the CIoS Skills Hub and CIoS LEP Apprenticeships and Employment Officer to plan a schedule of events/webinars aimed at employers. - Schedule to include stand-alone Apprenticeship events and linking with relevant partner events. - Involve employers in message/information delivery or even hosting events e.g. employer hosting a breakfast event for other employers in a similar sector or geography. - Promotion and event management. | - 6 or more events across the year. - Attracting/engaging at least 300 individual employers. |
| 5 | Apprenticeship Toolkit | - Taking and working with supplied content, design and create a simple hard copy toolkit for businesses. - Again, taking and working with supplied content, design and create a simple hard copy toolkit for business intermediaries. | - Two useful and practical printed documents/leaflets to hand out to employers and business intermediaries. - Hard copy toolkit to be available no later than spring 2019. - Toolkit design files to be provided electronically and copyright free to allow for any future updates and print runs. |

Note:  The successful delivery organisation will be expected to work and communicate with both the CIoS Skills Hub Manager, the CIoS LEP Apprenticeships and Employment Manager to agree all elements and messaging and ensure the Campaign is aligned to other employer focussed Campaigns.  The social media/Campaign Plan to be shared, at the earliest opportunity, with key stakeholders e.g. training providers and Colleges so that they can adopt and embed the Campaign into their own marketing/social media plans.  The CIoS Skills Hub is currently undertaking its own Apprenticeship research/survey with employers and this work must be used to help inform this new Apprenticeship Campaign. The CIoS LEP Apprenticeships and Employment Officer will set up a new Apprenticeship stakeholder group and the delivery organisation will be asked to present/attend Group meetings, face to face, via video conference or teleconference, to update on the Campaign at key intervals three times during the campaign.

The Skills Hub is part funded by the European Union and as such, the CIoS Apprenticeship Campaign must comply with EU Branding & Publicity Guidelines (Annexe A).

# Budget

The Innovation Fund available for this Apprenticeship Campaign a maximum of £40,000 excluding VAT and the Skills Hub is looking to commission one lead delivery organisation to design and deliver the Campaign for the period until October 2019.

A further tender will be issued later in 2019 to commission an evaluation of the Apprenticeship Campaign.

# Tender Information & Requirements

This section provides instructions and defines the format Tenderers should use in responding to this ITT along with specific information Tenderers should supply and information on how the tenders will be assessed.

## Tender Timetable

This procurement will follow a clear, structured and transparent process at all times and all Tenderers will be treated equally.

The key dates for this procurement timetable are currently anticipated to be as follows:

| Timetable |  |
| --- | --- |
| Event | Date |
| Issue ITT | 13/12/18 |
| Deadline for receipt of clarifications | 09/01/19 |
| Target date for responses to clarifications | 11/01/19 |
| Deadline for return of Tenders (Return Date) | 21/01/19 at 17:00 (5pm) |
| Evaluation of Tenders | 22/01/19 to 08/02/19 |
| Notification of contract award decision | 11/02/19 |
| Target contract Commencement Date | 25/02/19 |

CDC reserves the right to change the above timetable and Tenderers will be notified accordingly where there is a change in the timetable.

## Discrepancies, Omissions, Clarification and Enquiries

Should the Tenderer find discrepancies in, or omissions from, the Tender Documents, the Tenderer shall notify CDC immediately.

Any clarification queries arising from these Tender Documents which may have a bearing on the offer should be raised with the CDC contact (Josh Hoole, josh@ciosskillshub.com) as soon as possible and in accordance with the Tender Timetable above. Responses to all relevant queries will be posted on Contracts Finder.

There will be no negotiation on any of the substantive terms of these Tender Documents. All clarifications need to be submitted by email to the CDC contact.

No representation by way of explanation or otherwise to persons or corporations tendering or desirous of tendering as to the meaning of the tender, Contract or other Tender Documents or as to any other matter or thing to be done under the proposed Contract shall bind CDC unless such representation is in writing and duly signed by a Director/Partner of the provider. All such correspondence shall be returned with the Tender Documents and shall form part of the Contract.

Where the Company considers any question or request for clarification to be significant, the anonymised query and response will be communicated to all Tenderers via Contracts Finder.

## Tender Submission

All tender returns must include a covering letter setting out the following;

- That the provider has the resources available to meet the requirements outlined in the brief - and within the tender timetable.

- That the provider will be able to meet the CDC Corporate Requirements (see below), to include confirmation that Equality and Diversity and Environmental policies are in place and if successful supporting documentation will be provided as evidence together with the appropriate conflicts of interest policy statement.

- The provider shall provide confirmation that insurance policies are current and if they are due to expire during the course of the commission to provide renewal notices prior to their expiry date(s).

- That the provider accepts all the Terms and Conditions of the Contract attached at Annexe B

- The point of contact within your organisation in relation to this tender.

The Tender submission should also include:

- Project Summary stating:

  - How your proposal meets the issues, criteria and elements set out in this tender.

  - How your proposal aligns with the CIoS LEP Employment and Skills Strategy.

- Project Narrative detailing the Project Activity you aim to undertake stating:

  - Your experience related to delivering the Campaign – examples of 2 similar Campaigns you have delivered successfully.

  - Knowledge and understanding of Apprenticeships and how to engage employers, or how you will obtain this.

  - How you intend to deliver the Campaign elements and expected outcomes.

  - If you are using a sub-contractor, which elements will you be using them to deliver.

  - The project timescales and milestones.

  - What makes your proposal innovative in relation to the previous Cornwall Apprenticeship Campaign

  - Detail of the staff involved in the Campaign.  Including maximum 2-page CV’s (not included in word count).

  - How you will engage relevant stakeholders.

- Sustainability

  - How you suggest we build sustainability/legacy into the Campaign

- Project Costs

Total project costs to deliver of each of the Campaign Elements as detailed in the commission above.

## Corporate Requirements

CDC wishes to ensure that its contractors, suppliers and advisers comply with its corporate requirements when facilitating the delivery of its services. It is therefore necessary to ensure that the Tenderer can evidence its ability to meet these requirements when providing the services under this commission.

All tender returns must include evidence of the following. This is a pre-requisite if the tender return is to be considered.

Equality and Diversity

CDC is committed to providing services in a way that promotes equality of opportunity. It is expected that the successful tenderer will be equally committed to equality and diversity in its service provision and will ensure compliance with all anti-discrimination legislation. If successful you will be required to provide a copy of your Equality and Diversity Policies/Practices

Environmental Policy

CDC is committed to sustainable development and the promotion of good environmental management. It is expected that the successful tenderer will be committed to a process of improvement with regard to environmental issues.  If successful you will be required to provide a copy of your Environmental Policy Policies/Practices

Indemnity and Insurance

The consultant/supplier must effect and maintain with reputable insurers such policy or policies of insurance as may be necessary to cover the supplier’s obligations and liabilities under this commission, including but not limited to:

- Public liability insurance with a limit of liability of not less than £2 million;

- Employers liability insurance with a limit if liability of not less than £2 million;

All insurances shall cover for any one occurrence or series of occurrences arising out of any one event during the performance of this contract.

The Tenderer should note that the following Corporate Requirements will also apply;

Freedom of Information Legislation

CDC may be obliged to disclose information provided by bidders in response to this tender under the Freedom of Information Act 2000 and all subordinate legislation made under this Act and the Environmental Information Regulations 2004 (“the Freedom of Information Legislation”).

Tenderers should therefore be aware that the information they provide could be disclosed in response to a request under the Freedom of Information Legislation. CDC will proceed on the basis of disclosure unless an appropriate exemption applies. Tenderers should be aware that despite the availability of some exemptions, information may still be disclosed if it is in the public interest.

Prevention of Bribery

Tenderers are hereby notified that CDC is subject to the regulations of the Bribery Act 2010 and therefore has a duty to ensure that all tenderers will comply with applicable laws, regulations, codes and sanctions relating to anti-bribery and anti-corruption including, but not limited to, this legislation.

Health and Safety

The Consultant must at all times comply with the requirements of the Health and Safety at Work Act 1974, the Management of Health and Safety at Work Regulations 1992 and all other statutory and regulatory requirements.

Conflicts of Interest

Tenderers must provide a clear statement with regard to potential conflicts of interests.

Therefore, please confirm whether, to the best of your knowledge, there is any conflict of interest between your organisation and CDC or its project team that is likely to influence the outcome of this procurement either directly or indirectly through financial, economic or other personal interest which might be perceived to compromise the impartiality and independence of any party in the context of this procurement procedure.

Receipt of this statement will permit CDC to ensure that, in the event of a conflict of interest being notified/noticed, appropriate steps are taken to ensure that the evaluation of any submission will be undertaken by an independent and impartial panel.

Exclusion

CDC shall exclude the tenderer from participation in this procurement procedure where they have established or are otherwise aware that the organisation, to include administrative, management or supervisory staff that have powers of representation, decision or control of the applicant’s company, has been the subject of a conviction by final judgment of one of the following reasons:

- Participation in a criminal organisation

- Corruption

- Fraud

- Terrorist offences or offences linked to terrorist activities

- Money laundering or terrorist financing

- Child labour and other forms of trafficking in human beings

Document Retention

All documentation (electronic and hard copy) produced as part of this contract will need to be returned to CDC at the end of the contract so that we can retain them for future reference/audit. The Contractor will not be expected to store these documents for future reference.

All documents must be written in English.

## Tender Return

Tenders may be returned by email or post, or by delivery in person.

Latest date to be returned:   5pm – 21 January 2019

If submitting by email, tenders should be sent electronically to tenders@cornwalldevelopmentcompany.co.uk with the following message clearly noted in the Subject box;

‘Tender TEN 442 - Strictly Confidential – Tender for Innovation Challenge Fund for Cornwall & Isles of Scilly Skills Hub’

Tenderers are advised to request an acknowledgement of receipt when submitting by email.

If submitting by post or in person, the Tender must be enclosed in a sealed envelope, only marked as follows:

‘Tender TEN 442 - Strictly Confidential – Tender for Innovation Challenge Fund for Cornwall & Isles of Scilly Skills Hub’

For the attention of Nicky Pooley, Head of Corporate Services

Cornwall Development Company

Bickford House

South Wheal Crofty

Station Road

Pool, Redruth

Cornwall

TR15 3QG

The envelope should not give any indication to the Tenderer’s identity.  Marking by the carrier will not disqualify the tender.

Note that if you are delivering the Tender by hand or by courier, it should be delivered during normal working hours (0900 – 1700 Monday to Friday) and an official receipt obtained.  Tenders delivered by hand to any other location will not qualify and will be rejected.

PLEASE DO NOT EMAIL YOUR TENDER SUBMISSION TO THE CORNWALL DEVELOPMENT COMPANY OR THE CONTACT OFFICER.

# Evaluation of Tenders

Each Tender will be checked for completeness and compliance with all requirements of the ITT.

Tenders will be evaluated to determine the most economically advantageous offer taking into consideration the following award criteria:

Tender Evaluation Criteria

| Section 1: Covering Letter |  |
| --- | --- |
| Covering letter (2 pages maximum) stating: - That the provider has the resources available to meet the requirements outlined in the brief - and within the tender timetable. - That the provider will be able to meet the CDC Corporate Requirements (see below), to include confirmation that Equality and Diversity and Environmental policies are in place and if successful supporting documentation will be provided as evidence together with the appropriate conflicts of interest policy statement. - The provider shall provide confirmation that insurance policies are current and if they are due to expire during the course of the commission to provide renewal notices prior to their expiry date(s). - That the provider accepts all the Terms and Conditions of the Contract attached at Annexe B - The point of contact within your organisation in relation to this tender. | Pass/ Fail |
| Section 2: Project Summary Total 20% (as distributed below) |  |
| Summary (600 words maximum) of the project stating: - How your proposal meets the issues, criteria and elements set out in commission above. - How your proposal aligns with the CIoS LEP Employment and Skills Strategy. | 20 |
| Section 3: Project Narrative Total 50% (as distributed below) |  |
| Detail of the Project Activity (2000 words maximum) you aim to undertake stating: - Your experience related to delivering the Campaign – examples of 2 similar Campaigns you have delivered successfully. - Knowledge and understanding of Apprenticeships and how to engage employers, or how you will obtain this. - How you intend to deliver the Campaign elements and expected outcomes. - Whether you will be using a sub-contractor to deliver any elements. - The project timescales and milestones. - What makes your proposal innovative in relation to the previous Apprenticeship campaign? - Detail of the staff involved in the Campaign. Including maximum 2-page CV’s (not included in word count). - How you will engage relevant stakeholders. | 50 |
| Section 4: Legacy Total 5% |  |
| Legacy (600 words maximum) stating: - How you will suggest we build legacy into the Campaign. | 5 |
| Section 5: Budget Total 25% |  |
| - Total project costs to deliver of each of the Campaign Elements. The lowest bid will be awarded the full 25 marks. Other bids will be awarded a mark that is proportionate to the level of their bid in comparison to the lowest bid i.e. Marks awarded = 25 x lowest bid / bid | 25 |

Assessment of the Tender

The Company is not bound to accept the lowest or any Tender.  This Tender does not constitute an offer to enter into a contractual relationship.  The Company will not reimburse any expense incurred by the Tenderers in preparing their responses to this Tender.

It is anticipated that the selection process will be carried out in one stage; assessment of the tender submission - reviewing ability to meet criteria listed above.

The reviewer will award a percentage of the marks depending upon their assessment of the applicant’s tender submission and will use the following scoring to assess the response:

| Scoring Matrix for Evaluation Criteria |  |  |
| --- | --- | --- |
| Score % | Judgement | Interpretation |
| 100 | Excellent | Exceptional demonstration of the relevant ability, understanding, experience, skills, resource and/or quality measures required to provide the goods/works/services. Full evidence provided where required to support the response. |
| 80 | Good | Above average demonstration of the relevant ability, understanding, experience, skills, resource and/or quality measures required to provide the goods/works/services. Majority evidence provided to support the response. |
| 60 | Acceptable | Demonstration of the relevant ability, understanding, experience, skills, resource and/or quality measures required to provide the goods/works/services, with some evidence to support the response. |
| 40 | Minor Reservations | Some minor reservations of the relevant ability, understanding, experience, skills, resource and/or quality measures required to provide the goods/works/services, with little or no evidence to support the response. |
| 20 | Serious Reservations | Considerable reservations of the relevant ability, understanding, experience, skills, resource and/or quality measures required to provide the goods/works/services, with little or no evidence to support the response. |
| 0 | Unacceptable | Does not comply and/or insufficient information provided to demonstrate that there is the ability, understanding, experience, skills, resource and/or quality measures required to provide the goods/works/services, with little or no evidence to support the response. |

## Notification

Following evaluation of the Tenders, CDC will make a decision on which, if any, Tender shall be accepted. This decision will be based on the most economically advantageous tender response.

Any contract award will be conditional on the Contract being approved in accordance with the CDC’s internal procedures and CDC being generally able to proceed.

Intellectual Property

The client shall be entitled to share the outcome of the work in whole or part with others at its discretion.  All outputs of the contract will remain the property of Cornwall Development Company.

Tender Award

Any contract awarded as a result of this tender process will be in accordance with the attached CDC standard terms and conditions (Annexe B).

# Further Information

The CIoS Skills Hub projects are in receipt of funding from the European Union and as such it is necessary for documentation (including every accessible/viewable option) to properly accredit the key support from the European Union.  Principally, this will include use of the ESF logo as appropriate. More details can be found in Annexe A.

# Disclaimer

The issue of this documentation does not commit CDC to award any contract pursuant to the bid process or enter into a contractual relationship with any provider of the service. Nothing in the documentation or in any other communications made between CDC or its agents and any other party, or any part thereof, shall be taken as constituting a contract, agreement or representation between CDC and any other party (save for a formal award of contract made in writing by or on behalf of CDC).

Bidders must obtain for themselves, at their own responsibility and expense, all information necessary for the preparation of their tender responses. Information supplied to bidders by CDC or any information contained in CDC’s publications is supplied only for general guidance in the preparation of the tender response.

Bidders must satisfy themselves by their own investigations as to the accuracy of any such information and no responsibility is accepted by CDC for any loss or damage of whatever kind and howsoever caused arising from the use by bidders of such information.

Bidders shall be responsible for their own costs and expenses in connection with or arising out of their response.

CDC reserves the right to vary or change all or any part of the basis of the procedures for the procurement process at any time or not to proceed with the proposed procurement at all.

Cancellation of the procurement process (at any time) under any circumstances will not render CDC liable for any costs or expenses incurred by bidders during the procurement process.

--------------------------------------------------------------------------------------------

Annexe A – EU Branding & Publicity Guidelines

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/634288/ESIF_Branding_and_Publicity_Requirements.pdf

## Annexe B: Terms and Conditions