Prelims - JCT 2016 - D&B

Site 8  - Hermitage Road

November 2017

TABLE OF CONTENTS

A10 PROJECT PARTICULARS	4

A11 TENDER AND CONTRACT DOCUMENTS	7

A12 THE SITE/ EXISTING BUILDINGS	9

A13 DESCRIPTION OF THE WORK	11

A20 JCT DESIGN AND BUILD CONTRACT (DB)	13

A30 TENDERING/ SUBLETTING/ SUPPLY	21

A31 PROVISION, CONTENT AND USE OF DOCUMENTS	27

A32 MANAGEMENT OF THE WORKS	32

A33 QUALITY STANDARDS/ CONTROL	37

A34 SECURITY/ SAFETY/ PROTECTION	44

A35 SPECIFIC LIMITATIONS ON METHOD/  SEQUENCE/  TIMING	51

A36 FACILITIES/ TEMPORARY WORK/ SERVICES	53

A37 OPERATION/ MAINTENANCE OF THE FINISHED WORKS	57

A40 CONTRACTOR’S GENERAL COST ITEMS: MANAGEMENT AND STAFF	62

A41 CONTRACTOR’S GENERAL COST ITEMS: SITE ACCOMMODATION	64

A42 CONTRACTOR’S GENERAL COST ITEMS: SERVICES AND FACILITIES	66

A43 CONTRACTOR’S GENERAL COST ITEMS: MECHANICAL PLANT	68

A44 CONTRACTOR’S GENERAL COST ITEMS: TEMPORARY WORKS	70

A50 WORK/ PRODUCTS BY/ ON BEHALF OF THE EMPLOYER	72

A53 WORK BY STATUTORY AUTHORITIES/ UNDERTAKERS	74

A54 PROVISIONAL WORK/ ITEMS	76

A56 ADVANCE PROCUREMENT	78

JCT 2016 Design and Build Contract

A10

PROJECT PARTICULARS

# A10 PROJECT PARTICULARS

110	THE PROJECT

•  Name:  	Brick By Brick – Site 8 Hermitage Road

•	 Nature:  Residential Development of 9 Market sale units

•	 Location: Land to the west of 83, 85 and 113 Hermitage Road, Upper Norwood, London, SE19 3QN	•	 Length of contract:  January 2018 to be completed by December 18.

120	EMPLOYER (CLIENT)

•	 Name: Brick By Brick Croydon Limited.

•	 Address: Bernard Weatherill House, 8 Mint Walk, Croydon, London, CR10 1EA.

•	 Contact: Amena Matin.

•	 Telephone: 0208 7266000.

•	 E-mail: Amena.Matin@croydon.gov.uk

130	PRINCIPAL CONTRACTOR (CDM)

•	 Name: (TBC).

•	 Address:

•	 Contact:

•	 Telephone:

•	 E-mail:

132	PRINCIPAL CONTRACTOR (SWMP)

•	 Name: (TBC)

•	 Address:

•	 Contact:

•	 Telephone:

•	 E-mail:

140	EMPLOYER'S AGENT

•	 Name: Faithful+Gould.

•	 Address: Wellington Gate, 7 – 9 Church Road, Tunbridge Wells, Kent TN1 1HT

•	 Contact: Steven Moore

•	 Telephone: 01892 775 004

•	 E-mail: Steven.Moore@fgould.com

150	PRINCIPAL DESIGNER

•	 Name: Faithful+Gould

•	 Address: Wellington Gate, 7 – 9 Church Road, Tunbridge Wells, TN1 1HT

•	 Contact: David Holmes

•	 Telephone: 07776 243 814

•	 E-mail: david.holmes@gfould.com

150	QUANTITY SURVEYOR

•	 Name: Faithful+Gould

•	 Address: Wellington Gate, 7 – 9 Church Road, Tunbridge Wells, TN1 1HT

•	 Contact: Charlotte Bond

•	 Telephone: 01892 775 019

•	 E-mail: charlotte.bond@gfould.com

170	ARCHITECT

•	 Name: Mikhail Riches

•	 Address: 15-29 Windsor Street, London, N1 8QG

•	 Contact: Amy Waite

•	 Telephone: 0207 608 1505

•	 E-mail: aw@mikhailriches.com

170	STRUCTURAL ENGINEER

•	 Name: Aksward.

•	 Address: 1 Westsmithfield, London, EC1A 9JU

•	 Contact: Stephen Gibbs

•	 Telephone: 0207 236 0161

•	 E-mail: Stephen.gibbs@aksward.com

175	SERVICES ENGINEER

•	 Name: Sweco.

•	 Address: 1 Bath Road, Maidenhead, SL6 4AQ

•	 Contact: Edmund Vaughan

•	 Telephone: 01628 623 423

•	 E-mail: Edmund.vaughn@sweco.co.uk

180	LANDSCAPE ARCHITECT

•	 Name: TBC

•	 Address:

•	 Contact:

•	 Telephone:

•	 E-mail:

190	CLERK OF WORKS

•	 Name: TBC

•	 Address:

•	 Contact:

•	 Telephone:

•	 E-mail:

A11

TENDER AND CONTRACT DOCUMENTS

# A11 TENDER AND CONTRACT DOCUMENTS

110	TENDER DRAWINGS

•	  The tender drawings are: See Employer’s Requirements included in the tender documents.

120	CONTRACT DRAWINGS

•	  The contract drawings: Same as the tender drawings.

•	  Exceptions: N / A

160	PRECONSTRUCTION INFORMATION

•	  Format: The Preconstruction information is described in these preliminaries in Section A34.

It refers to information given elsewhere in the preliminaries and other tender documents.

180	OTHER DOCUMENTS

•	The documents include: Refer to planning application available on the Planning Portal Number 16/05891/FUL

http://publicaccess2.croydon.gov.uk/online-applications/search.do?action=simple&searchType=Application.

A12

THE SITE/ EXISTING BUILDINGS

# A12 THE SITE/ EXISTING BUILDINGS

110	THE SITE

•	  Description: See PCI included in the tender documents.

120	EXISTING BUILDINGS ON/ ADJACENT TO THE SITE

•	Description The site is clear of buildings, being currently used as an informal parking area. Existing dwellings lie adjacent to the site on the SE side as well as a new school and residential development to the NW of the site.

140	EXISTING UTILITIES AND SERVICES

•	Drawings: (Information shown is indicative only): See Acradis Technical Due Diligence Report included in the tender documents.

160	SOILS AND GROUND WATER

•	  Information: Included in the tender documents

170	SITE INVESTIGATION

•	  Report: Included in the tender documents

180	HEALTH AND SAFETY FILE

•	  Availability for inspection: N/A

200	ACCESS TO THE SITE

•	  Description: See PCI included in the tender documents.

•	  Limitations: See PCI included in the tender documents.

210	PARKING

•	Restrictions on parking of the Contractor's and employees' vehicles: Please refer to Arcadis Construction Logistic Plan included in the tender documents.

220	USE OF THE SITE

•	  General: Do not use the site for any purpose other than carrying out the Works.

•	  Limitations: 	-   Access Points to be kept clear: Hermitage Road and the residential properties on it

- Access routes to be kept clear: Public Highways unless a formal closure is in place

-   Please refer to Arcadis Construction Logistic Plan included in the tender documents for any

other site restrictions.

230	SURROUNDING LAND/ BUILDING USES

•	  General: Adjacent or nearby uses or activities are as follows: Residential property and a school.

A12/240	HEALTH AND SAFETY HAZARDS

-	General: The nature and condition of the site/ building cannot be fully and certainly ascertained before it is opened up. However particular attention is drawn to the Pre Construction Information Document.

-	Information: The accuracy and sufficiency of this information is not guaranteed by the Employer or the Employer's representative. Ascertain if any additional information is required to ensure the safety of all persons and the Works.

250	SITE VISIT

•	  Assessment: Ascertain the nature of the site, access thereto and all local conditions and

Restrictions likely to affect the execution of the Works.

•	  Arrangements for visit: The Site has open access.

A13

DESCRIPTION OF THE WORK

# A13 DESCRIPTION OF THE WORK

110	PREPARATORY WORK BY OTHERS

•	  Works: Carried out under a separate contract and completed before the start of work on

site for this Contract.

•	  Description: Site clearance of fly tipping

120	THE WORKS

•	  Description: Site clearance and construction of Block of 7 apartments and 2 houses.

130	WORK BY OTHERS CONCURRENT WITH THE CONTRACT

•	  Description: Not Applicable.

140	COMPLETION WORK BY OTHERS

•	  Description: Not Applicable. 
		A20

JCT DESIGN AND BUILD CONTRACT (DB)

# A20 JCT DESIGN AND BUILD CONTRACT (DB)

JCT DESIGN AND BUILD CONTRACT

•	It is the intention of Brick By Brick to let each site on an individual JCT Design and Build Contract (DB) 2016 Edition, with the following recitals and articles.

•	 The contract: JCT Design and Build Contract (DB), 2016 Edition.

•	 Requirement: Allow for the obligations, liabilities and services described in Contract

Amendments prepared by Gowlings.

THE RECITALS

First - THE WORKS

•	Comprise of: Site clearance and construction of a new residential block of 7 apartments and 2 houses.

Fifth - DIVISION OF THE WORKS INTO SECTIONS

•	  The Fifth Recital is to be deleted.

THE ARTICLES

3 - EMPLOYER'S AGENT

•	  Employer's Agent: See clause A10/140.

5 - PRINCIPAL DESIGNER

•	  Principal Designer: See clause A10/150.

5 - PRINCIPAL DESIGNER

•	  Article 5 will be deleted.

6 - PRINCIPAL CONTRACTOR

•	  Principal Contractor: See clause A10/130.

6 - PRINCIPAL CONTRACTOR

•	  Article 6 will be deleted.

9 - LEGAL PROCEEDINGS

•	  Amendments: see contract amendments.

CONTRACT PARTICULARS

Fourth recital and clause 4.5 - CONSTRUCTION INDUSTRY SCHEME (CIS)

•	  Employer at the Base Date is a contractor for the purposes of the CIS.

Fifth Recital - DESCRIPTION OF SECTIONS

•	  Description of Sections: Not applicable

Sixth Recital - FRAMEWORK AGREEMENT

•	Framework agreement: Contractor Framework Agreement for Residential Development Programme Croydon.

•	  Details:

-	Date: (TBC).

-	Title: Contractor Framework Agreement

-	    Parties: Brick By Brick Croydon Limited and (Contractor TBC).

Seventh Recital and Part 1 of Schedule 2 - SUPPLEMENTAL PROVISIONS - PART 1

•	 Named subcontractors: Supplemental Provision 1 does not apply.

•	 Valuation of changes - Contractor's estimates: Supplemental Provision 2 applies.

•	 Loss and expense - Contractor's estimates: Supplemental Provision 3 applies.

Seventh Recital and Part 2 of Schedule 2 - SUPPLEMENTAL PROVISIONS - PART 2

•	 Acceleration quotation: Supplemental Provision 4 applies.

•	 Collaborative working: Supplemental Provision 5 applies.

•	 Health and safety: Supplemental Provision 6 applies.

•	 Cost savings and value improvements: Supplemental Provision 7 applies.

•	Sustainable developments and environmental considerations: Supplemental Provision 8 applies.

•	 Performance indicators and monitoring: Supplemental Provision 9 does not apply.

•	 Notification and negotiation of disputes: Supplemental Provision 10 applies.

•	 Where Supplemental Provision 10 applies, the respective nominees of the parties are:

-	Employer's nominee: Colm Lacey

-	Contractor's nominee: TBC.

Or such replacement as each party may notify to the other from time to time.

Article 4 - EMPLOYER'S REQUIREMENTS, CONTRACTOR'S PROPOSALS, CONTRACT SUM ANALYSIS

•	 Employer's Requirements: See Employer’s Requirements.

•	 Contractor's Proposals: TBA

•	 Contract Sum Analysis: See section 15 of the tender documents.

Article 8 - ARBITRATION

•	 Article 8 and clauses 9.3 to 9.8 (arbitration) shall not apply.

Clause 1.1 - BASE DATE

•	 Base Date: Ten days before the tender return date.

Clause 1.1 - BIM PROTOCOL

•	 BIM Protocol (where applicable): N/A

Clause 1.1 - DATE FOR COMPLETION OF THE WORKS

•	Date for completion of the Works (where completion by sections does not apply): By December 2018

Clause 1.1 - DATES FOR COMPLETION OF SECTIONS

•	 Dates for completion of sections: Not Applicable

-	Section: See Site Specific Prelims.:  Date:

Clause 1.7 - ADDRESSES FOR SERVICE OF NOTICES

•	 Employer:

-	Address: Brick by Brick, Bernard Weatherill House, 8 Mint Walk, Croydon, London, CR10 1EA

•	 Contractor:

-	Address: TBC

Clause 2.3 - DATE OF POSSESSION OF THE SITE

•	 Date of Possession of the site: January 2018

Clause 2.3 - DATE OF POSSESSION OF THE SITE

•	 Dates of Possession of Sections: Not Applicable

-	Section: See Site Specific Prelims.: Date: See Site Specific Prelims..

Clause 2.4 - DEFERMENT OF POSSESSION OF THE SITE

•	 Clause 2.4 The standard period of six months shall apply

Clause 2.4 - DEFERMENT OF POSSESSION OF THE SITE

•	 Clause 2.4 The standard period of six months shall apply

Where clause 2.4 applies, maximum period of deferment is:

-	Section: See Site Specific Prelims.: Maximum period: See Site Specific Prelims..

Clause 2.17.3 - LIMIT OF CONTRACTOR'S LIABILITY FOR LOSS OF USE, ETC.

•	 Limit of Contractor's liability for loss of use: TBC.

Clause 2.29.2 - LIQUIDATED DAMAGES

•	 Damages: At the rate of £1,800 per week.

Clause 2.29.2 - LIQUIDATED DAMAGES

•	 Damages: Not applicable

-	Section See Site Specific Prelims.

Clause 2.34 - SECTION SUMS

•	 Section sums: Not applicable

-	Section See Site Specific Prelims.

Clause 2.35 - RECTIFICATION PERIOD

•	 Period: (12 months) from the date of practical completion of the Works.

Clause 2.35 - RECTIFICATION PERIOD

•	 Period from the date of Practical Completion of each section: Not applicable

-	Section.

Clause 4.2, 4.12 and 4.13 - FLUCTUATIONS PROVISION

•	 Fluctuations Provision: Does not apply.

•	 Where JCT Fluctuations Option A or B applies:

-	Percentage addition (paragraph A.12 or paragraph B.13): N/A.

•	 Where JCT Fluctuations Option C applies:

-	Rule 3: Base Month: N/A.

-	Rule 3: Non-Adjustable Element: N/A.

Rules 10 and 30(i): N/A.

Clause 4.6 - ADVANCE PAYMENT AND ADVANCE PAYMENT BOND

•	 Advance payment: Clause 4.6 does not apply.

Clause 4.7 - METHOD OF PAYMENT - ALTERNATIVE B

•	 Payment: Periodically, in accordance with Alternative B.

Clause 4.7.2 - INTERIM PAYMENTS - INTERIM VALUATION DATES

•	The first Interim Valuation Date is: four weeks after date of possession and thereafter the same date in each month. Or the nearest Business Day in that month.

Clause 4.15.4 - LISTED ITEMS - UNIQUELY IDENTIFIED

•	 Listed items: Clause 4.15.5 will be deleted.

Clause 4.15.4 - LISTED ITEMS - UNIQUELY IDENTIFIED

•	 Listed items: A bond in respect of payment for such items is required for: N/A

Clause 4.15.5 - LISTED ITEMS - NOT UNIQUELY IDENTIFIED

•	 Listed items: A bond is not required.

Clause 4.15.5 - LISTED ITEMS - NOT UNIQUELY IDENTIFIED

•	 Listed items: A bond in respect of payment for such items is required for: N/A.

Clause 4.17 - CONTRACTOR'S RETENTION BOND

•	 Clause 4.17 does not apply.

Clause 4.17 - CONTRACTOR'S RETENTION BOND

•	 Clause 4.17 does not apply.

-	The maximum aggregate sum for the purposes of clause 2 of the bond is N/A.

For the purposes of clause 6.3 of the bond, the expiry date shall be N/A.

Clause 4.18.1 - RETENTION PERCENTAGE

•	 Retention: 5% (five per cent)
Clause 5.5 - DAYWORK

•	 Percentage additions to each section of the prime cost or, if they apply in respect of labour,

the All-Inclusive Rates, are set out in the following document: See pricing schedule.

Clause 6.4.1 - CONTRACTOR'S PUBLIC LIABILITY INSURANCE: INJURY TO PERSONS OR PROPERTY

•	Insurance cover for any one occurrence or series of occurrences arising out of one event £10,000,000 (ten million).

Clause 6.5.1 - INSURANCE - LIABILITY OF EMPLOYER

•	 Minimum amount of indemnity for any one occurrence or series of occurrences arising out of

one event: £10,000,000 (ten million).

Clause 6.7 and schedule 3 - WORKS INSURANCE - INSURANCE OPTIONS APPLICABLE

•	 Schedule 3:

-	Insurance Option A (Contractor).

-	Percentage to cover professional fees: 15%

•	Where Insurance Option A applies, annual renewal date (as supplied by the Contractor): TBC.

•	 Where Insurance Option C applies:

-	Paragraph C1: N/A.

-	If paragraph C1 does not apply, the C1 Replacement Schedule is: N/A

Clause 6.10 and Schedule 3 - TERRORISM COVER

•	 Details of the required cover:

- Not required.

Clause 6.15 - PROFESSIONAL INDEMNITY INSURANCE

•	 Level of cover: Amount of indemnity required:

-  £5,000,000

-	and is: For each and every claim

Cover for pollution and contamination claims: £10m.

Expiry of required period of Professional Indemnity Insurance:12 years

Clause 6.17 - JOINT FIRE CODE

•	 The Joint Fire Code: Applies.

•	 If the Joint Fire Code Applies, the insurer has stated that the Works are a 'Large Project':

Clause 6.20 - JOINT FIRE CODE - AMENDMENTS AND REVISIONS

•	Joint Fire Code - Amendments/ revisions: The cost, if any, of compliance with amendments or revisions to the Joint Fire Code shall be borne by the contractor.

Clause 7.2 - ASSIGNMENT/ GRANT BY EMPLOYER OF RIGHTS UNDER CLAUSE 7.2

•	 Clause 7.2 will apply

Clause 7.2 - ASSIGNMENT/ GRANT BY EMPLOYER OF RIGHTS UNDER CLAUSE 7.2

•	 Sections: Rights under clause 7.2 apply to each Section.

Clause 7.3.1 - PERFORMANCE BOND OR GUARANTEE

•	A PCG is required where this a Parent Company if there is no Parent Company a Bond in lieu will be required.

Clause 7.3.2 - GUARANTEE FROM THE CONTRACTOR'S PARENT COMPANY

•	 Guarantee:

-	Parent company's name and registration number: TBC.

The required form of guarantee is set out in: See Contract Amendments.

Clause 7.4 - THIRD PARTY RIGHTS AND COLLATERAL WARRANTIES

•	 Details: Are required from all Sub-Consultants and Sub-Contractors with Design Responsibility

Clause 8.9.2 - PERIOD OF SUSPENSION (TERMINATION BY CONTRACTOR)

•	 Period of suspension: 2 months.

Clauses 8.11.1.1 to 8.11.1.6 - PERIOD OF SUSPENSION (TERMINATION BY EITHER PARTY)

•	 Period of suspension: 2 months.

Clause 9.2.1 - ADJUDICATION

•	 The Adjudicator is: is not named

Nominating body: Where no Adjudicator is named or where the named Adjudicator is

unwilling or unable to act (whenever that is established): The Royal Institution of Chartered Surveyors.

Clause 9.4.1 - ARBITRATION

•	 Appointor of Arbitrator (and of any replacement): President or a Vice President of the RICS.

THE CONDITIONS

SECTION 1: DEFINITIONS AND INTERPRETATION

1.5 - RECKONING PERIODS OF DAYS

•	 Amendments: None.

1.11 - APPLICABLE LAW

•	 Amendments: None.

SECTION 2: CARRYING OUT THE WORKS

SECTION 3: CONTROL OF THE WORKS

SECTION 4: PAYMENT

SECTION 5: CHANGES

SECTION 6: INJURY, DAMAGE AND INSURANCE

SECTION 7: ASSIGNMENT, THIRD PARTY RIGHTS AND COLLATERAL WARRANTIES

SECTION 8: TERMINATION

SECTION 9: SETTLEMENT OF DISPUTES – See Contract Amendments

JCT PUBLIC SECTOR SUPPLEMENT

-	Document: The JCT Public Sector Supplement 2011 – Fair Payment, Transparency and Building Information Modelling.

EXECUTION

•	 The Contract: Will be executed as a Deed.

CONTRACT GUARANTEE BOND

- Contract Guarantee Bond: is required where there is no PCG available.

A30

TENDERING/ SUBLETTING/ SUPPLY

# A30 TENDERING/ SUBLETTING/ SUPPLY

MAIN CONTRACT TENDERING

110 SCOPE

•	 General: These conditions are supplementary to those stated in the Invitation to Tender

and on the form of tender along with the Employers Requirements.

145 TENDERING PROCEDURE

•	General: In accordance with the principles of JCT Practice Note 6 (Series 2) ‘Main Contract Tendering’

•  Arithmetical errors: Alternative 2 is dominant.

160 EXCLUSIONS

•	 Inability to tender: Immediately inform if any parts of the work as defined in the tender

documents cannot be tendered.

•	 Relevant parts of the work: Define those parts, stating reasons for the inability to tender.

170 ACCEPTANCE OF TENDER

•	Acceptance: No guarantee is offered that any tender will be recommended for acceptance or be accepted, or that reasons for non acceptance will be given.

•	 Costs: No liability is accepted for any cost incurred in the preparation of any tender.

190 PERIOD OF VALIDITY

•	 Period: After submission or lodgement, keep tender open for consideration (unless

previously withdrawn) for not less than. 90 Days

•	 Date for possession: See section A20.

PRICING/ SUBMISSION OF DOCUMENTS

210 PRELIMINARIES IN THE SPECIFICATION

•	 The Preliminaries/ General conditions sections (A10-A56 inclusive) have been prepared in

accordance with NRM.

220 PRICING OF PRELIMINARIES

•	 Abbreviations: The following have been used:

-	F   = Fixed charge item.

-	TR = Time related charge item.

•		Charges: If the Contractor requires interim payments to include fixed and time related charges for specific items in the Preliminaries, those charges must be clearly shown against the items.

A30/250 PRICED DOCUMENTS

-	Alterations: Do not alter or qualify the priced documents without written consent. Tenders containing unauthorised alterations or qualifications may be rejected.

-		Measurements: Where not stated, ascertain from the drawings.

-	Deemed included: Costs relating to items, which are not priced, will be deemed to have been included elsewhere in the tender.

-		Submit: Fully priced work schedules with tender return.

A30/300 QUANTITIES IN THE PRICED DOCUMENT

-	Quantities: Where included in the priced document, these have been prepared in accordance with NRM only where and to the extent stated.

-	Other items, descriptions and measurements not prepared in accordance with NRM: Must be priced taking account of the information given elsewhere in the tender documents, including for all associated and ancillary work shown or clearly apparent as being necessary for the complete and proper execution of the work.

310 TENDER

•	 General: Tenders must include for all work shown or described in the tender documents as

a whole or clearly apparent as being necessary for the complete and proper execution of

the Works.

A30/350 PC AND PROVISIONAL SUMS

-	Contractor's profit on PC Sums: -

-	Provisional sums and items: None

-	Submit: A copy of sections A51-A55 (as applicable), priced to include profit, attendance and percentage adjustments with the tender return.

A30/440	SCHEDULE OF RATES

- Content: A full schedule of rates shall be provided by the Contractor.

- Fully priced copy: Submit with tender

440	CONTRACT SUM ANALYSIS

•	 Content of the Analysis: A breakdown of the Contract Sum into at least the following

categories:

-	NRM elemental summary.

-   Fully priced copy: Submit with tender.

A30/460	ANALYSIS OF THE CONTRACTOR’S DESIGNED PORTION

-	Fully priced copy: Submit with the tender.

480	PROGRAMME

•	 Programme of work: Prepare a summary showing the sequence and timing of the principal

parts of the Works and periods for planning and design. Itemize any work which is

excluded.

•	 Submit with Tender.

A30/490	INFORMATION RELEASE SCHEDULE

-	Compatibility with programme: At the same time as submitting the proposed programme or summary, confirm that it is compatible with the Information Release Schedule.

-	Alternative proposals: If any part of the programme is not compatible with the Schedule submit alternative proposals and reasons for varying the times for release of information.

500	TENDER STAGE METHOD STATEMENTS

Method statements –

A30/510	ALTERNATIVE METHOD TENDERS

-	General: In addition to and at the same time as tendering for the Works as defined in the tender documents, alternative methods of construction/ installation may be submitted for consideration. Alternatives, which would involve significant changes to other work, may not be considered.

-	Alternative tenders: Such alternatives will be deemed to be alternative tenders and each must include a complete and precise statement of the effects on cost and programme.

-	Safety method statement: Carry out a health and safety risk assessment for each alternative and where appropriate provide a safety method statement suitable for incorporation in the Health and Safety Plan.

-	Full technical data: Submit for each alternative together with details of any consequential amendments to the design and/ or construction of other parts of the Works.

-	Submit: A fully detailed programme with tender.

515	ALTERNATIVE TIME TENDERS

•	 General: In addition to and at the same time as tendering based upon the date or period

specified in section A20, an alternative tender based upon a different date for completion

or period may be submitted.

•	 Date for completion: If any such tender is accepted the date for completion inserted in the

Contract will be the date stated in the alternative tender or determined from the period

stated in the alternative tender.

520 CONTRACTOR'S PROPOSALS

•	 Proposals: Include the following:

-	Design drawings

-	Technical information

-	Submit: With tender.

A30/530 SUBSTITUTE PRODUCTS

-	Details: If products of different manufacture to those specified are proposed, submit details with the tender giving reasons for each proposed substitution. Substitutions, which have not been notified at tender stage, may not be considered.

-	Compliance: Substitutions accepted will be subject to the verification requirements of clause A31/200.

540 QUALITY CONTROL RESOURCES

•	 Statement: Describe the organisation and resources to control the quality of the Works,

including the work of subcontractors.

•	 QA staff: Identify in the statement the number and type of staff responsible for quality

control, with details of their qualifications and duties.

•	 Submit: with Tender.

550 HEALTH AND SAFETY INFORMATION

•	 Content: Describe the organisation and resources to safeguard the health and safety of

operatives, including those of subcontractors, and of any person whom the Works may

affect.

•	  Include:

-	A copy of the contractor's health and safety policy document, including risk assessment

procedures.

-	Accident and sickness records for the past five years.

-	Records of previous Health and Safety Executive enforcement action.

-	Records of training and training policy.

-	The number and type of staff responsible for health and safety on this project with details

of their qualifications and duties.

•	 Submit: with Tender.

570 OUTLINE CONSTRUCTION PHASE HEALTH AND SAFETY PLAN

•	 Content: Submit the following information within one week of request:

-	Method statements on how risks from hazards identified in the pre-construction

information and other hazards identified by the contractor will be addressed.

-	Details of the management structure and responsibilities.

-	Arrangements for issuing health and safety directions.

-	Procedures for informing other contractors and employees of health and safety hazards.

-	Selection procedures for ensuring competency of other contractors, the self-employed

and designers.

-	Procedures for communications between the project team, other contractors and site

operatives.

-	Arrangements for cooperation and coordination between contractors.

-	Procedures for carrying out risk assessment and for managing and controlling the risk.

-	Emergency procedures including those for fire prevention and escape.

-	Arrangements for ensuring that all accidents, illness and dangerous occurrences are

recorded.

-	Arrangements for welfare facilities.

-	Procedures for ensuring that all persons on site have received relevant health and safety

information and training.

-	Arrangements for consulting with and taking the views of people on site.

-	Arrangements for preparing site rules and drawing them to the attention of those affected

and ensuring their compliance.

-	Monitoring procedures to ensure compliance with site rules, selection and management

procedures, health and safety standards and statutory requirements.

-	Review procedures to obtain feedback.

590 SITE WASTE MANAGEMENT PLAN

•	  Person responsible for developing the Plan: The Contractor.

•	  Content: Include details of:

-	Principal Contractor for the purposes of the plan

-	Location of the site.

-	Description of the project.

-	Estimated project cost.

-	Types and quantities of waste that will be generated.

-	Resource management options for these wastes including proposals for minimization/

reuse/ recycling.

-	The use of appropriate and licensed waste management contractors.

-	Record keeping procedures.

-	Waste auditing protocols.

•	 Additional requirements: N/A

•	 Submit with tender.

595 ENVIRONMENTAL POLICY

•	  Employer's Environmental Policy:

-	Location: See A11/180.

-	Evidence of compliance: Submit: With Tender.

•	  Project Environmental Management System: Develop a system compatible with the

Employer's policy.

-	Format: TBC.

-	Specific Requirements: TBC

•	  Supporting information: Supply as necessary, including:

-	Information: TBC

-	Format: TBC.

Submit: TBC.

599 FREEDOM OF INFORMATION

•	 Records: Retain, make available for inspection and supply on request information

reasonably required to allow response to requests made under the provisions of the

Freedom of Information Act.

•	 Determination: Submit requests received. Do not supply information to anyone other than

the project participants without express written permission.

•	 Confidentiality: Maintain at all times.

SUBLETTING/ SUPPLY

630 DOMESTIC SUBCONTRACTS

•	 General: Comply with the Construction Industry Board 'Code of Practice for the selection of

subcontractors'.

•	 List: Provide details of all subcontractors and the work for which they will be responsible.

•	 Submit: with Tender.

A31

PROVISION, CONTENT AND USE OF DOCUMENTS

# A31 PROVISION, CONTENT AND USE OF DOCUMENTS

## DEFINITIONS AND INTERPRETATIONS

A31/110	DEFINITIONS

-	Meaning: Terms, derived terms and synonyms used in the preliminaries/ general conditions and specification are as stated therein or in the appropriate British Standard or British Standard glossary.

A31/120	COMMUNICATION

-	Definition: Includes advise, inform, submit, give notice, instruct, agree, confirm, seek or obtain information, consent or instructions, or make arrangements.

-	Format: In writing to the person named in clause A10/140 unless specified otherwise.

-	Response: Do not proceed until response has been received.

A31/130	PRODUCTS

-	Definition: Materials, both manufactured and naturally occurring, and goods, including components, equipment and accessories, intended for the permanent incorporation in the Works.

-	Includes: Goods, plant, materials, site materials and things for incorporation into the Works.

A31/135	SITE EQUIPMENT

-	Definition: All appliances or things of whatsoever nature required in or about the construction for completion of the Works but not materials or other things intended to form or forming part of the Permanent Works.

-	Includes: Construction appliances, vehicles, consumables, tools, temporary works, scaffolding, cabins and other site facilities.

A31/140	DRAWINGS

-	Definitions: To BSRIA BG 6/2009 A design framework for building services. Design activities and drawing definitions.

-	CAD data: In accordance with BS 1192.

A31/145	CONTRACTOR'S CHOICE

-	Meaning: Selection delegated to the Contractor, but liability to remain with the specifier.

A31/150	CONTRACTOR'S DESIGN

-	Meaning: Design to be carried out or completed by the Contractor and supported by appropriate contractual arrangements, to correspond with specified requirements.

A31/155	SUBMIT PROPOSALS

-	Meaning: Submit information in response to specified requirements.

A31/160	TERMS USED IN SPECIFICATION

-	Remove: Disconnect, dismantle as necessary and take out the designated products or work and associated accessories, fixings, supports, linings and bedding materials. Dispose of unwanted materials. Excludes taking out and disposing of associated pipework, wiring, ductwork or other services.

-	Fix: Receive, unload, handle, store, protect, place and fasten in position and disposal of waste and surplus packaging including all labour, materials and site equipment for that purpose.

-	Supply and fix: As above, but including supply or products to be fixed. All products to be supplied and fixed unless stated otherwise.

-	Keep for reuse: Do not damage designated products or work. Clean off bedding and jointing materials. Stack neatly, adequately protect and store until required by the Employer/ Purchaser or for use in the Works as instructed.

-	Make good: Execute local remedial work to designated work. Make secure, sound and neat. Excludes redecoration and/ or replacement.

-	Replace: Supply and fix new products matching those removed. Execute work to match original new state of that removed.

-	Repair: Execute remedial work to designated products. Make secure, sound and neat. Excludes redecoration and/ or replacement.

-	Refix: Fix removed products.

-	Ease: Adjust moving parts of designated products or work to achieve free movement and good fit in open and closed positions.

-	Match existing: Provide products and work of the same appearance and features as the original, excluding ageing and weathering. Make joints between existing and new work as inconspicuous as possible.

-	System: Equipment, accessories, controls, supports and ancillary items, including installation, necessary for that section of the work to function.

A31/170	MANUFACTURER AND PRODUCT REFERENCE

-	Definition: When used in this combination:

-	Manufacturer: The firm under whose name the particular product is marketed.

-	Product reference: The proprietary brand name and/ or reference by which the particular product is identified.

-	Currency: References are to the particular product as specified in the manufacturer’s technical literature current on the date of the invitation to tender.

A31/200	SUBSTITUTION OF PRODUCTS

-	Products: If an alternative product to that specified is proposed, obtain approval before ordering the product.

-	Reasons: Submit reasons for the proposed substitution.

-	Documentation: Submit relevant information, including:

-	manufacturer and product reference;

-	cost;

-	availability;

-	relevant standards;

-	performance;

-	function;

-	compatibility of accessories;

-	proposed revisions to drawings and specification;

-	compatibility with adjacent work;

-	appearance;

-	copy of warranty/ guarantee.

-	Alterations to adjacent work: If needed, advise scope, nature and cost.

-	Manufacturer’s guarantees: If substitution is accepted, submit before ordering products.

A31/210	CROSS REFERENCES

-	Accuracy: Check remainder of the annotation or item description against the terminology used in the section or clause referred to.

-	Related terminology: Where a numerical cross-reference is not given the relevant sections and clauses of the specification will apply.

-	Relevant clauses: Clauses in the referred to specification section dealing with general matters, ancillary products and execution also apply.

-	Discrepancy or ambiguity: Before proceeding, obtain clarification or instructions.

A31/220	REFERENCED DOCUMENTS

-	Conflicts: Specification prevails over referenced documents.

A31/222	DISCLAIMER: This document and its contents have been prepared and are intended solely for the Client’s information and use in relation to the design and build of residential units in Croydon for Brick by Brick. Faithful+Gould assumes no responsibility to any other party in respect of or arising out of or in connection with this document and/or its contents.

A31/225	COPYRIGHT: The copyright of this document is vested in Faithful+Gould. This document may not be reproduced in whole or in part without their express written permission.

A31/230	EQUIVALENT PRODUCTS

-	Inadvertent omission: Wherever products are specified by proprietary name the phrase 'or equivalent' is to be deemed included.

A31/240	SUBSTITUTION OF STANDARDS

-	Specification to British Standard or European Standard: Substitution may be proposed complying with a grade or category within a national standard of another Member State of the European Community or an international standard recognised in the UK.

-	Before ordering: Submit notification of all such substitutions.

-	Documentary evidence: Submit for verification when requested as detailed in clause A31/200. Any submitted foreign language documents must be accompanied by certified translations into English.

A31/250	CURRENCY OF DOCUMENTS

-	Currency: References to published documents are to the editions, including amendments and revisions, current on the date of the Invitation to Tender.

A31/260	SIZES

-	General dimensions: Products are specified by their co-ordinating sizes.

-	Timber: Cross section dimensions shown on drawings are:

-	Target sizes as defined in BS EN 336 for structural softwood and hardwood sections.

-	Finished sizes for non-structural softwood or hardwood sawn and further processed sections.

## DOCUMENTS PROVIDED ON BEHALF OF EMPLOYER

A31/410	ADDITIONAL COPIES OF THE DRAWINGS/ DOCUMENTS

-	Additional copies: Issued on request and charged to the Contractor.

A31/440	DIMENSIONS

-	Scaled dimensions: Do not rely on.

A31/450	MEASURED QUANTITIES

-	Ordering products and constructing the Works: The accuracy and sufficiency of the measured quantities is not guaranteed.

-	Precedence: The specification and drawings shall override the measured quantities.

A31/460	THE SPECIFICATION

-	Coordination: All sections must be read in conjunction with Main Contract Preliminaries/ General conditions.

A31/470	DIVERGENCE FROM THE STATUTORY REQUIREMENTS

-	Divergence: Between the drawings or specification and the requirements of the Building Regulations, other Statutes, statutory undertakers and other regulatory authorities.

-	Action: Inform immediately.

## DOCUMENTS PROVIDED BY CONTRACTOR/ SUBCONTRACTORS/ SUPPLIERS

A31/510	CHANGES/ AMENDMENTS TO EMPLOYER'S REQUIREMENTS

-	Contractor’s changes to Employer's Requirements: Support request for substitution or variation with all relevant information.

-	Employer’s amendments to Employer’s Requirements: If considered to involve a variation, which has not already been acknowledged as a variation, notify without delay (maximum period 7 days), and do not proceed until instructed. Claims for extra cost, if made after the variation has been carried out, may not be allowed.

A31/600	CONTRACTOR’S DESIGN INFORMATION

-	General: Complete the design and detailing of parts of the Works as specified.

-	Provide:

-	Production information based on the drawings, specification and other information.

-	Liaison to ensure coordination of the work with related building elements and services.

-	Master programme: Make reasonable allowance for completing design/ production information, submission (including to the CDM Coordinator), comment, inspection, amendment, resubmission and reinspection.

-	Submit: Within one week of request.

A31/610	PRODUCTION INFORMATION

-	Contractor/ Domestic subcontractor provide: All necessary design information.

-	Submit:

-	For comment and make any necessary amendments.

-	Sufficient copies of final version for distribution to all affected parties.

A31/620	AS BUILT DRAWINGS AND INFORMATION

-	Contractor’s designed work: Provide drawings/ information.

-	Submit: At least two weeks before date for completion.

A31/630	TECHNICAL LITERATURE

-	Information: Keep on site for reference by all supervisory personnel:

-	Manufacturers' current literature relating to all products to be used in the Works.

-	Relevant British Standards.

A31/640	MAINTENANCE INSTRUCTIONS AND GUARANTEES

-	Components and equipment: Obtain or retain copies, register with manufacturer and hand over on or before completion of the Works.

-	Information location: In the Building Manual.

-	Emergency call out services: Provide telephone numbers for use after completion.

## DOCUMENT/ DATA INTERCHANGE

A31/850	ELECTRONIC DATA INTERCHANGE (EDI)

-	Data: Types and classes of communication: All forms of communication between parties can be exchanged electronically.

A32

MANAGEMENT OF THE WORKS

# A32 MANAGEMENT OF THE WORKS

## GENERALLY

A32/110	SUPERVISION

-	General: Accept responsibility for coordination, supervision and administration of the Works, including subcontracts.

-	Coordination: Arrange and monitor a programme with each subcontractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for coordination of the work.

A32/115	CONSIDERATE CONSTRUCTORS SCHEME

-	Registration: Before starting work, register the site and pay the appropriate fee:

-	Contact:

-	Address: Considerate Constructors Scheme Office, PO Box 75, Great Amwell, Ware, Hertfordshire, SG12 0YX.

-	Tel. 01920 485959.

-	Fax. 01920 485958.

-	Free phone 0800 7831423.

-	Web. www.ccscheme.org.uk

-	Standard: Comply with the Scheme's Code of Considerate Practice to achieve a minimum score of 35

A32/117	CONSTRUCTING BETTER HEALTH SCHEME

-	Membership: Register and submit evidence of registration.

-	Contact:

-	Constructing Better Health, B&CE Building, Manor Royal.

-	Crawley, West Sussex.

-	RH10 9QP.

-	Tel: 0845 873 7726

-	Email: info@cbhscheme.co.uk

-	Website: www.cbhscheme.co.uk

A32/120	INSURANCE

-	Documentary evidence: Before starting work on site submit details, and/ or policies and receipts for the insurances required by the Conditions of Contract.

A32/130	INSURANCE CLAIMS

-	Notice: If any event occurs which may give rise to any claim or proceeding in respect of loss or damage to the Works or injury or damage to persons or property arising out of the Works, immediately give notice to the Employer, the person named in clause A10/140 and the Insurers.

-	Failure to notify: Indemnify the Employer against any loss, which may be caused by failure to give such notice.

A32/140	CLIMATIC CONDITIONS

-	Information: Record accurately and retain:

-	Daily maximum and minimum air temperatures (including overnight).

-	Delays due to adverse weather, including description of the weather, types of work affected and number of hours lost.

A32/150	OWNERSHIP

-	Alteration/ clearance work: Materials arising become the property of the Contractor except where otherwise stated. Remove from site as work proceeds.

## PROGRAMME/ PROGRESS

A32/210	PROGRAMME

-	Master programme: When requested and before starting work on site, submit in an approved form a master programme for the Works, which must include details of:

-	Design, production information and proposals provided by the Contractor/ Subcontractors/ Suppliers, including inspection and checking (see section A31).

-	Planning and mobilization by the Contractor.

-	Earliest and latest start and finish dates for each activity and identification of all critical activities.

-	Running in, adjustment, commissioning and testing of all engineering services and installations

-	Work resulting from instructions issued in regard to the expenditure of provisional sums (see section A54)

-	Work by or on behalf of the Employer and concurrent with the Contract (see section A50). The nature and scope of which, the relationship with preceding and following work and any relevant limitations are suitably defined in the Contract Documents.

-	Exclusions: Where and to the extent that the programme implications for work which is not so defined are impossible to assess, the Contractor should exclude it and confirm this when submitting the programme.

-	Submit: 6 copies to the EA.

A32/215	REVISED PROGRAMME

-	Format and content: Compatible with master programme.

-	Revised programme interval: Described in the contract data part one.

-	Number of copies: 6 copies.

A32/230	SUBMISSION OF PROGRAMME

-	Further information: Submission of the programme will not relieve the Contractor of the responsibility to advise of the need for further drawings or details or instructions in accordance with the Contract.

A32/240	COMMENCEMENT OF WORK

-	Notice: Before the proposed date for commencement of work on site give minimum notice of one month.

A32/250	MONITORING

-	Progress: Record on a copy of the programme kept on site.

-	Avoiding delays: If any circumstances arise which may affect the progress of the Works submit proposals or take other action as appropriate to minimize any delay and to recover any lost time.

A32/255	NOTIFICATION OF COMPENSATION EVENT

-	Content: Notwithstanding the Contractor's obligations under the Contract written notice must also be given of all other causes which apply concurrently.

A32/260	SITE MEETINGS

-	General: Site meetings will be held to review progress and other matters arising from administration of the Contract.

-	Frequency: Monthly.

-	Location: Contractor to provide suitable accommodation within his site compound on site or other location as agreed with the client.

-	Accommodation: Ensure availability at the time of such meetings – (allow for 4 members of the client team)

-	Attendees: Attend meetings and inform subcontractors and suppliers when their presence is required.

-	Chairperson (who will also take and distribute minutes): The EA.

A32/265	CONTRACTOR’S PROGRESS REPORT

-	General: Submit a progress report at least two days before the site meeting.

-	Content: Notwithstanding the Contractor's obligations under the Contract the report must include:

-	A progress statement by reference to the master programme for the Works.

-	Details of any matters materially affecting the regular progress of the Works.

-	Subcontractors' and suppliers' progress reports.

-	Any requirements for further drawings or details or instructions.

A32/270	CONTRACTOR’S SITE MEETINGS

-	General: Hold meetings with appropriate subcontractors and suppliers shortly before main site meetings to facilitate accurate reporting of progress.

A32/280	PHOTOGRAPHS

-	Provide a suitable number of progress photographs (a minimum of 10 per month) to indicate weekly progress to all areas of work and include a selection within each Contractor’s Progress Report.

A32/285	EARLY POSSESSION/ TAKE OVER OF PARTS OF THE WORKS BY THE EMPLOYER

-	Possession/ take over of parts of the Works: As completed, provided all necessary access, services and other associated facilities are also complete.

A32/290	NOTICE OF COMPLETION

-	Requirement: Give notice of the anticipated dates of completion of the whole or parts of the Works.

-	Associated works: Ensure necessary access, services and facilities are complete.

-	Period of notice (minimum): Two weeks.

A32/310	EXTENSIONS OF TIME

-	Notice: When a notice of the cause of any delay or likely delay in the progress of the Works is given under the conditions of contract, written notice must also be given of all other causes which apply concurrently.

-	Details: As soon as possible submit:

-	Relevant particulars of the expected effects, if appropriate, related to the concurrent causes.

-	An estimate of the extent, if any, of the expected delay in the completion of the Works beyond the date for completion.

-	All other relevant information required.

## CONTROL OF COST

A32/410	CASH FLOW FORECAST

-	Submission: Before starting work on site, submit a forecast showing the gross valuation of the Works at the date of each Interim Certificate throughout the Contract period. Base on the programme for the Works.

A32/420	REMOVAL/ REPLACEMENT OF EXISTING WORK

-	Extent and location: Agree before commencement.

-	Execution: Carry out in ways that minimize the extent of work.

A32/430	PROPOSED INSTRUCTIONS

-	Estimates: If a proposed instruction requests an estimate of cost, submit without delay and in any case within seven days.

-	Include:

-	A detailed breakdown of the cost, including any allowance for direct loss and expense.

-	Details of any additional resources required.

-	Details of any adjustments to be made to the programme for the Works.

-	Any other information as is reasonably necessary to fully assess the implications of issuing such an instruction.

-	Inability to comply: Inform immediately if it is not possible to comply with any of the above requirements.

A32/440	MEASUREMENT

-	Covered work: Give notice before covering work required to be measured.

A32/450	DAYWORK VOUCHERS

-	Before commencing work: Give reasonable notice to person countersigning daywork vouchers.

-	Content: Before delivery, each voucher must be:

-	Referenced to the instruction under which the work is authorized.

-	Signed by the Contractor's person in charge as evidence that the operatives' names, the time daily spent by each and the equipment and products employed are correct.

A32/460	INTERIM VALUATIONS

-	Applications: Include details of amounts requested under the Contract together with all necessary supporting information.

-	Submission: At least seven days before established dates.

A32/470	PRODUCTS NOT INCORPORATED INTO THE WORKS

-	Ownership: At the time of each valuation, supply details of those products not incorporated into the Works which are subject to any reservation of title inconsistent with passing of property as required by the Conditions of Contract, together with their respective values.

-	Evidence: When requested, provide evidence of freedom of reservation of title.

A32/475	LISTED PRODUCTS STORED OFF SITE

-	Evidence of Title: Submit reasonable proof that the property in items stored off site to be included in valuations is vested in the Contractor.

-	Include for products purchased from a supplier:

-	a copy of the contract of sale;

-	a written statement from the supplier that any conditions of the sale relating to the passing of property have been fulfilled and the products are not subject to any encumbrance or charge.

-	Include for products purchased from a supplier by a subcontractor or manufactured or assembled by any subcontractor:

-	Copies of the subcontract with the subcontractor and a written statement from the subcontractor that any conditions relating to the passing of property have been fulfilled.

A32/480	LABOUR AND EQUIPMENT RETURNS

-	Records: Provide for verification at the beginning of each week in respect of each of the previous seven days.

-	Records must show:

-	The number and description of craftsmen, labourers and other persons directly or indirectly employed on or in connection with the Works or Services, including those employed by subcontractors.

-	The number, type and capacity of all mechanical, electrical and power-operated equipment employed in connection with the Works or Services

A33

QUALITY STANDARDS/ CONTROL

# A33 QUALITY STANDARDS/ CONTROL

## STANDARDS OF PRODUCTS AND EXECUTIONS

A33/110	INCOMPLETE DOCUMENTATION

-	General: Where and to the extent that products or work are not fully documented, they are to be:

-	Of a kind and standard appropriate to the nature and character of that part of the Works where they will be used.

-	Suitable for the purposes stated or reasonably to be inferred from the project documents.

-	Contract documents: Omissions or errors in description and/ or quantity shall not vitiate the Contract nor release the Contractor from any obligations or liabilities under the Contract.

A33/120	WORKMANSHIP SKILLS

-	Operatives: Appropriately skilled and experienced for the type and quality of work.

-	Registration: With Construction Skills Certification Scheme.

-	Evidence: Operatives must produce evidence of skills/ qualifications when requested.

A33/130	QUALITY OF PRODUCTS

-	Generally: New (Proposals for recycled products may be considered).

-	Supply of each product: From the same source or manufacturer.

-	Whole quantity of each product required to complete the Works: Consistent in kind, size, quality and overall appearance.

-	Tolerances: Where critical, measure a sufficient quantity to determine compliance.

-	Deterioration: Prevent. Order in suitable quantities to a programme and use in appropriate sequence.

A33/135	QUALITY OF EXECUTION

-	Generally: Fix, apply, install or lay products securely, accurately, plumb, neatly and in alignment.

-	Colour batching: Do not use different colour batches where they can be seen together.

-	Dimensions: Check on-site dimensions.

-	Finished work: Not defective, e.g. not damaged, disfigured, dirty, faulty, or out of tolerance.

-	Location and fixing of products: Adjust joints open to view so they are even and regular.

A33/140	COMPLIANCE

-	Compliance with proprietary specifications: Retain on site evidence that the proprietary product specified has been supplied.

-	Compliance with performance specifications: Submit evidence of compliance, including test reports indicating:

-	Properties tested.

-	Pass/ fail criteria.

-	Test methods and procedures.

-	Test results.

-	Identity of testing agency.

-	Test dates and times.

-	Identities of witnesses.

-	Analysis of results.

A33/150	INSPECTIONS

-	Products and executions: Inspection or any other action must not be taken as approval unless confirmed in writing referring to:

-	Date of inspection.

-	Part of the work inspected.

-	Respects or characteristics which are approved.

-	Extent and purpose of the approval.

-	Any associated conditions.

A33/160	RELATED WORK

-	Details: Provide all trades with necessary details of related types of work. Before starting each new type or section of work ensure previous related work is:

-	Appropriately complete.

-	In accordance with the project documents.

-	To a suitable standard.

-	In a suitable condition to receive the new work.

-	Preparatory work: Ensure all necessary preparatory work has been carried out.

A33/170	MANUFACTURER’S RECOMMENDATIONS/ INSTRUCTIONS

-	General: Comply with manufacturer's printed recommendations and instructions current on the date of the Invitation to tender.

-	Changes to recommendations or instructions: Submit details.

-	Ancillary products and accessories: Use those supplied or recommended by main product manufacturer.

-	Agrément certified products: Comply with limitations, recommendations and requirements of relevant valid certificates.

A33/180	WATER FOR THE WORKS

-	Mains supply: Clean and uncontaminated.

-	Other: Do not use until:

-	Evidence of suitability is provided.

-	Tested to BS EN 1008 if instructed.

## SAMPLES/ APPROVALS

A33/210	SAMPLES

-	Products or executions:	- Windows

- Doors

- Brick Panel

- Roof Finish

- Powder coated infill metal panels

- Any product / materials substituted for those specified in the ER’s

A33/220	APPROVAL OF PRODUCTS

-	Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.

-	Approval: Relates to a sample of the product and not to the product as used in the Works. Do not confirm orders or use the product until approval of the sample has been obtained.

-	Complying sample: Retain in good, clean condition on site. Remove when no longer required.

A33/230	APPROVAL OF EXECUTION

-	Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.

-	Approval: Relates to the stated characteristics of the sample. (If approval of the finished work as a whole is required this is specified separately). Do not conceal, or proceed with affected work until compliance with requirements is confirmed.

-	Complying sample: Retain in good, clean condition on site. Remove when no longer required.

## ACCURACY/ SETTING OUT GENERALLY

A33/310	ACCURACY OF INSTRUMENTS

-	Accuracy in measurement: Use instruments and methods described in BS 5606, Appendix A.

A33/320	SETTING OUT

-	General: Submit details of methods and equipment to be used in setting out the Works.

-	Levels and dimensions: Check and record the results on a copy of drawings. Notify discrepancies and obtain instructions before proceeding.

-	Inform: When complete and before commencing construction.

A33/330	APPEARANCE AND FIT

-	Tolerances and dimensions: If likely to be critical to execution or difficult to achieve, as early as possible either:

-	Submit proposals; or

-	Arrange for inspection of appearance of relevant aspects of partially finished work.

-	General tolerances (maximum): To BS 5606, tables 1 and 2.

A33/340	CRITICAL DIMENSIONS

-	Critical dimensions: Set out and construct the Works to ensure compliance with the tolerances stated.

A33/350	LEVELS OF STRUCTURAL FLOORS

-	Maximum tolerances for designed levels to be:

-	Floors to be self-finished, and floors to receive sheet or tile finishes directly bedded in adhesive: +/- 10 mm.

-	Floors to receive dry board/ panel construction with little or no tolerance on thickness: +/- 10 mm.

-	Floors to receive mastic asphalt flooring/ underlays directly: +/- 10 mm.

-	Floors to receive mastic asphalt flooring/ underlays laid on mastic asphalt levelling coat(s): +/- 15 mm.

-	Floors to receive fully bonded screeds/ toppings/ beds: +/- 15 mm.

-	Floors to receive unbonded or floating screeds/ beds: +/- 20 mm.

A33/360	RECORD DRAWINGS

-	Site setting out drawing: Record details of all grid lines, setting-out stations, benchmarks and profiles. Retain on site throughout the contract and hand over on completion.

## SERVICES GENERALLY

A33/410	SERVICES REGULATIONS

-	New or existing services: Comply with the Byelaws or Regulations of the relevant Statutory Authority.

A33/420	WATER REGULATIONS/ BYELAWS NOTIFICATION

-	Requirements: Notify Water Undertaker of any work carried out to or which affects new or existing services and submit any required plans, diagrams and details.

-	Consent: Allow adequate time to receive Undertaker's consent before starting work. Inform immediately if consent is withheld or is granted subject to significant conditions.

A33/430	WATER REGULATIONS/ BYELAWS CONTRACTOR’S CERTIFICATE

-	On completion of the work: Submit (copy where also required to the Water Undertaker) a certificate including:

-	The address of the premises.

-	A brief description of the new installation and/ or work carried out to an existing installation.

-	The Contractor's name and address.

-	A statement that the installation complies with the relevant Water Regulations or Byelaws.

-	The name and signature of the individual responsible for checking compliance.

-	The date on which the installation was checked.

A33/435	ELECTRICAL INSTALLATION CERTIFICATE

-	Submit: When relevant electrical work is completed.

-	Original certificate: To be lodged in the Building Manual.

A33/440	GAS, OIL AND SOLID FUEL APPLIANCE INSTALLATION CERTIFICATE

-	Before the completion date stated in the contract: Submit a certificate stating:

-	The address of the premises.

-	A brief description of the new installation and/ or work carried out to an existing installation.

-	Any special recommendations or instructions for the safe use and operation of appliances and flues.

-	The Contractor's name and address.

-	A statement that the installation complies with the appropriate safety, installation and use regulations.

-	The name, qualification and signature of the competent person responsible for checking compliance.

-	The date on which the installation was checked.

-	Certificate location: Health and Safety File.

A33/450	MECHANICAL AND ELECTRICAL SERVICES

-	Final tests and commissioning: Carry out so that services are in full working order at completion of the Works.

-	Building Regulations notice: Copy to be lodged in the Building Manual.

## SUPERVISION/ INSPECTION/ DEFECTIVE WORK

A33/510	SUPERVISION

-	General: In addition to the constant management and supervision of the Works provided by the Contractor's person in charge, all significant types of work must be under the close control of competent trade supervisors to ensure maintenance of satisfactory quality and progress.

-	Replacement: Give maximum possible notice before changing person in charge or site agent.

A33/520	COORDINATION OF ENGINEERING SERVICES

-	Suitability: Site organisation staff must include one or more persons with appropriate knowledge and experience of mechanical and electrical engineering services to ensure compatibility between engineering and the Works generally.

-	Evidence: Submit when requested CVs or other documentary evidence relating to the staff concerned.

A33/530	OVERTIME WORKING

-	Notice: Generally overtime working will not be permitted unless in exceptional circumstances with agreement from the Brick By Brick and Employer’s Agent. Prior to overtime being worked, submit details of times, types and locations of work to be done.

-	Minimum period of notice: 3 Days. (Any cost impact of overtime working must be approved in writing by the Employer’s Agent prior to work commencing).

-	Concealed work: If executed during overtime for which notice has not been given, it may be required to be opened up for inspection and reinstated at the Contractor's expense.

A33/540	DEFECTS IN EXISTING WORK

-	Undocumented defects: When discovered, immediately give notice. Do not proceed with affected related work until response has been received.

-	Documented remedial work: Do not execute work which may:

-	Hinder access to defective products or work; or

-	Be rendered abortive by remedial work.

A33/550	ACCESS FOR INSPECTION

-	Removal: Before removing scaffolding or other facilities for access, give notice of not less than 5 working days.

A33/560	TESTS AND INSPECTIONS

-	Timing: Agree and record dates and times of tests and inspections to enable all affected parties to be represented.

-	Confirmation: One working day prior to each such test or inspection. If sample or test is not ready, agree a new date and time.

-	Records: Submit a copy of test certificates and retain copies on site.

A33/570	AIR PERMEABILITY

-	Testing organization: UKAS Accredited. Registered by the British Institute of Non-destructive Testing.

-	Method: Pressure test in accordance with the ATTMA publication: TS 1: Measuring Air Permeability of Building Envelopes.

-	Permeability:

-	Internal to external pressure difference (maximum): To be in accordance with building regulations.

-	Air leakage rate (maximum): To be in accordance with building regulations.

-	Results: Submit no later than seven days following final test.

-	Content: Include test results and all supporting data.

-	Number of copies: Two. Include also in building manual.

A33/580	CONTINUITY OF THERMAL INSULATION

-	Record and report: Confirm that work to new, renovated or upgraded thermal elements has been carried out to conform to specification. Include:

-	The address of the premises.

-	The Contractor's name and address.

-	The name, qualification and signature of the competent person responsible for checking compliance.

-	The date on which the installation was checked.

-	Submit: Before completion of the Works.

-	Copy: To be lodged in the Building Manual.

A33/595	ENERGY PERFORMANCE CERTIFICATE

-	Assessment: Undertaken by a member of an approved accreditation scheme. Submit details of scheme name and evidence of qualifications when requested.

-	Format:

-	Certificate: To be incorporated in the Building Manual.

-	Submit: 5 days before the date for completion stated in the contract.

A33/610	PROPOSALS FOR RECTIFICATION OF DEFECTIVE PRODUCTS/ EXECUTIONS

-	Proposals: Immediately any execution or product is known, or appears, to be not in accordance with the Contract, submit proposals for opening up, inspection, testing, making good, adjustment of the Contract Sum, or removal and re-execution.

-	Acceptability: Such proposals may be unacceptable and contrary instructions may be issued.

A33/620	MEASURES TO ESTABLISH ACCEPTABILITY

-	General: Wherever inspection or testing shows that the work, materials or goods are not in accordance with the contract and measures (e.g. testing, opening up, experimental making good) are taken to help in establishing whether or not the work is acceptable, such measures:

-	Will be at the expense of the Contractor.

-	Will not be considered as grounds for revision of the completion date.

A33/630	QUALITY CONTROL

-	Procedures: Establish and maintain to ensure that the Works, including the work of subcontractors, comply with specified requirements.

-	Records: Maintain full records, keep copies on site for inspection, and submit copies on request.

-	Content of records:

-	Identification of the element, item, batch or lot including location in the Works.

-	Nature and dates of inspections, tests and approvals.

-	Nature and extent of nonconforming work found.

-	Details of corrective action.

## WORK AT OR AFTER COMPLETION

A33/710	WORK BEFORE COMPLETION

-	General: Make good all damage consequent upon the Works.

-	Temporary markings, coverings and protective wrappings: Remove unless otherwise instructed.

-	Cleaning: Clean the Works thoroughly inside and out, including all accessible ducts and voids. Remove all splashes, deposits, efflorescence, rubbish and surplus materials.

-	Cleaning materials and methods: As recommended by manufacturers of products being cleaned, and must not damage or disfigure other materials or construction.

-	COSHH dated data sheets: Obtain for all materials used for cleaning and ensure they are used only as recommended by their manufacturers.

-	Minor faults: Touch up in newly painted work, carefully matching colour and brushing out edges. Repaint badly marked areas back to suitable breaks or junctions.

-	Moving parts of new work: Adjust, ease and lubricate as necessary to ensure easy and efficient operation, including doors, windows, drawers, ironmongery, appliances, valves and controls.

A33/720	SECURITY AT COMPLETION

-	General: Leave the Works secure with, where appropriate, all accesses closed and locked.

-	Keys: Account for and adequately label all keys and hand over to Employer with itemized schedule, retaining duplicate schedule signed by Employer as a receipt.

A33/730	MAKING GOOD DEFECTS

-	Remedial work: Arrange access with the Employers Agent.

-	Rectification: Give reasonable notice for access to the various parts of the Works.

-	Completion: Notify when remedial works have been completed.

A33/740	HIGHWAY/ SEWER ADOPTION

-	Work to be adopted under the Highways Act, Section 38, or the Roads (Scotland) Act, Section 16 to 18, or the Water Industry Act, Section 104.

-	Work for adoption must be:

-	Completed by the Contractor to the satisfaction of the Highway/ Sewer Authorities before the certificate stating the Works are complete is issued.

-	Subject to a Defects Liability/ Rectification Period of 12 months (see Appendix to the Contract/ Contract Particulars).

-	Maintained during the Defects Liability/ Rectification Period, including making good of damage due to reasonable wear and tear occurring during the Period and cleaning at the end of the Period, all to the satisfaction of the Highway/ Sewer Authorities.

A34

SECURITY/ SAFETY/ PROTECTION

# A34 SECURITY/ SAFETY/ PROTECTION

SECURITY, HEALTH AND SAFETY

A34/110	PRECONSTRUCTION INFORMATION

-	Location: Integral with the project Preliminaries, including but not restricted to the following sections:

-	Description of project: Sections A10 and A11.

-	Client's consideration and management requirements: Sections A12, A13 and A36.

-	Environmental restrictions and on-site risks: Section A12, A35 and A34.

-	Significant design and construction hazards: Section A34.

-	The Health and Safety File: Section A37.

A34/120	EXECUTION HAZARDS

-	Common hazards: Not listed. Control by good management and site practice.

A34/130	PRODUCT HAZARDS

-	Hazardous substances: Site personnel levels must not exceed occupational exposure standards and maximum exposure limits stated in the current version of HSE document EH40: Workplace Exposure Limits.

-	Common hazards: Not listed. Control by good management and site practice.

A34/140	CONSTRUCTION PHASE HEALTH AND SAFETY PLAN

-	Submission: Present to the Employer/ Client no later than one month from Practical Completion.

-	Confirmation: Do not start construction work until the Employer has confirmed in writing that the Construction Phase Health and Safety Plan includes the procedures and arrangements required by CDM Regulations.

-	Content: Develop the plan from and draw on the Outline Construction Phase Health and Safety Plan, clause A30/570, and the Pre-tender Health and Safety Plan/ Preconstruction information.

A34/150	SECURITY

-	Protection: Safeguard the site, the Works, products, materials, and any existing buildings affected by the Works from damage and theft.

-	Access: Take all reasonable precautions to prevent unauthorized access to the site, the Works and adjoining property. Secure wite from public footpath and adjoining properties.

-	Special requirements: Single representative from the contractor is to be responsible for site security at all times.

A34/160	STABILITY

-	Responsibility: Maintain the stability and structural integrity of the Works and adjacent structures during the Contract.

-	Design loads: Obtain details, support as necessary and prevent overloading.

A34/170	OCCUPIED PREMISES

-	Extent: Existing buildings will be occupied and/ or used during the Contract as follows: N/A

-	Works: Carry out without undue inconvenience and nuisance and without danger to occupants and users.

-	Overtime: If compliance with this clause requires certain operations to be carried out during overtime, and such overtime is not required for any other reason, the extra cost will be allowed, provided that such overtime is authorized in advance.

A34/180	PASSES

-	Controlled areas: The Contractor will be required to operate his own pass system for access to and around the site during the works. The system is to extend to all employees, subcontractors and visitors. A CRB check will only be required for members of the contractor’s personnel when returning to the site post completion to rectify defects. In this instance the CRB check will be required for at least one member of staff who will be responsible for those staff not CRB checked. Each element of work/work force to have at least one member of staff CRB checked working together. No lone working of non CRB checked employees, subcontractors and visitors.

-	Control type: Visible passes to be worn be personnel at all times. The contractor is responsible for ensuring this system is upheld at all times.

-	Authorised persons: Submit a list of the names of all persons requiring passes together with any other related information reasonably required.

-	Return of control keys: When requested or on completion of the work to which the controlled area relates.

A34/190	OCCUPIER'S RULES AND REGULATIONS

-	Compliance: Conform to the occupier's rules and regulations affecting the site, please refer to PCI Estate Rule for Croydon

A34/200	MOBILE TELEPHONES AND PORTABLE ELECTRONIC EQUIPMENT

-	Restrictions on use:

-	Use only in designated areas and as permitted by the Contractor’s site manager and in ways and times which do not cause disturbance to occupiers of adjacent properties.

A34/210	EMPLOYER'S REPRESENTATIVES SITE VISITS

-	Safety: Submit details in advance, to the Employer or the person identified in clause A10/140, of safety provisions and procedures (including those relating to materials, which may be deleterious), which will require their compliance when visiting the site.

-	Protective clothing and/ or equipment: Provide and maintain on site for the Employer and the person stated in clause A10/140 and other visitors to the site.

A34/220	WORKING PRECAUTIONS/ RESTRICTIONS

-	Hazardous areas: Operatives must take precautions when working in the area(s) as contained in the Pre-Construction Health and Safety Plan.

Permit to work procedures will operate for all work carried out in the areas as contained in the Pre-Construction Health and Safety Plan.

## PROTECT AGAINST THE FOLLOWING

A34/310	EXPLOSIVES

-	Use: Not permitted.

A34/330	NOISE AND VIBRATION

-	Standard: Comply with the recommendations of BS 5228-1, in particular clause 7.3, to minimize noise levels during the execution of the Works. Please refer to London Borough of Croydon Construction Code of Practice.

-	Noise levels from the Works: Maximum level: Are to be kept to the necessary minimum. Planning conditions may stipulate additional requirements which the contractor must take into consideration.

-	Site is bordered by residential properties. Refer to Please refer to London Borough of Croydon Construction Code of Practice. on the Control of Noise and Pollution from Construction Sites as referenced in the planning consent.

-	Equipment: Fit compressors, percussion tools and vehicles with effective silencers of a type recommended by manufacturers of the compressors, tools or vehicles.

-	Restrictions: Do not use:

-	Percussion tools and other noisy appliances without consent during the hours specified within the planning requirements (No noisy works outside the hours of 9am-17:30).

-	Radios or other audio equipment or permit employees to use in ways or at times that may cause nuisance.

A34/340	POLLUTION

-	Prevention: Protect the site, the Works and the general environment including the atmosphere, lands, streams and waterways against pollution.

-	Contamination: If pollution occurs inform immediately, including to the appropriate Authorities and provide relevant information.

A34/350	PESTICIDES

-	Use: Not permitted.

A34/360	NUISANCE

-	Duty: Prevent nuisance from smoke, dust, rubbish, vermin and other causes.

-	Surface water: Prevent hazardous build-up on site, in excavations and to surrounding areas and roads.

A34/370	ASBESTOS CONTAINING MATERIALS

-	Duty: Report immediately any suspected materials discovered during execution of the Works.

-	Do not disturb.

-	Agree methods for safe removal or encapsulation.

A34/371	DANGEROUS OR HAZARDOUS SUBSTANCES

-	Duty: Report immediately suspected materials discovered during execution of the Works.

-	Do not disturb.

-	Agree methods for safe removal or remediation.

A34/375	ANTIQUITIES

-	Duty: Report immediately any fossils, antiquities and other objects of interest or value discovered during execution of the works.

-	Preservation: Keep objects in the exact position and condition in which they were found.

A34/380	FIRE PREVENTION

-	Duty: Prevent personal injury or death, and damage to the Works or other property from fire.

-	Standard: Comply with Joint Code of Practice 'Fire Prevention on Construction Sites', published by the Construction Confederation and The Fire Protection Association (The 'Joint Fire Code').

A34/390	SMOKING ON SITE

-	Smoking on site: Not permitted.

A34/400	BURNING ON SITE

-	Burning on site: Not permitted.

A34/410	MOISTURE

-	Wetness or dampness: Prevent, where this may cause damage to the Works.

-	Drying out: Control humidity and the application of heat to prevent:

-	Blistering and failure of adhesion.

-	Damage due to trapped moisture.

-	Excessive movement.

A34/420	INFECTED TIMBER/ CONTAMINATED MATERIALS

-	Removal: Where instructed to remove material affected by fungal/ insect attack from the building, minimize the risk of infecting other parts of the building.

-	Testing: carry out and keep records of appropriate tests to demonstrate that hazards presented by concentrations of airborne particles, toxins and other micro organisms are within acceptable levels.

A34/430	WASTE

-	Includes: Rubbish, debris, spoil, surplus material, containers and packaging.

-	General: Minimize production. Prevent accumulations. Keep the site and Works clean and tidy.

-	Handling: Collect and store in suitable containers. Remove frequently and dispose off site in a safe and competent manner:

-	Non-hazardous material: In a manner approved by the Waste Regulation Authority.

-	Hazardous material: As directed by the Waste Regulation Authority and in accordance with relevant regulations.

-	Recyclable material: Sort and dispose at a Materials Recycling Facility approved by the Waste Regulation Authority.

-	Voids and cavities in the construction: Remove rubbish, dirt and residues before closing in.

-	Waste transfer documentation: Retain on site.

A34/440	ELECTROMAGNETIC INTERFERENCE

-	Duty: Prevent excessive electromagnetic disturbance to apparatus outside the site.

A34/450	LASER EQUIPMENT

-	Construction laser equipment: Install, use and store in accordance with BS EN 60825-1 and the manufacturer's instructions.

-	Class 1 or Class 2 laser equipment: Ensure laser beam is not set at eye level and is terminated at the end of its useful path.

-	Class 3A and Class 3B laser equipment: Do not use without approval and subject to submission of a method statement on its safe use.

A34/460	POWER ACTUATED FIXING SYSTEMS

-	Use: Not permitted.

A34/470	INVASIVE SPECIES

-	General: Prevent the spread of species (e.g. plants or animals) that may adversely affect the site or Works economically, environmentally or ecologically.

-	Duty: Report immediately any suspected invasive species discovered during execution of the Works.

-	Do not disturb.

-	Agree methods for safe eradication or removal.

## PROTECT THE FOLLOWING

A34/510	EXISTING SERVICES

-	Confirmation: Notify all service authorities, statutory undertakers and/ or adjacent owners of proposed works not less than one week before commencing site operations.

-	Identification: Before starting work, check and mark positions of utilities/ services. Where positions are not shown on drawings obtain relevant details from service authorities, statutory undertakers or other owners.

-	Work adjacent to services:

-	Comply with service authority's/ statutory undertaker's recommendations.

-	Adequately protect, and prevent damage to services: Do not interfere with their operation without consent of service authorities/ statutory undertakers or other owners.

-	Identifying services:

-	Below ground: Use signboards, giving type and depth;

-	Overhead: Use headroom markers.

-	Damage to services: If any results from execution of the Works:

-	Immediately give notice and notify appropriate service authority/ statutory undertaker.

-	Make arrangements for the work to be made good without delay to the satisfaction of service authority/ statutory undertaker or other owner as appropriate.

-	Any measures taken to deal with an emergency will not affect the extent of the Contractor's liability.

-	Marker tapes or protective covers: Replace, if disturbed during site operations, to service authority's/ statutory undertaker's recommendations.

A34/520	ROADS AND FOOTPATHS

-	Duty: Maintain roads and footpaths within and adjacent to the site and keep clear of mud and debris.

-	Damage caused by site traffic or otherwise consequent upon the Works: Make good to the satisfaction of the Employer, Local Authority or other owner.

A34/530	EXISTING TOPSOIL/ SUBSOIL

-	Duty: Prevent over compaction of existing topsoil and subsoil in those areas which may be damaged by construction traffic, parking of vehicles, temporary site accommodation or storage of materials and which will require reinstatement prior to completion of the Works.

-	Protection: Before starting work submit proposals for protective measures.

A34/540	RETAINED TREES/ SHRUBS/ GRASSED AREAS

-	Protection: Preserve and prevent damage, except those not required.

-	Replacement: Mature trees and shrubs if uprooted, destroyed, or damaged beyond reasonable chance of survival in their original shape, as a consequence of the Contractor's negligence, must be replaced with those of a similar type and age at the Contractor's expense.

A34/550	RETAINED TREES

-	Protected area: Unless agreed otherwise do not:

-	Dump spoil or rubbish, excavate or disturb topsoil, park vehicles or plant, store materials or place temporary accommodation within an area which is the larger of the branch spread of the tree or an area with a radius of half the tree's height, measured from the trunk.

-	Sever roots exceeding 25 mm in diameter. If unintentionally severed give notice and seek advice.

-	Change level of ground within an area 3 m beyond branch spread.

A34/555	WILDLIFE SPECIES AND HABITATS

-	Protected habitats and species: Upon discovery immediately advise. Do not proceed until instruction is received.

-	Education: Ensure employees and visitors to the site receive suitable instruction and awareness training.

A34/560	EXISTING FEATURES

-	Protection: Prevent damage to existing buildings, fences, gates, walls, roads, paved areas etc. Surrounding the site.

A34/570	EXISTING WORK

-	Protection: Prevent damage to existing work, structures or other property during the course of the work. Please refer to details of existing works contained within the ER documentation.

-	Removal: Minimum amount necessary.

-	Replacement work: To match existing.

A34/580	BUILDING INTERIORS

-	Protection: Prevent damage from exposure to the environment, including weather, flora, fauna, and other causes of material degradation during the course of the work.

A34/600	EXISTING FURNITURE, FITTINGS AND EQUIPMENT

-	Protection: Prevent damage or move as necessary to enable the Works to be executed. Reinstate in original positions.

-	Extent: The Contractor is to employ the services of a professional removal company to undertake the removal of all furniture and equipment before work in each room starts and reinstatement upon completion.

A34/610	ESPECIALLY VALUABLE/ VULNERABLE ITEMS

-	Protection: Ensure provision and maintenance of special protective measures to prevent damage.

-	Method statement: Submit within one week of request describing special protection to be provided.

A34/620	ADJOINING PROPERTY

-	Permission: Obtain as necessary from owners if requiring to erect scaffolding on or otherwise use adjoining property.

A34/625	ADJOINING PROPERTY RESTRICTIONS

-	Precautions:

-	Prevent trespass of workpeople and take precautions to prevent damage to adjoining property.

-	Pay all charges.

-	Remove and make good on completion or when directed.

-	Damage: Bear cost of repairing damage arising from execution of the Works.

A34/630	EXISTING STRUCTURES

-	Duty: Check proposed methods of work for effects on adjacent structures inside and outside the site boundary.

-	Supports: During execution of the Works:

-	Provide and maintain all incidental shoring, strutting, needling and other supports as may be necessary to preserve stability of existing structures on the site or adjoining that may be endangered or affected by the Works.

-	Do not remove until new work is strong enough to support existing structure.

-	Prevent overstressing of completed work when removing supports.

-	Adjacent structures: Monitor and immediately report excessive movement.

-	Standard: Comply with BS 5975 and BS EN 12812.

A34/640	MATERIALS FOR RECYCLING/ REUSE

-	Duty: Sort and prevent damage to stated products or materials, clean off bedding and jointing materials and other contaminants.

-	Storage: Stack neatly and protect until required by the Employer or for use in the Works as instructed.

A35

SPECIFIC LIMITATIONS ON METHOD/ SEQUENCE/

TIMING

# A35 SPECIFIC LIMITATIONS ON METHOD/  SEQUENCE/  TIMING

A35/110	SCOPE

-	General: The limitations described in this section are supplementary to limitations described or implicit in information given in other sections or on the drawings.

A35/120	DESIGN CONSTRAINTS

- Details: As set out in the Design Risk Assessment, Planning Application, Employers Requirements and Tender Documents. Planning Application can be provided on request by the Contractor and accessed online. Design and construct in accordance with the above or other scheme agreed with the client.

A35/130	METHOD/ SEQUENCE OF WORK

-	Specific Limitations: Include the following in the programme:

-	Sequence/phasing will be as architect’s phasing plans. This phasing sequence cannot be altered.  Contractor to ensure all perimeter vehicle access is kept clear at all times.

A35/140	SCAFFOLDING

-	Scaffolding: Make available to subcontractors and others at all times.

A35/160	USE OR DISPOSAL OF MATERIALS

- Specific limitations: Comply with ISO14001.

A35/170	WORKING HOURS

- Specific limitations: Will need to comply with planning restrictions.

  - 08:00 to 18:00 Monday to Friday

  - 08:00 to 13:00 Saturday

  - In accordance with Arcadis Construction Logistic Plan and Planning Consent.

A35/180	COMPLETION IN SECTIONS OR IN PARTS

-	General: Where the Employer is to take possession of any section or part of the Works and such section or part will, after its possession, depend for its adequate functioning on work located elsewhere on the site: Complete such other work in time to permit such possession to take place.

-	Remainder of the Works: During execution, ensure that completed sections or parts of the Works have continuous and adequate provision of services, fire precautions, means of escape and safe access.

A36

FACILITIES/ TEMPORARY WORK/ SERVICES

# A36 FACILITIES/ TEMPORARY WORK/ SERVICES

GENERALLY

A36/110	SPOIL HEAPS, TEMPORARY WORKS AND SERVICES

-	Location: Give notice and details of intended siting.

-	Maintenance: Alter, adapt and move as necessary. Remove when no longer required and make good.

## ACCOMMODATION

A36/210	ROOM FOR MEETINGS

-	Facilities: Provide suitable temporary accommodation for site meetings, adequately heated and lit. The room may be part of the Contractor's own site offices.

-	Furniture and Equipment: Please refer to A32/260.

A36/260	SANITARY ACCOMMODATION

-	Requirement: Provide sanitary accommodation for the Employer/ Purchaser, and other members of the consultant team, either separate or shared with the Contractor’s supervisory staff. Maintain in clean condition and provide all consumables.

A36/270	ACCOMMODATION/ LAND NOT INCLUDED IN THE SITE

-	General: The following may be used for the duration of the Contract without charge provided that:

-	It is used solely for the purposes of carrying out the Contract works.

-	The use to which it is put does not involve undue risk of damage.

-	Any temporary adaptations are approved by or on behalf of the Employer/ Purchaser before being carried out.

-	It is vacated on completion of the Contract work or determination of the Contract.

-	When vacated, its condition is at least equivalent to its condition at the start of the Contract.

-	Available services: Power and water to be provided from the existing supplies and will be sub-metered and paid for by the Contractor.

A36/290	PARKING

-	No parking will be available on site outside of the Contractor’s site compound.

## TEMPORARY WORKS

A36/310	ROADS

-	Permanent roads, hard standings and footpaths on the site may be used, subject to clause A34/520.

A36/320	TEMPORARY WORKS

-	Employer's Specific Requirements: None.

A36/330	TEMPORARY PROTECTION TO EXISTING TREES/ VEGETATION

-	Temporary protection: See Site Specific Prelims.

-	Protective barriers and any other relevant physical protection measures: To BS 5837.

-	Integrity of protection: Maintain for the duration of the Works. Remove on completion of the works and make good disturbed area.

A36/340	NAME BOARDS/ ADVERTISEMENTS

-	Name boards/ advertisements: Name boards permitted fixed to hoarding. P

-	The client requires the contractor to provide erection of a project sign board with project details, consultants etc.

## SERVICES AND FACILITIES

A36/410	LIGHTING

-	Finishing work and inspection: Provide temporary lighting, the intensity and direction of which closely resembles that delivered by the permanent installation.

A36/420	LIGHTING AND POWER

-	Supply: Contractor to provide own power supply fort the works.

-	Continuity: The Employer will not be responsible for the consequences of failure or restriction in supply.

A36/430	WATER

-	Supply: The Employer's mains may be used for the Works as follows. This shall be sub-metered and paid for by the Contractor.

-	Continuity: The Employer will not be responsible for the consequences of failure or restriction in supply.

A36/440	TELEPHONES

-	Temporary on site telephone: Provide as soon as practicable after the start on site for joint use by the Contractor and Subcontractors and pay all charges.

-	Responses: Make arrangements (e.g. an external bell) to ensure that incoming calls are answered promptly.

A36/440	TELEPHONES

-	Temporary on site telephone: Provide as soon as practicable after the start on site for joint use by the Contractor, Subcontractors and those acting on behalf of the Employer, and pay all charges reasonably incurred.

-	Responses: Make arrangements (e.g. an external bell) to ensure that incoming calls are answered promptly.

-	Employer's call charges: Allow for the cost of a modest number of calls made by those acting on behalf of the Employer.

A36/470	E-MAIL AND INTERNET FACILITY

-	General: As soon as practicable after the start on site provide a suitable e-mail facility on site, with a separate dedicated telephone line, for the use of the Contractor, Subcontractors and those acting on behalf of the Employer.

-	Use on behalf of Employer: Allow for the cost of a reasonable number of transmissions made by those acting on behalf of the Employer.

-	Peripherals: Scanner, copier and printer.

A36/480	PHOTOCOPIER

-	General: Provide reasonably unrestricted access to and reasonably limited free use of an on site photocopier, which may be located in the Contractor's own site offices.

A36/510	TEMPERATURE AND HUMIDITY

-	Levels required by the Employer: Maintain suitable conditions for an office working environment.

A36/520	USE OF PERMANENT HEATING SYSTEM

-	Permanent heating installation: May be used for drying out the Works/ services and controlling temperature and humidity levels.

-	Installation: If used:

-	Take responsibility for operation, maintenance and remedial work.

-	Arrange supervision by and indemnification of the appropriate Subcontractors.

-	Pay costs arising.

A36/530	BENEFICIAL USE OF INSTALLED SYSTEMS

-	Permanent systems: Unless specific permission is given by the Employer and installer, do not use for any purpose other than running in, testing and commissioning.

-	Other uses: If permission is given for any other use of a system before the Works are accepted as complete, it must be subject to a separate written agreement between the parties and in accordance with the recommended procedures given in NJCC Guidance Note 10.

A36/540	METER READINGS

-	Charges for service supplies: Where to be apportioned ensure that:

-	Meter readings are taken by relevant authority at possession and/ or completion as appropriate.

-	Copies of readings are supplied to interested parties.

A36/550	THERMOMETERS

-	General: Provide on site and maintain in accurate condition a maximum and minimum thermometer for measuring atmospheric shade temperature, in an approved location.

A36/570	PERSONAL PROTECTIVE EQUIPMENT

-	General: Provide for the sole use of those acting on behalf of the Employer, in sizes to be specified:

-	Safety helmets to BS EN 397, neither damaged nor time expired. Number required:4

-	High visibility waistcoats to BS EN 471 Class 2. Number required:4.

-	Safety boots with steel insole and toecap to BS EN ISO 20345. Pairs required:4

-	Disposable respirators to BS EN 149.FFP1S.

-	Eye protection to BS EN 166.

-	Ear protection - muffs to BS EN 352-1, plugs to BS EN 352-2.

-	Hand protection - to BS EN 388, 407, 420 or 511 as appropriate.

A37

OPERATION/ MAINTENANCE OF THE FINISHED

WORKS

# A37 OPERATION/ MAINTENANCE OF THE FINISHED WORKS

GENERALLY

A37/110	THE BUILDING MANUAL

-	Purpose: The Manual is to be a comprehensive information source and guide for owners and users of the completed Works. It should provide an overview of the main design principles and describe key components and systems to enable proper understanding, efficient and safe operation and maintenance.

-	Scope:

-	Part 1: General: [Content as clause 120].

-	Part 2: Fabric: [Content as clause 130].

-	Part 3: Services: [Content as clause 140].

-	Part 4: The Health and Safety File: [prepared and supplied by the CDM Coordinator]. [Content as clause 150].

-	Responsibility: The Building Manual is to be produced by the Contractor and must be complete no later than three weeks before completion.

-	Compilation:

-	Prepare all information for Contractor designed or performance specified work including as-built drawings.

-	Obtain or prepare all other information to be included in the Manual.

-	Reviewing the Manual: Submit a complete draft. Amend in the light of any comments and resubmit. Do not proceed with production of the final copies until authorized.

-	Final copies of the Manual:

-	Number of copies: 3.

-	Format: One set electronic and two sets hard copy.

-	Latest date for submission: three weeks before the date for completion stated in the contract.

-	As-built drawings and schedules:

-	Number of copies: 3 .

-	Format: One set electronic and two sets hard copy.

A37/115	The Health and Safety File

-	Responsibility: The Contractor.

-	Format: One set electronic and two sets hard copy.

-	Delivery to: the CDM Co-ordinator By (date): Formal handover meeting.

A37/120	CONTENT OF THE BUILDING MANUAL PART 1: GENERAL

-	Content: Obtain and provide the following, including all relevant details not included in other parts of the manual:

-	Index: list the constituent parts of the manual, together with their location in the document.

-	The Works:

-	Description of the buildings and facilities.

-	Ownership and tenancy, where relevant.

-	Health and Safety information – other than that specifically required by the Construction (Design and Management) Regulations.

-	The Contract:

-	Names and addresses and contact details of all significant consultants, Contractors, subcontractors, suppliers and manufacturers.

-	Overall design criteria.

-	Environmental performance requirements.

-	Relevant authorities, consents and approvals.

-	Third party certification, such as those made by ‘competent’ persons  in accordance with the Building Regulations.

-	Operational requirements and constraints of a general nature:

-	Maintenance contracts and Contractors.

-	Fire safety strategy for the buildings and the site. Include drawings showing emergency escape and fire appliance routes, fire resisting doors location of emergency alarm and fire fighting systems, services, shut off valves switches, etc.

-	Emergency procedures and contact details in case of emergency.

-	Description and location of other key documents.

-	Timescale for completion: As clause 110.

A37/130	CONTENT OF THE BUILDING MANUAL PART 2: BUILDING FABRIC

-	Content: Obtain and provide the following, including all relevant details not included in other parts of the manual:

-	Detailed design criteria, including:

-	Floor and roof loadings.

-	Durability of individual components and elements.

-	Loading restrictions.

-	Insulation values.

-	Fire ratings.

-	Other relevant performance requirements.

-	Construction of the building:

-	A detailed description of methods and materials used.

-	As-built drawings recording the construction, together with an index.

-	Information and guidance concerning repair, renovation or demolition/ deconstruction.

-	Periodic building maintenance guide chart.

-	Inspection reports.

-	Manufacturer's instructions index, including relevant COSHH data sheets and recommendations for cleaning, repair and maintenance of components.

-	Fixtures, fittings and components schedule and index.

-	Guarantees, warranties and maintenance agreements – obtain from manufacturers, suppliers and subcontractors.

-	Test certificates and reports required in the specification or in accordance with legislation, including:

-	Air permeability.

-	Resistance to passage of sound.

-	Continuity of insulation.

-	Electricity and Gas safety.

-	Timescale for completion: As clause 110 .

A37/140	CONTENT OF THE BUILDING MANUAL PART 3: BUILDING SERVICES

-	Content: Obtain and provide the following, including all relevant details not included in other parts of the manual:

-	Detailed design criteria and description of the systems, including:

-	Services capacity, loadings and restrictions.

-	Services instructions.

-	Services log sheets.

-	Manufacturers' instruction manuals and leaflets index.

-	Fixtures, fittings and component schedule index.

-	Detailed description of methods and materials used.

-	As-built drawings for each system recording the construction, together with an index, including:

-	Diagrammatic drawings indicating principal items of plant, equipment and fittings.

-	Record drawings showing overall installation.

-	Schedules of plant, equipment, valves, etc. describing location, design performance and unique identification cross referenced to the record drawings.

-	Identification of services – a legend for colour coded services.

-	Product details, including for each item of plant and equipment:

-	Name, address and contact details of the manufacturer.

-	Catalogue number or reference.

-	Manufacturer's technical literature, including detailed operating and maintenance instructions.

-	Information and guidance concerning dismantling, repair, renovation or decommissioning.

-	Operation: A description of the operation of each system, including:

-	Starting up, operation and shutting down.

-	Control sequences.

-	Procedures for seasonal changeover.

-	Procedures for diagnostics, troubleshooting and faultfinding.

-	Guarantees, warranties and maintenance agreements – obtain from manufacturers, suppliers and subcontractors.

-	Commissioning records and test certificates list for each item of plant, equipment, valves, etc. used in the installations – including:

-	Electrical circuit tests.

-	Corrosion tests.

-	Type tests.

-	Work tests.

-	Start and commissioning tests.

-	Equipment settings: Schedules of fixed and variable equipment settings established during commissioning.

-	Preventative maintenance: Recommendations for frequency and procedures to be adopted to ensure efficient operation of the systems.

-	Lubrication: Schedules of all lubricated items.

-	Consumables: A list of all consumable items and their source.

-	Spares: A list of recommended spares to be kept in stock, being those items subject to wear and tear or deterioration and which may involve an extended delivery time when replacements are required.

-	Emergency procedures for all systems, significant items of plant and equipment.

-	Annual maintenance summary chart.

-	Timescale for completion: Ad clause 110.

A37/150	CONTENT OF THE BUILDING MANUAL PART 4: THE HEALTH AND SAFETY FILE

-	Content: obtain and provide the following, including all relevant details not included in other parts of the manual, including:

-	residual hazards and how they have been dealt with.

-	hazardous materials used.

-	information regarding the removal or dismantling of installed plant and equipment.

-	health and safety information about equipment provided for cleaning or maintaining the structure.

-	the nature, location and markings of significant services.

-	information and as-built drawings of the structure, its plant and equipment.

-	Timescale for completion: As clause 110.

-	Submit to: CDM Co-ordinator.

A37/160	PRESENTATION OF BUILDING MANUAL

-	Format: A4 size, plastics covered, loose leaf, four ring binders with hard covers, each indexed, divided and appropriately cover titled.

-	Selected drawings needed to illustrate or locate items mentioned in the Manual: Where larger than A4, to be folded and accommodated in the binders so that they may be unfolded without being detached from the rings.

-	As-built drawings: The main sets may form annexes to the Manual.

A37/210	INFORMATION FOR COMMISSIONING OF SERVICES

-	General: Submit relevant drawings and preliminary performance data to enable the building user's staff to familiarise themselves with the installation.

-	Time of submission: At commencement of commissioning.

A37/220	TRAINING

-	Objective: Before Completion, explain and demonstrate to designated maintenance staff the purpose, function and operation of the installations including items and procedures listed in the Building Manual.

-	Time allowance: Include a minimum of one day.

A37/230	SPARE PARTS

-	General: Before Completion submit a priced schedule of spare parts that the Contractor recommends should be obtained and kept in stock for maintenance of the services installations.

-	Content: Include in the priced schedule for:

-	Manufacturers' current prices, including packaging and delivery to site.

-	Checking receipts, marking and numbering in accordance with the schedule of spare parts.

-	Referencing to the plant and equipment list in Part 3 of the Building Manual.

-	Painting, greasing, etc. and packing to prevent deterioration during storage.

-	Latest date for submission: one week before the date for practical completion stated in the contract.

A37/250	TOOLS

-	General: Provide tools and portable indicating instruments for the operation and maintenance of all services, plant and equipment (except any installed under Named Subcontracts) together with suitable means of identifying, storing and securing.

-	Quantity: Two complete sets.

-	Time of submission: At completion.

A40

CONTRACTOR’S GENERAL COST ITEMS:

MANAGEMENT AND STAFF

# A40 CONTRACTOR’S GENERAL COST ITEMS: MANAGEMENT AND STAFF

A40/110	MANAGEMENT AND STAFF.

A41

CONTRACTOR’S GENERAL COST ITEMS: SITE

ACCOMMODATION

# A41 CONTRACTOR’S GENERAL COST ITEMS: SITE ACCOMMODATION

A41/110	SITE ACCOMMODATION

-	Details: Site accommodation required or made/ not made available by the Employer: See section A36.

A42

CONTRACTOR’S GENERAL COST ITEMS: SERVICES

AND FACILITIES

# A42 CONTRACTOR’S GENERAL COST ITEMS: SERVICES AND FACILITIES

A42/110	POWER

A42/120	LIGHTING

A42/130	FUELS

A42/140	WATER

A42/150	TELEPHONE AND ADMINISTRATION

A42/160	SAFETY, HEALTH AND WELFARE

-	See clause A34/210.

A42/170	STORAGE OF MATERIALS

A42/180	RUBBISH DISPOSAL

-	See clause A34/430.

A42/190	CLEANING

-	See clause A33/710.

A42/200	DRYING OUT

-	See clause A34/410.

A42/210	PROTECTION OF WORK IN SECTIONS

A42/220	SECURITY

-	See clause A34/150.

A42/230	MAINTAIN PUBLIC AND PRIVATE ROADS

-	See clause A34/520.

A42/240	SMALL PLANT AND TOOLS

A42/250	OTHERS

A42/310	ADDITIONAL SERVICES AND FACILITIES ITEMS

A43

CONTRACTOR’S GENERAL COST ITEMS:

MECHANICAL PLANT

# A43 CONTRACTOR’S GENERAL COST ITEMS: MECHANICAL PLANT

A43/110	CRANES

A43/120	HOISTS

A43/130	PERSONNEL TRANSPORT

A43/140	TRANSPORT

A43/150	EARTHMOVING PLANT

A43/160	CONCRETE PLANT

A43/170	PILING PLANT

A43/180	PAVING AND SURFACING PLANT

A43/200	ADDITIONAL MECHANICAL PLANT

A44

CONTRACTOR’S GENERAL COST ITEMS:

TEMPORARY WORKS

# A44 CONTRACTOR’S GENERAL COST ITEMS: TEMPORARY WORKS

A44/110	TEMPORARY WORKS

-	Details: Temporary works required or made/ not made available by the Employer: See section A36.

A44/110	TEMPORARY ROADS

A44/120	TEMPORARY WALKWAYS

A44/130	ACCESS SCAFFOLDING

A44/140	SUPPORT SCAFFOLDING AND PROPPING

A44/150	HOARDINGS, FANS, FENCING, ETC.

A44/160	HARDSTANDING

A44/170	TRAFFIC REGULATIONS

A44/200	ADDITIONAL TEMPORARY WORKS

A50

WORK/ PRODUCTS BY/ ON BEHALF OF THE

EMPLOYER

# A50 WORK/ PRODUCTS BY/ ON BEHALF OF THE EMPLOYER

A50/110	WORK BY/ ON BEHALF OF EMPLOYER

-	Description of work: None.

A50/120	PRODUCTS PROVIDED BY/ ON BEHALF OF EMPLOYER

-	General: Details of such products are given in the work sections, for fixing as part of the contract. Use for no other purpose than the Works.

-	Handling: Accept delivery, check against receipts and take into appropriate storage.

-	Surplus products: Keep safe and obtain instructions.

A53

WORK BY STATUTORY AUTHORITIES/

UNDERTAKERS

# A53 WORK BY STATUTORY AUTHORITIES/ UNDERTAKERS

110	WORK BY LOCAL AUTHORITY

- 	Not applicable

120	WORK BY STATUTORY UNDERTAKERS

-	New UKPN connection

-	Water main diversion

- 	New water connection

-	New BT connection

-	New gas connection

-	Foul and surface water connections

A54

PROVISIONAL WORK/ ITEMS

# A54 PROVISIONAL WORK/ ITEMS

110	PROVISIONAL SUMS FOR DEFINED WORK, FOR USE WITH SMM7/ NRM2

•	 Item: None.

210	PROVISIONAL SUMS FOR UNDEFINED WORK, FOR USE WITH SMM7/ NRM2

•	 Item: None.

A56

ADVANCE PROCUREMENT

# A56 ADVANCE PROCUREMENT

110	FIXING

•	 Scope: Items procured in advance do not include for Main Contractor's receiving,

unloading, handling, storing, returning packing, hoisting into position and fixing, which must

be allowed for in the appropriate work section.

120	PLANTING

•	 Scope: Items for plants and trees do not include for planting, maintenance and guarantee,

which should be allowed for in the appropriate work section.